## PS-5 EIT INSPECTION REGISTER
PS-5 EIT INSPECTION REGISTER
[8 empty] | INSTALLATION & TESTING INSPECTION |  |  |  |  | GLANDING & TERMINATION INSPECTION
Task ID | Asset - Tag | Description | For CHECKING Vlookup_BW | Discipline | Asset - Description |  | Systemization - Subsystem (Summary) | QC RFI# | Inspection Date | STATUS OF RFI | QC INSPECTOR | INSPECTION TYPE (PULLING/CABLE TESTING/ EQUIPMENT INSTALLATION) | QC RFI# | RFI STATUS | INSPECTION DATE | QC INSPECTOR | Remarks
T-00018-0098 | PS5-61-ISR-0101 | CPX02 - Power transformer | #N/A | E | Shunt Reactor |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00018-0099 | PS5-61-ISR-0102 | CPX02 - Power transformer | #N/A | E | Shunt Reactor |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
| PS5-08-52BT-0136-CS01 | CPX | #N/A | E | Cable FROM PS5-08-11CB-1901 TO PS5-08-52BT-0136 |  | NA | CPP-RFI-68-331-05-0239 | 30-April-20206 | Accepted With Punch | Bertus Wikael | PULLING
T-00018-0100 | PS5-61-IU-0010 | CPX02 - Power transformer | #N/A | E | LLHT Oil Transformer |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010)
T-00018-0101 | PS5-61-IU-0011 | CPX02 - Power transformer | #N/A | E | LLHT Oil Transformer |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011)
T-00018-0102 | PS5-61-IV-0001A | CPX02 - Power transformer | #N/A | E | Distribution Transformer |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-332-02-0331 | 2026-06-11 | Accepted with coment | Bertus Wikael | INSTALLATION
T-00018-0103 | PS5-61-IV-0001B | CPX02 - Power transformer | #N/A | E | Distribution Transformer |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-332-02-0395 | 2026-06-30 | CANCELED | Bertus Wikael | INSTALLATION
T-00018-0104 | PS5-63-IV-0010 | CPX02 - Power transformer | #N/A | E | Earthing Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00018-0105 | PS5-63-IV-0011 | CPX02 - Power transformer | #N/A | E | Earthing Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00018-0121 | PS5-61-IV-0002A | CPX02 - Power transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-332-02-0395 | 2026-06-30 | CANCELED | Bertus Wikael | INSTALLATION
T-00018-0122 | PS5-61-IV-0002B | CPX02 - Power transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-332-02-0395 | 2026-06-30 | CANCELED | Bertus Wikael | INSTALLATION
T-00018-0123 | PS5-61-IV-0007A | CPX02 - Power transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-332-02-0395 | 2026-06-30 | CANCELED | Bertus Wikael | INSTALLATION
T-00018-0124 | PS5-61-IV-0007B | CPX02 - Power transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-332-02-0395 | 2026-06-30 | CANCELED | Bertus Wikael | INSTALLATION
T-00018-0171 | PS5-61-IU-3100A | CPX02 - Power transformer | #N/A | E | VFD Transformer |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-332-02-0304 | 2026-05-29 | Accepted | Bertus Wikael | Installation
T-00018-0172 | PS5-61-IU-3100B | CPX02 - Power transformer | #N/A | E | VFD Transformer |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-332-02-0304 | 2026-05-29 | Accepted | Bertus Wikael | Installation
T-00018-0173 | PS5-61-IU-3100C | CPX02 - Power transformer | #N/A | E | VFD Transformer |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-332-02-0304 | 2026-05-29 | Accepted | Bertus Wikael | Installation
T-00018-0192 | PS5-61-IU-0001A | CPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-01 - Power Generation Package A
T-00018-0193 | PS5-61-IU-0001B | CPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-04 - Power Generation Package B
T-00018-0194 | PS5-61-IU-0001C | CPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-07 - Power Generation Package C
T-00018-0195 | PS5-61-IU-0001D | CPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-10 - Power Generation Package D
T-00018-0196 | PS5-61-IU-0001E | CPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-13 - Power Generation Package E
T-00018-0197 | PS5-61-IU-0001F | CPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-16 - Power Generation Package F
T-00018-0198 | PS5-61-IU-0001G | CPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-19 - Power Generation Package G
T-00018-0237 | PS5-79-IV-0001 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 1 |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | CPP-RFI-68-33/2-02-0301 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00018-0238 | PS5-79-IV-0002 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 2 |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | CPP-RFI-68-33/2-02-0301 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00018-0239 | PS5-79-IV-0003 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 3 |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | CPP-RFI-68-33/2-02-0301 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00018-0240 | PS5-79-IV-0004 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 4 |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | CPP-RFI-68-33/2-02-0301 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00018-0241 | PS5-79-IV-0005 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 5 |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | CPP-RFI-68-33/2-02-0301 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00018-0242 | PS5-79-IV-0006 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 6 |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | CPP-RFI-68-33/2-02-0301 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00018-0243 | PS5-79-IV-0007 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 7 |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | CPP-RFI-68-33/2-02-0301 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00018-0244 | PS5-79-IV-0008 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 8 |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | CPP-RFI-68-33/2-02-0301 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00018-0245 | PS5-79-IV-0009 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 9 |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | CPP-RFI-68-33/2-02-0301 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00018-0246 | PS5-79-IV-0010 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 9 |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | CPP-RFI-68-33/2-02-0301 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00018-0247 | PS5-79-IV-0011 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 11 |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | CPP-RFI-68-33/2-02-0301 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00018-0248 | PS5-79-IV-0012 | CPX02 - Power transformer | #N/A | E | Feeder to EHT Transformer / DB 12 |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00018-0249 | PS5-87-IRF-0001 | CPX02 - Power transformer | #N/A | E | Transformer Rectifier Unit 1-for tank (PS5-53-TR-4100) |  | PS5-53-01 - Utility Water / Storage Tank
T-00018-0250 | PS5-87-IRF-0002 | CPX02 - Power transformer | #N/A | E | Transformer Rectifier Unit 2-for tank (PS5-71-TR-4100) |  | PS5-71-04 - CFO Storage Tank
T-00018-0251 | PS5-87-IRF-0003 | CPX02 - Power transformer | #N/A | E | Transformer Rectifier Unit 3-for tank (PS5-71-TR-4200) |  | PS5-71-12 - CFO Service Tank
T-00018-0252 | PS5-87-IRF-0004 | CPX02 - Power transformer | #N/A | E | Transformer Rectifier Unit 4-for tank ( PS5-71-TR-4400) |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00018-0294 | PS5-61-IV-0005A | CPX02 - Power transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00018-0295 | PS5-61-IV-0005B | CPX02 - Power transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00019-0035 | PS5-61-IK-0003 | CPX05 - LV switchboard | #N/A | E | LV SWGR |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/2-13-0402 | 2026-07-05 | Accepted with punch | Bertus Wikael | Installation | N/A | N/A | N/A | N/A
T-00019-0036 | PS5-61-IK-0006 | CPX05 - LV switchboard | #N/A | E | LV SWGR |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006)
T-00022-3316 | PS5-25-DM-3100A-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3317 | PS5-25-DM-3100A-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3318 | PS5-25-DM-3100A-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3319 | PS5-25-DM-3100A-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3320 | PS5-25-DM-3100A-CH05 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3321 | PS5-25-DM-3100A-CH06 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3322 | PS5-25-DM-3100B-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3323 | PS5-25-DM-3100B-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3324 | PS5-25-DM-3100B-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3325 | PS5-25-DM-3100B-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3326 | PS5-25-DM-3100B-CH05 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3327 | PS5-25-DM-3100B-CH06 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3328 | PS5-25-DM-3100C-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3329 | PS5-25-DM-3100C-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3330 | PS5-25-DM-3100C-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3331 | PS5-25-DM-3100C-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3332 | PS5-25-DM-3100C-CH05 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3333 | PS5-25-DM-3100C-CH06 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0216 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00022-3334 | PS5-60-IJ-0001A-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100A TO PS5-60-IJ-0001A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-168 | 2026-03-06 | Accepted | Ferdinand | PULLING
T-00022-3335 | PS5-60-IJ-0001B-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100B TO PS5-60-IJ-0001B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-168 | 2026-03-06 | Accepted | Ferdinand | PULLING
T-00022-3336 | PS5-60-IJ-0001C-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100C TO PS5-60-IJ-0001C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-168 | 2026-03-06 | Accepted | Ferdinand | PULLING
T-00022-3337 | PS5-60-IJ-0001D-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100D TO PS5-60-IJ-0001D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-168 | 2026-03-06 | Accepted | Ferdinand | PULLING
T-00022-3338 | PS5-60-IJ-0001E-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100E TO PS5-60-IJ-0001E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-05-168 | 2026-03-06 | Accepted | Ferdinand | PULLING
T-00022-3339 | PS5-60-IJ-0001F-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100F TO PS5-60-IJ-0001F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-05-168 | 2026-03-06 | Accepted | Ferdinand | PULLING
T-00022-3340 | PS5-60-IJ-0001G-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100G TO PS5-60-IJ-0001G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-05-168 | 2026-03-05 | Accepted | Ferdinand | PULLING
T-00022-3341 | PS5-61-IDH-3100A-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3342 | PS5-61-IDH-3100A-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3343 | PS5-61-IDH-3100A-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3344 | PS5-61-IDH-3100A-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3345 | PS5-61-IDH-3100A-CH05 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3346 | PS5-61-IDH-3100A-CH06 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3347 | PS5-61-IDH-3100A-CH07 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3348 | PS5-61-IDH-3100A-CH08 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3349 | PS5-61-IDH-3100A-CH09 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3350 | PS5-61-IDH-3100A-CH10 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3351 | PS5-61-IDH-3100A-CH11 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3352 | PS5-61-IDH-3100A-CH12 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3353 | PS5-61-IDH-3100B-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3354 | PS5-61-IDH-3100B-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3355 | PS5-61-IDH-3100B-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3356 | PS5-61-IDH-3100B-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3357 | PS5-61-IDH-3100B-CH05 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3358 | PS5-61-IDH-3100B-CH06 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3359 | PS5-61-IDH-3100B-CH07 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3360 | PS5-61-IDH-3100B-CH08 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3361 | PS5-61-IDH-3100B-CH09 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3362 | PS5-61-IDH-3100B-CH10 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3363 | PS5-61-IDH-3100B-CH11 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3364 | PS5-61-IDH-3100B-CH12 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3365 | PS5-61-IDH-3100C-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3366 | PS5-61-IDH-3100C-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3367 | PS5-61-IDH-3100C-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3368 | PS5-61-IDH-3100C-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3369 | PS5-61-IDH-3100C-CH05 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3370 | PS5-61-IDH-3100C-CH06 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3371 | PS5-61-IDH-3100C-CH07 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3372 | PS5-61-IDH-3100C-CH08 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3373 | PS5-61-IDH-3100C-CH09 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3374 | PS5-61-IDH-3100C-CH10 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3375 | PS5-61-IDH-3100C-CH11 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3376 | PS5-61-IDH-3100C-CH12 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3377 | PS5-61-IJ-0001-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3378 | PS5-61-IJ-0001-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3379 | PS5-61-IJ-0001-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3380 | PS5-61-IJ-0001-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3381 | PS5-61-IJ-0001-CH05 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3382 | PS5-61-IJ-0001-CH06 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3383 | PS5-61-IJ-0001-CH07 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3384 | PS5-61-IJ-0001-CH08 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3385 | PS5-61-IJ-0001-CH09 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3386 | PS5-61-IJ-0001-CH10 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3387 | PS5-61-IJ-0001-CH11 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3388 | PS5-61-IJ-0001-CH12 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3389 | PS5-61-IJ-0001-CH13 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3390 | PS5-61-IJ-0001-CH14 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3391 | PS5-61-IJ-0001-CH15 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3392 | PS5-61-IJ-0001-CH16 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3393 | PS5-61-IJ-0001-CH17 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3394 | PS5-61-IJ-0001-CH18 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3395 | PS5-61-IJ-0001-CH19 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3396 | PS5-61-IJ-0001-CH20 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3397 | PS5-61-IJ-0001-CH21 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-05-0196 | 2026-03-31 | Accepted with Punch | Ferdinand | PULLING
T-00022-3398 | PS5-61-IJ-0010-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IJ-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-05-0198 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3399 | PS5-61-IJ-0010-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IJ-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-05-0198 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3400 | PS5-61-IJ-0010-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IJ-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-05-0198 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3401 | PS5-61-IJ-0011-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IJ-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-05-0198 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3402 | PS5-61-IJ-0011-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IJ-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-05-0198 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3403 | PS5-61-IJ-0011-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IJ-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-05-0198 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3404 | PS5-61-ISR-0101-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0101 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3405 | PS5-61-ISR-0101-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0101 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3406 | PS5-61-ISR-0101-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0101 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3407 | PS5-61-ISR-0102-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0102 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3408 | PS5-61-ISR-0102-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0102 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3409 | PS5-61-ISR-0102-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0102 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-03-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3410 | PS5-61-IU-0001A-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3411 | PS5-61-IU-0001A-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3412 | PS5-61-IU-0001A-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3413 | PS5-61-IU-0001B-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3414 | PS5-61-IU-0001B-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3415 | PS5-61-IU-0001B-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3416 | PS5-61-IU-0001C-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3417 | PS5-61-IU-0001C-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3418 | PS5-61-IU-0001C-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3419 | PS5-61-IU-0001D-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3420 | PS5-61-IU-0001D-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3421 | PS5-61-IU-0001D-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3422 | PS5-61-IU-0001E-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3423 | PS5-61-IU-0001E-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3424 | PS5-61-IU-0001E-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3425 | PS5-61-IU-0001F-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3426 | PS5-61-IU-0001F-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3427 | PS5-61-IU-0001F-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3428 | PS5-61-IU-0001G-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3429 | PS5-61-IU-0001G-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3430 | PS5-61-IU-0001G-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-05-161 | 2026-02-20 | Accepted with Punch | Ferdinand | PULLING
T-00022-3431 | PS5-61-IU-0010-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3432 | PS5-61-IU-0010-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3433 | PS5-61-IU-0010-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3434 | PS5-61-IU-0011-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3435 | PS5-61-IU-0011-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3436 | PS5-61-IU-0011-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3437 | PS5-61-IU-3100A-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-181 | 2026-03-18 | Accepted with Punch | Ferdinand | PULLING
T-00022-3438 | PS5-61-IU-3100A-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-181 | 2026-03-18 | Accepted with Punch | Ferdinand | PULLING
T-00022-3439 | PS5-61-IU-3100A-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-181 | 2026-03-18 | Accepted with Punch | Ferdinand | PULLING
T-00022-3440 | PS5-61-IU-3100A-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0006A TO PS5-61-IU-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3441 | PS5-61-IU-3100B-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-181 | 2026-03-18 | Accepted with Punch | Ferdinand | PULLING
T-00022-3442 | PS5-61-IU-3100B-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-181 | 2026-03-18 | Accepted with Punch | Ferdinand | PULLING
T-00022-3443 | PS5-61-IU-3100B-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-181 | 2026-03-18 | Accepted with Punch | Ferdinand | PULLING
T-00022-3444 | PS5-61-IU-3100B-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0006B TO PS5-61-IU-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3445 | PS5-61-IU-3100C-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-181 | 2026-03-18 | Accepted with Punch | Ferdinand | PULLING
T-00022-3446 | PS5-61-IU-3100C-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-181 | 2026-03-18 | Accepted with Punch | Ferdinand | PULLING
T-00022-3447 | PS5-61-IU-3100C-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-181 | 2026-03-18 | Accepted with Punch | Ferdinand | PULLING
T-00022-3448 | PS5-61-IU-3100C-CH04 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0006C TO PS5-61-IU-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0192 | 2026-03-28 | Accepted with Punch | Elizabeth | PULLING
T-00022-3449 | PS5-61-IV-0001A-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001A |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3450 | PS5-61-IV-0001A-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001A |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3451 | PS5-61-IV-0001A-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001A |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3452 | PS5-61-IV-0001B-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001B |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3453 | PS5-61-IV-0001B-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001B |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3454 | PS5-61-IV-0001B-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001B |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3455 | PS5-61-IV-0002A-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002A |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3456 | PS5-61-IV-0002A-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002A |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3457 | PS5-61-IV-0002A-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002A |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3458 | PS5-61-IV-0002B-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002B |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3459 | PS5-61-IV-0002B-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002B |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3460 | PS5-61-IV-0002B-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002B |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3461 | PS5-61-IV-0005A-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005A |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00022-3462 | PS5-61-IV-0005A-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005A |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00022-3463 | PS5-61-IV-0005A-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005A |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00022-3464 | PS5-61-IV-0005B-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005B |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00022-3465 | PS5-61-IV-0005B-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005B |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00022-3466 | PS5-61-IV-0005B-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005B |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00022-3467 | PS5-61-IV-0007A-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007A |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3468 | PS5-61-IV-0007A-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007A |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3469 | PS5-61-IV-0007A-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007A |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3470 | PS5-61-IV-0007B-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007B |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3471 | PS5-61-IV-0007B-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007B |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3472 | PS5-61-IV-0007B-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007B |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0184 | 2026-03-22 | Accepted with Punch | Ferdinand | PULLING
T-00022-3473 | PS5-61-NER-0010-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-NER-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00022-3474 | PS5-61-NER-0011-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-NER-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00022-3475 | PS5-63-IV-0010-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0010 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3476 | PS5-63-IV-0010-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0010 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3477 | PS5-63-IV-0010-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0010 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3478 | PS5-63-IV-0011-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0011 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3479 | PS5-63-IV-0011-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0011 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3480 | PS5-63-IV-0011-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0011 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted with Punch | Ferdinand | PULLING
T-00022-3481 | PS5-63-NER-0010-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-63-IV-0010 TO PS5-63-NER-0010 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0210 | 2026-04-11 | HOLD BY EACOP | Bertus Wikael | PULLING
T-00022-3482 | PS5-63-NER-0011-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-63-IV-0011 TO PS5-63-NER-0011 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0210 | 2026-04-11 | HOLD BY EACOP | Bertus Wikael | PULLING
T-00022-3483 | PS5-79-BH-0001-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0010 TO PS5-79-BH-0001 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
| PS5-08-01FB-0913-CS01 | CPX08 | #N/A | E | PS5-08-01FB-0913 |  |  | CPP-RFI-68-331-05-0210 | 2026-06-03 | HOLD BY EACOP | Bertus Wikael | Pulling
| PS5-08-01FB-0913-CS02 | CPX08 | #N/A | E | PS5-08-13CB-1001 |  |  | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
| PS5-08-01FB-1013-CS02 | CPX08 | #N/A | E | PS5-08-13CB-1001 |  |  | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
| PS5-08-01FB-1101-CS01 | CPX08 | #N/A | E | PS5-08-01FB-1101 |  |  | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
| PS5-08-01FB-1106-CS01 | CPX08 | #N/A | E | PS5-08-01FB-1106 |  |  | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-03FB-0101-CS01 | CPX08 | #N/A | E | PS5-08-03FB-0101 | [11 empty] | CABLE NOT FOUND AT SITE
| PS5-08-52BT-0138-CS01 | CPX08 | #N/A | E | PS5-08-52BT-0138 |  |  | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00022-3484 | PS5-79-BH-0001-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0010 TO PS5-79-BH-0001 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00022-3485 | PS5-79-BH-0001-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0010 TO PS5-79-BH-0001 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00022-3486 | PS5-79-BH-0002-CH01 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0011 TO PS5-79-BH-0002 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00022-3487 | PS5-79-BH-0002-CH02 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0011 TO PS5-79-BH-0002 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00022-3488 | PS5-79-BH-0002-CH03 | CPX08 - HV Power Cable | #N/A | E | Cable FROM PS5-61-IJ-0011 TO PS5-79-BH-0002 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00023-10060 | PS5-62-IE-0001-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10061 | PS5-62-IE-0001-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10062 | PS5-62-IE-0001-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10063 | PS5-62-IE-0001-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10064 | PS5-62-IE-0001-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10065 | PS5-62-IE-0001-CL51 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10066 | PS5-62-IE-0001-CL52 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10067 | PS5-62-IE-0001-CL53 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10068 | PS5-62-IE-0001-CL54 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10069 | PS5-62-IE-0001-CL55 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10070 | PS5-62-IE-0001-CL56 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10071 | PS5-62-IE-0001-CL57 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10072 | PS5-62-IE-0001-CL58 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10073 | PS5-62-IE-0001-CL59 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00023-10074 | PS5-62-IE-0002-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10075 | PS5-62-IE-0002-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10076 | PS5-62-IE-0002-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10077 | PS5-62-IE-0002-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10078 | PS5-62-IE-0002-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10079 | PS5-62-IE-0002-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10080 | PS5-62-IE-0002-CL52 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10081 | PS5-62-IE-0002-CL53 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10082 | PS5-62-IE-0002-CL54 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10083 | PS5-62-IE-0002-CL55 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10084 | PS5-62-IE-0002-CL56 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10085 | PS5-62-IE-0002-CL57 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10086 | PS5-62-IE-0002-CL58 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10087 | PS5-62-IE-0002-CL59 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10088 | PS5-62-IE-0002-CL60 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00023-10535 | PS5-06-GB-0003-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building
T-00023-10536 | PS5-60-IN-0002A-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00023-10537 | PS5-60-IN-0002B-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00023-10538 | PS5-60-IN-0002C-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00023-10539 | PS5-60-IN-0002D-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00023-10540 | PS5-60-IN-0002E-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00023-10541 | PS5-60-IN-0002F-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00023-10542 | PS5-60-IN-0002G-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00023-10584 | PS5-05-BE-0001-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00023-10585 | PS5-06-IG-0004A-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-IG-0004A |  | PS5-06-02 - AC UPS - Power Generator Building
T-00023-10586 | PS5-06-IG-0004B-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003B TO PS5-06-IG-0004B |  | PS5-06-02 - AC UPS - Power Generator Building
T-00023-10587 | PS5-25-DM-3100A-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-10588 | PS5-25-DM-3100A-CG02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-10589 | PS5-25-DM-3100B-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00023-10590 | PS5-25-DM-3100B-CG02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00023-10591 | PS5-25-DM-3100C-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00023-10592 | PS5-25-DM-3100C-CG02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00023-10593 | PS5-60-IH-0001A-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs
T-00023-10594 | PS5-60-IH-0001B-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs
T-00023-10595 | PS5-60-IH-0001C-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs
T-00023-10596 | PS5-60-IH-0001D-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs
T-00023-10597 | PS5-60-IH-0001E-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00023-10598 | PS5-60-IH-0001F-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00023-10599 | PS5-60-IH-0001G-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00023-10600 | PS5-60-IH-0002-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-10601 | PS5-60-IH-0002-CG02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-10602 | PS5-61-IH-0004-CG01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-10603 | PS5-61-IH-0004-CG02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-10604 | PS5-61-IH-0004-CG03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-10605 | PS5-61-IH-0004-CG04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-10616 | PS5-61-IK-0003-CG07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00023-10886 | PS5-28-DM-31100-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-28-ISO-2008 TO PS5-28-DM-31100 |  | PS5-28-10 - Oil Skimmer Package
T-00023-10887 | PS5-60-BE-0007A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-10888 | PS5-60-BE-0007A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-10889 | PS5-60-BE-0007B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-10890 | PS5-60-BE-0007B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-10891 | PS5-60-BE-0007C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-10892 | PS5-60-BE-0007C-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-10893 | PS5-60-BE-0007D-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING
T-00023-10894 | PS5-60-BE-0007D-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING
T-00023-10895 | PS5-60-BE-0007E-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-10896 | PS5-60-BE-0007E-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-10897 | PS5-60-BE-0007F-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-10898 | PS5-60-BE-0007F-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-10899 | PS5-60-BE-0007G-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-10900 | PS5-60-BE-0007G-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-10901 | PS5-60-ISO-62800A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-ISO-62800A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-10902 | PS5-60-ISO-62800C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-ISO-62800C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs
T-00023-10903 | PS5-60-ISO-62800E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-ISO-62800E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-10904 | PS5-60-ISO-62800G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-ISO-62800G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00023-4695 | PS5-01-BE-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-01-BE-0001 |  | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-4696 | PS5-01-FCV-0003A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-01-FCV-0003A |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4697 | PS5-01-FCV-0003B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-01-FCV-0003B |  | PS5-01-03 - Fire Water Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4698 | PS5-01-FCV-0004A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-01-FCV-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4699 | PS5-01-FCV-0004B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-01-FCV-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4710 | PS5-01-IG-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-01-IG-0001 |  | PS5-01-10 - Water Mist Package
T-00023-4711 | PS5-01-LB-0004-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-01-LB-0004 |  | PS5-01-11 - Inergen for Power Gen Building
T-00023-4712 | PS5-01-LB-0004-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-01-LB-0004 |  | PS5-01-11 - Inergen for Power Gen Building
T-00023-4713 | PS5-01-LB-0004-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-01-LB-0004 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-4714 | PS5-01-MOV-8701-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-01-MOV-8701 |  | PS5-01-05 - Foam Skid
T-00023-4724 | PS5-03-SEA-0002-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0006 TO PS5-03-SEA-0002 |  | PS5-03-22 - FZ-G1 - Guard House
T-00023-4725 | PS5-03-SEA-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-03-SEA-0003 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00023-4727 | PS5-05-BE-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-4728 | PS5-05-BE-0001-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-4729 | PS5-05-BE-0001-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-4730 | PS5-05-BE-0001-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-4731 | PS5-05-BE-0001-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-4732 | PS5-05-BE-0001-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-4733 | PS5-05-BE-0001-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
| PS5-08-01FB-1106-CS02 | CPX09 - LV Power Cable | #N/A | E |  |  | PS5-08-01 | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-4734 | PS5-05-BE-0001-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-4735 | PS5-05-BE-0001-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-4736 | PS5-05-BE-0001-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-4737 | PS5-05-BE-0001-CL11 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-4738 | PS5-05-IE-8100-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP)
T-00023-4739 | PS5-05-IE-8100-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP)
T-00023-4742 | PS5-05-IG-0009-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IG-0009 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4743 | PS5-05-IG-0009-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-05-IG-0009 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4744 | PS5-05-IG-0025-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IG-0025 |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | CPP-RFI-68-33/1-05-0309 | 2026-06-04 | Accepted With Commend | Ferdinand | Pulling
T-00023-4745 | PS5-05-IG-0026-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IG-0026 |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | CPP-RFI-68-33/1-05-0309 | 2026-06-04 | Accepted With Commend | Ferdinand | Pulling
T-00023-4746 | PS5-06-GB-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4747 | PS5-06-GB-0003-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4748 | PS5-06-GB-0003-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4749 | PS5-06-GB-0003-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4750 | PS5-06-GB-0003-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4751 | PS5-06-GB-0003-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4752 | PS5-06-GU-0003A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-06-GU-0003A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4753 | PS5-06-GU-0003B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-06-GU-0003B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4754 | PS5-06-GU-0003C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-06-GU-0003C |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4756 | PS5-06-IG-0004A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-IG-0004A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4757 | PS5-06-IG-0004A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-IG-0004A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4758 | PS5-06-IG-0004A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-IG-0004A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4759 | PS5-06-IG-0004A-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-IG-0004A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4761 | PS5-06-IG-0004B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003B TO PS5-06-IG-0004B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4762 | PS5-06-IG-0004B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003B TO PS5-06-IG-0004B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4763 | PS5-06-IG-0004B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003B TO PS5-06-IG-0004B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4764 | PS5-06-IG-0004B-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-GU-0003B TO PS5-06-IG-0004B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-05-0298 | 2026-05-25 | Rejected | Ferdinand | PULLING
T-00023-4808 | PS5-08-11CB-1501-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0006 TO PS5-08-11CB-1501 |  | PS5-08-11 - Corporate LAN (SIE)
T-00023-4809 | PS5-08-11CB-1901-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-08-11CB-1901 |  | PS5-08-11 - Corporate LAN (SIE)
T-00023-4810 | PS5-08-11CB-1901-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-08-11CB-1901 |  | PS5-08-11 - Corporate LAN (SIE)
T-00023-4811 | PS5-08-11CB-1901-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-08-11CB-1901 |  | PS5-08-11 - Corporate LAN (SIE)
T-00023-4878 | PS5-09-LB-0008-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building
T-00023-4879 | PS5-09-LB-0008-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building
| PS5-08-01FB-0901-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-01FB-0901 |  | PAGA Flashing Beacon | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-01FB-1001-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-01FB-1001 |  | PAGA Flashing Beacon | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-03FB-0001-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-03FB-0001 |  | TELEPHONE WITH BEACON/SOUNDER | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-03FB-0002-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-03FB-0002 |  | TELEPHONE WITH BEACON/SOUNDER | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-03FB-0103-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-03FB-0103 |  | TELEPHONE WITH BEACON/SOUNDER | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-06-IG-0004A-CD01 | TPX | #N/A | E | [12 empty] | Cable not found
| PS5-08-01FB-0901-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING |  |  |  |  | Cable not found
| PS5-08-03FB-0001-CS01 | TPX | #N/A | E | [12 empty] | Cable not found
| PS5-08-12BT-0001-CS01 | TPX | #N/A | E | [12 empty] | Cable not found
| PS5-08-52BT-0139-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing |  |  |  |  | Cable not found
| PS5-08-85CP-0024-CS01 | TPX | #N/A | E | [12 empty] | Cable not found
| PS5-08-85CP-0025-CS01 | TPX | #N/A | E | [12 empty] | Cable not found
| PS5-08-12BT-0001-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-12BT-0001 |  | WAP JUNCTION BOX-1 | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-12BT-0104-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-12BT-0104 |  | WAP JUNCTION BOX-4 | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-12BT-0105-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-12BT-0105 |  | WAP JUNCTION BOX-5 | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-12BT-0106-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-12BT-0106 |  | WAP JUNCTION BOX-6 | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-15CP-0002-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-15CP-0002 |  | Control Panel-2 | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-52BT-0132-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-52BT-0132 |  | JUNCTION BOX PTZ CAMERA-6 | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-52BT-0133-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-52BT-0133 |  | JUNCTION BOX PTZ CAMERA-7 | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-52BT-0139-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-52BT-0139 |  | JUNCTION BOX PTZ CAMERA-13 | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-85CP-0024-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-85CP-0024 |  | CONTROL PANEL POB-1 | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-85CP-0025-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-85CP-0025 |  | CONTROL PANEL POB-2 | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4882 | PS5-25-DM-3100A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4883 | PS5-25-DM-3100A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0014 TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4886 | PS5-25-DM-3100B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4887 | PS5-25-DM-3100B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0014 TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4890 | PS5-25-DM-3100C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4891 | PS5-25-DM-3100C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0014 TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4904 | PS5-25-ESDV-0021-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4905 | PS5-25-ESDV-0023-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-ESDV-0023 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4906 | PS5-25-FCV-0003A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-FCV-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4907 | PS5-25-FCV-0003B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-FCV-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4908 | PS5-25-FCV-0003C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-FCV-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4909 | PS5-25-FCV-0004-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-FCV-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00023-4918 | PS5-25-MOV-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4919 | PS5-25-MOV-0002-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0002 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4920 | PS5-25-MOV-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0003 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4921 | PS5-25-MOV-0008-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-MOV-0008 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4922 | PS5-25-MOV-0011-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0011 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4923 | PS5-25-MOV-0012-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0012 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4924 | PS5-25-MOV-0025-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0025 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4925 | PS5-25-MOV-0026-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0026 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4926 | PS5-25-MOV-0027-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-MOV-0027 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4927 | PS5-25-MOV-0028-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0028 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4928 | PS5-25-SDV-0022-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4929 | PS5-25-SDV-0035A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4930 | PS5-25-SDV-0035B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4931 | PS5-25-SDV-0035C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4932 | PS5-25-SDV-0036A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4933 | PS5-25-SDV-0036B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4934 | PS5-25-SDV-0036C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4935 | PS5-25-SDV-0046-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4936 | PS5-25-SDV-0052-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0052 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-52BT-0135-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-11CB-1901 TO PS5-08-52BT-0135 |  | JUNCTION BOX PTZ CAMERA-9 | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-52BT-0140-CS01 | CPX09 - LV Power Cable | #N/A | E | PS5-08-11CB-1901 TO PS5-08-52BT-0140 |  | JUNCTION BOX PTZ CAMERA-14 | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4937 | PS5-25-SDV-0054A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4938 | PS5-25-SDV-0054B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4939 | PS5-25-SDV-0054C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4941 | PS5-25-XV-0053-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-331-05-0210 | 2026-06-03 | HOLD BY EACOP | Bertus Wikael | Pulling
T-00023-4942 | PS5-25-XV-0070-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-XV-0070 |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00023-4944 | PS5-28-BE-0002A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-28-BE-0002A |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-331-05-0238 | 2026-04-30 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4946 | PS5-28-BE-0002B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-28-BE-0002B |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-331-05-0238 | 2026-04-30 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-52BT-0134-CS01 | CPX09LV Cable | #N/A | E | Cbale FROM PS5-08-11CB-1901 TO PS5-08-52BT-0134 |  | NA | CPP-RFI-68-331-05-0238 | 2026-04-30 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4962 | PS5-28-HE-2100-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-28-HE-2100 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-331-05-0238 | 2026-04-30 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4964 | PS5-28-HE-2200-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-28-HE-2200 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-4966 | PS5-28-LB-8200-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-28-LB-8200 |  | PS5-28-11 - Open Drain Interceptor | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-4967 | PS5-28-SDV-0045-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump
T-00023-4968 | PS5-28-SDV-0053A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4969 | PS5-28-SDV-0053B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPP-RFI-68-331-05-0239 | 30-April-20206 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4970 | PS5-28-SDV-0053C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPP-RFI-68-331-05-0238 | 2026-04-30 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-4978 | PS5-60-BE-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 |  | PS5-60-27 - Compressed Air Starting Skid | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-4979 | PS5-60-BE-0001-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 |  | PS5-60-27 - Compressed Air Starting Skid | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-4981 | PS5-60-BE-0001-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0001 |  | PS5-60-27 - Compressed Air Starting Skid | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-4982 | PS5-60-BE-0002-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 |  | PS5-60-26 - Instrument Air Compressor Skid | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-4983 | PS5-60-BE-0002-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 |  | PS5-60-26 - Instrument Air Compressor Skid | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-4984 | PS5-60-BE-0002-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 |  | PS5-60-26 - Instrument Air Compressor Skid | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-4986 | PS5-60-BE-0002-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0002 |  | PS5-60-26 - Instrument Air Compressor Skid | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-4987 | PS5-60-BE-0003A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-4988 | PS5-60-BE-0003B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-4989 | PS5-60-BE-0003C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0003C |  | PS5-60-07 - Power Generation Package C
T-00023-4990 | PS5-60-BE-0003D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0003D |  | PS5-60-10 - Power Generation Package D
T-00023-4991 | PS5-60-BE-0003E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0003E |  | PS5-60-13 - Power Generation Package E
T-00023-4992 | PS5-60-BE-0003F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0003F |  | PS5-60-16 - Power Generation Package F
T-00023-4993 | PS5-60-BE-0003G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0003G |  | PS5-60-19 - Power Generation Package G
T-00023-4994 | PS5-60-BE-0004A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0004A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A
T-00023-4995 | PS5-60-BE-0004B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0004B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B
T-00023-4996 | PS5-60-BE-0004C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0004C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C
T-00023-4997 | PS5-60-BE-0004D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0004D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D
T-00023-4998 | PS5-60-BE-0004E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0004E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E
T-00023-4999 | PS5-60-BE-0004F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0004F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F
T-00023-5000 | PS5-60-BE-0004G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0004G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G
T-00023-5001 | PS5-60-BE-0005A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0005A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING
T-00023-5002 | PS5-60-BE-0005B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0005B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING
T-00023-5003 | PS5-60-BE-0005C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0005C |  | PS5-60-07 - Power Generation Package C
T-00023-5004 | PS5-60-BE-0005D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0005D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5005 | PS5-60-BE-0005E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0005E |  | PS5-60-13 - Power Generation Package E
T-00023-5006 | PS5-60-BE-0005F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0005F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5007 | PS5-60-BE-0005G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0005G |  | PS5-60-19 - Power Generation Package G
T-00023-5008 | PS5-60-BE-0011A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5009 | PS5-60-BE-0011A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5010 | PS5-60-BE-0011A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5011 | PS5-60-BE-0011A-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5012 | PS5-60-BE-0011A-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5013 | PS5-60-BE-0011A-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5014 | PS5-60-BE-0011B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5015 | PS5-60-BE-0011B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5016 | PS5-60-BE-0011B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5017 | PS5-60-BE-0011B-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5018 | PS5-60-BE-0011B-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5019 | PS5-60-BE-0011B-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5020 | PS5-60-BE-0012A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5021 | PS5-60-BE-0012A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5022 | PS5-60-BE-0012A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5023 | PS5-60-BE-0012A-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5024 | PS5-60-BE-0012A-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5025 | PS5-60-BE-0012A-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5026 | PS5-60-BE-0012B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5027 | PS5-60-BE-0012B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5028 | PS5-60-BE-0012B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5029 | PS5-60-BE-0012B-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5030 | PS5-60-BE-0012B-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5031 | PS5-60-BE-0012B-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00023-5032 | PS5-60-BE-0013A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C
T-00023-5033 | PS5-60-BE-0013A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C
T-00023-5034 | PS5-60-BE-0013A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C
T-00023-5035 | PS5-60-BE-0013A-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C
T-00023-5036 | PS5-60-BE-0013A-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C
T-00023-5037 | PS5-60-BE-0013A-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C
T-00023-5038 | PS5-60-BE-0013B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C
T-00023-5039 | PS5-60-BE-0013B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C
T-00023-5040 | PS5-60-BE-0013B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C
T-00023-5041 | PS5-60-BE-0013B-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C
T-00023-5042 | PS5-60-BE-0013B-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C
T-00023-5043 | PS5-60-BE-0013B-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C
T-00023-5044 | PS5-60-BE-0014A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D
T-00023-5045 | PS5-60-BE-0014A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D
T-00023-5046 | PS5-60-BE-0014A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D
T-00023-5047 | PS5-60-BE-0014A-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D
T-00023-5048 | PS5-60-BE-0014A-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D
T-00023-5049 | PS5-60-BE-0014A-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D
T-00023-5050 | PS5-60-BE-0014B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D
T-00023-5051 | PS5-60-BE-0014B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D
T-00023-5052 | PS5-60-BE-0014B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D
T-00023-5053 | PS5-60-BE-0014B-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D
T-00023-5054 | PS5-60-BE-0014B-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D
T-00023-5055 | PS5-60-BE-0014B-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D
T-00023-5056 | PS5-60-BE-0015A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E
T-00023-5057 | PS5-60-BE-0015A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E
T-00023-5058 | PS5-60-BE-0015A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E
T-00023-5059 | PS5-60-BE-0015A-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E
T-00023-5060 | PS5-60-BE-0015A-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E
T-00023-5061 | PS5-60-BE-0015A-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E
T-00023-5062 | PS5-60-BE-0015B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E
T-00023-5063 | PS5-60-BE-0015B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E
T-00023-5064 | PS5-60-BE-0015B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E
T-00023-5065 | PS5-60-BE-0015B-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E
T-00023-5066 | PS5-60-BE-0015B-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E
T-00023-5067 | PS5-60-BE-0015B-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E
T-00023-5068 | PS5-60-BE-0016A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F
T-00023-5069 | PS5-60-BE-0016A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F
T-00023-5070 | PS5-60-BE-0016A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F
T-00023-5071 | PS5-60-BE-0016A-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F
T-00023-5072 | PS5-60-BE-0016A-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F
T-00023-5073 | PS5-60-BE-0016A-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F
T-00023-5074 | PS5-60-BE-0016B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F
T-00023-5075 | PS5-60-BE-0016B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F
T-00023-5076 | PS5-60-BE-0016B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F
T-00023-5077 | PS5-60-BE-0016B-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F
T-00023-5078 | PS5-60-BE-0016B-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F
T-00023-5079 | PS5-60-BE-0016B-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F
T-00023-5080 | PS5-60-BE-0017A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G
T-00023-5081 | PS5-60-BE-0017A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G
T-00023-5082 | PS5-60-BE-0017A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G
T-00023-5083 | PS5-60-BE-0017A-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G
T-00023-5084 | PS5-60-BE-0017A-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G
T-00023-5085 | PS5-60-BE-0017A-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G
T-00023-5086 | PS5-60-BE-0017B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G
T-00023-5087 | PS5-60-BE-0017B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G
T-00023-5088 | PS5-60-BE-0017B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G
T-00023-5089 | PS5-60-BE-0017B-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G
T-00023-5090 | PS5-60-BE-0017B-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G
T-00023-5091 | PS5-60-BE-0017B-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G
T-00023-5092 | PS5-60-BE-0021A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021A |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0309 | 2026-06-04 | Accepted With Commend | Ferdinand | Pulling
T-00023-5093 | PS5-60-BE-0021B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021B |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5094 | PS5-60-BE-0024A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A |  | PS5-60-35 - Injector Tip Cooling Module A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling
T-00023-5095 | PS5-60-BE-0024A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A |  | PS5-60-35 - Injector Tip Cooling Module A | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling
T-00023-5096 | PS5-60-BE-0024B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B |  | PS5-60-36 - Injector Tip Cooling Module B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling
T-00023-5097 | PS5-60-BE-0024B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B |  | PS5-60-36 - Injector Tip Cooling Module B | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling
T-00023-5098 | PS5-60-BE-0024C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C |  | PS5-60-37 - Injector Tip Cooling Module C | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5099 | PS5-60-BE-0024C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C |  | PS5-60-37 - Injector Tip Cooling Module C | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5100 | PS5-60-BE-0024D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D |  | PS5-60-38 - Injector Tip Cooling Module D | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling
T-00023-5101 | PS5-60-BE-0024D-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D |  | PS5-60-38 - Injector Tip Cooling Module D | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling
T-00023-5102 | PS5-60-BE-0024E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0024E |  | PS5-60-39 - Injector Tip Cooling Module E
T-00023-5103 | PS5-60-BE-0024E-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0024E |  | PS5-60-39 - Injector Tip Cooling Module E | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5104 | PS5-60-BE-0024F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0024F |  | PS5-60-40 - Injector Tip Cooling Module F
T-00023-5105 | PS5-60-BE-0024F-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0024F |  | PS5-60-40 - Injector Tip Cooling Module F | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5106 | PS5-60-BE-0024G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0024G |  | PS5-60-41 - Injector Tip Cooling Module G | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5107 | PS5-60-BE-0024G-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0024G |  | PS5-60-41 - Injector Tip Cooling Module G
T-00023-5108 | PS5-60-BE-0025A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0025A |  | PS5-60-35 - Injector Tip Cooling Module A | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5109 | PS5-60-BE-0025B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0025B |  | PS5-60-36 - Injector Tip Cooling Module B | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5110 | PS5-60-BE-0025C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0025C |  | PS5-60-37 - Injector Tip Cooling Module C | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5111 | PS5-60-BE-0025D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0025D |  | PS5-60-38 - Injector Tip Cooling Module D | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5112 | PS5-60-BE-0025E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0025E |  | PS5-60-39 - Injector Tip Cooling Module E
T-00023-5113 | PS5-60-BE-0025F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0025F |  | PS5-60-40 - Injector Tip Cooling Module F
T-00023-5114 | PS5-60-BE-0025G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0025G |  | PS5-60-41 - Injector Tip Cooling Module G | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5115 | PS5-60-BE-0026A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A |  | PS5-60-70 - Engine A Cooling system | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5116 | PS5-60-BE-0026A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A |  | PS5-60-70 - Engine A Cooling system | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5117 | PS5-60-BE-0026B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B |  | PS5-60-71 - Engine B Cooling system | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5118 | PS5-60-BE-0026B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B |  | PS5-60-71 - Engine B Cooling system | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5119 | PS5-60-BE-0026C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C |  | PS5-60-72 - Engine C Cooling system | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5120 | PS5-60-BE-0026C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C |  | PS5-60-72 - Engine C Cooling system | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5121 | PS5-60-BE-0026D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D |  | PS5-60-73 - Engine D Cooling system | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling
T-00023-5122 | PS5-60-BE-0026D-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D |  | PS5-60-73 - Engine D Cooling system | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling
T-00023-5123 | PS5-60-BE-0026E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0026E |  | PS5-60-74 - Engine E Cooling system
T-00023-5124 | PS5-60-BE-0026E-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0026E |  | PS5-60-74 - Engine E Cooling system | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling
T-00023-5125 | PS5-60-BE-0026F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0026F |  | PS5-60-75 - Engine F Cooling system
T-00023-5126 | PS5-60-BE-0026F-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0026F |  | PS5-60-75 - Engine F Cooling system | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling
T-00023-5127 | PS5-60-BE-0026G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0026G |  | PS5-60-76 - Engine G Cooling system | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5128 | PS5-60-BE-0026G-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0026G |  | PS5-60-76 - Engine G Cooling system | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5129 | PS5-60-BI-0005A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0005A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
| PS5-08-01FB-0902-CS01 | CPX09 - LV Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
| PS5-08-01FB-0904-CS01 | CPX09 - LV Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
| PS5-08-01FB-1007-CS01 | CPX09 - LV Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
| PS5-08-01FB-1010-CS01 | CPX09 - LV Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
| PS5-08-01FB-1105-CS01 | CPX09 - LV Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5130 | PS5-60-BI-0005B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0005B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5131 | PS5-60-BI-0005C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0005C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5132 | PS5-60-BI-0005D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0005D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5133 | PS5-60-BI-0005E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0005E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5134 | PS5-60-BI-0005F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0005F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5135 | PS5-60-BI-0005G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0005G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5136 | PS5-60-BI-0015A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0438 | 28-July-2026 | Open | Ferdinand | Pulling
T-00023-5137 | PS5-60-BI-0015A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5138 | PS5-60-BI-0015A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5139 | PS5-60-BI-0015B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0438 | 28-July-2026 | Open | Ferdinand | Pulling
T-00023-5140 | PS5-60-BI-0015B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5141 | PS5-60-BI-0015B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5142 | PS5-60-BI-0015C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C |  | PS5-60-07 - Power Generation Package C
T-00023-5143 | PS5-60-BI-0015C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C |  | PS5-60-07 - Power Generation Package C
T-00023-5144 | PS5-60-BI-0015C-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C |  | PS5-60-07 - Power Generation Package C
T-00023-5145 | PS5-60-BI-0015D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D |  | PS5-60-10 - Power Generation Package D
T-00023-5146 | PS5-60-BI-0015D-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5147 | PS5-60-BI-0015D-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5148 | PS5-60-BI-0015E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E |  | PS5-60-13 - Power Generation Package E
T-00023-5149 | PS5-60-BI-0015E-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E |  | PS5-60-13 - Power Generation Package E
T-00023-5150 | PS5-60-BI-0015E-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E |  | PS5-60-13 - Power Generation Package E
T-00023-5151 | PS5-60-BI-0015F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F |  | PS5-60-16 - Power Generation Package F
T-00023-5152 | PS5-60-BI-0015F-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F |  | PS5-60-16 - Power Generation Package F
T-00023-5153 | PS5-60-BI-0015F-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F |  | PS5-60-16 - Power Generation Package F
T-00023-5154 | PS5-60-BI-0015G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G |  | PS5-60-19 - Power Generation Package G
T-00023-5155 | PS5-60-BI-0015G-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G |  | PS5-60-19 - Power Generation Package G
T-00023-5156 | PS5-60-BI-0015G-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G |  | PS5-60-19 - Power Generation Package G
T-00023-5157 | PS5-60-DD-62800A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-DD-62800A |  | PS5-60-01 - Power Generation Package A
T-00023-5159 | PS5-60-DD-62800C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-DD-62800C |  | PS5-60-07 - Power Generation Package C
T-00023-5161 | PS5-60-DD-62800E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-DD-62800E |  | PS5-60-13 - Power Generation Package E
T-00023-5163 | PS5-60-DD-62800G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-DD-62800G |  | PS5-60-19 - Power Generation Package G
T-00023-5166 | PS5-60-IE-0002A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5167 | PS5-60-IE-0002A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5168 | PS5-60-IE-0002A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5169 | PS5-60-IE-0002B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0309 | 2026-06-04 | Accepted With Commend | Ferdinand | Pulling
T-00023-5170 | PS5-60-IE-0002B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00023-5171 | PS5-60-IE-0002B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5172 | PS5-60-IE-0002C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C
T-00023-5173 | PS5-60-IE-0002C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5174 | PS5-60-IE-0002C-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C
T-00023-5175 | PS5-60-IE-0002D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5176 | PS5-60-IE-0002D-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5177 | PS5-60-IE-0002D-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D
T-00023-5178 | PS5-60-IE-0002E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5179 | PS5-60-IE-0002E-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5180 | PS5-60-IE-0002E-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E
T-00023-5181 | PS5-60-IE-0002F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F
T-00023-5182 | PS5-60-IE-0002F-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F
T-00023-5183 | PS5-60-IE-0002F-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F
T-00023-5184 | PS5-60-IE-0002G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G
T-00023-5185 | PS5-60-IE-0002G-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G
T-00023-5186 | PS5-60-IE-0002G-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G
T-00023-5187 | PS5-60-IE-0003A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5188 | PS5-60-IE-0003A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5189 | PS5-60-IE-0003B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5190 | PS5-60-IE-0003B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5191 | PS5-60-IE-0003C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00023-5192 | PS5-60-IE-0003C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00023-5193 | PS5-60-IE-0003D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00023-5194 | PS5-60-IE-0003D-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5195 | PS5-60-IE-0003E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00023-5196 | PS5-60-IE-0003E-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00023-5197 | PS5-60-IE-0003F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00023-5198 | PS5-60-IE-0003F-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00023-5199 | PS5-60-IE-0003G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00023-5200 | PS5-60-IE-0003G-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00023-5201 | PS5-60-IE-0004-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5202 | PS5-60-IE-0004-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5204 | PS5-60-IH-0001A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00023-5205 | PS5-60-IH-0001A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
| PS5-08-01FB-1102-CS01 | CPX09 - LV Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-01FB-1103-CS01 | CPX09 - LV Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-08-01FB-1104-CS01 | CPX09 - LV Power Cable | #N/A | E
| PS5-08-03FB-1903-CS01 | CPX09 - LV Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5206 | PS5-60-IH-0001A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00023-5207 | PS5-60-IH-0001A-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00023-5208 | PS5-60-IH-0001A-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5209 | PS5-60-IH-0001A-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5211 | PS5-60-IH-0001B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00023-5212 | PS5-60-IH-0001B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00023-5213 | PS5-60-IH-0001B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00023-5214 | PS5-60-IH-0001B-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00023-5215 | PS5-60-IH-0001B-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5216 | PS5-60-IH-0001B-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5218 | PS5-60-IH-0001C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5219 | PS5-60-IH-0001C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5220 | PS5-60-IH-0001C-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5221 | PS5-60-IH-0001C-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5222 | PS5-60-IH-0001C-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs
T-00023-5223 | PS5-60-IH-0001C-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs
T-00023-5225 | PS5-60-IH-0001D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs
T-00023-5226 | PS5-60-IH-0001D-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs
T-00023-5227 | PS5-60-IH-0001D-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs
T-00023-5228 | PS5-60-IH-0001D-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs
T-00023-5229 | PS5-60-IH-0001D-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5230 | PS5-60-IH-0001D-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs
T-00023-5232 | PS5-60-IH-0001E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00023-5233 | PS5-60-IH-0001E-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00023-5234 | PS5-60-IH-0001E-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00023-5235 | PS5-60-IH-0001E-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00023-5236 | PS5-60-IH-0001E-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00023-5237 | PS5-60-IH-0001E-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00023-5239 | PS5-60-IH-0001F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00023-5240 | PS5-60-IH-0001F-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00023-5241 | PS5-60-IH-0001F-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00023-5242 | PS5-60-IH-0001F-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00023-5243 | PS5-60-IH-0001F-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00023-5244 | PS5-60-IH-0001F-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00023-5246 | PS5-60-IH-0001G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00023-5247 | PS5-60-IH-0001G-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00023-5248 | PS5-60-IH-0001G-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00023-5249 | PS5-60-IH-0001G-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5250 | PS5-60-IH-0001G-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00023-5251 | PS5-60-IH-0001G-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00023-5254 | PS5-60-IH-0002-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5255 | PS5-60-IH-0002-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5256 | PS5-60-IH-0002-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5257 | PS5-60-IH-0002-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5258 | PS5-60-IH-0002-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5259 | PS5-60-IH-0002-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5260 | PS5-60-IH-0002-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5261 | PS5-60-IH-0002-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5262 | PS5-60-IH-0002-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5263 | PS5-60-IH-0002-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5264 | PS5-60-IN-0001A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5265 | PS5-60-IN-0001B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5266 | PS5-60-IN-0001C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C
T-00023-5267 | PS5-60-IN-0001D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5268 | PS5-60-IN-0001E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E
T-00023-5269 | PS5-60-IN-0001F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F
T-00023-5270 | PS5-60-IN-0001G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G
T-00023-5271 | PS5-60-IN-0002A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5272 | PS5-60-IN-0002A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5273 | PS5-60-IN-0002A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5274 | PS5-60-IN-0002B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5275 | PS5-60-IN-0002B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5276 | PS5-60-IN-0002B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5277 | PS5-60-IN-0002C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00023-5278 | PS5-60-IN-0002C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00023-5279 | PS5-60-IN-0002C-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00023-5280 | PS5-60-IN-0002D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5281 | PS5-60-IN-0002D-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5282 | PS5-60-IN-0002D-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5283 | PS5-60-IN-0002E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00023-5284 | PS5-60-IN-0002E-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00023-5285 | PS5-60-IN-0002E-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00023-5286 | PS5-60-IN-0002F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00023-5287 | PS5-60-IN-0002F-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00023-5288 | PS5-60-IN-0002F-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00023-5289 | PS5-60-IN-0002G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00023-5290 | PS5-60-IN-0002G-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00023-5291 | PS5-60-IN-0002G-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00023-5292 | PS5-60-IWK-0001A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001A |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0438 | 28-July-2026 | Open | Ferdinand | Pulling
T-00023-5293 | PS5-60-IWK-0001A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001A |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0438 | 28-July-2026 | Open | Ferdinand | Pulling
T-00023-5294 | PS5-60-IWK-0001B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001B |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5295 | PS5-60-IWK-0001B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001B |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5296 | PS5-60-IWK-0001C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001C |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5297 | PS5-60-IWK-0001C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001C |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5298 | PS5-60-LA-0002A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5299 | PS5-60-LA-0002A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5300 | PS5-60-LA-0002B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00023-5301 | PS5-60-LA-0002B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00023-5302 | PS5-60-LA-0002C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00023-5303 | PS5-60-LA-0002C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00023-5304 | PS5-60-LA-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0003 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5305 | PS5-60-LA-0003-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0003 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5306 | PS5-60-MOV-0005-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-60-MOV-0005 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5307 | PS5-60-MOV-0006-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-60-MOV-0006 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5308 | PS5-60-MOV-0011-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-60-MOV-0011 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5309 | PS5-60-MOV-0012-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-60-MOV-0012 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5310 | PS5-60-SEA-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00023-5311 | PS5-60-SEA-0001-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00023-5312 | PS5-60-VS-9100A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-VS-9100A |  | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5313 | PS5-60-VS-9100B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-VS-9100B |  | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5314 | PS5-60-VS-9100C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-VS-9100C |  | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C
T-00023-5315 | PS5-60-VS-9100D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-VS-9100D |  | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5316 | PS5-60-VS-9100E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-VS-9100E |  | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5317 | PS5-60-VS-9100F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-VS-9100F |  | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F
T-00023-5318 | PS5-60-VS-9100G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-VS-9100G |  | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G
T-00023-5319 | PS5-61-BI-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-61-BI-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5320 | PS5-61-BI-0002-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-61-BI-0002 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5321 | PS5-61-BI-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-61-BI-0003 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5322 | PS5-61-BI-0004-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-61-BI-0004 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5323 | PS5-61-BI-0005-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-61-BI-0005 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5324 | PS5-61-BI-0006-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-61-BI-0006 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5325 | PS5-61-BI-0007-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-61-BI-0007 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5335 | PS5-61-IG-0015-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IG-0015 |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00023-5336 | PS5-61-IG-0016-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IG-0016 |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5343 | PS5-61-IH-0004-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5344 | PS5-61-IH-0004-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5345 | PS5-61-IH-0004-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5346 | PS5-61-IH-0004-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5347 | PS5-61-IH-0004-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5348 | PS5-61-IH-0004-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5349 | PS5-61-IH-0004-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5350 | PS5-61-IH-0004-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5351 | PS5-61-IH-0004-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5352 | PS5-61-IH-0004-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5353 | PS5-61-IH-0004-CL11 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5354 | PS5-61-IH-0004-CL12 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5355 | PS5-61-IH-0004-CL13 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5356 | PS5-61-IH-0004-CL14 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5357 | PS5-61-IH-0004-CL15 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5358 | PS5-61-IH-0004-CL16 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5359 | PS5-61-IH-0004-CL17 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5360 | PS5-61-IH-0004-CL18 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5361 | PS5-61-IH-0004-CL19 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5362 | PS5-61-IH-0004-CL20 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5363 | PS5-61-IH-0004-CL21 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5364 | PS5-61-IH-0004-CL22 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00023-5425 | PS5-61-IK-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-5426 | PS5-61-IK-0003-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-5427 | PS5-61-IK-0003-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003)
T-00023-5428 | PS5-61-IK-0003-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5429 | PS5-61-IK-0003-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5430 | PS5-61-IK-0003-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5431 | PS5-61-IK-0003-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5432 | PS5-61-IK-0003-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5433 | PS5-61-IK-0003-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5434 | PS5-61-IK-0003-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5435 | PS5-61-IK-0003-CL11 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5436 | PS5-61-IK-0003-CL12 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5437 | PS5-61-IK-0003-CL13 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5438 | PS5-61-IK-0003-CL14 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5439 | PS5-61-IK-0003-CL15 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5440 | PS5-61-IK-0003-CL16 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5441 | PS5-61-IK-0003-CL17 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5442 | PS5-61-IK-0003-CL18 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5443 | PS5-61-IK-0003-CL19 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5444 | PS5-61-IK-0003-CL20 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5445 | PS5-61-IK-0003-CL21 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5446 | PS5-61-IK-0003-CL22 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5447 | PS5-61-IK-0003-CL23 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5448 | PS5-61-IK-0003-CL24 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5449 | PS5-61-IK-0003-CL25 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5450 | PS5-61-IK-0003-CL26 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5451 | PS5-61-IK-0003-CL27 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5452 | PS5-61-IK-0003-CL28 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5453 | PS5-61-IK-0003-CL29 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5454 | PS5-61-IK-0003-CL30 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5455 | PS5-61-IK-0003-CL31 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5456 | PS5-61-IK-0003-CL32 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5457 | PS5-61-IK-0003-CL33 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5458 | PS5-61-IK-0003-CL34 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5459 | PS5-61-IK-0003-CL35 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5460 | PS5-61-IK-0003-CL36 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5461 | PS5-61-IK-0003-CL37 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5462 | PS5-61-IK-0003-CL38 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5463 | PS5-61-IK-0003-CL39 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5464 | PS5-61-IK-0003-CL40 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5465 | PS5-61-IK-0003-CL41 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5466 | PS5-61-IK-0003-CL42 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5467 | PS5-61-IK-0003-CL43 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5468 | PS5-61-IK-0003-CL44 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5469 | PS5-61-IK-0003-CL45 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5470 | PS5-61-IK-0003-CL46 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5471 | PS5-61-IK-0003-CL47 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5472 | PS5-61-IK-0003-CL48 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5473 | PS5-61-IK-0003-CL49 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5474 | PS5-61-IK-0003-CL50 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5475 | PS5-61-IK-0003-CL51 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5476 | PS5-61-IK-0003-CL52 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5477 | PS5-61-IK-0003-CL53 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5478 | PS5-61-IK-0003-CL54 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5479 | PS5-61-IK-0003-CL55 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0238 | 2026-04-30 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5480 | PS5-61-IK-0003-CL56 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0238 | 2026-04-30 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5481 | PS5-61-IK-0003-CL57 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5482 | PS5-61-IK-0003-CL58 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5483 | PS5-61-IK-0003-CL59 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5484 | PS5-61-IK-0003-CL60 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5485 | PS5-61-IK-0003-CL61 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0438 | 28-July-2026 | Open | Ferdinand | Pulling
T-00023-5486 | PS5-61-IK-0003-CL62 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5487 | PS5-05-IG-0002-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IG-0002 |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00023-5492 | PS5-61-IK-0006-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5493 | PS5-61-IK-0006-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5494 | PS5-61-IK-0006-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5495 | PS5-61-IK-0006-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5496 | PS5-61-IK-0006-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5497 | PS5-61-IK-0006-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5498 | PS5-61-IK-0006-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5499 | PS5-61-IK-0006-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5500 | PS5-61-IK-0006-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5501 | PS5-61-IK-0006-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5502 | PS5-61-IK-0006-CL11 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5503 | PS5-61-IK-0006-CL12 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5504 | PS5-61-IK-0006-CL13 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5505 | PS5-61-IK-0006-CL14 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5506 | PS5-61-IK-0006-CL15 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5507 | PS5-61-IK-0006-CL16 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5508 | PS5-61-IK-0006-CL17 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5509 | PS5-61-IK-0006-CL18 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5510 | PS5-61-IK-0006-CL19 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00023-5511 | PS5-61-IK-0006-CL20 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00023-5512 | PS5-61-IK-0006-CL21 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00023-5513 | PS5-61-IK-0006-CL22 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00023-5514 | PS5-61-IK-0006-CL23 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5515 | PS5-61-IK-0006-CL24 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5516 | PS5-61-IK-0006-CL25 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5517 | PS5-61-IK-0006-CL26 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-5518 | PS5-61-IK-0006-CL27 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-5519 | PS5-61-IK-0006-CL28 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00023-5520 | PS5-61-IK-0006-CL29 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006)
T-00023-5521 | PS5-61-IK-0006-CL30 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006)
T-00023-5522 | PS5-61-IK-0006-CL31 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006)
T-00023-5523 | PS5-61-IK-0006-CL32 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006)
T-00023-5524 | PS5-61-IK-0006-CL33 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00023-5525 | PS5-61-IK-0006-CL34 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00023-5532 | PS5-61-IU-3100A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-61-IU-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0217 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00023-5533 | PS5-61-IU-3100B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-61-IU-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0217 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00023-5534 | PS5-61-IU-3100C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-61-IU-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0217 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00023-5537 | PS5-61-IV-0002A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IV-0002A |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5538 | PS5-61-IV-0002B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IV-0002B |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5542 | PS5-61-IV-0007A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IV-0007A |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5543 | PS5-61-IV-0007B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IV-0007B |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00023-5546 | PS5-62-IE-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5547 | PS5-62-IE-0002-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5561 | PS5-71-FCV-0018-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-FCV-0018 |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00023-5562 | PS5-71-FCV-0019-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-FCV-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5563 | PS5-71-FCV-0020-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-FCV-0020 |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5567 | PS5-71-HE-2200-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-71-HE-2200 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5569 | PS5-71-HE-2300-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-71-HE-2300 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5570 | PS5-71-HE-2400A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IE-0001 TO PS5-71-HE-2400A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00023-5571 | PS5-71-HE-2400A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IE-0001 TO PS5-71-HE-2400A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00023-5572 | PS5-71-HE-2400A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IE-0001 TO PS5-71-HE-2400A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5573 | PS5-71-HE-2400A-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IE-0001 TO PS5-71-HE-2400A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5574 | PS5-71-HE-2400B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IE-0002 TO PS5-71-HE-2400B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5575 | PS5-71-HE-2400B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IE-0002 TO PS5-71-HE-2400B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5576 | PS5-71-HE-2400B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IE-0002 TO PS5-71-HE-2400B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5577 | PS5-71-HE-2400B-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IE-0002 TO PS5-71-HE-2400B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5578 | PS5-71-IN-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP)
T-00023-5579 | PS5-71-IN-0001-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP)
T-00023-5580 | PS5-71-IN-0001-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5581 | PS5-71-IN-0002-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP)
T-00023-5582 | PS5-71-IN-0002-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP)
T-00023-5583 | PS5-71-IN-0002-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP)
T-00023-5584 | PS5-71-IN-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5585 | PS5-71-IN-0003-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-5586 | PS5-71-IN-0003-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-33/1-05-0309 | 2026-06-04 | Accepted With Commend | Ferdinand | Pulling
T-00023-5587 | PS5-71-IN-0004A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5588 | PS5-71-IN-0004A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-331-05-0407 | 2026-07-09 | HOLD | Bertus Wikael | PULLING
T-00023-5589 | PS5-71-IN-0004A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5590 | PS5-71-IN-0004B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00023-5591 | PS5-71-IN-0004B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00023-5592 | PS5-71-IN-0004B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5593 | PS5-71-LCV-4101-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-LCV-4101 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5594 | PS5-71-MOV-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0001 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5595 | PS5-71-MOV-0002-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0002 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5596 | PS5-71-MOV-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5597 | PS5-71-MOV-0004-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0004 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5598 | PS5-71-MOV-0007-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0007 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5599 | PS5-71-MOV-0008-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0008 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5600 | PS5-71-MOV-0009-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0009 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5601 | PS5-71-MOV-0010-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0010 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5602 | PS5-71-SDV-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5603 | PS5-71-SDV-0022-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank
T-00023-5604 | PS5-71-SDV-0029-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5605 | PS5-71-SDV-0039-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5606 | PS5-71-UZ-6200-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0014 TO PS5-71-UZ-6200 |  | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5607 | PS5-71-XV-0089-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5608 | PS5-71-XV-0090-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5609 | PS5-71-XV-0091-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module
T-00023-5610 | PS5-71-XV-0092-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5612 | PS5-74-LB-5101-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-74-LB-5101 |  | PS5-74-02 - N2 Generation Skid (UCP) | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5613 | PS5-74-LB-5101-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-74-LB-5101 |  | PS5-74-02 - N2 Generation Skid (UCP) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5620 | PS5-75-MOV-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-75-MOV-0001 |  | PS5-28-07 - Open Drains (OD2) | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00023-5621 | PS5-75-UI-6200-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0001A TO PS5-75-UI-6200 |  | PS5-75-01 - DRA Injection Package
T-00023-5622 | PS5-75-UI-6200-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-06-IG-0001B TO PS5-75-UI-6200 |  | PS5-75-01 - DRA Injection Package
T-00023-5623 | PS5-78-JC-9100A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-78-JC-9100A |  | PS5-78-01 - Lifting and handling equipment
T-00023-5624 | PS5-78-JC-9100B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-78-JC-9100B |  | PS5-78-01 - Lifting and handling equipment
T-00023-5625 | PS5-78-JC-9100C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-78-JC-9100C |  | PS5-78-01 - Lifting and handling equipment
T-00023-5626 | PS5-78-JC-9100D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-78-JC-9100D |  | PS5-78-01 - Lifting and handling equipment
T-00023-5640 | PS5-87-IRF-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-87-IRF-0001 |  | PS5-53-01 - Utility Water / Storage Tank | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-5641 | PS5-87-IRF-0002-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-87-IRF-0002 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5642 | PS5-87-IRF-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-87-IRF-0003 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-5643 | PS5-87-IRF-0004-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-87-IRF-0004 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00023-8829 | PS5-79-IG-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0001 TO PS5-79-IG-0001 |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00023-8830 | PS5-79-IG-0002-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0002 TO PS5-79-IG-0002 |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00023-8831 | PS5-79-IG-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0003 TO PS5-79-IG-0003 |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00023-8832 | PS5-79-IG-0004-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0004 TO PS5-79-IG-0004 |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00023-8833 | PS5-79-IG-0005-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0005 TO PS5-79-IG-0005 |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00023-8834 | PS5-79-IG-0006-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0006 TO PS5-79-IG-0006 |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00023-8835 | PS5-79-IG-0007-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0007 TO PS5-79-IG-0007 |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00023-8836 | PS5-79-IG-0008-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0008 TO PS5-79-IG-0008 |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00023-8837 | PS5-79-IG-0009-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0009 TO PS5-79-IG-0009 |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00023-8838 | PS5-79-IG-0010-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0010 TO PS5-79-IG-0010 |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00023-8839 | PS5-79-IG-0011-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0011 TO PS5-79-IG-0011 |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00023-8840 | PS5-79-IG-0012-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-79-IV-0012 TO PS5-79-IG-0012 |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00023-9120 | PS5-02-SWSI-0001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-02-SWSI-0001 |  | PS5-02-01 - Miscellaneous Safety equipment | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | Pulling
T-00023-9121 | PS5-02-SWSI-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-02-SWSI-0003 |  | PS5-02-01 - Miscellaneous Safety equipment
T-00023-9122 | PS5-06-GU-0005-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0007 TO PS5-06-GU-0005 |  | PS5-06-04 - AC UPS - Guard House
T-00023-9128 | PS5-09-LB-7001-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-05-IG-0007 TO PS5-09-LB-7001 |  | PS5-09-02 - HVAC for Guard House
T-00023-9131 | PS5-60-BE-0007A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-9132 | PS5-60-BE-0007B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00023-9133 | PS5-60-BE-0007C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9134 | PS5-60-BE-0007D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00023-9135 | PS5-60-BE-0007E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9136 | PS5-60-BE-0007F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9137 | PS5-60-BE-0007G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9138 | PS5-60-BE-0027A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0027A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9139 | PS5-60-BE-0027B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0027B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B
T-00023-9140 | PS5-60-BE-0027C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0027C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9141 | PS5-60-BE-0027D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0027D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9142 | PS5-60-BE-0027E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0027E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9143 | PS5-60-BE-0027F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0027F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9144 | PS5-60-BE-0027G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0027G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9145 | PS5-60-BE-0028A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0028A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9146 | PS5-60-BE-0028B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0028B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9147 | PS5-60-BE-0028C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0028C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9148 | PS5-60-BE-0028D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0028D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9149 | PS5-60-BE-0028E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0028E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9150 | PS5-60-BE-0028F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0028F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9151 | PS5-60-BE-0028G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0028G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9152 | PS5-60-BI-0006A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9153 | PS5-60-BI-0006A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00023-9154 | PS5-60-BI-0006A-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9155 | PS5-60-BI-0006A-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9156 | PS5-60-BI-0006A-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9157 | PS5-60-BI-0006A-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9158 | PS5-60-BI-0006A-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9159 | PS5-60-BI-0006A-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9160 | PS5-60-BI-0006A-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9161 | PS5-60-BI-0006A-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9162 | PS5-60-BI-0006A-CL11 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9163 | PS5-60-BI-0006B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9164 | PS5-60-BI-0006B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9165 | PS5-60-BI-0006B-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9166 | PS5-60-BI-0006B-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9167 | PS5-60-BI-0006B-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9168 | PS5-60-BI-0006B-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9169 | PS5-60-BI-0006B-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9170 | PS5-60-BI-0006B-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9171 | PS5-60-BI-0006B-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9172 | PS5-60-BI-0006B-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9173 | PS5-60-BI-0006B-CL11 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9174 | PS5-60-BI-0006C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9175 | PS5-60-BI-0006C-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9176 | PS5-60-BI-0006C-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9177 | PS5-60-BI-0006C-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9178 | PS5-60-BI-0006C-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9179 | PS5-60-BI-0006C-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9180 | PS5-60-BI-0006C-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9181 | PS5-60-BI-0006C-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9182 | PS5-60-BI-0006C-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9183 | PS5-60-BI-0006C-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9184 | PS5-60-BI-0006C-CL11 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9185 | PS5-60-BI-0006D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9186 | PS5-60-BI-0006D-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9187 | PS5-60-BI-0006D-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9188 | PS5-60-BI-0006D-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9189 | PS5-60-BI-0006D-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9190 | PS5-60-BI-0006D-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9191 | PS5-60-BI-0006D-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9192 | PS5-60-BI-0006D-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9193 | PS5-60-BI-0006D-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9194 | PS5-60-BI-0006D-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9195 | PS5-60-BI-0006D-CL11 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9196 | PS5-60-BI-0006E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9197 | PS5-60-BI-0006E-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9198 | PS5-60-BI-0006E-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9199 | PS5-60-BI-0006E-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9200 | PS5-60-BI-0006E-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9201 | PS5-60-BI-0006E-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9202 | PS5-60-BI-0006E-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9203 | PS5-60-BI-0006E-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9204 | PS5-60-BI-0006E-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9205 | PS5-60-BI-0006E-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9206 | PS5-60-BI-0006E-CL11 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9207 | PS5-60-BI-0006F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9208 | PS5-60-BI-0006F-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9209 | PS5-60-BI-0006F-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9210 | PS5-60-BI-0006F-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9211 | PS5-60-BI-0006F-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9212 | PS5-60-BI-0006F-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9213 | PS5-60-BI-0006F-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9214 | PS5-60-BI-0006F-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9215 | PS5-60-BI-0006F-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9216 | PS5-60-BI-0006F-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9217 | PS5-60-BI-0006F-CL11 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9218 | PS5-60-BI-0006G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9219 | PS5-60-BI-0006G-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9220 | PS5-60-BI-0006G-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9221 | PS5-60-BI-0006G-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9222 | PS5-60-BI-0006G-CL05 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9223 | PS5-60-BI-0006G-CL06 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9224 | PS5-60-BI-0006G-CL07 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9225 | PS5-60-BI-0006G-CL08 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9226 | PS5-60-BI-0006G-CL09 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9227 | PS5-60-BI-0006G-CL10 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9228 | PS5-60-BI-0006G-CL11 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9229 | PS5-60-BI-0017A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9230 | PS5-60-BI-0017B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9231 | PS5-60-BI-0017C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9232 | PS5-60-BI-0017D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9233 | PS5-60-BI-0017E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0017E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9234 | PS5-60-BI-0017F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0017F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9235 | PS5-60-BI-0017G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0017G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9236 | PS5-60-EA-2900A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-EA-2900A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A
T-00023-9237 | PS5-60-EA-2900B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-EA-2900B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B
T-00023-9238 | PS5-60-EA-2900C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-EA-2900C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00023-9239 | PS5-60-EA-2900D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-EA-2900D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00023-9240 | PS5-60-EA-2900E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-EA-2900E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00023-9241 | PS5-60-EA-2900F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-EA-2900F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00023-9242 | PS5-60-EA-2900G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-EA-2900G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00023-9243 | PS5-61-IK-0005-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-61-IK-0005 |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00023-9244 | PS5-71-BE-0004-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-331-05-0399 | 2026-07-02 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-9245 | PS5-71-BE-0004-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00023-9246 | PS5-71-BE-0004-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-331-05-0399 | 2026-07-02 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-9247 | PS5-71-BI-0003-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-331-05-0399 | 2026-07-02 | Accepted With Punch | Bertus Wikael | PULLING
T-00023-9248 | PS5-71-BI-0003-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00023-9249 | PS5-71-BI-0003-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00023-9250 | PS5-71-BI-0003-CL04 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00023-9251 | PS5-71-BI-0004-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00023-9252 | PS5-71-BI-0005-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9253 | PS5-71-BI-0005-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9254 | PS5-71-BI-0005-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00023-9255 | PS5-71-BI-0006-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-05-0377 | 24-June-2026 | Rejected | Ferdinand | PULLING
T-00023-9680 | PS5-09-AHU-8111A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8111A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9681 | PS5-09-AHU-8111B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8111B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9682 | PS5-09-AHU-8211A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8211A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9683 | PS5-09-AHU-8211B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8211B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9684 | PS5-09-AHU-8311A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8311A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9685 | PS5-09-AHU-8311A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8311A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9686 | PS5-09-AHU-8311B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8311B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9687 | PS5-09-AHU-8311B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8311B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9688 | PS5-09-AHU-8321A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8321A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9689 | PS5-09-AHU-8321A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8321A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9690 | PS5-09-AHU-8321B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8321B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9691 | PS5-09-AHU-8321B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8321B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9692 | PS5-09-AHU-8331A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8331A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9693 | PS5-09-AHU-8331A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8331A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9694 | PS5-09-AHU-8331B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8331B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9695 | PS5-09-AHU-8331B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8331B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9696 | PS5-09-AHU-8341-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8341 |  | PS5-09-03 - HVAC for Generator Building
T-00023-9697 | PS5-09-AHU-8341-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8341 |  | PS5-09-03 - HVAC for Generator Building
T-00023-9698 | PS5-09-AHU-8411A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9699 | PS5-09-AHU-8411A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9700 | PS5-09-AHU-8411B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9701 | PS5-09-AHU-8411B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9702 | PS5-09-FCU-8442A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9703 | PS5-09-FCU-8442B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9704 | PS5-09-FCU-8442C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442C |  | PS5-09-03 - HVAC for Generator Building
T-00023-9705 | PS5-09-FCU-8442D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442D |  | PS5-09-03 - HVAC for Generator Building
T-00023-9706 | PS5-09-FCU-8442E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442E |  | PS5-09-03 - HVAC for Generator Building
T-00023-9707 | PS5-09-FCU-8442F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442F |  | PS5-09-03 - HVAC for Generator Building
T-00023-9708 | PS5-09-FCU-8442G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442G |  | PS5-09-03 - HVAC for Generator Building
T-00023-9709 | PS5-09-FCU-8442H-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442H |  | PS5-09-03 - HVAC for Generator Building
T-00023-9710 | PS5-09-LB-0008-CL03 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building
T-00023-9711 | PS5-09-PA-84500A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-PA-84500A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9712 | PS5-09-PA-84500B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-PA-84500B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9713 | PS5-09-QX-8451A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-QX-8451A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9714 | PS5-09-QX-8451A-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-QX-8451A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9715 | PS5-09-QX-8451B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-QX-8451B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9716 | PS5-09-QX-8451B-CL02 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-QX-8451B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9717 | PS5-09-RF-81200A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-81200A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9718 | PS5-09-RF-81200B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-81200B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9719 | PS5-09-RF-81200C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-81200C |  | PS5-09-03 - HVAC for Generator Building
T-00023-9720 | PS5-09-RF-82200A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-82200A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9721 | PS5-09-RF-82200B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-82200B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9722 | PS5-09-RF-82200C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-82200C |  | PS5-09-03 - HVAC for Generator Building
T-00023-9723 | PS5-09-RF-82200D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-82200D |  | PS5-09-03 - HVAC for Generator Building
T-00023-9724 | PS5-09-RF-83500A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9725 | PS5-09-RF-83500B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9726 | PS5-09-RF-83500C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500C |  | PS5-09-03 - HVAC for Generator Building
T-00023-9727 | PS5-09-RF-83500D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500D |  | PS5-09-03 - HVAC for Generator Building
T-00023-9728 | PS5-09-RF-83500E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500E |  | PS5-09-03 - HVAC for Generator Building
T-00023-9729 | PS5-09-RF-83500F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500F |  | PS5-09-03 - HVAC for Generator Building
T-00023-9730 | PS5-09-RF-83500G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500G |  | PS5-09-03 - HVAC for Generator Building
T-00023-9731 | PS5-09-RF-83500H-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500H |  | PS5-09-03 - HVAC for Generator Building
T-00023-9732 | PS5-09-RF-83500J-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500J |  | PS5-09-03 - HVAC for Generator Building
T-00023-9733 | PS5-09-RF-83500K-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500K |  | PS5-09-03 - HVAC for Generator Building
T-00023-9734 | PS5-09-RF-83500L-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500L |  | PS5-09-03 - HVAC for Generator Building
T-00023-9735 | PS5-09-RF-83500M-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500M |  | PS5-09-03 - HVAC for Generator Building
T-00023-9736 | PS5-09-RF-83500N-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500N |  | PS5-09-03 - HVAC for Generator Building
T-00023-9737 | PS5-09-RF-83500P-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500P |  | PS5-09-03 - HVAC for Generator Building
T-00023-9738 | PS5-09-RF-83600A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9739 | PS5-09-RF-83600B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9740 | PS5-09-RF-83600C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600C |  | PS5-09-03 - HVAC for Generator Building
T-00023-9741 | PS5-09-RF-83600D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600D |  | PS5-09-03 - HVAC for Generator Building
T-00023-9742 | PS5-09-RF-83600E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600E |  | PS5-09-03 - HVAC for Generator Building
T-00023-9743 | PS5-09-RF-83600F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600F |  | PS5-09-03 - HVAC for Generator Building
T-00023-9744 | PS5-09-RF-83600G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600G |  | PS5-09-03 - HVAC for Generator Building
T-00023-9745 | PS5-09-RF-83600H-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600H |  | PS5-09-03 - HVAC for Generator Building
T-00023-9746 | PS5-09-RF-83600J-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600J |  | PS5-09-03 - HVAC for Generator Building
T-00023-9747 | PS5-09-RF-83600K-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600K |  | PS5-09-03 - HVAC for Generator Building
T-00023-9748 | PS5-09-RF-83600L-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600L |  | PS5-09-03 - HVAC for Generator Building
T-00023-9749 | PS5-09-RF-83600M-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600M |  | PS5-09-03 - HVAC for Generator Building
T-00023-9750 | PS5-09-RF-83600N-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600N |  | PS5-09-03 - HVAC for Generator Building
T-00023-9751 | PS5-09-RF-83600P-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600P |  | PS5-09-03 - HVAC for Generator Building
T-00023-9752 | PS5-09-RF-83700A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9753 | PS5-09-RF-83700B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9754 | PS5-09-RF-83700C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700C |  | PS5-09-03 - HVAC for Generator Building
T-00023-9755 | PS5-09-RF-83700D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700D |  | PS5-09-03 - HVAC for Generator Building
T-00023-9756 | PS5-09-RF-83700E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700E |  | PS5-09-03 - HVAC for Generator Building
T-00023-9757 | PS5-09-RF-83700F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700F |  | PS5-09-03 - HVAC for Generator Building
T-00023-9758 | PS5-09-RF-83700G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700G |  | PS5-09-03 - HVAC for Generator Building
T-00023-9759 | PS5-09-RF-83700H-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700H |  | PS5-09-03 - HVAC for Generator Building
T-00023-9760 | PS5-09-RF-83700J-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700J |  | PS5-09-03 - HVAC for Generator Building
T-00023-9761 | PS5-09-RF-83700K-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700K |  | PS5-09-03 - HVAC for Generator Building
T-00023-9762 | PS5-09-RF-83700L-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700L |  | PS5-09-03 - HVAC for Generator Building
T-00023-9763 | PS5-09-RF-83700M-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700M |  | PS5-09-03 - HVAC for Generator Building
T-00023-9764 | PS5-09-RF-83700N-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700N |  | PS5-09-03 - HVAC for Generator Building
T-00023-9765 | PS5-09-RF-83700P-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700P |  | PS5-09-03 - HVAC for Generator Building
T-00023-9766 | PS5-09-RF-83800A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9767 | PS5-09-RF-83800B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9768 | PS5-09-RF-83800C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800C |  | PS5-09-03 - HVAC for Generator Building
T-00023-9769 | PS5-09-RF-83800D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800D |  | PS5-09-03 - HVAC for Generator Building
T-00023-9770 | PS5-09-RF-83800E-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800E |  | PS5-09-03 - HVAC for Generator Building
T-00023-9771 | PS5-09-RF-83800F-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800F |  | PS5-09-03 - HVAC for Generator Building
T-00023-9772 | PS5-09-RF-83800G-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800G |  | PS5-09-03 - HVAC for Generator Building
T-00023-9773 | PS5-09-RF-84200A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-84200A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9774 | PS5-09-RF-84200B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-84200B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9775 | PS5-09-UZ-84600-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-09-IH-0004 TO PS5-09-UZ-84600 |  | PS5-09-03 - HVAC for Generator Building
T-00023-9776 | PS5-61-IH-0004A-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-61-IH-0004A |  | PS5-09-03 - HVAC for Generator Building
T-00023-9777 | PS5-61-IH-0004B-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-61-IH-0004B |  | PS5-09-03 - HVAC for Generator Building
T-00023-9778 | PS5-61-IH-0004C-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-61-IH-0004C |  | PS5-09-03 - HVAC for Generator Building
T-00023-9779 | PS5-61-IH-0004D-CL01 | CPX09 - LV Power Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-61-IH-0004D |  | PS5-09-03 - HVAC for Generator Building
T-00024-2028 | PS5-05-IE-8100-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2029 | PS5-05-IE-8100-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2030 | PS5-05-IE-8100-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2031 | PS5-05-IE-8100-CD04 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2032 | PS5-05-IE-8100-CD05 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2033 | PS5-05-IE-8100-CD06 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-61-IE-0002-CD48 | CPX10 - Multicore Electrical Control Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-61-IE-0002-CD49 | CPX10 - Multicore Electrical Control Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-61-IE-0002-CD50 | CPX10 - Multicore Electrical Control Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-61-IE-0003-CD11 | CPX10 - Multicore Electrical Control Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-61-IE-0003-CD12 | CPX10 - Multicore Electrical Control Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-61-IE-0003-CD13 | CPX10 - Multicore Electrical Control Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-05-BE-0001-CL12 | CPX10 - Multicore Electrical Control Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2034 | PS5-05-IE-8100-CD07 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2035 | PS5-05-IE-8100-CD08 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0391 | 2026-06-30 | Accepted with punch | Bertus Wikael | Pulling
T-00024-2037 | PS5-05-IE-8100-CD10 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0391 | 2026-06-30 | Accepted with punch | Bertus Wikael | Pulling
T-00024-2038 | PS5-05-IE-8100-CD11 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2039 | PS5-05-IE-8100-CD12 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0391 | 2026-06-30 | Accepted with punch | Bertus Wikael | Pulling
T-00024-2040 | PS5-05-IE-8100-CD13 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0391 | 2026-06-30 | Accepted with punch | Bertus Wikael | Pulling
T-00024-2041 | PS5-05-IE-8100-CD14 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0391 | 2026-06-30 | Accepted with punch | Bertus Wikael | Pulling
T-00024-2042 | PS5-05-IE-8100-CD15 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0391 | 2026-06-30 | Accepted with punch | Bertus Wikael | Pulling
T-00024-2043 | PS5-05-IE-8100-CD16 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0391 | 2026-06-30 | Accepted with punch | Bertus Wikael | Pulling
T-00024-2044 | PS5-05-IE-8100-CD17 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0391 | 2026-06-30 | Accepted with punch | Bertus Wikael | Pulling
T-00024-2045 | PS5-05-IE-8100-CD18 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2046 | PS5-05-IE-8100-CD19 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2047 | PS5-05-IE-8100-CD20 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2048 | PS5-05-IE-8100-CD21 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0391 | 2026-06-30 | Accepted with punch | Bertus Wikael | Pulling
T-00024-2052 | PS5-05-IE-8100-CD25 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0312 | 2026-06-03 | Accepted with punch | Bertus Wikael | Pulling
T-00024-2061 | PS5-25-DM-3100A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00024-2062 | PS5-25-DM-3100B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00024-2063 | PS5-25-DM-3100C-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00024-2067 | PS5-25-IES-3100A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-IES-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2068 | PS5-25-IES-3100B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-IES-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2069 | PS5-25-IES-3100C-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-IES-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2097 | PS5-50-IE-0001-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-50-IE-0001 |  | PS5-50-01 - Water Well Submersible Pumps (3100)
T-00024-2098 | PS5-50-IE-0002-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-50-IE-0002 |  | PS5-50-02 - Water Well Submersible Pumps (3200)
T-00024-2101 | PS5-60-IE-0002A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2102 | PS5-60-IE-0002A-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2103 | PS5-60-IE-0002A-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2104 | PS5-60-IE-0002B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2105 | PS5-60-IE-0002B-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2106 | PS5-60-IE-0002B-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2107 | PS5-60-IE-0002C-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-05-0399 | 2026-07-02 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2108 | PS5-60-IE-0002C-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-05-0399 | 2026-07-02 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2109 | PS5-60-IE-0002C-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-05-0399 | 2026-07-02 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2110 | PS5-60-IE-0002D-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-331-05-0399 | 2026-07-02 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2111 | PS5-60-IE-0002D-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-331-05-0399 | 2026-07-02 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2112 | PS5-60-IE-0002D-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D
T-00024-2113 | PS5-60-IE-0002E-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E
T-00024-2114 | PS5-60-IE-0002E-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E
T-00024-2115 | PS5-60-IE-0002E-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E
T-00024-2116 | PS5-60-IE-0002F-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F
T-00024-2117 | PS5-60-IE-0002F-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F
T-00024-2118 | PS5-60-IE-0002F-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F
T-00024-2119 | PS5-60-IE-0002G-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G
T-00024-2120 | PS5-60-IE-0002G-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G
T-00024-2121 | PS5-60-IE-0002G-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G
T-00024-2123 | PS5-60-IE-0003A-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00024-2124 | PS5-60-IE-0003A-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00024-2125 | PS5-60-IE-0003A-CD04 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0005A TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00024-2126 | PS5-60-IE-0003A-CD05 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00024-2135 | PS5-60-IE-0003A-CD14 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00024-2136 | PS5-60-IE-0003A-CD15 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00024-2138 | PS5-60-IE-0003B-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2139 | PS5-60-IE-0003B-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2140 | PS5-60-IE-0003B-CD04 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0005B TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2141 | PS5-60-IE-0003B-CD05 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00024-2150 | PS5-60-IE-0003B-CD14 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-05-0347 | 2026-06-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-2151 | PS5-60-IE-0003B-CD15 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00024-2153 | PS5-60-IE-0003C-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C
T-00024-2154 | PS5-60-IE-0003C-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C
T-00024-2155 | PS5-60-IE-0003C-CD04 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0005C TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2156 | PS5-60-IE-0003C-CD05 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C
T-00024-2165 | PS5-60-IE-0003C-CD14 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C
T-00024-2166 | PS5-60-IE-0003C-CD15 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C
T-00024-2168 | PS5-60-IE-0003D-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D
T-00024-2169 | PS5-60-IE-0003D-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00024-2170 | PS5-60-IE-0003D-CD04 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0005D TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00024-2171 | PS5-60-IE-0003D-CD05 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
T-00024-2180 | PS5-60-IE-0003D-CD14 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
| PS5-61-IG-0015-CL01 | CPX | #N/A |  |  |  |  | CPP-RFI-68-33/1-05-0346 | 2026-06-17 | Acceptable with comments | Ferdinand | Pulling
#N/A
T-00024-2181 | PS5-60-IE-0003D-CD15 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D
T-00024-2183 | PS5-60-IE-0003E-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E
T-00024-2184 | PS5-60-IE-0003E-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E
T-00024-2185 | PS5-60-IE-0003E-CD04 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0005E TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2186 | PS5-60-IE-0003E-CD05 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E
T-00024-2195 | PS5-60-IE-0003E-CD14 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E
T-00024-2196 | PS5-60-IE-0003E-CD15 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E
T-00024-2198 | PS5-60-IE-0003F-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F
T-00024-2199 | PS5-60-IE-0003F-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F
T-00024-2200 | PS5-60-IE-0003F-CD04 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0005F TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2201 | PS5-60-IE-0003F-CD05 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F
T-00024-2210 | PS5-60-IE-0003F-CD14 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F
T-00024-2211 | PS5-60-IE-0003F-CD15 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F
T-00024-2213 | PS5-60-IE-0003G-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G
T-00024-2214 | PS5-60-IE-0003G-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G
T-00024-2215 | PS5-60-IE-0003G-CD04 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0005G TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-05-0387 | 2026-06-29 | Accepted With Punch | Bertus Wikael | Pulling
T-00024-2216 | PS5-60-IE-0003G-CD05 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G
T-00024-2225 | PS5-60-IE-0003G-CD14 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G
T-00024-2226 | PS5-60-IE-0003G-CD15 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G
T-00024-2233 | PS5-61-IDH-3100A-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-05-0217 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00024-2236 | PS5-61-IDH-3100B-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-05-0217 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00024-2239 | PS5-61-IDH-3100C-CD03 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-05-0217 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00024-2288 | PS5-62-IE-0001-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-62-IE-0002 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00024-3288 | PS5-79-IG-0001-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0001 TO PS5-79-IG-0001 |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00024-3289 | PS5-79-IG-0002-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0002 TO PS5-79-IG-0002 |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00024-3290 | PS5-79-IG-0003-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0003 TO PS5-79-IG-0003 |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00024-3291 | PS5-79-IG-0004-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0004 TO PS5-79-IG-0004 |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00024-3292 | PS5-79-IG-0005-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0005 TO PS5-79-IG-0005 |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00024-3293 | PS5-79-IG-0006-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0006 TO PS5-79-IG-0006 |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00024-3294 | PS5-79-IG-0007-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0007 TO PS5-79-IG-0007 |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00024-3295 | PS5-79-IG-0008-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0008 TO PS5-79-IG-0008 |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00024-3296 | PS5-79-IG-0009-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0009 TO PS5-79-IG-0009 |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00024-3297 | PS5-79-IG-0010-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0010 TO PS5-79-IG-0010 |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00024-3298 | PS5-79-IG-0011-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0011 TO PS5-79-IG-0011 |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00024-3299 | PS5-79-IG-0012-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-79-IV-0012 TO PS5-79-IG-0012 |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00024-3399 | PS5-06-GU-0003A-CD02 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-06-GB-0003 TO PS5-06-GU-0003A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-331-05-0368 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
T-00024-3634 | PS5-09-IES-8101A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8101A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3635 | PS5-09-IES-8101B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8101B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3636 | PS5-09-IES-8102A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8102A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3637 | PS5-09-IES-8102B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8102B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3638 | PS5-09-IES-8102C-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8102C |  | PS5-09-03 - HVAC for Generator Building
T-00024-3639 | PS5-09-IES-8201A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8201A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3640 | PS5-09-IES-8201B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8201B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3641 | PS5-09-IES-8202A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8202A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3642 | PS5-09-IES-8202B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8202B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3643 | PS5-09-IES-8202C-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8202C |  | PS5-09-03 - HVAC for Generator Building
T-00024-3644 | PS5-09-IES-8202D-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8202D |  | PS5-09-03 - HVAC for Generator Building
T-00024-3645 | PS5-09-IES-8301A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8301A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3646 | PS5-09-IES-8301B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8301B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3647 | PS5-09-IES-8302A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8302A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3648 | PS5-09-IES-8302B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8302B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3649 | PS5-09-IES-8304A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8304A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3650 | PS5-09-IES-8304B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8304B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3651 | PS5-09-IES-8305A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8305A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3652 | PS5-09-IES-8305B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8305B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3653 | PS5-09-IES-8307A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8307A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3654 | PS5-09-IES-8307B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8307B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3655 | PS5-09-IES-8308A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8308A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3656 | PS5-09-IES-8308B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8308B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3657 | PS5-09-IES-8311A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8311A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3658 | PS5-09-IES-8311B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8311B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3659 | PS5-09-IES-8313-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-IES-8313 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3660 | PS5-09-IES-8314-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-IES-8314 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3661 | PS5-09-IES-8315-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8315 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3662 | PS5-09-IES-8316-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-IES-8316 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3663 | PS5-09-IES-8317-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-IES-8317 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3664 | PS5-09-IES-8318-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8318 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3665 | PS5-09-IES-8319-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-IES-8319 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3666 | PS5-09-IES-8321-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-IES-8321 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3667 | PS5-09-IES-8322-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8322 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3668 | PS5-09-IES-8323-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-IES-8323 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3669 | PS5-09-IES-8324-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-IES-8324 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3670 | PS5-09-IES-8325-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8325 |  | PS5-09-03 - HVAC for Generator Building
T-00024-3671 | PS5-09-IES-8401A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8401A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3672 | PS5-09-IES-8401B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8401B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3673 | PS5-09-IES-8403A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8403A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3674 | PS5-09-IES-8403B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8403B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3675 | PS5-09-IES-8404A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8404A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3676 | PS5-09-IES-8404B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8404B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3677 | PS5-09-IES-8405A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8405A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3678 | PS5-09-IES-8405B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8405B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3679 | PS5-09-IES-8406A-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406A |  | PS5-09-03 - HVAC for Generator Building
T-00024-3680 | PS5-09-IES-8406B-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406B |  | PS5-09-03 - HVAC for Generator Building
T-00024-3681 | PS5-09-IES-8406C-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406C |  | PS5-09-03 - HVAC for Generator Building
T-00024-3682 | PS5-09-IES-8406D-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406D |  | PS5-09-03 - HVAC for Generator Building
T-00024-3683 | PS5-09-IES-8406E-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406E |  | PS5-09-03 - HVAC for Generator Building
T-00024-3684 | PS5-09-IES-8406F-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406F |  | PS5-09-03 - HVAC for Generator Building
T-00024-3685 | PS5-09-IES-8406G-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406G |  | PS5-09-03 - HVAC for Generator Building
T-00024-3686 | PS5-09-IES-8406H-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406H |  | PS5-09-03 - HVAC for Generator Building
T-00024-3687 | PS5-09-IES-8407-CD01 | CPX10 - Multicore Electrical Control Cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8407 |  | PS5-09-03 - HVAC for Generator Building
T-00025-0013 | PS5-25-DM-3100A | CPX12 - HV Motor | #N/A | E | CRUDE OIL EXPORT PUMP A MOTOR |  | PS5-25-02 - Crude Oil Export Pump A
T-00025-0014 | PS5-25-DM-3100B | CPX12 - HV Motor | #N/A | E | CRUDE OIL EXPORT PUMP B MOTOR |  | PS5-25-03 - Crude Oil Export Pump B
T-00025-0015 | PS5-25-DM-3100C | CPX12 - HV Motor | #N/A | E | CRUDE OIL EXPORT PUMP C MOTOR |  | PS5-25-04 - Crude Oil Export Pump C
T-00026-0155 | PS5-28-DM-3300 | CPX13 - LV Motor | #N/A | E | Relief Drum Pump Motor |  | PS5-28-06 - Relief Drum and Pump
T-00026-0156 | PS5-28-DM-3400 | CPX13 - LV Motor | #N/A | E | Closed Drain Drum 01 Pump Motor |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00026-0157 | PS5-28-DM-3500 | CPX13 - LV Motor | #N/A | E | Oily Water Sump Pump Motor |  | PS5-28-08 - Open Drain Sump and Pumps
T-00026-0158 | PS5-28-DM-3600A | CPX13 - LV Motor | #N/A | E | Open Drain Sump Pump Motor A |  | PS5-28-08 - Open Drain Sump and Pumps
T-00026-0159 | PS5-28-DM-3600B | CPX13 - LV Motor | #N/A | E | Open Drain Sump Pump Motor B |  | PS5-28-08 - Open Drain Sump and Pumps
T-00026-0160 | PS5-28-DM-3700A | CPX13 - LV Motor | #N/A | E | Closed Drain Drum 02 Pump Motor A |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00026-0161 | PS5-28-DM-3700B | CPX13 - LV Motor | #N/A | E | Closed Drain Drum 02 Pump Motor B |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00026-0162 | PS5-28-DM-3800A | CPX13 - LV Motor | #N/A | E | Seal Oil Drain Drum Pump Motor A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00026-0163 | PS5-28-DM-3800B | CPX13 - LV Motor | #N/A | E | Seal Oil Drain Drum Pump Motor B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00026-0164 | PS5-28-DM-3800C | CPX13 - LV Motor | #N/A | E | Seal Oil Drain Drum Pump Motor C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00026-0165 | PS5-28-DM-3900A | CPX13 - LV Motor | #N/A | E | Reinjection Pump Motor A |  | PS5-28-17 - Reinjection Pump
T-00026-0166 | PS5-28-DM-3900B | CPX13 - LV Motor | #N/A | E | Reinjection Pump Motor B |  | PS5-28-17 - Reinjection Pump
T-00026-0167 | PS5-53-DM-3100A | CPX13 - LV Motor | #N/A | E | Water Distribution Pump Motor A |  | PS5-53-02 - Water Distribution Pump A/B
T-00026-0168 | PS5-53-DM-3100B | CPX13 - LV Motor | #N/A | E | Water Distribution Pump Motor B |  | PS5-53-02 - Water Distribution Pump A/B
T-00026-0169 | PS5-60-DM-3300 | CPX13 - LV Motor | #N/A | E | Cooling Water Pump Motor |  | PS5-60-24 - Cooling Water Tank & Pump
T-00026-0170 | PS5-60-DM-3400 | CPX13 - LV Motor | #N/A | E | Cooling Water Return Pump Motor |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump
T-00026-0171 | PS5-71-DM-3100A | CPX13 - LV Motor | #N/A | E | Diesel Fuel Supply Pump Motor A |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00026-0172 | PS5-71-DM-3100B | CPX13 - LV Motor | #N/A | E | Diesel Fuel Supply Pump Motor B |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00026-0173 | PS5-71-DM-3200 | CPX13 - LV Motor | #N/A | E | Diesel Fuel Make-Up Pump Motor |  | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station
T-00026-0174 | PS5-71-DM-3300A | CPX13 - LV Motor | #N/A | E | Crude Fuel Oil Transfer Pump Motor A |  | PS5-71-05 - CFO Transfer Pump A/B
T-00026-0175 | PS5-71-DM-3300B | CPX13 - LV Motor | #N/A | E | Crude Fuel Oil Transfer Pump Motor B |  | PS5-71-05 - CFO Transfer Pump A/B
T-00026-0176 | PS5-71-DM-3400A | CPX13 - LV Motor | #N/A | E | Crude Fuel Oil Service Pump Motor A |  | PS5-71-13 - CFO Service Pump A/B
T-00026-0177 | PS5-71-DM-3400B | CPX13 - LV Motor | #N/A | E | Crude Fuel Oil Service Pump Motor B |  | PS5-71-13 - CFO Service Pump A/B
T-00026-0178 | PS5-71-DM-3500A | CPX13 - LV Motor | #N/A | E | Diesel Transfer Pump Motor A |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00026-0179 | PS5-71-DM-3500B | CPX13 - LV Motor | #N/A | E | Diesel Transfer Pump Motor B |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00026-0286 | PS5-28-DM-31100 | CPX13 - LV Motor | #N/A | E | OIL SKIMMER MOTOR |  | PS5-28-10 - Oil Skimmer Package
T-00028-0462 | PS5-01-IG-0001 | CPX15 - Distribution Board | #N/A | E | Water Mist System Main Distribution Board |  | PS5-01-10 - Water Mist Package
T-00028-0463 | PS5-05-IG-0002 | CPX15 - Distribution Board | #N/A | E | Indoor Emergency L&SP DB Office and Facilities Building |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00028-0464 | PS5-05-IG-0004 | CPX15 - Distribution Board | #N/A | E | Outdoor Emergency Lighting Distribution Board PS-5 |  | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | CPP-RFI-68-332-03-0341 | 2026-06-15 | Accepted with punch | Bertus Wikael | Installation
T-00028-0465 | PS5-05-IG-0006 | CPX15 - Distribution Board | #N/A | E | Outdoor Emergency Lighting Distribution Board PS-5 |  | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | CPP-RFI-68-332-03-0341 | 2026-06-15 | Accepted with punch | Bertus Wikael | Installation
T-00028-0466 | PS5-05-IG-0007 | CPX15 - Distribution Board | #N/A | E | Indoor Emergency L&SP DB - Guard House |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00028-0467 | PS5-05-IG-0025 | CPX15 - Distribution Board | #N/A | E | CRO Generator Building Emergency Lighting Distribution Board PS-5 |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00028-0468 | PS5-05-IG-0026 | CPX15 - Distribution Board | #N/A | E | Generator Electrical Building Emergency Lighting Distribution Board PS-5 |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00028-0469 | PS5-06-IG-0004A | CPX15 - Distribution Board | #N/A | E | AC UPS DB - Generator Electrical Bldng |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-332-03-0406 | 2026-07-09 | Accepted with punch | Bertus Wikael | Installation
T-00028-0470 | PS5-06-IG-0004B | CPX15 - Distribution Board | #N/A | E | AC UPS DB - Generator Electrical Bldng |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-332-03-0406 | 2026-07-09 | Accepted with punch | Bertus Wikael | Installation
T-00028-0471 | PS5-61-IG-0006 | CPX15 - Distribution Board | #N/A | E | Outdoor Normal Lighting Distribution Board PS-5 |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | CPP-RFI-68-332-03-0341 | 2026-06-15 | Accepted with punch | Bertus Wikael | Installation
T-00028-0472 | PS5-61-IG-0007 | CPX15 - Distribution Board | #N/A | E | Outdoor Normal Lighting Distribution Board PS-5 |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | CPP-RFI-68-332-03-0341 | 2026-06-15 | Accepted with punch | Bertus Wikael | Installation
T-00028-0473 | PS5-61-IG-0014 | CPX15 - Distribution Board | #N/A | E | Outdoor Power Distribution Board PS-5 |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | CPP-RFI-68-332-03-0341 | 2026-06-15 | Accepted with punch | Bertus Wikael | Installation
T-00028-0474 | PS5-61-IG-0015 | CPX15 - Distribution Board | #N/A | E | CRO Generator Building Normal L&SP Distribution Board PS-5 |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00028-0475 | PS5-61-IG-0016 | CPX15 - Distribution Board | #N/A | E | Generator Electrical Building Normal L&SP Distribution Board PS-5 |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00028-0476 | PS5-61-IG-0042 | CPX15 - Distribution Board | #N/A | E | Outdoor valves Distribution Board PS-5 |  | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | CPP-RFI-68-332-03-0341 | 2026-06-15 | Accepted with punch | Bertus Wikael | Installation
T-00028-0477 | PS5-61-IG-0043 | CPX15 - Distribution Board | #N/A | E | Outdoor valves Distribution Board PS-5 |  | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | CPP-RFI-68-332-03-0341 | 2026-06-15 | Accepted with punch | Bertus Wikael | Installation
T-00028-0478 | PS5-74-IG-5101 | CPX15 - Distribution Board | #N/A | E | Nitrogen Generation Skid Power Distribution Panel |  | PS5-74-01 - N2 Generation Skid
T-00028-0479 | PS5-79-IG-0001 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 1 |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | CPP-RFI-68-33/2-03-0302 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00028-0480 | PS5-79-IG-0002 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 2 |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | CPP-RFI-68-33/2-03-0302 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00028-0481 | PS5-79-IG-0003 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 3 |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | CPP-RFI-68-33/2-03-0302 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00028-0482 | PS5-79-IG-0004 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 4 |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | CPP-RFI-68-33/2-03-0302 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00028-0483 | PS5-79-IG-0005 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 5 |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | CPP-RFI-68-33/2-03-0302 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00028-0484 | PS5-79-IG-0006 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 6 |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | CPP-RFI-68-33/2-03-0302 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00028-0485 | PS5-79-IG-0007 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 7 |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | CPP-RFI-68-33/2-03-0302 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00028-0486 | PS5-79-IG-0008 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 8 |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | CPP-RFI-68-33/2-03-0302 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00028-0487 | PS5-79-IG-0009 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 9 |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | CPP-RFI-68-33/2-03-0302 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00028-0488 | PS5-79-IG-0010 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 10 |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | CPP-RFI-68-33/2-03-0302 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00028-0489 | PS5-79-IG-0011 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 11 |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | CPP-RFI-68-33/2-03-0302 | 2026-05-26 | Accepted with punch | Bertus Wikael | Installation
T-00028-0490 | PS5-79-IG-0012 | CPX15 - Distribution Board | #N/A | E | EHT Distribution Board 12 |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00029-0234 | PS5-06-GU-0003A | CPX16 - Charger/Inverter | #N/A | E | AC UPS Generator Building |  | PS5-06-02 - AC UPS - Power Generator Building
T-00029-0235 | PS5-06-GU-0003B | CPX16 - Charger/Inverter | #N/A | E | AC UPS Generator Building |  | PS5-06-02 - AC UPS - Power Generator Building
T-00029-0236 | PS5-06-GU-0003C | CPX16 - Charger/Inverter | #N/A | E | AC UPS Generator Building - BYPASS |  | PS5-06-02 - AC UPS - Power Generator Building
T-00031-1264 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1265 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1266 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1267 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1268 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1269 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1270 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1271 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1272 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1273 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1274 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1275 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1276 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00031-1277 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00031-1278 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00031-1279 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00031-1280 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00031-1281 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00031-1282 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00031-1283 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00031-1284 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00031-1285 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00031-1286 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00031-1287 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00031-1288 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00031-1289 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00031-1290 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00031-1291 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00031-1292 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00031-1293 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00031-1294 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1295 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1296 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1297 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1298 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1299 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1300 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1301 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1302 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1303 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1304 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1305 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00031-1306 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00031-1307 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00031-1308 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00031-1309 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00031-1310 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00031-1311 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00031-1312 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00031-1313 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00031-1314 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00031-1315 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00031-1316 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00031-1317 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00031-1318 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00031-1319 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00031-1320 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00031-1321 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00031-1322 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00031-1323 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00031-1324 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00031-1325 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010
T-00031-1326 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010
T-00031-1327 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010
T-00031-1328 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1329 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1330 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1331 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1332 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1333 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1334 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1335 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1336 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1337 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1338 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1339 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1340 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1341 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00031-1342 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00031-1343 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00031-1344 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00031-1345 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00031-1346 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00031-1347 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111
T-00031-1348 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112
T-00031-1349 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1350 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1351 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1352 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1353 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1354 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1355 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1356 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1357 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1358 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1359 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1360 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1361 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1362 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1363 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00031-1364 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1365 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1366 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1367 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1368 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1369 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1370 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1371 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1372 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1373 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1374 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1375 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1376 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1377 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1378 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00031-1379 |  | CPX18 - Lighting Circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00032-0165 | PS5-25-UD-3100A | CPX19 - Power Socket Outlet | #N/A | E | 5 pin 32A plug and socket for Oil Purifier Control Panel(Portable Load) |  | PS5-25-02 - Crude Oil Export Pump A
T-00032-0166 | PS5-28-ISO-2008 | CPX19 - Power Socket Outlet | #N/A | E | Socket Outlet 63A for mobile oil skimmer (PS5-28-UZ-8100) |  | PS5-28-10 - Oil Skimmer Package
T-00032-0438 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00032-0439 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00032-0440 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00032-0441 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00032-0442 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00032-0443 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-06-05 - AC UPS - Workshop & Warehouse
T-00032-0444 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-06-05 - AC UPS - Workshop & Warehouse
T-00032-0445 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-06-05 - AC UPS - Workshop & Warehouse
T-00032-0446 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00032-0447 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00032-0448 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00032-0449 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00032-0450 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00032-0451 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00032-0452 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00032-0453 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00032-0454 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00032-0455 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00032-0456 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00032-0457 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010
T-00032-0458 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010
T-00032-0459 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00032-0460 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00032-0461 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00032-0462 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00032-0463 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00032-0464 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00032-0465 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00032-0466 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00032-0467 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00032-0468 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00032-0469 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00032-0470 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00032-0471 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00032-0472 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111
T-00032-0473 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111
T-00032-0474 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112
T-00032-0475 |  | CPX19 - Power Socket Outlet | #N/A | E |  |  | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112
T-00033-0044 | PS5-28-HE-2100 | CPX20 - Heater | #N/A | E | CLOSED DRAIN DRUM HEATER 01 |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00033-0045 | PS5-28-HE-2200 | CPX20 - Heater | #N/A | E | CLOSED DRAIN DRUM HEATER 02 |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00033-0046 | PS5-71-HE-2200 | CPX20 - Heater | #N/A | E | CRUDE FUEL OIL SERVICE TANK HEATER |  | PS5-71-12 - CFO Service Tank
T-00033-0047 | PS5-71-HE-2300 | CPX20 - Heater | #N/A | E | CRUDE FUEL OIL STORAGE TANK HEATER |  | PS5-71-04 - CFO Storage Tank
T-00033-0048 | PS5-71-HE-2400A | CPX20 - Heater | #N/A | E | CRUDE FUEL OIL STORAGE TANK FEED HEATER |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00033-0049 | PS5-71-HE-2400B | CPX20 - Heater | #N/A | E | CRUDE FUEL OIL STORAGE TANK FEED HEATER |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00033-0068 | PS5-25-HE-2100 | CPX20 - Heater | #N/A | E | Crude Oil Export Pump Motor A - Lube Oil System Oil Reservoir Heater |  | PS5-25-02 - Crude Oil Export Pump A
T-00033-0069 | PS5-25-HE-2200 | CPX20 - Heater | #N/A | E | Crude Oil Export Pump Motor B - Lube Oil System Oil Reservoir Heater |  | PS5-25-03 - Crude Oil Export Pump B
T-00033-0070 | PS5-25-HE-2300 | CPX20 - Heater | #N/A | E | Crude Oil Export Pump Motor C - Lube Oil System Oil Reservoir Heater |  | PS5-25-04 - Crude Oil Export Pump C
T-00034-0041 | PS5-61-NER-0010 | CPX21 - Neutral Earthing Resistor | #N/A | E | LLHT Transformer NER |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010)
T-00034-0042 | PS5-61-NER-0011 | CPX21 - Neutral Earthing Resistor | #N/A | E | LLHT Transformer NER |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011)
T-00034-0043 | PS5-63-NER-0010 | CPX21 - Neutral Earthing Resistor | #N/A | E | Earthing Transformer NER |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00034-0044 | PS5-63-NER-0011 | CPX21 - Neutral Earthing Resistor | #N/A | E | Earthing Transformer NER |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00034-0059 | PS5-60-IJ-0001A | CPX21 - Neutral Earthing Resistor | #N/A | E | Neutral Grounding resistor for Generator set 1 (A) |  | PS5-60-01 - Power Generation Package A
T-00034-0060 | PS5-60-IJ-0001B | CPX21 - Neutral Earthing Resistor | #N/A | E | Neutral Grounding resistor for Generator set 2 (B) |  | PS5-60-04 - Power Generation Package B
T-00034-0061 | PS5-60-IJ-0001C | CPX21 - Neutral Earthing Resistor | #N/A | E | Neutral Grounding resistor for Generator set 3 (C) |  | PS5-60-07 - Power Generation Package C
T-00034-0062 | PS5-60-IJ-0001D | CPX21 - Neutral Earthing Resistor | #N/A | E | Neutral Grounding resistor for Generator set 4 (D) |  | PS5-60-10 - Power Generation Package D
T-00034-0063 | PS5-60-IJ-0001E | CPX21 - Neutral Earthing Resistor | #N/A | E | Neutral Grounding resistor for Generator set 5 (E) |  | PS5-60-13 - Power Generation Package E
T-00034-0064 | PS5-60-IJ-0001F | CPX21 - Neutral Earthing Resistor | #N/A | E | Neutral Grounding resistor for Generator set 6 (F) |  | PS5-60-16 - Power Generation Package F
T-00034-0065 | PS5-60-IJ-0001G | CPX21 - Neutral Earthing Resistor | #N/A | E | Neutral Grounding resistor for Generator set 7 (G) |  | PS5-60-19 - Power Generation Package G
T-00035-1357 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1358 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1359 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1360 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1361 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1362 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1363 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1364 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1365 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1366 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1367 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1368 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1369 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1370 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1371 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1372 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1373 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1374 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1375 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1376 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1377 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1378 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1379 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1380 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1381 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1382 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1383 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1384 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1385 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00035-1386 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1387 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1388 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1389 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1390 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1391 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1392 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1393 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1394 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1395 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1396 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1397 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1398 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1399 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1400 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1401 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1402 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1403 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1404 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1405 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1406 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1407 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1408 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1409 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1410 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1411 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1412 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1413 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1414 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1415 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00035-1416 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1417 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1418 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1419 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1420 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1421 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1422 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1423 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1424 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1425 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1426 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1427 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1428 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1429 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1430 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1431 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1432 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1433 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1434 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1435 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1436 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1437 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1438 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1439 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1440 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1441 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1442 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1443 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1444 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00035-1445 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1446 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1447 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1448 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1449 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1450 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1451 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1452 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1453 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1454 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1455 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1456 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1457 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1458 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1459 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1460 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1461 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1462 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1463 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1464 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1465 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1466 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1467 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1468 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1469 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1470 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1471 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00035-1472 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1473 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1474 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1475 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1476 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1477 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1478 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1479 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1480 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1481 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1482 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1483 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1484 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1485 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1486 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1487 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1488 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1489 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1490 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1491 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1492 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1493 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1494 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1495 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1496 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1497 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1498 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1499 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00035-1500 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1501 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1502 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1503 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1504 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1505 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1506 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1507 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1508 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1509 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1510 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1511 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1512 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1513 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1514 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1515 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1516 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1517 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1518 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1519 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1520 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1521 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1522 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1523 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1524 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1525 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1526 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1527 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1528 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1529 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1530 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1531 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00035-1532 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1533 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1534 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1535 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1536 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1537 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1538 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1539 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1540 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1541 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1542 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1543 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1544 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1545 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1546 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1547 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1548 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1549 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1550 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1551 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1552 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1553 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1554 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1555 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1556 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1557 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1558 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1559 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1560 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1561 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1562 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1563 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00035-1564 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1565 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1566 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1567 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1568 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1569 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1570 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1571 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1572 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1573 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1574 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1575 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1576 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1577 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1578 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1579 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1580 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1581 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1582 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1583 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1584 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1585 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1586 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1587 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1588 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1589 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1590 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1591 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1592 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1593 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1594 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1595 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00035-1596 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1597 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1598 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1599 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1600 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1601 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1602 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1603 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1604 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1605 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1606 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1607 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1608 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1609 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1610 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1611 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1612 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1613 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1614 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1615 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1616 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1617 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1618 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1619 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1620 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1621 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1622 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1623 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1624 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1625 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1626 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1627 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00035-1628 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1629 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1630 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1631 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1632 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1633 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1634 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1635 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1636 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1637 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1638 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1639 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1640 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1641 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1642 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1643 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1644 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1645 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1646 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1647 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1648 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1649 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1650 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1651 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1652 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1653 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1654 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1655 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1656 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1657 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00035-1658 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1659 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1660 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1661 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1662 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1663 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1664 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1665 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1666 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1667 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1668 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1669 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1670 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1671 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1672 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1673 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1674 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1675 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1676 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1677 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1678 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1679 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1680 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1681 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1682 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1683 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1684 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1685 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1686 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1687 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00035-1688 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1689 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1690 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1691 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1692 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1693 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1694 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1695 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1696 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1697 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1698 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1699 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1700 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1701 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1702 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1703 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1704 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1705 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1706 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1707 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1708 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1709 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1710 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1711 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1712 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1713 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1714 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1715 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1716 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1717 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1718 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1719 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1720 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1721 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00035-1722 |  | CPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00039-0283 | PS5 - CFO AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0284 | PS5 - CHEMICAL AND WASTE STORAGE AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0285 | PS5 - CLOSED DRAIN DRUM AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0286 | PS5 - DIESEL FUEL STORAGE AND PUMP AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0287 | PS5 - EXPORT PUMP VSD AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0288 | PS5 - EXPORT LOADING PUMP AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0289 | PS5 - FENCE EAST AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0290 | PS5 - FENCE SOUTH WEST AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0291 | PS5 - FENCE WEST AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0292 | PS5 - FENCE SOUTH EAST AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0293 | PS5 - LAUNCHER/RECEIVER AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0294 | PS5 - OBSERVATION BASIN AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0295 | PS5 - POWER DISTRIBUTION AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0296 | PS5 - POWER GENERATION BUILDING AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0297 | PS5 - POWER GENERATION COOLING TOWER AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0298 | PS5 - TURNSTILE GATE AND OFFICE BUILDING AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0299 | PS5 - UTILITY AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0300 | PS5 - UTILITY/FIRE WATER STORAGE TANK AREA_Earthing | CPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00039-0301 | PS5-82-OB-0001_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Office and Facilities building |  | PS5-63-02 - Electrical Earthing - Office and Facilities building
T-00039-0302 | PS5-82-OB-0005_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Guard House |  | PS5-63-06 - Electrical Earthing - Guard House
T-00039-0303 | PS5-82-OB-0009A_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Guard Hut A |  | PS5-63-05 - Electrical Earthing - Guard Hut A & B
T-00039-0304 | PS5-82-OB-0009B_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Guard Hut B |  | PS5-63-05 - Electrical Earthing - Guard Hut A & B
T-00039-0306 | PS5-84-OB-0001_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Workshop & Warehouse |  | PS5-63-07 - Electrical Earthing - Workshop & Warehouse
T-00039-0307 | PS5-84-OB-0003_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Hazardous Waste Shelter |  | PS5-63-01 - Electrical Earthing
T-00039-0308 | PS5-84-OB-0004_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Non-Hazardous Waste Shelter |  | PS5-63-01 - Electrical Earthing
T-00039-0309 | PS5-84-OB-0005_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Generator Electrical Building |  | PS5-63-03 - Electrical Earthing - Generator Building
T-00039-0310 | PS5-84-OB-0006_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Chemical Storage Shelter |  | PS5-63-01 - Electrical Earthing
T-00039-0311 | PS5-84-OB-0007_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Chemical Waste Storage Shelter |  | PS5-63-01 - Electrical Earthing
T-00039-0312 | PS5-86-OB-0001_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Closed Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00039-0313 | PS5-86-OB-0002_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Relief Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00039-0314 | PS5-86-OB-0003_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Fire Water Pump Shelter |  | PS5-63-01 - Electrical Earthing
T-00039-0315 | PS5-86-OB-0004_Earthing | CPX26 - Earthing system | #N/A | E | Earthing for Closed Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00040-0052 | PS5 - RECEIVER AND LAUNCHER AREA_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning |  | PS5-63-01 - Electrical Earthing
T-00040-0053 | PS5-82-OB-0001_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Office and Facilities building |  | PS5-63-02 - Electrical Earthing - Office and Facilities building
T-00040-0054 | PS5-82-OB-0005_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Guard House |  | PS5-63-06 - Electrical Earthing - Guard House
T-00040-0055 | PS5-82-OB-0009A_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Guard Hut A |  | PS5-63-05 - Electrical Earthing - Guard Hut A & B
T-00040-0056 | PS5-82-OB-0009B_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Guard Hut B |  | PS5-63-05 - Electrical Earthing - Guard Hut A & B
T-00040-0057 | PS5-84-OB-0001_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Workshop & Warehouse |  | PS5-63-07 - Electrical Earthing - Workshop & Warehouse
T-00040-0058 | PS5-84-OB-0003_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Hazardous Waste Shelter |  | PS5-63-01 - Electrical Earthing
T-00040-0059 | PS5-84-OB-0005_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Generator Electrical Building |  | PS5-63-03 - Electrical Earthing - Generator Building
T-00040-0060 | PS5-84-OB-0006_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Chemical Storage Shelter |  | PS5-63-01 - Electrical Earthing
T-00040-0061 | PS5-84-OB-0007_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Chemical Waste Storage Shelter |  | PS5-63-01 - Electrical Earthing
T-00040-0062 | PS5-86-OB-0001_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Closed Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00040-0063 | PS5-86-OB-0002_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Relief Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00040-0064 | PS5-86-OB-0003_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Fire Water Pump Shelter |  | PS5-63-01 - Electrical Earthing
T-00040-0065 | PS5-86-OB-0004_Lightning | CPX28 - Lightning protection system | #N/A | E | Lightning for Closed Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00041-0026 | PS5-82-OB-0001 | CPX29 - MCT cabling | #N/A | E | Office and Facilities building |  | PS5-82-05 - Office and Facilities building
T-00041-0027 | PS5-82-OB-0005 | CPX29 - MCT cabling | #N/A | E | Guard House |  | PS5-82-06 - Guard House Building
T-00041-0028 | PS5-84-OB-0005 | CPX29 - MCT cabling | #N/A | E | Generator Electrical Building |  | PS5-84-01 - Generator Building
T-00042-0142 | PS5_AREA_COMPLETION_FOR_BUILDING_AREA_-_NORTH | CPX30 - Cable tray / ladder | #N/A | E | Area completion |  | PS5-99-01 - Area Completion for Building area
T-00042-0143 | PS5_AREA_COMPLETION_FOR_BUILDING_AREA_-_NORTH_WEST | CPX30 - Cable tray / ladder | #N/A | E | Area completion |  | PS5-99-01 - Area Completion for Building area
T-00042-0144 | PS5_AREA_COMPLETION_FOR_CFO_AREA | CPX30 - Cable tray / ladder | #N/A | E | Area completion |  | PS5-99-05 - Area Completion for CFO area
T-00042-0145 | PS5_AREA_COMPLETION_FOR_POWER_DISTRIBUTION_AREA | CPX30 - Cable tray / ladder | #N/A | E | Area completion |  | PS5-99-03 - Area Completion for Power Distribution area
T-00042-0146 | PS5_AREA_COMPLETION_FOR_POWER_GENERATION_AREA | CPX30 - Cable tray / ladder | #N/A | E | Area completion |  | PS5-99-06 - Area Completion for Power Generation area
T-00042-0147 | PS5_AREA_COMPLETION_FOR_PROCESS_AREA | CPX30 - Cable tray / ladder | #N/A | E | Area completion |  | PS5-99-04 - Area Completion for Process area
T-00042-0148 | PS5_AREA_COMPLETION_FOR_PROCESS_AREA_-_NORTH | CPX30 - Cable tray / ladder | #N/A | E | Area completion |  | PS5-99-04 - Area Completion for Process area
T-00042-0149 | PS5_AREA_COMPLETION_FOR_PROCESS_AREA_SOUTH | CPX30 - Cable tray / ladder | #N/A | E | Area completion |  | PS5-99-04 - Area Completion for Process area
T-00042-0150 | PS5_AREA_COMPLETION_FOR_UTILITY_AREA | CPX30 - Cable tray / ladder | #N/A | E | Area completion |  | PS5-99-02 - Area Completion for Utility area
T-00042-0167 | PS5-82-OB-0001 | CPX30 - Cable tray / ladder | #N/A | E | Office and Facilities building |  | PS5-82-05 - Office and Facilities building
T-00042-0168 | PS5-82-OB-0005 | CPX30 - Cable tray / ladder | #N/A | E | Guard House |  | PS5-82-06 - Guard House Building
T-00042-0169 | PS5-84-OB-0005 | CPX30 - Cable tray / ladder | #N/A | E | Generator Electrical Building |  | PS5-84-01 - Generator Building
T-00042-0208 | PS5-83-OB-0001_Installation | CPX30 - Cable tray / ladder | #N/A | E | EITS Building |  | PS5-83-01 - EITS Building
T-00043-0045 | PS5-79-BH-0001 | CPX31 - Junction and marshalling box | #N/A | E | LLHT High Voltage Power Junction Box |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010)
T-00043-0046 | PS5-79-BH-0002 | CPX31 - Junction and marshalling box | #N/A | E | LLHT High Voltage Power Junction Box |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011)
T-00044-0090 | PS5-60-IE-0003A | CPX32 - Console / control panel | #N/A | E | GCP G-1 (A) |  | PS5-60-02 - Power Gen Package A (UCP)
T-00044-0091 | PS5-60-IE-0003B | CPX32 - Console / control panel | #N/A | E | GCP G-2 (B) |  | PS5-60-05 - Power Gen Package B (UCP)
T-00044-0092 | PS5-60-IE-0003C | CPX32 - Console / control panel | #N/A | E | GCP G-3 (C) |  | PS5-60-08 - Power Gen Package C (UCP)
T-00044-0093 | PS5-60-IE-0003D | CPX32 - Console / control panel | #N/A | E | GCP G-4 (D) |  | PS5-60-11 - Power Gen Package D (UCP)
T-00044-0094 | PS5-60-IE-0003E | CPX32 - Console / control panel | #N/A | E | GCP G-5 (E) |  | PS5-60-14 - Power Gen Package E (UCP)
T-00044-0095 | PS5-60-IE-0003F | CPX32 - Console / control panel | #N/A | E | GCP G-6 (F) |  | PS5-60-17 - Power Gen Package F (UCP)
T-00044-0096 | PS5-60-IE-0003G | CPX32 - Console / control panel | #N/A | E | GCP G-7 (G) |  | PS5-60-20 - Power Gen Package G (UCP)
T-00044-0097 | PS5-60-IE-0004 | CPX32 - Console / control panel | #N/A | E | MCP- MASTER CONTROL PANEL |  | PS5-60-22 - Power Gen Master UCP
T-00044-0098 | PS5-60-IH-0001A | CPX32 - Console / control panel | #N/A | E | GENSET MCC -1 - G1 (A) |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs
T-00044-0099 | PS5-60-IH-0001B | CPX32 - Console / control panel | #N/A | E | GENSET MCC -2 - G2 (B) |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs
T-00044-0100 | PS5-60-IH-0001C | CPX32 - Console / control panel | #N/A | E | GENSET MCC -3 - G3 (C) |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs
T-00044-0101 | PS5-60-IH-0001D | CPX32 - Console / control panel | #N/A | E | GENSET MCC -4 - G4 (D) |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs
T-00044-0102 | PS5-60-IH-0001E | CPX32 - Console / control panel | #N/A | E | GENSET MCC -5 - G5 (E) |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00044-0103 | PS5-60-IH-0001F | CPX32 - Console / control panel | #N/A | E | GENSET MCC -6 - G6 (F) |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00044-0104 | PS5-60-IH-0001G | CPX32 - Console / control panel | #N/A | E | GENSET MCC -7 - G7 (G) |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00044-0105 | PS5-60-IH-0002 | CPX32 - Console / control panel | #N/A | E | COMMON / TREATMENT MCC |  | PS5-60-22 - Power Gen Master UCP
T-00044-0106 | PS5-60-IE-0002A | CPX32 - Console / control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-01 - Power Generation Package A
T-00044-0107 | PS5-60-IE-0002B | CPX32 - Console / control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-04 - Power Generation Package B
T-00044-0108 | PS5-60-IE-0002C | CPX32 - Console / control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-07 - Power Generation Package C
T-00044-0109 | PS5-60-IE-0002D | CPX32 - Console / control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-10 - Power Generation Package D
T-00044-0110 | PS5-60-IE-0002E | CPX32 - Console / control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-13 - Power Generation Package E
T-00044-0111 | PS5-60-IE-0002F | CPX32 - Console / control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-16 - Power Generation Package F
T-00044-0112 | PS5-60-IE-0002G | CPX32 - Console / control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-19 - Power Generation Package G
T-00044-0175 | PS5-01-IE-0001A | CPX32 - Console / control panel | #N/A | E | Foam Package (PS5-01-UV-8700 Pump Control Panel A) |  | PS5-01-05 - Foam Skid
T-00044-0176 | PS5-01-IE-0001B | CPX32 - Console / control panel | #N/A | E | Foam Package (PS5-01-UV-8700 Pump Control Panel B) |  | PS5-01-05 - Foam Skid
T-00044-0177 | PS5-01-IE-0002A | CPX32 - Console / control panel | #N/A | E | Fire Water Jockey Pump Control Panel A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00044-0178 | PS5-01-IE-0002B | CPX32 - Console / control panel | #N/A | E | Fire Water Jockey Pump Control Panel B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00044-0179 | PS5-01-IE-0009A | CPX32 - Console / control panel | #N/A | E | Fire Water starter pump Local Control Panel A |  | PS5-01-02 - Fire Water Pump A
T-00044-0180 | PS5-01-IE-0009B | CPX32 - Console / control panel | #N/A | E | Fire Water starter pump Local Control Panel B |  | PS5-01-03 - Fire Water Pump B
T-00044-0182 | PS5-05-IE-8100 | CPX32 - Console / control panel | #N/A | E | Unit Control Panel for Emergency Diesel Generator |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-332-03-0406 | 2026-07-09 | Accepted with punch | Bertus Wikael | Installation
T-00044-0183 | PS5-50-IE-0001 | CPX32 - Console / control panel | #N/A | E | Water Well Submersible Pump Control Panel A |  | PS5-50-01 - Water Well Submersible Pumps (3100)
T-00044-0184 | PS5-50-IE-0002 | CPX32 - Console / control panel | #N/A | E | Water Well Submersible Pump Control Panel B |  | PS5-50-02 - Water Well Submersible Pumps (3200)
T-00044-0185 | PS5-60-IN-0002A | CPX32 - Console / control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00044-0186 | PS5-60-IN-0002B | CPX32 - Console / control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00044-0187 | PS5-60-IN-0002C | CPX32 - Console / control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00044-0188 | PS5-60-IN-0002D | CPX32 - Console / control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00044-0189 | PS5-60-IN-0002E | CPX32 - Console / control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00044-0190 | PS5-60-IN-0002F | CPX32 - Console / control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00044-0191 | PS5-60-IN-0002G | CPX32 - Console / control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00044-0192 | PS5-61-IH-0004 | CPX32 - Console / control panel | #N/A | E | HVAC MCC |  | PS5-09-03 - HVAC for Generator Building
T-00044-0193 | PS5-61-IH-0004A | CPX32 - Console / control panel | #N/A | E | LOCAL STARTER PANEL FOR GENRATOR BAY 1 EXHAUST FANS |  | PS5-09-03 - HVAC for Generator Building
T-00044-0194 | PS5-61-IH-0004B | CPX32 - Console / control panel | #N/A | E | LOCAL STARTER PANEL FOR GENRATOR BAY 2 EXHAUST FANS |  | PS5-09-03 - HVAC for Generator Building
T-00044-0195 | PS5-62-IE-0001 | CPX32 - Console / control panel | #N/A | E | Lighting Control panel 1 - Pump Station 5 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPP-RFI-68-332-03-0341 | 2026-06-15 | Accepted with punch | Bertus Wikael | Installation
T-00044-0196 | PS5-62-IE-0002 | CPX32 - Console / control panel | #N/A | E | Lighting Control panel 2 - Pump Station 5 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPP-RFI-68-332-03-0341 | 2026-06-15 | Accepted with punch | Bertus Wikael | Installation
T-00044-0197 | PS5-71-IN-0001 | CPX32 - Console / control panel | #N/A | E | DFO- SEPARATOR CONTROL PANEL |  | PS5-71-19 - Diesel Separator Module (UCP)
T-00044-0198 | PS5-71-IN-0002 | CPX32 - Console / control panel | #N/A | E | CRO-PRE PRESSURECONTROL PANEL |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP)
T-00044-0199 | PS5-71-IN-0003 | CPX32 - Console / control panel | #N/A | E | DFO- PRE PRESSURE CONTROL PANEL |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP)
T-00044-0200 | PS5-71-IN-0004A | CPX32 - Console / control panel | #N/A | E | CRO- SEPARATOR CONTROL PANEL-1 |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00044-0201 | PS5-71-IN-0004B | CPX32 - Console / control panel | #N/A | E | CRO- SEPARATOR CONTROL PANEL-2 |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00044-0267 | PS5-09-LB-0008 | CPX32 - Console / control panel | #N/A | E | HUCP |  | PS5-09-03 - HVAC for Generator Building
T-00044-0268 | PS5-61-IH-0004C | CPX32 - Console / control panel | #N/A | E | LOCAL STARTER PANEL FOR GENRATOR BAY 3 EXHAUST FANS |  | PS5-09-03 - HVAC for Generator Building
T-00044-0269 | PS5-61-IH-0004D | CPX32 - Console / control panel | #N/A | E | LOCAL STARTER PANEL FOR GENRATOR BAY 4 EXHAUST FANS |  | PS5-09-03 - HVAC for Generator Building
T-00044-0279 | PS5-09-LB-7001 | CPX32 - Console / control panel | #N/A | E | HVAC UCP - Guard House |  | PS5-09-02 - HVAC for Guard House
T-00045-0008 | PS5-53-TR-4100 | CPX33 - Cathodic protection | #N/A | E | UTILITY WATER / FIRE WATER STORAGE TANK |  | PS5-53-01 - Utility Water / Storage Tank
T-00045-0009 | PS5-71-TR-4100 | CPX33 - Cathodic protection | #N/A | E | CRUDE FUEL OIL STORAGE TANK |  | PS5-71-04 - CFO Storage Tank
T-00045-0010 | PS5-71-TR-4200 | CPX33 - Cathodic protection | #N/A | E | CRUDE FUEL OIL SERVICE TANK |  | PS5-71-12 - CFO Service Tank
T-00045-0011 | PS5-71-TR-4400 | CPX33 - Cathodic protection | #N/A | E | DIESEL FUEL STORAGE TANK |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00046-0013 | PS5-01-UK-6100 | CZX01E - Package | #N/A | E | DELUGE VALVE SKID |  | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100)
T-00046-0014 | PS5-01-UV-8700 | CZX01E - Package | #N/A | E | FOAM SKID |  | PS5-01-05 - Foam Skid
T-00046-0291 | PS5-60-UR-8100A | CZX01E - Package | #N/A | E | POWER GENERATION PACKAGE A |  | PS5-60-01 - Power Generation Package A
T-00046-0292 | PS5-60-UR-8100B | CZX01E - Package | #N/A | E | POWER GENERATION PACKAGE B |  | PS5-60-04 - Power Generation Package B
T-00046-0293 | PS5-60-UR-8100C | CZX01E - Package | #N/A | E | POWER GENERATION PACKAGE C |  | PS5-60-07 - Power Generation Package C
T-00046-0294 | PS5-60-UR-8100D | CZX01E - Package | #N/A | E | POWER GENERATION PACKAGE D |  | PS5-60-10 - Power Generation Package D
T-00046-0295 | PS5-60-UR-8100E | CZX01E - Package | #N/A | E | POWER GENERATION PACKAGE E |  | PS5-60-13 - Power Generation Package E
T-00046-0296 | PS5-60-UR-8100F | CZX01E - Package | #N/A | E | POWER GENERATION PACKAGE F |  | PS5-60-16 - Power Generation Package F
T-00046-0297 | PS5-60-UR-8100G | CZX01E - Package | #N/A | E | POWER GENERATION PACKAGE G |  | PS5-60-19 - Power Generation Package G
T-00046-0298 | PS5-05-UR-8100 | CZX01E - Package | #N/A | E | EMERGENCY DIESEL ENGINE GENERATOR PACKAGE |  | PS5-05-01 - Emergency Diesel Generator Package
T-00046-0299 | PS5-71-UZ-6200 | CZX01E - Package | #N/A | E | DIESEL FUEL DISPENSER STATION |  | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station
T-00046-0300 | PS5-60-UA-5100 | CZX01E - Package | #N/A | E | COMPRESSOR AIR STARTING SKID |  | PS5-60-27 - Compressed Air Starting Skid
T-00046-0301 | PS5-60-UO-81100A | CZX01E - Package | #N/A | E | LUBE OIL SEPARATOR MODULE |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A
T-00046-0302 | PS5-60-UO-81100B | CZX01E - Package | #N/A | E | LUBE OIL SEPARATOR MODULE |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B
T-00046-0303 | PS5-60-UO-81100C | CZX01E - Package | #N/A | E | LUBE OIL SEPARATOR MODULE |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C
T-00046-0304 | PS5-60-UO-81100D | CZX01E - Package | #N/A | E | LUBE OIL SEPARATOR MODULE |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D
T-00046-0305 | PS5-60-UO-81100E | CZX01E - Package | #N/A | E | LUBE OIL SEPARATOR MODULE |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E
T-00046-0306 | PS5-60-UO-81100F | CZX01E - Package | #N/A | E | LUBE OIL SEPARATOR MODULE |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F
T-00046-0307 | PS5-60-UO-81100G | CZX01E - Package | #N/A | E | LUBE OIL SEPARATOR MODULE |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G
T-00046-0308 | PS5-60-UZ-8200A | CZX01E - Package | #N/A | E | INJECTOR TIP COOLING MODULE |  | PS5-60-35 - Injector Tip Cooling Module A
T-00046-0309 | PS5-60-UZ-8200B | CZX01E - Package | #N/A | E | INJECTOR TIP COOLING MODULE |  | PS5-60-36 - Injector Tip Cooling Module B
T-00046-0310 | PS5-60-UZ-8200C | CZX01E - Package | #N/A | E | INJECTOR TIP COOLING MODULE |  | PS5-60-37 - Injector Tip Cooling Module C
T-00046-0311 | PS5-60-UZ-8200D | CZX01E - Package | #N/A | E | INJECTOR TIP COOLING MODULE |  | PS5-60-38 - Injector Tip Cooling Module D
T-00046-0312 | PS5-60-UZ-8200E | CZX01E - Package | #N/A | E | INJECTOR TIP COOLING MODULE |  | PS5-60-39 - Injector Tip Cooling Module E
T-00046-0313 | PS5-60-UZ-8200F | CZX01E - Package | #N/A | E | INJECTOR TIP COOLING MODULE |  | PS5-60-40 - Injector Tip Cooling Module F
T-00046-0314 | PS5-60-VS-9100A | CZX01E - Package | #N/A | E | OIL MIST SEPARATOR SKID |  | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A
T-00046-0315 | PS5-60-VS-9100B | CZX01E - Package | #N/A | E | OIL MIST SEPARATOR SKID |  | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B
T-00046-0316 | PS5-60-VS-9100C | CZX01E - Package | #N/A | E | OIL MIST SEPARATOR SKID |  | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C
T-00046-0317 | PS5-60-VS-9100D | CZX01E - Package | #N/A | E | OIL MIST SEPARATOR SKID |  | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D
T-00046-0318 | PS5-60-VS-9100E | CZX01E - Package | #N/A | E | OIL MIST SEPARATOR SKID |  | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E
T-00046-0319 | PS5-60-VS-9100F | CZX01E - Package | #N/A | E | OIL MIST SEPARATOR SKID |  | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F
T-00046-0320 | PS5-60-VS-9100G | CZX01E - Package | #N/A | E | OIL MIST SEPARATOR SKID |  | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G
T-00046-0321 | PS5-71-UZ-6500 | CZX01E - Package | #N/A | E | DIESEL FUEL SEPARATOR MODULE |  | PS5-71-18 - Diesel Separator Module
T-00046-0322 | PS5-71-UZ-6800A | CZX01E - Package | #N/A | E | CRUDE FUEL SEPARATOR MODULE A |  | PS5-71-06 - Crude Fuel Separation Module
T-00046-0323 | PS5-71-UZ-6800B | CZX01E - Package | #N/A | E | CRUDE FUEL SEPARATOR MODULE B |  | PS5-71-06 - Crude Fuel Separation Module
T-00046-0324 | PS5-01-UZ-6900 | CZX01E - Package | #N/A | E | WATER MIST FIRE PROTECTION PACKAGE |  | PS5-01-10 - Water Mist Package
T-00046-0325 | PS5-53-UT-8100 | CZX01E - Package | #N/A | E | WATER PRE-TREATMENT PACKAGE |  | PS5-50-03 - Water Pre-Treatment Package
T-00046-0326 | PS5-53-UT-8200 | CZX01E - Package | #N/A | E | WATER TREATMENT/ PURIFICATION PACKAGE |  | PS5-53-04 - Water Treatment Purification Package
T-00046-0327 | PS5-60-EA-2100A | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-70 - Engine A Cooling system
T-00046-0328 | PS5-60-EA-2100B | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-70 - Engine A Cooling system
T-00046-0329 | PS5-60-EA-21100A | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-01 - Power Generation Package A
T-00046-0330 | PS5-60-EA-21100B | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-04 - Power Generation Package B
T-00046-0331 | PS5-60-EA-21100C | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-07 - Power Generation Package C
T-00046-0332 | PS5-60-EA-21100D | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-10 - Power Generation Package D
T-00046-0333 | PS5-60-EA-21100E | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-13 - Power Generation Package E
T-00046-0334 | PS5-60-EA-21100F | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-16 - Power Generation Package F
T-00046-0335 | PS5-60-EA-21100G | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-19 - Power Generation Package G
T-00046-0336 | PS5-60-EA-21200A | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-01 - Power Generation Package A
T-00046-0337 | PS5-60-EA-21200B | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-04 - Power Generation Package B
T-00046-0338 | PS5-60-EA-21200C | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-07 - Power Generation Package C
T-00046-0339 | PS5-60-EA-21200D | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-10 - Power Generation Package D
T-00046-0340 | PS5-60-EA-21200E | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-13 - Power Generation Package E
T-00046-0341 | PS5-60-EA-21200F | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-16 - Power Generation Package F
T-00046-0342 | PS5-60-EA-21200G | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-19 - Power Generation Package G
T-00046-0343 | PS5-60-EA-2200A | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-71 - Engine B Cooling system
T-00046-0344 | PS5-60-EA-2200B | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-71 - Engine B Cooling system
T-00046-0345 | PS5-60-EA-2300A | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-72 - Engine C Cooling system
T-00046-0346 | PS5-60-EA-2300B | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-72 - Engine C Cooling system
T-00046-0347 | PS5-60-EA-2400A | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-73 - Engine D Cooling system
T-00046-0348 | PS5-60-EA-2400B | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-73 - Engine D Cooling system
T-00046-0349 | PS5-60-EA-2500A | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-74 - Engine E Cooling system
T-00046-0350 | PS5-60-EA-2500B | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-74 - Engine E Cooling system
T-00046-0351 | PS5-60-EA-2600A | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-75 - Engine F Cooling system
T-00046-0352 | PS5-60-EA-2600B | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-75 - Engine F Cooling system
T-00046-0353 | PS5-60-EA-2700A | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-76 - Engine G Cooling system
T-00046-0354 | PS5-60-EA-2700B | CZX01E - Package | #N/A | E | POWER GENERATION ENGINE RADIATOR |  | PS5-60-76 - Engine G Cooling system
T-00046-0355 | PS5-60-EA-2800A | CZX01E - Package | #N/A | E | RADIATOR |  | PS5-60-35 - Injector Tip Cooling Module A
T-00046-0356 | PS5-60-EA-2800B | CZX01E - Package | #N/A | E | RADIATOR |  | PS5-60-36 - Injector Tip Cooling Module B
T-00046-0357 | PS5-60-EA-2800C | CZX01E - Package | #N/A | E | RADIATOR |  | PS5-60-37 - Injector Tip Cooling Module C
T-00046-0358 | PS5-60-EA-2800D | CZX01E - Package | #N/A | E | RADIATOR |  | PS5-60-38 - Injector Tip Cooling Module D
T-00046-0359 | PS5-60-EA-2800E | CZX01E - Package | #N/A | E | RADIATOR |  | PS5-60-39 - Injector Tip Cooling Module E
T-00046-0360 | PS5-60-EA-2800F | CZX01E - Package | #N/A | E | RADIATOR |  | PS5-60-40 - Injector Tip Cooling Module F
T-00046-0361 | PS5-60-EA-2800G | CZX01E - Package | #N/A | E | RADIATOR |  | PS5-60-41 - Injector Tip Cooling Module G
T-00046-0362 | PS5-60-EA-2900A | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A
T-00046-0363 | PS5-60-EA-2900B | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B
T-00046-0364 | PS5-60-EA-2900C | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00046-0365 | PS5-60-EA-2900D | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00046-0366 | PS5-60-EA-2900E | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00046-0367 | PS5-60-EA-2900F | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00046-0368 | PS5-60-EA-2900G | CZX01E - Package | #N/A | E | COOLING SKID |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00046-0369 | PS5-60-TCV-0001A | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-70 - Engine A Cooling system
T-00046-0370 | PS5-60-TCV-0001B | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-71 - Engine B Cooling system
T-00046-0371 | PS5-60-TCV-0001C | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-72 - Engine C Cooling system
T-00046-0372 | PS5-60-TCV-0001D | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-73 - Engine D Cooling system
T-00046-0373 | PS5-60-TCV-0001E | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-74 - Engine E Cooling system
T-00046-0374 | PS5-60-TCV-0001F | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-75 - Engine F Cooling system
T-00046-0375 | PS5-60-TCV-0001G | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-76 - Engine G Cooling system
T-00046-0376 | PS5-60-TCV-0002A | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-70 - Engine A Cooling system
T-00046-0377 | PS5-60-TCV-0002B | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-71 - Engine B Cooling system
T-00046-0378 | PS5-60-TCV-0002C | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-72 - Engine C Cooling system
T-00046-0379 | PS5-60-TCV-0002D | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-73 - Engine D Cooling system
T-00046-0380 | PS5-60-TCV-0002E | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-74 - Engine E Cooling system
T-00046-0381 | PS5-60-TCV-0002F | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-75 - Engine F Cooling system
T-00046-0382 | PS5-60-TCV-0002G | CZX01E - Package | #N/A | E | THERMAL REGULATING VALVE SKID |  | PS5-60-76 - Engine G Cooling system
T-00046-0383 | PS5-60-UA-5200 | CZX01E - Package | #N/A | E | INSTRUMENT AIR COMPRESSOR MODULE |  | PS5-60-26 - Instrument Air Compressor Skid
T-00046-0384 | PS5-60-UR-8200A | CZX01E - Package | #N/A | E | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-01 - Power Generation Package A
T-00046-0385 | PS5-60-UR-8200B | CZX01E - Package | #N/A | E | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-04 - Power Generation Package B
T-00046-0386 | PS5-60-UR-8200C | CZX01E - Package | #N/A | E | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-07 - Power Generation Package C
T-00046-0387 | PS5-60-UR-8200D | CZX01E - Package | #N/A | E | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-10 - Power Generation Package D
T-00046-0388 | PS5-60-UR-8200E | CZX01E - Package | #N/A | E | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-13 - Power Generation Package E
T-00046-0389 | PS5-60-UR-8200F | CZX01E - Package | #N/A | E | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-16 - Power Generation Package F
T-00046-0390 | PS5-60-UR-8200G | CZX01E - Package | #N/A | E | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-19 - Power Generation Package G
T-00046-0391 | PS5-60-UZ-8200G | CZX01E - Package | #N/A | E | INJECTOR TIP COOLING MODULE |  | PS5-60-41 - Injector Tip Cooling Module G
T-00046-0392 | PS5-60-UZ-8900A | CZX01E - Package | #N/A | E | FUEL CONDITIONING MODULE |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A
T-00046-0393 | PS5-60-UZ-8900B | CZX01E - Package | #N/A | E | FUEL CONDITIONING MODULE |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B
T-00046-0394 | PS5-60-UZ-8900C | CZX01E - Package | #N/A | E | FUEL CONDITIONING MODULE |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00046-0395 | PS5-60-UZ-8900D | CZX01E - Package | #N/A | E | FUEL CONDITIONING MODULE |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00046-0396 | PS5-60-UZ-8900E | CZX01E - Package | #N/A | E | FUEL CONDITIONING MODULE |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00046-0397 | PS5-60-UZ-8900F | CZX01E - Package | #N/A | E | FUEL CONDITIONING MODULE |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00046-0398 | PS5-60-UZ-8900G | CZX01E - Package | #N/A | E | FUEL CONDITIONING MODULE |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00046-0399 | PS5-71-UN-7200 | CZX01E - Package | #N/A | E | CRUDE FUEL OIL ALLOCATION METERING PACKAGE |  | PS5-71-02 - CFO Allocation Metering Package
T-00046-0400 | PS5-71-UZ-6400 | CZX01E - Package | #N/A | E | CRUDE FUEL OIL PRE-PRESSURE MODULE |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00046-0401 | PS5-71-UZ-6700 | CZX01E - Package | #N/A | E | DIESEL FUEL OIL PRE-PRESSURE MODULE |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00046-0402 | PS5-74-UB-5100 | CZX01E - Package | #N/A | E | NITROGEN GENERATION PACKAGE |  | PS5-74-01 - N2 Generation Skid
T-00046-0403 | PS5-75-UI-6100 | CZX01E - Package | #N/A | E | BIOCIDE INJECTION PACKAGE |  | PS5-75-02 - Biocide Injection Package
T-00046-0404 | PS5-75-UI-6200 | CZX01E - Package | #N/A | E | DRA PACKAGE |  | PS5-75-01 - DRA Injection Package
T-00046-0405 | PS5-75-UI-6300 | CZX01E - Package | #N/A | E | CORROSION INHIBITOR PACKAGE |  | PS5-75-03 - Corrosion Inhibitor Injection Package
T-00046-0406 | PS5-77-UZ-8200 | CZX01E - Package | #N/A | E | WATER DEIONIZATION PACKAGE |  | PS5-53-03 - Water Softener Package
T-00046-0407 | PS5-82-UZ-8100 | CZX01E - Package | #N/A | E | SEWAGE TREATMENT PLANT PACKAGE |  | PS5-82-02 - Sewage Treatment Plant Package
T-00046-0542 | PS5-83-EHO-0001A | CZX01E - Package | #N/A | E | VSD E-HOUSE |  | PS5-25-02 - Crude Oil Export Pump A
T-00046-0543 | PS5-83-EHO-0001B | CZX01E - Package | #N/A | E | VSD E-HOUSE |  | PS5-25-03 - Crude Oil Export Pump B
T-00046-0544 | PS5-83-EHO-0001C | CZX01E - Package | #N/A | E | VSD E-HOUSE |  | PS5-25-04 - Crude Oil Export Pump C
T-00046-0549 | PS5-01-UZ-610 | CZX01E - Package | #N/A | E | Fire suppression skid |  | PS5-01-11 - Inergen for Power Gen Building
T-00046-0552 | PS5-60-UR-8300A | CZX01E - Package | #N/A | E | POWER GENERATION - Cooler Module |  | PS5-60-35 - Injector Tip Cooling Module A
T-00046-0553 | PS5-60-UR-8300B | CZX01E - Package | #N/A | E | POWER GENERATION - Cooler Module |  | PS5-60-36 - Injector Tip Cooling Module B
T-00046-0554 | PS5-60-UR-8300C | CZX01E - Package | #N/A | E | POWER GENERATION - Cooler Module |  | PS5-60-37 - Injector Tip Cooling Module C
T-00046-0555 | PS5-60-UR-8300D | CZX01E - Package | #N/A | E | POWER GENERATION - Cooler Module |  | PS5-60-38 - Injector Tip Cooling Module D
T-00046-0556 | PS5-60-UR-8300E | CZX01E - Package | #N/A | E | POWER GENERATION - Cooler Module |  | PS5-60-39 - Injector Tip Cooling Module E
T-00046-0557 | PS5-60-UR-8300F | CZX01E - Package | #N/A | E | POWER GENERATION - Cooler Module |  | PS5-60-40 - Injector Tip Cooling Module F
T-00046-0558 | PS5-60-UR-8300G | CZX01E - Package | #N/A | E | POWER GENERATION - Cooler Module |  | PS5-60-41 - Injector Tip Cooling Module G
T-00064-0412 | PS5-01-RAB-61001A | CJX00 - Miscellaneous | #N/A | I | DISCHARGE SOUNDER & BEACON |  | PS5-01-11 - Inergen for Power Gen Building
T-00064-0413 | PS5-01-RAB-61001B | CJX00 - Miscellaneous | #N/A | I | PRE-DISCHARGE SOUNDER & BEACON |  | PS5-01-11 - Inergen for Power Gen Building
T-00064-0414 | PS5-01-RAB-61002A | CJX00 - Miscellaneous | #N/A | I | DISCHARGE SOUNDER & BEACON |  | PS5-01-11 - Inergen for Power Gen Building
T-00064-0415 | PS5-01-RAB-61002B | CJX00 - Miscellaneous | #N/A | I | PRE-DISCHARGE SOUNDER & BEACON |  | PS5-01-11 - Inergen for Power Gen Building
T-00064-0416 | PS5-01-RAB-61003A | CJX00 - Miscellaneous | #N/A | I | DISCHARGE SOUNDER & BEACON |  | PS5-01-11 - Inergen for Power Gen Building
T-00064-0417 | PS5-01-RAB-61003B | CJX00 - Miscellaneous | #N/A | I | PRE-DISCHARGE SOUNDER & BEACON |  | PS5-01-11 - Inergen for Power Gen Building
T-00064-0418 | PS5-01-RAB-61004A | CJX00 - Miscellaneous | #N/A | I | DISCHARGE SOUNDER & BEACON |  | PS5-01-11 - Inergen for Power Gen Building
T-00064-0419 | PS5-01-RAB-61004B | CJX00 - Miscellaneous | #N/A | I | PRE-DISCHARGE SOUNDER & BEACON |  | PS5-01-11 - Inergen for Power Gen Building
T-00064-0437 | PS5-03-RAB-B402 | CJX00 - Miscellaneous | #N/A | I | Audible and Visual alarm |  | PS5-03-24 - FZ - Office and Facilities Building
T-00064-0438 | PS5-03-RAB-B902 | CJX00 - Miscellaneous | #N/A | I | Audible and Visual alarm |  | PS5-03-24 - FZ - Office and Facilities Building
T-00064-0439 | PS5-03-RAB-W502 | CJX00 - Miscellaneous | #N/A | I | Audible and Visual alarm |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00065-0115 | PS5-25-PSV-1103 | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00065-0116 | PS5-28-PSV-0064C | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00065-0117 | PS5-25-PSV-1203 | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00065-0118 | PS5-28-PRV-0047B | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00065-0119 | PS5-74-PSV-0003 | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-74-03 - Nitrogen Receiver
T-00065-0120 | PS5-28-PRV-0040 | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00065-0121 | PS5-50-PSV-0004A | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-50-01 - Water Well Submersible Pumps (3100)
T-00065-0122 | PS5-71-PSV-2403A | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00065-0123 | PS5-28-PSV-3901B | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-17 - Reinjection Pump
T-00065-0124 | PS5-28-PRV-0047A | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00065-0125 | PS5-71-PVSV-4202 | CJX03 - Relief valve | #N/A | I | Pressure / Vacuum Safety Valve |  | PS5-71-12 - CFO Service Tank
T-00065-0126 | PS5-71-PVSV-4102 | CJX03 - Relief valve | #N/A | I | Pressure / Vacuum Safety Valve |  | PS5-71-04 - CFO Storage Tank
T-00065-0127 | PS5-28-PRV-0046A | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00065-0128 | PS5-28-PRV-0008 | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00065-0129 | PS5-28-PSV-0064A | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00065-0130 | PS5-28-PRV-0054 | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00065-0131 | PS5-28-PSV-0044 | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00065-0132 | PS5-71-PRV-0016 | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-71-04 - CFO Storage Tank
T-00065-0133 | PS5-28-PRV-0046B | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00065-0134 | PS5-71-PRV-0015 | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-71-04 - CFO Storage Tank
T-00065-0135 | PS5-71-PRV-0018 | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-71-12 - CFO Service Tank
T-00065-0136 | PS5-71-PRV-0041 | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-71-12 - CFO Service Tank
T-00065-0137 | PS5-71-PSV-2403B | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00065-0138 | PS5-28-PRV-0046C | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00065-0139 | PS5-28-PRV-0047C | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00065-0140 | PS5-28-PRV-0055 | CJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00065-0141 | PS5-28-PSV-0061 | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00065-0142 | PS5-28-PSV-0064B | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00065-0143 | PS5-28-PSV-3901A | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-17 - Reinjection Pump
T-00065-0144 | PS5-50-PSV-0004B | CJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-50-02 - Water Well Submersible Pumps (3200)
T-00066-0059 | PS5-01-FCV-0004B | CJX06 - Tubing Hydraulic | #N/A | I | Flow Control Valve |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00066-0060 | PS5-25-FCV-0004 | CJX06 - Tubing Hydraulic | #N/A | I | Flow Control Valve |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00066-0061 | PS5-01-FCV-0003A | CJX06 - Tubing Hydraulic | #N/A | I | Flow Control Valve |  | PS5-01-02 - Fire Water Pump A
T-00066-0062 | PS5-01-FCV-0003B | CJX06 - Tubing Hydraulic | #N/A | I | Flow Control Valve |  | PS5-01-03 - Fire Water Pump B
T-00066-0063 | PS5-71-FCV-0018 | CJX06 - Tubing Hydraulic | #N/A | I | Flow Control Valve |  | PS5-71-13 - CFO Service Pump A/B
T-00066-0064 | PS5-25-FCV-0003B | CJX06 - Tubing Hydraulic | #N/A | I | Flow Control Valve |  | PS5-25-03 - Crude Oil Export Pump B
T-00066-0065 | PS5-71-LCV-4101 | CJX06 - Tubing Hydraulic | #N/A | I | Level Control Valve |  | PS5-71-04 - CFO Storage Tank
T-00066-0066 | PS5-71-FCV-0019 | CJX06 - Tubing Hydraulic | #N/A | I | Flow Control Valve |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00066-0067 | PS5-71-FCV-0020 | CJX06 - Tubing Hydraulic | #N/A | I | Flow Control Valve |  | PS5-71-05 - CFO Transfer Pump A/B
T-00066-0068 | PS5-01-FCV-0004A | CJX06 - Tubing Hydraulic | #N/A | I | Flow Control Valve |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00066-0069 | PS5-25-FCV-0003A | CJX06 - Tubing Hydraulic | #N/A | I | Flow Control Valve |  | PS5-25-02 - Crude Oil Export Pump A
T-00066-0070 | PS5-25-FCV-0003C | CJX06 - Tubing Hydraulic | #N/A | I | Flow Control Valve |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-0072 | PS5-03-RMAC-0101 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-01 - FZ-01 - Process Area
T-00067-0073 | PS5-03-RMAC-0102 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-01 - FZ-01 - Process Area
T-00067-0074 | PS5-03-RMAC-0103 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-01 - FZ-01 - Process Area
T-00067-0075 | PS5-03-RMAC-0120 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-01 - FZ-01 - Process Area
T-00067-0076 | PS5-03-RMAC-0301 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-03 - FZ-03 - Buildings Area
T-00067-0077 | PS5-03-RMAC-0401 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas
T-00067-0078 | PS5-03-RMAC-0402 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas
T-00067-0079 | PS5-03-RMAC-0613 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-06 - FZ-06 - Transformer Area
T-00067-0081 | PS5-03-RMAC-0827 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00067-0640 | PS5-03-NMR-0801 | CJX08 - Electrical instrument | #N/A | I | WATER MIST RELEASE PUSH BUTTON |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00067-0641 | PS5-03-NMR-0802 | CJX08 - Electrical instrument | #N/A | I | WATER MIST RELEASE PUSH BUTTON |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00067-0642 | PS5-03-NMR-0803 | CJX08 - Electrical instrument | #N/A | I | WATER MIST RELEASE PUSH BUTTON |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00067-0643 | PS5-03-NMR-0804 | CJX08 - Electrical instrument | #N/A | I | WATER MIST RELEASE PUSH BUTTON |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00067-0652 | PS5-03-RMAC-0304 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-03 - FZ-03 - Buildings Area
T-00067-0653 | PS5-03-RMAC-0706 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00067-0654 | PS5-03-RMAC-0707 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00067-0655 | PS5-03-RMAC-0824 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00067-0656 | PS5-03-RMAC-0825 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00067-0657 | PS5-03-RMAC-0834 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00067-0658 | PS5-03-RMAC-1301 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00067-0659 | PS5-03-RMAC-1409 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00067-0660 | PS5-03-RMAC-1410 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00067-0661 | PS5-03-RMAC-1411 | CJX08 - Electrical instrument | #N/A | I | MANUAL CALL POINT |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00067-2049 | PS5-25-ZIT-0001 | CJX08 - Electrical instrument | #N/A | I | Position transmitter |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2050 | PS5-25-ZS-1101 | CJX08 - Electrical instrument | #N/A | I | Position Switch |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2051 | PS5-03-HS-7002 | CJX08 - Electrical instrument | #N/A | I | Hand Switch |  | PS5-03-03 - FZ-03 - Buildings Area
T-00067-2052 | PS5-71-HZL-0059 | CJX08 - Electrical instrument | #N/A | I | Position Switch Closed |  | PS5-71-18 - Diesel Separator Module
T-00067-2053 | PS5-71-HZH-0059 | CJX08 - Electrical instrument | #N/A | I | Position Switch Opened |  | PS5-71-18 - Diesel Separator Module
T-00067-2054 | PS5-25-ZIT-0002 | CJX08 - Electrical instrument | #N/A | I | Position transmitter |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2055 | PS5-25-ZS-1201 | CJX08 - Electrical instrument | #N/A | I | Position Switch |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2056 | PS5-25-FIT-0003B | CJX08 - Electrical instrument | #N/A | I | Ultrasonic Flow Ind Transmitter |  | PS5-25-03 - Crude Oil Export Pump B
T-00067-2057 | PS5-71-FIT-0019 | CJX08 - Electrical instrument | #N/A | I | DP Flow Ind Transmitter |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00067-2058 | PS5-71-FIT-0011B | CJX08 - Electrical instrument | #N/A | I | Coriolis Flow Ind Transmitter |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00067-2059 | PS5-50-FIT-0001 | CJX08 - Electrical instrument | #N/A | I | DP Flow Ind Transmitter |  | PS5-50-03 - Water Pre-Treatment Package
T-00067-2060 | PS5-01-FIT-0003B | CJX08 - Electrical instrument | #N/A | I | Electromagnetic Flow Ind Transmitter |  | PS5-01-03 - Fire Water Pump B
T-00067-2061 | PS5-25-FIT-0003A | CJX08 - Electrical instrument | #N/A | I | Ultrasonic Flow Ind Transmitter |  | PS5-25-02 - Crude Oil Export Pump A
T-00067-2062 | PS5-71-FIT-0018 | CJX08 - Electrical instrument | #N/A | I | DP Flow Ind Transmitter |  | PS5-71-13 - CFO Service Pump A/B
T-00067-2063 | PS5-01-FIT-0003A | CJX08 - Electrical instrument | #N/A | I | Electromagnetic Flow Ind Transmitter |  | PS5-01-02 - Fire Water Pump A
T-00067-2064 | PS5-71-FIT-0020 | CJX08 - Electrical instrument | #N/A | I | DP Flow Ind Transmitter |  | PS5-71-05 - CFO Transfer Pump A/B
T-00067-2065 | PS5-25-FIT-0004 | CJX08 - Electrical instrument | #N/A | I | Ultrasonic Flow Ind Transmitter |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00067-2066 | PS5-25-FIT-0003C | CJX08 - Electrical instrument | #N/A | I | Ultrasonic Flow Ind Transmitter |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-2067 | PS5-25-FIT-0001 | CJX08 - Electrical instrument | #N/A | I | Ultrasonic Flow Ind Transmitter |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2068 | PS5-71-FIT-0012 | CJX08 - Electrical instrument | #N/A | I | DP Flow Ind Transmitter |  | PS5-71-17 - Diesel Fuel Distribution Header
T-00067-2069 | PS5-71-FIT-0005 | CJX08 - Electrical instrument | #N/A | I | DP Flow Ind Transmitter |  | PS5-71-17 - Diesel Fuel Distribution Header
T-00067-2070 | PS5-71-FIT-0011A | CJX08 - Electrical instrument | #N/A | I | Coriolis Flow Ind Transmitter |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00067-2071 | PS5-01-FIT-0004A | CJX08 - Electrical instrument | #N/A | I | Electromagnetic Flow Ind Transmitter |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00067-2072 | PS5-01-FIT-0004B | CJX08 - Electrical instrument | #N/A | I | Electromagnetic Flow Ind Transmitter |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00067-2073 | PS5-71-LIT-1202 | CJX08 - Electrical instrument | #N/A | I | DP Level Ind Transmitter |  | PS5-71-20 - Diesel Fuel Day Tank
T-00067-2074 | PS5-71-LIT-4202 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-71-12 - CFO Service Tank
T-00067-2075 | PS5-01-LIT-4101B | CJX08 - Electrical instrument | #N/A | I | Level Ind Transmitter |  | PS5-01-03 - Fire Water Pump B
T-00067-2076 | PS5-28-LIT-1301A | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00067-2077 | PS5-28-LIT-1102 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00067-2078 | PS5-50-LIT-0001 | CJX08 - Electrical instrument | #N/A | I | Level Ind Transmitter |  | PS5-50-01 - Water Well Submersible Pumps (3100)
T-00067-2079 | PS5-28-LIT-1301B | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00067-2080 | PS5-71-LIT-4101 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-71-04 - CFO Storage Tank
T-00067-2081 | PS5-60-LIT-4401 | CJX08 - Electrical instrument | #N/A | I | DP Level Ind Transmitter |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump
T-00067-2082 | PS5-71-LIT-4102 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-71-04 - CFO Storage Tank
T-00067-2083 | PS5-71-LIT-4401 | CJX08 - Electrical instrument | #N/A | I | DP Level Ind Transmitter |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00067-2084 | PS5-28-LIT-1202 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-28-06 - Relief Drum and Pump
T-00067-2085 | PS5-28-LIT-0002 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-28-08 - Open Drain Sump and Pumps
T-00067-2086 | PS5-53-LIT-4101 | CJX08 - Electrical instrument | #N/A | I | DP Level Ind Transmitter |  | PS5-53-01 - Utility Water / Storage Tank
T-00067-2087 | PS5-28-LIT-1402 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00067-2088 | PS5-71-LIT-4201 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-71-12 - CFO Service Tank
T-00067-2089 | PS5-28-LIT-1201 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-28-06 - Relief Drum and Pump
T-00067-2090 | PS5-60-LIT-4301 | CJX08 - Electrical instrument | #N/A | I | DP Level Ind Transmitter |  | PS5-60-24 - Cooling Water Tank & Pump
T-00067-2091 | PS5-28-LIT-1301C | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00067-2092 | PS5-28-LIT-1101 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00067-2093 | PS5-71-LIT-1201 | CJX08 - Electrical instrument | #N/A | I | DP Level Ind Transmitter |  | PS5-71-20 - Diesel Fuel Day Tank
T-00067-2094 | PS5-71-LIT-4402 | CJX08 - Electrical instrument | #N/A | I | DP Level Ind Transmitter |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00067-2095 | PS5-01-LIT-4101A | CJX08 - Electrical instrument | #N/A | I | Level Ind Transmitter |  | PS5-01-02 - Fire Water Pump A
T-00067-2096 | PS5-28-LIT-0008 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-28-08 - Open Drain Sump and Pumps
T-00067-2097 | PS5-28-LIT-1401 | CJX08 - Electrical instrument | #N/A | I | GWR Level Ind Transmitter |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00067-2098 | PS5-50-LIT-0002 | CJX08 - Electrical instrument | #N/A | I | Level Ind Transmitter |  | PS5-50-02 - Water Well Submersible Pumps (3200)
T-00067-2099 | PS5-53-LIT-4102 | CJX08 - Electrical instrument | #N/A | I | DP Level Ind Transmitter |  | PS5-53-01 - Utility Water / Storage Tank
T-00067-2100 | PS5-25-PDIT-0034A | CJX08 - Electrical instrument | #N/A | I | Diff Press Ind Transmitter |  | PS5-25-02 - Crude Oil Export Pump A
T-00067-2101 | PS5-25-PIT-0008C | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2102 | PS5-01-PDIT-0012B | CJX08 - Electrical instrument | #N/A | I | Diff Press Ind Transmitter |  | PS5-01-03 - Fire Water Pump B
T-00067-2103 | PS5-01-PIT-0010 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-01-07 - Fire Water Ring Main & Distribution
T-00067-2104 | PS5-25-PIT-0018 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2105 | PS5-01-PDIT-0011A | CJX08 - Electrical instrument | #N/A | I | Diff Press Ind Transmitter |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00067-2106 | PS5-25-PDIT-0050 | CJX08 - Electrical instrument | #N/A | I | Diff Press Ind Transmitter |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00067-2107 | PS5-28-PIT-0015 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-28-17 - Reinjection Pump
T-00067-2108 | PS5-28-PIT-0041 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-28-17 - Reinjection Pump
T-00067-2109 | PS5-25-PIT-0004C | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-2110 | PS5-25-PDIT-0034C | CJX08 - Electrical instrument | #N/A | I | Diff Press Ind Transmitter |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-2111 | PS5-01-PIT-0016 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-01-07 - Fire Water Ring Main & Distribution
T-00067-2112 | PS5-71-PDIT-0030 | CJX08 - Electrical instrument | #N/A | I | Diff Press Ind Transmitter |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00067-2113 | PS5-25-PIT-0071B | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2114 | PS5-01-PDIT-0011B | CJX08 - Electrical instrument | #N/A | I | Diff Press Ind Transmitter |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00067-2115 | PS5-25-PIT-0001 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2116 | PS5-71-PDIT-0056B | CJX08 - Electrical instrument | #N/A | I | Diff Press Ind Transmitter |  | PS5-71-05 - CFO Transfer Pump A/B
T-00067-2117 | PS5-25-PIT-1202 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2118 | PS5-25-PIT-0005B | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-03 - Crude Oil Export Pump B
T-00067-2119 | PS5-25-PIT-0004A | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-02 - Crude Oil Export Pump A
T-00067-2120 | PS5-01-PIT-0015 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-01-07 - Fire Water Ring Main & Distribution
T-00067-2121 | PS5-71-PDIT-0056A | CJX08 - Electrical instrument | #N/A | I | Diff Press Ind Transmitter |  | PS5-71-05 - CFO Transfer Pump A/B
T-00067-2122 | PS5-74-PIT-0002 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-74-04 - Nitrogen Distribution Header
T-00067-2123 | PS5-28-PIT-0033 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-28-06 - Relief Drum and Pump
T-00067-2124 | PS5-01-PIT-0017 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-01-07 - Fire Water Ring Main & Distribution
T-00067-2125 | PS5-25-PIT-1102 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2126 | PS5-25-PIT-0004B | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-03 - Crude Oil Export Pump B
T-00067-2127 | PS5-25-PIT-0007B | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-03 - Crude Oil Export Pump B
T-00067-2128 | PS5-01-PIT-0014 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-01-07 - Fire Water Ring Main & Distribution
T-00067-2129 | PS5-25-PIT-0071C | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2130 | PS5-53-PIT-0005 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-53-02 - Water Distribution Pump A/B
T-00067-2131 | PS5-25-PIT-0007A | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-02 - Crude Oil Export Pump A
T-00067-2132 | PS5-25-PIT-0005A | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-02 - Crude Oil Export Pump A
T-00067-2133 | PS5-25-PIT-0071A | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2134 | PS5-71-PIT-0014 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-71-17 - Diesel Fuel Distribution Header
T-00067-2135 | PS5-25-PIT-0013 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00067-2136 | PS5-71-PIT-2402A | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00067-2137 | PS5-71-PIT-2402B | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00067-2138 | PS5-01-PDIT-0012A | CJX08 - Electrical instrument | #N/A | I | Diff Press Ind Transmitter |  | PS5-01-02 - Fire Water Pump A
T-00067-2139 | PS5-01-PIT-0013 | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-01-07 - Fire Water Ring Main & Distribution
T-00067-2140 | PS5-25-PDIT-0034B | CJX08 - Electrical instrument | #N/A | I | Diff Press Ind Transmitter |  | PS5-25-03 - Crude Oil Export Pump B
T-00067-2141 | PS5-25-PIT-0005C | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-2142 | PS5-25-PIT-0007C | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-2143 | PS5-25-PIT-0008A | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2144 | PS5-25-PIT-0008B | CJX08 - Electrical instrument | #N/A | I | Pressure Transmitter |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2145 | PS5-71-TIT-0003 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00067-2146 | PS5-71-TIT-0006 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00067-2147 | PS5-71-TIT-4203 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-71-12 - CFO Service Tank
T-00067-2148 | PS5-28-TIT-1402 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00067-2149 | PS5-25-TIT-0002B | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-25-03 - Crude Oil Export Pump B
T-00067-2150 | PS5-25-TIT-1201 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2151 | PS5-25-TIT-0003B | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-25-03 - Crude Oil Export Pump B
T-00067-2152 | PS5-28-TIT-1401 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00067-2153 | PS5-25-TIT-0003A | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-25-02 - Crude Oil Export Pump A
T-00067-2154 | PS5-71-TIT-0007 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00067-2155 | PS5-28-TIT-1104 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00067-2156 | PS5-71-TIT-0004 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00067-2157 | PS5-71-TIT-4202 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-71-12 - CFO Service Tank
T-00067-2158 | PS5-25-TIT-0003C | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-2159 | PS5-25-TIT-1101 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2160 | PS5-28-TIT-1105 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00067-2161 | PS5-71-TIT-4103 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-71-04 - CFO Storage Tank
T-00067-2162 | PS5-25-TIT-0002C | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-2163 | PS5-71-TIT-4102 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-71-04 - CFO Storage Tank
T-00067-2164 | PS5-25-TIT-0001 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2165 | PS5-25-TIT-0002A | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-25-02 - Crude Oil Export Pump A
T-00067-2166 | PS5-25-TIT-0004 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00067-2167 | PS5-28-TIT-1201 | CJX08 - Electrical instrument | #N/A | I | Temperature Ind Transmitter |  | PS5-28-06 - Relief Drum and Pump
T-00067-2168 | PS5-71-HZL-0058 | CJX08 - Electrical instrument | #N/A | I | Position Switch Closed |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00067-2169 | PS5-71-HZH-0058 | CJX08 - Electrical instrument | #N/A | I | Position Switch Opened |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00067-2432 | PS5-25-IES-3200A | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump Motor A - Lube OilPump 1 Motor |  | PS5-25-02 - Crude Oil Export Pump A
T-00067-2433 | PS5-25-IES-3200B | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump Motor A - Lube OilPump 2 Motor |  | PS5-25-02 - Crude Oil Export Pump A
T-00067-2434 | PS5-25-IES-3300A | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump Motor B - Lube OilPump 1 Motor |  | PS5-25-03 - Crude Oil Export Pump B
T-00067-2435 | PS5-25-IES-3300B | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump Motor B - Lube OilPump 2 Motor |  | PS5-25-03 - Crude Oil Export Pump B
T-00067-2436 | PS5-25-IES-3400A | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump C - Lube OilPump 1 Motor |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-2437 | PS5-25-IES-3400B | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump C - Lube OilPump 2 Motor |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-2438 | PS5-25-IES-6400A | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump Motor A - Lube Oil Heat Exchanger Fan Motor 1 |  | PS5-25-02 - Crude Oil Export Pump A
T-00067-2439 | PS5-25-IES-6400B | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump Motor A- Lube Oil Heat Exchanger Fan Motor 2 |  | PS5-25-02 - Crude Oil Export Pump A
T-00067-2440 | PS5-25-IES-6500A | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump Motor B - Lube Oil Heat Exchanger Fan Motor 1 |  | PS5-25-03 - Crude Oil Export Pump B
T-00067-2441 | PS5-25-IES-6500B | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump Motor B- Lube Oil Heat Exchanger Fan Motor 2 |  | PS5-25-03 - Crude Oil Export Pump B
T-00067-2442 | PS5-25-IES-6600A | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump C - Lube Oil Heat Exchanger Fan Motor 1 |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-2443 | PS5-25-IES-6600B | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Oil Export Pump C - Lube Oil Heat Exchanger Fan Motor 2 |  | PS5-25-04 - Crude Oil Export Pump C
T-00067-2444 | PS5-28-IES-2008 | CJX08 - Electrical instrument | #N/A | I | LCS for Socket Outlet 63A for mobile oil skimmer (PS5-28-UZ-8100) |  | PS5-28-10 - Oil Skimmer Package
T-00067-2445 | PS5-28-IES-3300 | CJX08 - Electrical instrument | #N/A | I | LCS for Relief Drum Pump Motor |  | PS5-28-06 - Relief Drum and Pump
T-00067-2446 | PS5-28-IES-3400 | CJX08 - Electrical instrument | #N/A | I | LCS for Closed Drain Drum 01 Pump Motor |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00067-2447 | PS5-28-IES-3500 | CJX08 - Electrical instrument | #N/A | I | LCS for Oily Water Sump Pump Motor |  | PS5-28-08 - Open Drain Sump and Pumps
T-00067-2448 | PS5-28-IES-3600A | CJX08 - Electrical instrument | #N/A | I | LCS for Open Drain Sump Pump Motor A |  | PS5-28-08 - Open Drain Sump and Pumps
T-00067-2449 | PS5-28-IES-3600B | CJX08 - Electrical instrument | #N/A | I | LCS for Open Drain Sump Pump Motor B |  | PS5-28-08 - Open Drain Sump and Pumps
T-00067-2450 | PS5-28-IES-3700A | CJX08 - Electrical instrument | #N/A | I | LCS for Closed Drain Drum 02 Pump Motor A |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00067-2451 | PS5-28-IES-3700B | CJX08 - Electrical instrument | #N/A | I | LCS for Closed Drain Drum 02 Pump Motor B |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00067-2452 | PS5-28-IES-3800A | CJX08 - Electrical instrument | #N/A | I | LCS for Seal Oil Drain Drum Pump Motor A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00067-2453 | PS5-28-IES-3800B | CJX08 - Electrical instrument | #N/A | I | LCS for Seal Oil Drain Drum Pump Motor B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00067-2454 | PS5-28-IES-3800C | CJX08 - Electrical instrument | #N/A | I | LCS for Seal Oil Drain Drum Pump Motor C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00067-2455 | PS5-28-IES-3900A | CJX08 - Electrical instrument | #N/A | I | LCS for Reinjection Pump Motor A |  | PS5-28-17 - Reinjection Pump
T-00067-2456 | PS5-28-IES-3900B | CJX08 - Electrical instrument | #N/A | I | LCS for Reinjection Pump Motor B |  | PS5-28-17 - Reinjection Pump
T-00067-2457 | PS5-53-IES-3100A | CJX08 - Electrical instrument | #N/A | I | LCS for Water Distribution Pump Motor A |  | PS5-53-02 - Water Distribution Pump A/B
T-00067-2458 | PS5-53-IES-3100B | CJX08 - Electrical instrument | #N/A | I | LCS for Water Distribution Pump Motor B |  | PS5-53-02 - Water Distribution Pump A/B
T-00067-2459 | PS5-60-IES-3300 | CJX08 - Electrical instrument | #N/A | I | LCS for Cooling Water Pump Motor |  | PS5-60-24 - Cooling Water Tank & Pump
T-00067-2460 | PS5-60-IES-3400 | CJX08 - Electrical instrument | #N/A | I | LCS for Cooling Water Return Pump Motor |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump
T-00067-2461 | PS5-71-IES-3100A | CJX08 - Electrical instrument | #N/A | I | LCS for Diesel Fuel Supply Pump Motor A |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00067-2462 | PS5-71-IES-3100B | CJX08 - Electrical instrument | #N/A | I | LCS for Diesel Fuel Supply Pump Motor B |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00067-2463 | PS5-71-IES-3200 | CJX08 - Electrical instrument | #N/A | I | LCS for Diesel Fuel Make-Up Pump Motor |  | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station
T-00067-2464 | PS5-71-IES-3300A | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Fuel Oil Transfer Pump Motor A |  | PS5-71-05 - CFO Transfer Pump A/B
T-00067-2465 | PS5-71-IES-3300B | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Fuel Oil Transfer Pump Motor B |  | PS5-71-05 - CFO Transfer Pump A/B
T-00067-2466 | PS5-71-IES-3400A | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Fuel Oil Service Pump Motor A |  | PS5-71-13 - CFO Service Pump A/B
T-00067-2467 | PS5-71-IES-3400B | CJX08 - Electrical instrument | #N/A | I | LCS for Crude Fuel Oil Service Pump Motor B |  | PS5-71-13 - CFO Service Pump A/B
T-00067-2468 | PS5-71-IES-3500A | CJX08 - Electrical instrument | #N/A | I | LCS for Diesel Transfer Pump Motor A |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00067-2469 | PS5-71-IES-3500B | CJX08 - Electrical instrument | #N/A | I | LCS for Diesel Transfer Pump Motor B |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00067-2560 | PS5-01-LB-6101A | CJX08 - Electrical instrument | #N/A | I | STATUS PANEL JUNCTION BOX |  | PS5-01-11 - Inergen for Power Gen Building
T-00067-2561 | PS5-01-LB-6102A | CJX08 - Electrical instrument | #N/A | I | STATUS PANEL JUNCTION BOX |  | PS5-01-11 - Inergen for Power Gen Building
T-00067-2562 | PS5-01-LB-6103A | CJX08 - Electrical instrument | #N/A | I | STATUS PANEL JUNCTION BOX |  | PS5-01-11 - Inergen for Power Gen Building
T-00067-2563 | PS5-01-LB-6104A | CJX08 - Electrical instrument | #N/A | I | STATUS PANEL JUNCTION BOX |  | PS5-01-11 - Inergen for Power Gen Building
T-00067-2643 | PS5-03-RMAC-B401 | CJX08 - Electrical instrument | #N/A | I | Manual Call Point |  | PS5-03-24 - FZ - Office and Facilities Building
T-00067-2644 | PS5-03-RMAC-B901 | CJX08 - Electrical instrument | #N/A | I | Manual Call Point |  | PS5-03-24 - FZ - Office and Facilities Building
T-00067-2645 | PS5-03-RMAC-W501 | CJX08 - Electrical instrument | #N/A | I | Manual Call Point |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00067-2728 | PS5-09-AH-8401 | CJX08 - Electrical instrument | #N/A | I | HUMIDITY TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2729 | PS5-09-AH-8402 | CJX08 - Electrical instrument | #N/A | I | HUMIDITY TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2730 | PS5-09-AH-8403 | CJX08 - Electrical instrument | #N/A | I | HUMIDITY TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2731 | PS5-09-IES-8101A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2732 | PS5-09-IES-8101B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2733 | PS5-09-IES-8102A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2734 | PS5-09-IES-8102B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2735 | PS5-09-IES-8102C | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2736 | PS5-09-IES-8201A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2737 | PS5-09-IES-8201B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2738 | PS5-09-IES-8202A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2739 | PS5-09-IES-8202B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2740 | PS5-09-IES-8202C | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2741 | PS5-09-IES-8202D | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2742 | PS5-09-IES-8301A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2743 | PS5-09-IES-8301B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2744 | PS5-09-IES-8302A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2745 | PS5-09-IES-8302B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2746 | PS5-09-IES-8304A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2747 | PS5-09-IES-8304B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2748 | PS5-09-IES-8305A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2749 | PS5-09-IES-8305B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2750 | PS5-09-IES-8307A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2751 | PS5-09-IES-8307B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2752 | PS5-09-IES-8308A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2753 | PS5-09-IES-8308B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2754 | PS5-09-IES-8311A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2755 | PS5-09-IES-8311B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2756 | PS5-09-IES-8313 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2757 | PS5-09-IES-8314 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2758 | PS5-09-IES-8315 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2759 | PS5-09-IES-8316 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2760 | PS5-09-IES-8317 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2761 | PS5-09-IES-8318 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2762 | PS5-09-IES-8319 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2763 | PS5-09-IES-8321 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2764 | PS5-09-IES-8322 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2765 | PS5-09-IES-8323 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2766 | PS5-09-IES-8324 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2767 | PS5-09-IES-8325 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2768 | PS5-09-IES-8401A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2769 | PS5-09-IES-8401B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2770 | PS5-09-IES-8403A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2771 | PS5-09-IES-8403B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2772 | PS5-09-IES-8404A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2773 | PS5-09-IES-8404B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2774 | PS5-09-IES-8405A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2775 | PS5-09-IES-8405B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2776 | PS5-09-IES-8406A | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2777 | PS5-09-IES-8406B | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2778 | PS5-09-IES-8406C | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2779 | PS5-09-IES-8406D | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2780 | PS5-09-IES-8406E | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2781 | PS5-09-IES-8406F | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2782 | PS5-09-IES-8406G | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2783 | PS5-09-IES-8406H | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2784 | PS5-09-IES-8407 | CJX08 - Electrical instrument | #N/A | I | EMERGENCY STOP PUSH BUTTON |  | PS5-09-03 - HVAC for Generator Building
T-00067-2785 | PS5-09-PDIT-8207 | CJX08 - Electrical instrument | #N/A | I | DIFFERENTIAL PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2786 | PS5-09-PDIT-8407 | CJX08 - Electrical instrument | #N/A | I | DIFFERENTIAL PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2787 | PS5-09-PDIT-8408 | CJX08 - Electrical instrument | #N/A | I | DIFFERENTIAL PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2788 | PS5-09-PDIT-8409 | CJX08 - Electrical instrument | #N/A | I | DIFFERENTIAL PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2789 | PS5-09-PDIT-8411 | CJX08 - Electrical instrument | #N/A | I | DIFFERENTIAL PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2790 | PS5-09-PIT-8401 | CJX08 - Electrical instrument | #N/A | I | PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2791 | PS5-09-PIT-8402 | CJX08 - Electrical instrument | #N/A | I | PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2792 | PS5-09-PIT-8403 | CJX08 - Electrical instrument | #N/A | I | PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2793 | PS5-09-PIT-8404 | CJX08 - Electrical instrument | #N/A | I | PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2794 | PS5-09-TIT-8101 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2795 | PS5-09-TIT-8201 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2796 | PS5-09-TIT-8301 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2797 | PS5-09-TIT-8302 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2798 | PS5-09-TIT-8303 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2799 | PS5-09-TIT-8304 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2800 | PS5-09-TIT-8401 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2801 | PS5-09-TIT-8402 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2802 | PS5-09-TIT-8403 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2803 | PS5-09-TIT-8404 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2804 | PS5-09-TIT-8405 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2805 | PS5-09-TIT-8406 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2806 | PS5-09-TIT-8407 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2807 | PS5-09-TIT-8408 | CJX08 - Electrical instrument | #N/A | I | TEMPERATURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00067-2929 | PS5-23-SPZM-0003A | CJX08 - Electrical instrument | #N/A | I | CORROSION PROBE INTRUSIVE FLUSH TYPE - weight loss coupon [CP] |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2930 | PS5-23-SPZM-0003B | CJX08 - Electrical instrument | #N/A | I | CORROSION PROBE INTRUSIVE FLUSH TYPE - Bio-coupon [BP] |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2931 | PS5-23-SPZM-0003C | CJX08 - Electrical instrument | #N/A | I | CORROSION PROBE INTRUSIVE FLUSH TYPE - Electrical Resistance Probe [ ER] |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2932 | PS5-23-SPZM-0003D | CJX08 - Electrical instrument | #N/A | I | ULTRASONIC THICKNESS SENSORS NON INTRUSIVE - ultrasonic wall thickness [UT] sensors |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00067-2933 | PS5-23-SPZM-0004A | CJX08 - Electrical instrument | #N/A | I | CORROSION PROBE INTRUSIVE FLUSH TYPE - weight loss coupon [CP] |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2934 | PS5-23-SPZM-0004B | CJX08 - Electrical instrument | #N/A | I | CORROSION PROBE INTRUSIVE FLUSH TYPE - Bio-coupon [BP] |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2935 | PS5-23-SPZM-0004C | CJX08 - Electrical instrument | #N/A | I | CORROSION PROBE INTRUSIVE FLUSH TYPE - Electrical Resistance Probe [ ER] |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00067-2936 | PS5-23-SPZM-0004D | CJX08 - Electrical instrument | #N/A | I | ULTRASONIC THICKNESS SENSORS NON INTRUSIVE - ultrasonic wall thickness [UT] sensors |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00069-10850 | ps5 EIT | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0005 TO PS5-03-RAB-B402 |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10851 | PS5-03-RAB-B902-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0005 TO PS5-03-RAB-B902 |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10852 | PS5-03-RAB-W502-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0006 TO PS5-03-RAB-W502 |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10853 | PS5-03-RDHR-W101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W201A TO PS5-03-RDHR-W101A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10854 | PS5-03-RDHR-W101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101A TO PS5-03-RDHR-W101B |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10855 | PS5-03-RDHR-W101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101B TO PS5-03-RDHR-W101C |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10856 | PS5-03-RDHR-W101D-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101E TO PS5-03-RDHR-W101D |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10857 | PS5-03-RDHR-W101E-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101F TO PS5-03-RDHR-W101E |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10858 | PS5-03-RDHR-W101F-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101C TO PS5-03-RDHR-W101F |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10859 | PS5-03-RDHR-W101G-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101D TO PS5-03-RDHR-W101G |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10860 | PS5-03-RDHR-W101H-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101G TO PS5-03-RDHR-W101H |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10861 | PS5-03-RDHR-W101I-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101H TO PS5-03-RDHR-W101I |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10862 | PS5-03-RDHR-W601A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601B TO PS5-03-RDHR-W601A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10863 | PS5-03-RDHR-W601B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601C TO PS5-03-RDHR-W601B |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10864 | PS5-03-RDHR-W601C-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601D TO PS5-03-RDHR-W601C |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10865 | PS5-03-RDHR-W601D-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601E TO PS5-03-RDHR-W601D |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10866 | PS5-03-RDHR-W601E-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601F TO PS5-03-RDHR-W601E |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10867 | PS5-03-RDHR-W601F-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601G TO PS5-03-RDHR-W601F |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10868 | PS5-03-RDHR-W601G-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601H TO PS5-03-RDHR-W601G |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10869 | PS5-03-RDHR-W601H-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601I TO PS5-03-RDHR-W601H |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10870 | PS5-03-RDHR-W601I-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601J TO PS5-03-RDHR-W601I |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10871 | PS5-03-RDHR-W601J-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601K TO PS5-03-RDHR-W601J |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10872 | PS5-03-RDHR-W601K-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601L TO PS5-03-RDHR-W601K |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10873 | PS5-03-RDHR-W601L-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601M TO PS5-03-RDHR-W601L |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10874 | PS5-03-RDHR-W601M-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601N TO PS5-03-RDHR-W601M |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10875 | PS5-03-RDHR-W601N-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601O TO PS5-03-RDHR-W601N |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10876 | PS5-03-RDHR-W601O-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601P TO PS5-03-RDHR-W601O |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10877 | PS5-03-RDHR-W601P-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-W501 TO PS5-03-RDHR-W601P |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10878 | PS5-03-RDOS-B101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B101B TO PS5-03-RDOS-B101A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10879 | PS5-03-RDOS-B101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B101C TO PS5-03-RDOS-B101B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10880 | PS5-03-RDOS-B101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B101D TO PS5-03-RDOS-B101C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10881 | PS5-03-RDOS-B101D-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B401A TO PS5-03-RDOS-B101D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10882 | PS5-03-RDOS-B201A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B201B TO PS5-03-RDOS-B201A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10883 | PS5-03-RDOS-B201B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B201C TO PS5-03-RDOS-B201B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10884 | PS5-03-RDOS-B201C-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B201D TO PS5-03-RDOS-B201C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10885 | PS5-03-RDOS-B201D-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B201E TO PS5-03-RDOS-B201D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10886 | PS5-03-RDOS-B201E-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0005 TO PS5-03-RDOS-B201E |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10887 | PS5-03-RDOS-B301A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B101A TO PS5-03-RDOS-B301A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10888 | PS5-03-RDOS-B301B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B301A TO PS5-03-RDOS-B301B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10889 | PS5-03-RDOS-B301C-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B301B TO PS5-03-RDOS-B301C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10890 | PS5-03-RDOS-B301D-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B801A TO PS5-03-RDOS-B301D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10891 | PS5-03-RDOS-B401A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B401B TO PS5-03-RDOS-B401A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10892 | PS5-03-RDOS-B401B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B401C TO PS5-03-RDOS-B401B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10893 | PS5-03-RDOS-B401C-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-B401 TO PS5-03-RDOS-B401C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10894 | PS5-03-RDOS-B401D-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B501A TO PS5-03-RDOS-B401D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10895 | PS5-03-RDOS-B501A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B601A TO PS5-03-RDOS-B501A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10896 | PS5-03-RDOS-B601A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-B901 TO PS5-03-RDOS-B601A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10897 | PS5-03-RDOS-B701A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B901A TO PS5-03-RDOS-B701A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10898 | PS5-03-RDOS-B701B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701C TO PS5-03-RDOS-B701B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10899 | PS5-03-RDOS-B701C-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701D TO PS5-03-RDOS-B701C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10900 | PS5-03-RDOS-B701D-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701E TO PS5-03-RDOS-B701D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10901 | PS5-03-RDOS-B701E-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701F TO PS5-03-RDOS-B701E |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10902 | PS5-03-RDOS-B701F-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701G TO PS5-03-RDOS-B701F |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10903 | PS5-03-RDOS-B701G-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701I TO PS5-03-RDOS-B701G |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10904 | PS5-03-RDOS-B701H-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B301D TO PS5-03-RDOS-B701H |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10905 | PS5-03-RDOS-B701I-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701H TO PS5-03-RDOS-B701I |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10906 | PS5-03-RDOS-B801A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B801B TO PS5-03-RDOS-B801A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10907 | PS5-03-RDOS-B801B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701A TO PS5-03-RDOS-B801B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10908 | PS5-03-RDOS-B901A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B901B TO PS5-03-RDOS-B901A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10909 | PS5-03-RDOS-B901B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B901C TO PS5-03-RDOS-B901B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10910 | PS5-03-RDOS-B901C-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B901D TO PS5-03-RDOS-B901C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10911 | PS5-03-RDOS-B901D-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B901E TO PS5-03-RDOS-B901D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10912 | PS5-03-RDOS-B901E-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0005 TO PS5-03-RDOS-B901E |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10913 | PS5-03-RDOS-W201A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W201B TO PS5-03-RDOS-W201A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10914 | PS5-03-RDOS-W201B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W301A TO PS5-03-RDOS-W201B |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10915 | PS5-03-RDOS-W201C-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W201D TO PS5-03-RDOS-W201C |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10916 | PS5-03-RDOS-W201D-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501A TO PS5-03-RDOS-W201D |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10917 | PS5-03-RDOS-W301A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W401A TO PS5-03-RDOS-W301A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10918 | PS5-03-RDOS-W401A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W201C TO PS5-03-RDOS-W401A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10919 | PS5-03-RDOS-W501A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501B TO PS5-03-RDOS-W501A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10920 | PS5-03-RDOS-W501B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501C TO PS5-03-RDOS-W501B |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10921 | PS5-03-RDOS-W501C-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501D TO PS5-03-RDOS-W501C |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10922 | PS5-03-RDOS-W501D-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501E TO PS5-03-RDOS-W501D |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10923 | PS5-03-RDOS-W501E-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501F TO PS5-03-RDOS-W501E |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10924 | PS5-03-RDOS-W501F-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0006 TO PS5-03-RDOS-W501F |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-10925 | PS5-03-RMAC-B401-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B401D TO PS5-03-RMAC-B401 |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10926 | PS5-03-RMAC-B901-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0005 TO PS5-03-RMAC-B901 |  | PS5-03-24 - FZ - Office and Facilities Building
T-00069-10927 | PS5-03-RMAC-W501-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0006 TO PS5-03-RMAC-W501 |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00069-11574 | PS5-09-AH-8401-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11575 | PS5-09-AH-8401-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11576 | PS5-09-AH-8402-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11577 | PS5-09-AH-8402-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11578 | PS5-09-AH-8403-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11579 | PS5-09-AH-8403-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11580 | PS5-09-AS-8111A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8111A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11581 | PS5-09-AS-8111A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8111A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11582 | PS5-09-AS-8111B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8111B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11583 | PS5-09-AS-8111B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8111B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11584 | PS5-09-AS-8211A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8211A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11585 | PS5-09-AS-8211A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8211A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11586 | PS5-09-AS-8211B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8211B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11587 | PS5-09-AS-8211B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8211B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11588 | PS5-09-AS-8311A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11589 | PS5-09-AS-8311A-A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11590 | PS5-09-AS-8311B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11591 | PS5-09-AS-8311B-B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11592 | PS5-09-AS-8311C-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11593 | PS5-09-AS-8311C-A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11594 | PS5-09-AS-8311D-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311D |  | PS5-09-03 - HVAC for Generator Building
T-00069-11595 | PS5-09-AS-8311D-B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311D |  | PS5-09-03 - HVAC for Generator Building
T-00069-11596 | PS5-09-AS-8321A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11597 | PS5-09-AS-8321A-A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11598 | PS5-09-AS-8321B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11599 | PS5-09-AS-8321B-B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11600 | PS5-09-AS-8321C-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11601 | PS5-09-AS-8321C-A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11602 | PS5-09-AS-8321D-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321D |  | PS5-09-03 - HVAC for Generator Building
T-00069-11603 | PS5-09-AS-8321D-B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321D |  | PS5-09-03 - HVAC for Generator Building
T-00069-11604 | PS5-09-AS-8331A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11605 | PS5-09-AS-8331A-A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11606 | PS5-09-AS-8331B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11607 | PS5-09-AS-8331B-B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11608 | PS5-09-AS-8331C-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11609 | PS5-09-AS-8331C-A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11610 | PS5-09-AS-8331D-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331D |  | PS5-09-03 - HVAC for Generator Building
T-00069-11611 | PS5-09-AS-8331D-B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331D |  | PS5-09-03 - HVAC for Generator Building
T-00069-11612 | PS5-09-AS-8341A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8341A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11613 | PS5-09-AS-8341A-A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8341A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11614 | PS5-09-AS-8341B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8341B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11615 | PS5-09-AS-8341B-B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8341B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11616 | PS5-09-AS-8411A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11617 | PS5-09-AS-8411A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11618 | PS5-09-AS-8411B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11619 | PS5-09-AS-8411B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11620 | PS5-09-AS-8412A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8412A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11621 | PS5-09-AS-8412A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8412A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11622 | PS5-09-AS-8412B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8412B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11623 | PS5-09-AS-8412B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8412B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11624 | PS5-09-AS-8421A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8421A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11625 | PS5-09-AS-8421A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8421A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11626 | PS5-09-AS-8421B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8421B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11627 | PS5-09-AS-8421B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8421B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11628 | PS5-09-AS-8432A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8432A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11629 | PS5-09-AS-8432A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8432A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11630 | PS5-09-AS-8432B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8432B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11631 | PS5-09-AS-8432B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8432B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11632 | PS5-09-BI-8111A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8111A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11633 | PS5-09-BI-8111B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8111B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11634 | PS5-09-BI-8211A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8211A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11635 | PS5-09-BI-8211B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8211B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11636 | PS5-09-BI-8311A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8311A-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11637 | PS5-09-BI-8311A-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8311A-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11638 | PS5-09-BI-8311B-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8311B-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11639 | PS5-09-BI-8311B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8311B-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11640 | PS5-09-BI-8321A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8321A-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11641 | PS5-09-BI-8321A-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8321A-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11642 | PS5-09-BI-8321B-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8321B-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11643 | PS5-09-BI-8321B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8321B-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11644 | PS5-09-BI-8331A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8331A-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11645 | PS5-09-BI-8331A-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8331A-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11646 | PS5-09-BI-8331B-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8331B-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11647 | PS5-09-BI-8331B-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8331B-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11648 | PS5-09-BI-8341A-A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8341A-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11649 | PS5-09-BI-8341A-B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8341A-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11650 | PS5-09-BI-8411A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11651 | PS5-09-BI-8411B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11652 | PS5-09-FCU-8442A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11653 | PS5-09-FCU-8442A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11654 | PS5-09-FCU-8442B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11655 | PS5-09-FCU-8442B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11656 | PS5-09-FCU-8442C-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11657 | PS5-09-FCU-8442C-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11658 | PS5-09-FCU-8442D-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442D |  | PS5-09-03 - HVAC for Generator Building
T-00069-11659 | PS5-09-FCU-8442D-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442D |  | PS5-09-03 - HVAC for Generator Building
T-00069-11660 | PS5-09-FCU-8442E-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442E |  | PS5-09-03 - HVAC for Generator Building
T-00069-11661 | PS5-09-FCU-8442E-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442E |  | PS5-09-03 - HVAC for Generator Building
T-00069-11662 | PS5-09-FCU-8442F-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442F |  | PS5-09-03 - HVAC for Generator Building
T-00069-11663 | PS5-09-FCU-8442F-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442F |  | PS5-09-03 - HVAC for Generator Building
T-00069-11664 | PS5-09-FCU-8442G-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442G |  | PS5-09-03 - HVAC for Generator Building
T-00069-11665 | PS5-09-FCU-8442G-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442G |  | PS5-09-03 - HVAC for Generator Building
T-00069-11666 | PS5-09-FCU-8442H-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442H |  | PS5-09-03 - HVAC for Generator Building
T-00069-11667 | PS5-09-FCU-8442H-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442H |  | PS5-09-03 - HVAC for Generator Building
T-00069-11668 | PS5-09-FD-0019-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0019 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11669 | PS5-09-FD-0019-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0019 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11670 | PS5-09-FD-0019-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0019 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11671 | PS5-09-FD-0021-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0021 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11672 | PS5-09-FD-0021-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0021 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11673 | PS5-09-FD-0021-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0021 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11674 | PS5-09-FD-0024-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0024 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11675 | PS5-09-FD-0024-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0024 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11676 | PS5-09-FD-0024-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0024 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11677 | PS5-09-FD-0025-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0025 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11678 | PS5-09-FD-0025-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0025 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11679 | PS5-09-FD-0025-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0025 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11680 | PS5-09-FD-0026-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0026 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11681 | PS5-09-FD-0026-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0026 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11682 | PS5-09-FD-0026-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0026 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11683 | PS5-09-FD-0027-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0027 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11684 | PS5-09-FD-0027-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0027 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11685 | PS5-09-FD-0027-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0027 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11686 | PS5-09-FD-0028-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0028 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11687 | PS5-09-FD-0028-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0028 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11688 | PS5-09-FD-0028-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0028 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11689 | PS5-09-FD-0029-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0029 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11690 | PS5-09-FD-0029-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0029 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11691 | PS5-09-FD-0029-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0029 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11692 | PS5-09-FD-0030-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0030 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11693 | PS5-09-FD-0030-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0030 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11694 | PS5-09-FD-0030-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0030 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11695 | PS5-09-FD-0031-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0031 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11696 | PS5-09-FD-0031-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0031 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11697 | PS5-09-FD-0031-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0031 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11698 | PS5-09-FD-0032-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0032 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11699 | PS5-09-FD-0032-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0032 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11700 | PS5-09-FD-0032-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0032 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11701 | PS5-09-FD-0033-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0033 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11702 | PS5-09-FD-0033-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0033 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11703 | PS5-09-FD-0033-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0033 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11704 | PS5-09-HE-8401A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-61-IH-0004 TO PS5-09-HE-8401A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11705 | PS5-09-HE-8401B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-61-IH-0004 TO PS5-09-HE-8401B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11706 | PS5-09-LB-8111A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8111A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11707 | PS5-09-LB-8111B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8111B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11708 | PS5-09-LB-8211A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8211A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11709 | PS5-09-LB-8211B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8211B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11710 | PS5-09-LB-8311A-A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8311A-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11711 | PS5-09-LB-8311A-B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8311B-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11712 | PS5-09-LB-8311B-A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8311B-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11713 | PS5-09-LB-8311B-B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8321A-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11714 | PS5-09-LB-8321A-A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8321A-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11715 | PS5-09-LB-8321A-B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8321B-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11716 | PS5-09-LB-8321B-A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8321B-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11717 | PS5-09-LB-8321B-B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8331A-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11718 | PS5-09-LB-8331A-A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8331A-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11719 | PS5-09-LB-8331A-B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8331B-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11720 | PS5-09-LB-8331B-A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8331B-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11721 | PS5-09-LB-8331B-B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8341A-A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11722 | PS5-09-LB-8341A-A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8341A-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11723 | PS5-09-LB-8341A-B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8341A-B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11724 | PS5-09-LB-8411A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11725 | PS5-09-LB-8411B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11726 | PS5-09-LB-8442A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11727 | PS5-09-LB-8442B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11728 | PS5-09-LB-8442C-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11729 | PS5-09-LB-8442D-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442D |  | PS5-09-03 - HVAC for Generator Building
T-00069-11730 | PS5-09-LB-8442E-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442E |  | PS5-09-03 - HVAC for Generator Building
T-00069-11731 | PS5-09-LB-8442F-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442F |  | PS5-09-03 - HVAC for Generator Building
T-00069-11732 | PS5-09-LB-8442G-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442G |  | PS5-09-03 - HVAC for Generator Building
T-00069-11733 | PS5-09-LB-8442H-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442H |  | PS5-09-03 - HVAC for Generator Building
T-00069-11734 | PS5-09-LB-8451A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11735 | PS5-09-LB-8451A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11736 | PS5-09-LB-8451B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11737 | PS5-09-LB-8451B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11738 | PS5-09-PDIT-8207-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PDIT-8207 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11739 | PS5-09-PDIT-8407-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PDIT-8407 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11740 | PS5-09-PDIT-8408-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PDIT-8408 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11741 | PS5-09-PDIT-8409-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PDIT-8409 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11742 | PS5-09-PDIT-8411-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PDIT-8411 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11743 | PS5-09-PIT-8401-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PIT-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11744 | PS5-09-PIT-8402-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PIT-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11745 | PS5-09-PIT-8403-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PIT-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11746 | PS5-09-PIT-8404-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PIT-8404 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11747 | PS5-09-TCV-8401-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TCV-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11748 | PS5-09-TCV-8401-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TCV-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11749 | PS5-09-TCV-8402-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TCV-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11750 | PS5-09-TCV-8402-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TCV-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11751 | PS5-09-TIT-8101-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8101 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11752 | PS5-09-TIT-8201-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8201 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11753 | PS5-09-TIT-8301-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8301 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11754 | PS5-09-TIT-8302-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8302 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11755 | PS5-09-TIT-8303-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8303 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11756 | PS5-09-TIT-8304-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8304 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11757 | PS5-09-TIT-8401-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11758 | PS5-09-TIT-8402-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11759 | PS5-09-TIT-8403-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11760 | PS5-09-TIT-8404-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8404 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11761 | PS5-09-TIT-8405-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8405 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11762 | PS5-09-TIT-8406-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8406 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11763 | PS5-09-TIT-8407-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8407 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11764 | PS5-09-TIT-8408-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8408 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11765 | PS5-09-UZ-84600-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-UZ-84600 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11766 | PS5-09-UZ-84600-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-UZ-84600 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11767 | PS5-09-XV-8401-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11768 | PS5-09-XV-8401-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11769 | PS5-09-XV-8402-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11770 | PS5-09-XV-8402-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11771 | PS5-09-XV-8403-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11772 | PS5-09-XV-8403-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11773 | PS5-09-XV-8404-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8404 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11774 | PS5-09-XV-8404-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8404 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11775 | PS5-09-XV-8413-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8413 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11776 | PS5-09-XV-8413-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8413 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11777 | PS5-09-XV-8414-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8414 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11778 | PS5-09-XV-8414-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8414 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11779 | PS5-61-IH-0004A-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11780 | PS5-61-IH-0004A-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11781 | PS5-61-IH-0004A-CU03 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11782 | PS5-61-IH-0004A-CU04 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004A |  | PS5-09-03 - HVAC for Generator Building
T-00069-11783 | PS5-61-IH-0004B-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11784 | PS5-61-IH-0004B-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11785 | PS5-61-IH-0004B-CU03 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11786 | PS5-61-IH-0004B-CU04 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004B |  | PS5-09-03 - HVAC for Generator Building
T-00069-11787 | PS5-61-IH-0004C-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11788 | PS5-61-IH-0004C-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11789 | PS5-61-IH-0004C-CU03 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11790 | PS5-61-IH-0004C-CU04 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004C |  | PS5-09-03 - HVAC for Generator Building
T-00069-11791 | PS5-61-IH-0004-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11792 | PS5-61-IH-0004-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11793 | PS5-61-IH-0004-CU03 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11794 | PS5-61-IH-0004-CU04 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11795 | PS5-61-IH-0004-CU05 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11796 | PS5-61-IH-0004-CU06 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11797 | PS5-61-IH-0004-CU07 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11798 | PS5-61-IH-0004-CU08 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11799 | PS5-61-IH-0004-CU09 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11800 | PS5-61-IH-0004-CU10 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11801 | PS5-61-IH-0004-CU11 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11802 | PS5-61-IH-0004-CU12 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11803 | PS5-61-IH-0004-CU13 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11804 | PS5-61-IH-0004-CU14 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11805 | PS5-61-IH-0004-CU15 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11806 | PS5-61-IH-0004-CU16 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11807 | PS5-61-IH-0004-CU17 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11808 | PS5-61-IH-0004-CU18 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11809 | PS5-61-IH-0004-CU19 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11810 | PS5-61-IH-0004-CU20 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11811 | PS5-61-IH-0004-CU21 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11812 | PS5-61-IH-0004-CU22 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11813 | PS5-61-IH-0004-CU23 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11814 | PS5-61-IH-0004-CU24 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11815 | PS5-61-IH-0004-CU25 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11816 | PS5-61-IH-0004-CU26 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11817 | PS5-61-IH-0004-CU27 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11818 | PS5-61-IH-0004-CU28 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11819 | PS5-61-IH-0004-CU29 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00069-11820 | PS5-61-IH-0004D-CU01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004D |  | PS5-09-03 - HVAC for Generator Building
T-00069-11821 | PS5-61-IH-0004D-CU02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004D |  | PS5-09-03 - HVAC for Generator Building
T-00069-4210 | PS5-01-BI-0007-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-BI-0007 |  | PS5-01-11 - Inergen for Power Gen Building
T-00069-4211 | PS5-01-BI-0008-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-BI-0008 |  | PS5-01-11 - Inergen for Power Gen Building
T-00069-4212 | PS5-01-BI-0009-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-BI-0009 |  | PS5-01-11 - Inergen for Power Gen Building
T-00069-4223 | PS5-01-FCV-0003A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-FCV-0003A-HPU TO PS5-01-FCV-0003A |  | PS5-01-02 - Fire Water Pump A
T-00069-4224 | PS5-01-FCV-0003B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-FCV-0003B-HPU TO PS5-01-FCV-0003B |  | PS5-01-03 - Fire Water Pump B
T-00069-4225 | PS5-01-FCV-0004A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-FCV-0004A-HPU TO PS5-01-FCV-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4226 | PS5-01-FCV-0004B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-FCV-0004B-HPU TO PS5-01-FCV-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4227 | PS5-01-FIT-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FIT-0003A-CJ01 | I | Cable FROM PS5-01-BI-1117 TO PS5-01-FIT-0003A |  | PS5-01-02 - Fire Water Pump A
T-00069-4228 | PS5-01-FIT-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FIT-0003B-CJ01 | I | Cable FROM PS5-01-BI-1117 TO PS5-01-FIT-0003B |  | PS5-01-03 - Fire Water Pump B
T-00069-4229 | PS5-01-FIT-0004A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FIT-0004A-CJ01 | I | Cable FROM PS5-01-BI-1117 TO PS5-01-FIT-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4230 | PS5-01-FIT-0004B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FIT-0004B-CJ01 | I | Cable FROM PS5-01-BI-1117 TO PS5-01-FIT-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4231 | PS5-01-FXS-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FXS-0003A-CJ01 | I | Cable FROM PS5-01-BI-2110 TO PS5-01-FCV-0003A |  | PS5-01-02 - Fire Water Pump A
T-00069-4232 | PS5-01-FXS-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FXS-0003B-CJ01 | I | Cable FROM PS5-01-BI-2110 TO PS5-01-FCV-0003B |  | PS5-01-03 - Fire Water Pump B
T-00069-4233 | PS5-01-FXS-0004A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FXS-0004A-CJ01 | I | Cable FROM PS5-01-BI-2110 TO PS5-01-FCV-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4234 | PS5-01-FXS-0004B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FXS-0004B-CJ01 | I | Cable FROM PS5-01-BI-2110 TO PS5-01-FCV-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4235 | PS5-01-FY-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FY-0003A-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0003A |  | PS5-01-02 - Fire Water Pump A
T-00069-4236 | PS5-01-FY-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FY-0003B-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0003B |  | PS5-01-03 - Fire Water Pump B
T-00069-4237 | PS5-01-FY-0004A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FY-0004A-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4238 | PS5-01-FY-0004B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-FY-0004B-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4239 | PS5-01-HS-3108AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-IE-0009A TO PS5-03-MTX-0001 |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-64-04-0086
T-00069-4240 | PS5-01-HS-3108BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-IE-0009B TO PS5-03-MTX-0001 |  | PS5-01-03 - Fire Water Pump B | CPP-RFI-68-64-04-0086
T-00069-4252 | PS5-01-LB-6101A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-LB-6101A |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-04-0086
T-00069-4253 | PS5-01-LB-6102A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-LB-6102A |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-04-0086
T-00069-4254 | PS5-01-LB-6103A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-LB-6103A |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-04-0086
T-00069-4255 | PS5-01-LB-6104A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-LB-6104A |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-04-0086
T-00069-4256 | PS5-01-LIT-4101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-LIT-4101A-CJ01 | I | Cable FROM PS5-01-IE-0009A TO PS5-01-LIT-4101A |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-64-04-0086
T-00069-4257 | PS5-01-LIT-4101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-LIT-4101B-CJ01 | I | Cable FROM PS5-01-IE-0009B TO PS5-01-LIT-4101A |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-64-04-0086
T-00069-4259 | PS5-01-NMR-61001-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMR-61001 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-4-0091
T-00069-4260 | PS5-01-NMR-61002-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMR-61002 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-4-0091
T-00069-4261 | PS5-01-NMR-61003-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMR-61003 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-4-0091
T-00069-4262 | PS5-01-NMR-61004-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMR-61004 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-4-0091
T-00069-4263 | PS5-01-NMRA-61001-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMRA-61001 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-4-0091
T-00069-4264 | PS5-01-NMRA-61002-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMRA-61002 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-4-0091
T-00069-4265 | PS5-01-NMRA-61003-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMRA-61003 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-4-0091
T-00069-4266 | PS5-01-NMRA-61004-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMRA-61004 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-4-0091
T-00069-4267 | PS5-01-PDIT-0011A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PDIT-0011A-CJ01 | I | Cable FROM PS5-01-BI-1515 TO PS5-01-PDIT-0011A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4268 | PS5-01-PDIT-0011B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PDIT-0011B-CJ01 | I | Cable FROM PS5-01-BI-1515 TO PS5-01-PDIT-0011B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4269 | PS5-01-PDIT-0012A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PDIT-0012A-CJ01 | I | Cable FROM PS5-01-BI-1515 TO PS5-01-PDIT-0012A |  | PS5-01-02 - Fire Water Pump A
T-00069-4270 | PS5-01-PDIT-0012B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PDIT-0012B-CJ01 | I | Cable FROM PS5-01-BI-1515 TO PS5-01-PDIT-0012B |  | PS5-01-03 - Fire Water Pump B
T-00069-4271 | PS5-01-PIT-0003AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-0003AA-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0003A |  | PS5-01-02 - Fire Water Pump A
T-00069-4272 | PS5-01-PIT-0003BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-0003BA-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0003B |  | PS5-01-03 - Fire Water Pump B
T-00069-4273 | PS5-01-PIT-0004AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-0004AA-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4274 | PS5-01-PIT-0004BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-0004BA-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00069-4275 | PS5-01-PIT-0010-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-0010-CJ01 | I | Cable FROM PS5-01-BI-1501 TO PS5-01-PIT-0010 |  | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4276 | PS5-01-PIT-0013-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-BI-1515 TO PS5-01-PIT-0013 |  | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-4-0089
T-00069-4281 | PS5-01-PIT-8101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101A-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101A |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-4-0089
T-00069-4282 | PS5-01-PIT-8101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101B-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101B |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-4-0089
T-00069-4283 | PS5-01-PIT-8101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101C-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101C |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-4-0089
T-00069-4284 | PS5-01-PIT-8101D-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101D-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101D |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-4-0089
T-00069-4285 | PS5-01-PIT-8101E-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101E-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101E |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-4-0089
T-00069-4286 | PS5-01-PIT-8101F-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101F-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101F |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-4-0089
T-00069-4287 | PS5-01-PIT-8101G-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101G-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101G |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-4-0089
T-00069-4288 | PS5-01-PIT-8101H-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101H-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101H |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-4-0089
T-00069-4289 | PS5-01-RAB-61001A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61001A |  | PS5-01-11 - Inergen for Power Gen Building
T-00069-4290 | PS5-01-RAB-61001B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61001B |  | PS5-01-11 - Inergen for Power Gen Building
T-00069-4291 | PS5-01-RAB-61002A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61002A |  | PS5-01-11 - Inergen for Power Gen Building
T-00069-4292 | PS5-01-RAB-61002B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61002B |  | PS5-01-11 - Inergen for Power Gen Building
T-00069-4293 | PS5-01-RAB-61003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61003A |  | PS5-01-11 - Inergen for Power Gen Building
T-00069-4294 | PS5-01-RAB-61003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61003B |  | PS5-01-11 - Inergen for Power Gen Building
T-00069-4295 | PS5-01-RAB-61004A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61004A |  | PS5-01-11 - Inergen for Power Gen Building
T-00069-4296 | PS5-01-RAB-61004B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61004B |  | PS5-01-11 - Inergen for Power Gen Building
T-00069-4297 | PS5-01-SY-8101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101A-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101A |  | PS5-01-10 - Water Mist Package
T-00069-4298 | PS5-01-SY-8101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101B-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101B |  | PS5-01-10 - Water Mist Package
T-00069-4299 | PS5-01-SY-8101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101C-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101C |  | PS5-01-10 - Water Mist Package
T-00069-4300 | PS5-01-SY-8101D-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101D-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101D |  | PS5-01-10 - Water Mist Package
T-00069-4301 | PS5-01-SY-8101E-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101E-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101E |  | PS5-01-10 - Water Mist Package
T-00069-4302 | PS5-01-SY-8101F-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101F-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101F |  | PS5-01-10 - Water Mist Package
T-00069-4303 | PS5-01-SY-8101G-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101G-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101G |  | PS5-01-10 - Water Mist Package
T-00069-4304 | PS5-01-SY-8101H-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101H-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101H |  | PS5-01-10 - Water Mist Package
T-00069-4331 | PS5-03-GDIR-0901-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0901-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0901 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4332 | PS5-03-GDIR-0902-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0902-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0902 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4333 | PS5-03-GDIR-0903-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0903-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0903 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4334 | PS5-03-GDIR-0904-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0904-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0904 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4335 | PS5-03-GDIR-0906-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0906-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0906 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4336 | PS5-03-GDIR-0907-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0907-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0907 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4337 | PS5-03-GDIR-0908-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0908-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0908 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4338 | PS5-03-GDIR-0909-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0909-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0909 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4339 | PS5-03-GDIR-1001-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1001-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1001 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4340 | PS5-03-GDIR-1002-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1002-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1002 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4341 | PS5-03-GDIR-1003-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1003-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1003 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4342 | PS5-03-GDIR-1004-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1004-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1004 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4343 | PS5-03-GDIR-1006-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1006-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1006 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4344 | PS5-03-GDIR-1007-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1007-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1007 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4345 | PS5-03-GDIR-1008-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1008-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1008 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4346 | PS5-03-GDIR-1009-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1009-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1009 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4347 | PS5-03-GDIR-1101-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1101-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1101 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4348 | PS5-03-GDIR-1102-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1102-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1102 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4349 | PS5-03-GDIR-1103-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1103-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1103 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4350 | PS5-03-GDIR-1104-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1104-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1104 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4351 | PS5-03-GDIR-1106-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1106-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1106 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4352 | PS5-03-GDIR-1107-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1107-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1107 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4353 | PS5-03-GDIR-1108-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1108-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1108 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4354 | PS5-03-GDIR-1109-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1109-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1109 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4355 | PS5-03-GDIR-1201-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1201-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1201 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00069-4356 | PS5-03-GDIR-1202-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1202-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1202 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00069-4357 | PS5-03-GDIR-1203-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1203-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1203 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00069-4358 | PS5-03-GDIR-1204-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1204-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1204 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4359 | PS5-03-GDLHP-0137-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0137-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0137 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4360 | PS5-03-GDLHP-0142-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0142-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0142 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4361 | PS5-03-GDLHP-0143-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0143-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0143 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4362 | PS5-03-GDLHP-0144-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0144-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0144 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4363 | PS5-03-GDLHP-0146-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0146-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0146 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4364 | PS5-03-GDLHP-0147-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0147-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0147 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4365 | PS5-03-GDLHP-0149-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0149-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0149 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4366 | PS5-03-GDLHP-0150-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0150-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0150 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4367 | PS5-03-GDLHP-0401-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0401-CJ01 | I | Cable FROM PS5-03-BI-2512 TO PS5-03-GDLHP-0401 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4381 | PS5-03-RDH-0302-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-2510 TO PS5-03-RDH-0302 |  | PS5-03-03 - FZ-03 - Buildings Area
T-00069-4382 | PS5-03-RDH-0303-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-2510 TO PS5-03-RDH-0303 |  | PS5-03-03 - FZ-03 - Buildings Area
T-00069-4383 | PS5-03-RDH-0601-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0601-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0601 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4384 | PS5-03-RDH-0602-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0602-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0602 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4385 | PS5-03-RDH-0603-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0603-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0603 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4386 | PS5-03-RDH-0604-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0604-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0604 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4387 | PS5-03-RDH-0605-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0605-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0605 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4388 | PS5-03-RDH-0606-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0606-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0606 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4389 | PS5-03-RDH-0607-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0607-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0607 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00069-4390 | PS5-03-RDH-0608-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0608-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0608 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00069-4391 | PS5-03-RDH-0609-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0609-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0609 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00069-4392 | PS5-03-RDH-0610-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0610-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0610 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00069-4393 | PS5-03-RDH-0611-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0611-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0611 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00069-4394 | PS5-03-RDH-0612-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0612-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0612 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00069-4395 | PS5-03-RDH-0614-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0614-CJ01 | I | Cable FROM PS5-03-BI-2501 TO PS5-03-RDH-0614 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4396 | PS5-03-RDH-0615-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0615-CJ01 | I | Cable FROM PS5-03-BI-2501 TO PS5-03-RDH-0615 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4397 | PS5-03-RDH-0616-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0616-CJ01 | I | Cable FROM PS5-03-BI-2501 TO PS5-03-RDH-0616 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4398 | PS5-03-RDH-0617-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0617-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0617 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4399 | PS5-03-RDH-0618-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0618-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0618 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4400 | PS5-03-RDH-0620-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0620-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0620 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4401 | PS5-03-RDH-0828-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0828-CJ01 | I | Cable FROM PS5-03-BI-2505 TO PS5-03-RDH-0828 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00069-4402 | PS5-03-RDH-0829-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0829-CJ01 | I | Cable FROM PS5-03-BI-2505 TO PS5-03-RDH-0829 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00069-4403 | PS5-03-RDH-0830-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0830-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0830 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4404 | PS5-03-RDH-0831-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0831-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0831 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4405 | PS5-03-RDH-0901-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0901-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0901 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4406 | PS5-03-RDH-0902-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0902-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0902 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4407 | PS5-03-RDH-0903-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0903-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0903 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4408 | PS5-03-RDH-0904-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0904-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0904 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4409 | PS5-03-RDH-0905-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0905-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0905 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4410 | PS5-03-RDH-0906-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0906-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0906 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4411 | PS5-03-RDH-0909-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0909-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0909 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4412 | PS5-03-RDH-0910-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0910-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0910 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4413 | PS5-03-RDH-0911-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0911-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0911 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4414 | PS5-03-RDH-0912-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0912-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0912 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4415 | PS5-03-RDH-1001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1001-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1001 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4416 | PS5-03-RDH-1002-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1002-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1002 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4417 | PS5-03-RDH-1003-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1003-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1003 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4418 | PS5-03-RDH-1004-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1004-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1004 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4419 | PS5-03-RDH-1005-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1005-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1005 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4420 | PS5-03-RDH-1006-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1006-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1006 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4421 | PS5-03-RDH-1009-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1009-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1009 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4422 | PS5-03-RDH-1010-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1010-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1010 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4423 | PS5-03-RDH-1011-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1011-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1011 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4424 | PS5-03-RDH-1012-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1012-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1012 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4425 | PS5-03-RDH-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1101-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1101 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4426 | PS5-03-RDH-1102-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1102-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1102 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4427 | PS5-03-RDH-1103-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1103-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1103 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4428 | PS5-03-RDH-1104-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1104-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1104 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4429 | PS5-03-RDH-1105-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1105-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1105 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4430 | PS5-03-RDH-1106-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1106-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1106 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4431 | PS5-03-RDH-1109-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1109-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1109 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4432 | PS5-03-RDH-1110-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1110-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1110 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4433 | PS5-03-RDH-1111-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1111-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1111 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4434 | PS5-03-RDH-1112-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1112-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1112 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4435 | PS5-03-RDH-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1201-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RDH-1201 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00069-4436 | PS5-03-RDH-1202-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1202-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RDH-1202 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00069-4437 | PS5-03-RDH-1203-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1203-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RDH-1203 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00069-4438 | PS5-03-RDH-1204-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1204-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RDH-1204 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00069-4439 | PS5-03-RDH-1205-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1205-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RDH-1205 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00069-4440 | PS5-03-RDH-1302-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1302-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RDH-1302 |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00069-4441 | PS5-03-RDH-1303-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1303-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RDH-1303 |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00069-4442 | PS5-03-RDH-1304-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1304-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RDH-1304 |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00069-4443 | PS5-03-RDH-1901-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDH-1903 TO PS5-03-RDH-1901 |  | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room
T-00069-4444 | PS5-03-RDH-1903-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-1410 TO PS5-03-RDH-1903 |  | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room
T-00069-4445 | PS5-03-RDIR-0104-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0104-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0104 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0091 | 2026-07-10 | Accepted with Comments | G K RAO | PULLING
T-00069-4446 | PS5-03-RDIR-0105-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0105-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0105 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0091 | 2026-07-10 | Accepted with Comments | G K RAO | PULLING
T-00069-4447 | PS5-03-RDIR-0106-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0106-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0106 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0091 | 2026-07-10 | Accepted with Comments | G K RAO | PULLING
T-00069-4448 | PS5-03-RDIR-0107-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0107 |  | PS5-03-01 - FZ-01 - Process Area
T-00069-4449 | PS5-03-RDIR-0108-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0108-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0108 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4450 | PS5-03-RDIR-0109-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0109-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0109 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4451 | PS5-03-RDIR-0110-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0110-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0110 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4452 | PS5-03-RDIR-0111-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0111-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0111 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4453 | PS5-03-RDIR-0112-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0112-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0112 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4454 | PS5-03-RDIR-0113-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0113-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0113 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4455 | PS5-03-RDIR-0114-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0114-CJ01 | I | Cable FROM PS5-03-BI-1509 TO PS5-03-RDIR-0114 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4456 | PS5-03-RDIR-0115-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0115-CJ01 | I | Cable FROM PS5-03-BI-1509 TO PS5-03-RDIR-0115 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4457 | PS5-03-RDIR-0116-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0116-CJ01 | I | Cable FROM PS5-03-BI-1509 TO PS5-03-RDIR-0116 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4458 | PS5-03-RDIR-0117-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0117-CJ01 | I | Cable FROM PS5-03-BI-1509 TO PS5-03-RDIR-0117 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4459 | PS5-03-RDIR-0118-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0118-CJ01 | I | Cable FROM PS5-03-BI-1509 TO PS5-03-RDIR-0118 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4460 | PS5-03-RDIR-0121-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0121-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0121 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4461 | PS5-03-RDIR-0122-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0122-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0122 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4462 | PS5-03-RDIR-0123-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0123-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0123 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4463 | PS5-03-RDIR-0124-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0124 |  | PS5-03-01 - FZ-01 - Process Area
T-00069-4464 | PS5-03-RDIR-0125-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0125-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0125 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4465 | PS5-03-RDIR-0126-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0126-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0126 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4466 | PS5-03-RDIR-0127-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0127-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0127 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4467 | PS5-03-RDIR-0128-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0128 |  | PS5-03-01 - FZ-01 - Process Area
T-00069-4468 | PS5-03-RDIR-0129-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0129 |  | PS5-03-01 - FZ-01 - Process Area
T-00069-4469 | PS5-03-RDIR-0130-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0130 |  | PS5-03-01 - FZ-01 - Process Area
T-00069-4470 | PS5-03-RDIR-0131-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0131 |  | PS5-03-01 - FZ-01 - Process Area
T-00069-4471 | PS5-03-RDIR-0132-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0132 |  | PS5-03-01 - FZ-01 - Process Area
T-00069-4472 | PS5-03-RDIR-0133-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0133 |  | PS5-03-01 - FZ-01 - Process Area
T-00069-4473 | PS5-03-RDIR-0137-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0137-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0137 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0091 | 2026-07-10 | Accepted with Comments | G K RAO | PULLING
T-00069-4474 | PS5-03-RDIR-0138-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0138-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0138 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0089 | 2026-07-07 | Accepted | G K RAO | PULLING
T-00069-4475 | PS5-03-RDIR-0141-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0141-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0141 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0091 | 2026-07-10 | Accepted with Comments | G K RAO | PULLING
T-00069-4476 | PS5-03-RDIR-0142-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0142-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0142 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-4-0091 | 2026-07-10 | Accepted with Comments | G K RAO | PULLING
T-00069-4477 | PS5-03-RDIR-0403-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0403-CJ01 | I | Cable FROM PS5-03-BI-1503 TO PS5-03-RDIR-0403 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4478 | PS5-03-RDIR-0404-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0404-CJ01 | I | Cable FROM PS5-03-BI-1503 TO PS5-03-RDIR-0404 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-4-0091 | 2026-07-10 | Accepted with Comments | G K RAO | PULLING
T-00069-4479 | PS5-03-RDIR-0405-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0405-CJ01 | I | Cable FROM PS5-03-BI-1502 TO PS5-03-RDIR-0405 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-4-0091 | 2026-07-10 | Accepted with Comments | G K RAO | PULLING
T-00069-4480 | PS5-03-RDIR-0406-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1502 TO PS5-03-RDIR-0406 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas
T-00069-4481 | PS5-03-RDIR-0409-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0409-CJ01 | I | Cable FROM PS5-03-BI-1503 TO PS5-03-RDIR-0409 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-4-0091 | 2026-07-10 | Accepted with Comments | G K RAO | PULLING
T-00069-4482 | PS5-03-RDIR-0411-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0411-CJ01 | I | Cable FROM PS5-03-BI-1503 TO PS5-03-RDIR-0411 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-4-0091 | 2026-07-10 | Accepted with Comments | G K RAO | PULLING
T-00069-4483 | PS5-03-RDIR-0819-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0819-CJ01 | I | Cable FROM PS5-03-BI-1510 TO PS5-03-RDIR-0819 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4484 | PS5-03-RDIR-0820-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0820-CJ01 | I | Cable FROM PS5-03-BI-1510 TO PS5-03-RDIR-0820 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4485 | PS5-03-RDIR-0832-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0832-CJ01 | I | Cable FROM PS5-03-BI-1510 TO PS5-03-RDIR-0832 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4486 | PS5-03-RDIR-0833-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1510 TO PS5-03-RDIR-0833 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00069-4487 | PS5-03-RDOS-1401-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-1411 TO PS5-03-RDOS-1401 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-4488 | PS5-03-RDOS-1402-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1401 TO PS5-03-RDOS-1402 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-4489 | PS5-03-RDOS-1403-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1402 TO PS5-03-RDOS-1403 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-4490 | PS5-03-RDOS-1404-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1403 TO PS5-03-RDOS-1404 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-4491 | PS5-03-RDOS-1405-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1404 TO PS5-03-RDOS-1405 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-4492 | PS5-03-RDOS-1406-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1503 TO PS5-03-RDOS-1406 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-4493 | PS5-03-RDOS-1407-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1405 TO PS5-03-RDOS-1407 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-4494 | PS5-03-RDOS-1408-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1407 TO PS5-03-RDOS-1408 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-4495 | PS5-03-RDOS-1501-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1603 TO PS5-03-RDOS-1501 |  | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1
T-00069-4496 | PS5-03-RDOS-1502-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1501 TO PS5-03-RDOS-1502 |  | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1
T-00069-4497 | PS5-03-RDOS-1503-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1502 TO PS5-03-RDOS-1503 |  | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1
T-00069-4498 | PS5-03-RDOS-1601-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1702 TO PS5-03-RDOS-1601 |  | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2
T-00069-4499 | PS5-03-RDOS-1602-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1601 TO PS5-03-RDOS-1602 |  | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2
T-00069-4500 | PS5-03-RDOS-1603-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1602 TO PS5-03-RDOS-1603 |  | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2
T-00069-4501 | PS5-03-RDOS-1701-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1803 TO PS5-03-RDOS-1701 |  | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3
T-00069-4502 | PS5-03-RDOS-1702-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1701 TO PS5-03-RDOS-1702 |  | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3
T-00069-4503 | PS5-03-RDOS-1801-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDH-1901 TO PS5-03-RDOS-1801 |  | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4
T-00069-4504 | PS5-03-RDOS-1802-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1801 TO PS5-03-RDOS-1802 |  | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4
T-00069-4505 | PS5-03-RDOS-1803-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1802 TO PS5-03-RDOS-1803 |  | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4
T-00069-4506 | PS5-03-RDOS-2101-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-1409 TO PS5-03-RDOS-2101 |  | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit
T-00069-4507 | PS5-03-RDOS-2102-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-2101 TO PS5-03-RDOS-2102 |  | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit
T-00069-4508 | PS5-03-RDOS-2103-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-2102 TO PS5-03-RDOS-2103 |  | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit
T-00069-4509 | PS5-03-RDOS-G101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-G101B TO PS5-03-RDOS-G101A |  | PS5-03-22 - FZ-G1 - Guard House
T-00069-4510 | PS5-03-RDOS-G101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0002 TO PS5-03-RDOS-G101B |  | PS5-03-22 - FZ-G1 - Guard House
T-00069-4511 | PS5-03-RDUIR-0701-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0701-CJ01 | I | Cable FROM PS5-03-BI-1511 TO PS5-03-RDUIR-0701 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00069-4512 | PS5-03-RDUIR-0702-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0702-CJ01 | I | Cable FROM PS5-03-BI-1511 TO PS5-03-RDUIR-0702 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00069-4513 | PS5-03-RDUIR-0703-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0703-CJ01 | I | Cable FROM PS5-03-BI-1511 TO PS5-03-RDUIR-0703 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00069-4514 | PS5-03-RDUIR-0704-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0704-CJ01 | I | Cable FROM PS5-03-BI-1511 TO PS5-03-RDUIR-0704 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00069-4515 | PS5-03-RDUIR-0705-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0705-CJ01 | I | Cable FROM PS5-03-BI-1511 TO PS5-03-RDUIR-0705 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00069-4516 | PS5-03-RDUIR-0907-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0907-CJ01 | I | Cable FROM PS5-03-BI-1512 TO PS5-03-RDUIR-0907 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4517 | PS5-03-RDUIR-0908-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0908-CJ01 | I | Cable FROM PS5-03-BI-1512 TO PS5-03-RDUIR-0908 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00069-4518 | PS5-03-RDUIR-1007-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1007-CJ01 | I | Cable FROM PS5-03-BI-1513 TO PS5-03-RDUIR-1007 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4519 | PS5-03-RDUIR-1008-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1008-CJ01 | I | Cable FROM PS5-03-BI-1513 TO PS5-03-RDUIR-1008 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00069-4520 | PS5-03-RDUIR-1107-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1107-CJ01 | I | Cable FROM PS5-03-BI-1514 TO PS5-03-RDUIR-1107 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4521 | PS5-03-RDUIR-1108-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1108-CJ01 | I | Cable FROM PS5-03-BI-1514 TO PS5-03-RDUIR-1108 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00069-4522 | PS5-03-RDUIR-1207-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1207-CJ01 | I | Cable FROM PS5-03-BI-1516 TO PS5-03-RDUIR-1207 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00069-4523 | PS5-03-RDUIR-1208-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1208-CJ01 | I | Cable FROM PS5-03-BI-1516 TO PS5-03-RDUIR-1208 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00069-4524 | PS5-03-RMAC-0101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0101-CJ01 | I | Cable FROM PS5-03-BI-2504 TO PS5-03-RMAC-0101 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4525 | PS5-03-RMAC-0102-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0102-CJ01 | I | Cable FROM PS5-03-BI-2504 TO PS5-03-RMAC-0102 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4526 | PS5-03-RMAC-0103-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0103-CJ01 | I | Cable FROM PS5-03-BI-2504 TO PS5-03-RMAC-0103 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4528 | PS5-03-RMAC-0301-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-2509 TO PS5-03-RMAC-0301 |  | PS5-03-03 - FZ-03 - Buildings Area
T-00069-4529 | PS5-03-RMAC-0304-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-2509 TO PS5-03-RMAC-0304 |  | PS5-03-03 - FZ-03 - Buildings Area
T-00069-4530 | PS5-03-RMAC-0401-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0401-CJ01 | I | Cable FROM PS5-03-BI-2509 TO PS5-03-RMAC-0401 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4531 | PS5-03-RMAC-0402-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0402-CJ01 | I | Cable FROM PS5-03-BI-2509 TO PS5-03-RMAC-0402 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4532 | PS5-03-RMAC-0613-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0613-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RMAC-0613 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4533 | PS5-03-RMAC-0706-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0706-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RMAC-0706 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00069-4534 | PS5-03-RMAC-0707-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0707-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RMAC-0707 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00069-4536 | PS5-03-RMAC-0825-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0825-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RMAC-0825 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00069-4537 | PS5-03-RMAC-0827-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0827-CJ01 | I | Cable FROM PS5-03-BI-2505 TO PS5-03-RMAC-0827 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00069-4538 | PS5-03-RMAC-0834-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0834-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RMAC-0834 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00069-4539 | PS5-03-RMAC-1301-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-1301-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RMAC-1301 |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00069-4540 | PS5-03-RMAC-1410-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-2103 TO PS5-03-RMAC-1410 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-4541 | PS5-03-RMAC-1411-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1406 TO PS5-03-RMAC-1411 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-4542 | PS5-03-SEA-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-03-SEA-0001-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4551 | PS5-05-BI-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4552 | PS5-05-BI-0002-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC02 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4553 | PS5-05-BI-0002-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC03 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4554 | PS5-05-BI-0002-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC04 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4555 | PS5-05-BI-0002-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC05 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4556 | PS5-05-BI-0002-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC06 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4559 | PS5-05-BI-0002-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CJ01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00069-4560 | PS5-05-BI-0002-CJ02 | CJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CJ02 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00069-4561 | PS5-05-BI-0002-CJ03 | CJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CJ03 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4562 | PS5-05-GC-8100-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-05-GC-8100-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4565 | PS5-05-IE-8101-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-05-IE-8101-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4566 | PS5-05-IG-0009-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-05-IG-0009-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4567 | PS5-05-IG-0009-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-05-IG-0009-CC02 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4568 | PS5-05-IG-0009-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-05-IG-0009-CJ01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4569 | PS5-05-LIT-4101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-05-LIT-4101-CJ01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4570 | PS5-05-UH-8100-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-05-UH-8100-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4571 | PS5-05-UH-8100-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-05-UH-8100-CC02 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Bertus Wikael
T-00069-4611 | PS5-25-BI-1802A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-BI-1802A-CC01 | I | Cable FROM PS5-61-IDH-3100A TO PS5-25-BI-1802A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00069-4613 | PS5-25-BI-1802B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-BI-1802B-CC01 | I | Cable FROM PS5-61-IDH-3100B TO PS5-25-BI-1802B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00069-4615 | PS5-25-BI-1802C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-BI-1802C-CC01 | I | Cable FROM PS5-61-IDH-3100C TO PS5-25-BI-1802C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00069-4642 | PS5-25-ESDV-0021-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0021-CC01 | I | Cable FROM PS5-25-BI-1201 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4643 | PS5-25-ESDV-0021-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0021-CC02 | I | Cable FROM PS5-25-BI-2201 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00069-4644 | PS5-25-ESDV-0021-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0021-CC03 | I | Cable FROM PS5-25-BI-2203 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00069-4645 | PS5-25-ESDV-0023-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0023-CC01 | I | Cable FROM PS5-25-BI-1201 TO PS5-25-ESDV-0023 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4646 | PS5-25-ESDV-0023-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0023-CC02 | I | Cable FROM PS5-25-BI-2201 TO PS5-25-ESDV-0023 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00069-4647 | PS5-25-ESDV-0023-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0023-CC03 | I | Cable FROM PS5-25-BI-2203 TO PS5-25-ESDV-0023 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00069-4648 | PS5-25-ESY-0021A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ESY-0021A-CJ01 | I | Cable FROM PS5-25-BI-2205 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4649 | PS5-25-ESY-0021B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ESY-0021B-CJ01 | I | Cable FROM PS5-25-BI-2309 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4650 | PS5-25-ESY-0023B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ESY-0023B-CJ01 | I | Cable FROM PS5-25-BI-2309 TO PS5-25-ESDV-0023 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4651 | PS5-25-FCV-0003A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-FCV-0003A-HPU TO PS5-25-FCV-0003A |  | PS5-25-02 - Crude Oil Export Pump A
T-00069-4652 | PS5-25-FCV-0003B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-FCV-0003B-HPU TO PS5-25-FCV-0003B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4653 | PS5-25-FCV-0003C-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-FCV-0003C-HPU TO PS5-25-FCV-0003C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4654 | PS5-25-FCV-0004-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-FCV-0004-HPU TO PS5-25-FCV-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00069-4655 | PS5-25-FIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FIT-0001-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-FIT-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4656 | PS5-25-FIT-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FIT-0003A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FIT-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4657 | PS5-25-FIT-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FIT-0003B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FIT-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4658 | PS5-25-FIT-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FIT-0003C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-FIT-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-4-0109 | 2026-07-22 | OPEN | G K RAO | PULLING
T-00069-4659 | PS5-25-FIT-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FIT-0004-CJ01 | I | Cable FROM PS5-25-BI-1115 TO PS5-25-FIT-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4660 | PS5-25-FXS-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FXS-0003A-CJ01 | I | Cable FROM PS5-25-BI-2106 TO PS5-25-FCV-0003A |  | PS5-25-02 - Crude Oil Export Pump A
T-00069-4661 | PS5-25-FXS-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FXS-0003B-CJ01 | I | Cable FROM PS5-25-BI-2106 TO PS5-25-FCV-0003B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4662 | PS5-25-FXS-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FXS-0003C-CJ01 | I | Cable FROM PS5-25-BI-2106 TO PS5-25-FCV-0003C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4663 | PS5-25-FXS-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FXS-0004-CJ01 | I | Cable FROM PS5-25-BI-2105 TO PS5-25-FCV-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00069-4664 | PS5-25-FY-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FY-0003A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FCV-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4665 | PS5-25-FY-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FY-0003B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FCV-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4666 | PS5-25-FY-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FY-0003C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-FCV-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-4-0109 | 2026-07-22 | OPEN | G K RAO | PULLING
T-00069-4667 | PS5-25-FY-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-FY-0004-CJ01 | I | Cable FROM PS5-25-BI-1115 TO PS5-25-FCV-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4668 | PS5-25-HS-8101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8101A-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8101A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4669 | PS5-25-HS-8101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8101B-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8101B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4670 | PS5-25-HS-8101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8101C-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8101C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4671 | PS5-25-HS-8102A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8102A-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8102A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4672 | PS5-25-HS-8102B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8102B-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8102B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4673 | PS5-25-HS-8102C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8102C-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8102C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4674 | PS5-25-MOV-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0001-CC01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00069-4675 | PS5-25-MOV-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0002-CC01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0002 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4676 | PS5-25-MOV-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0003-CC01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0003 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4677 | PS5-25-MOV-0008-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0008-CC01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0008 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00069-4678 | PS5-25-MOV-0011-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0011-CC01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0011 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4679 | PS5-25-MOV-0012-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0012-CC01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0012 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4680 | PS5-25-MOV-0025-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0025-CC01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0025 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00069-4681 | PS5-25-MOV-0026-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0026-CC01 | I | Cable FROM PS5-25-BI-2103 TO PS5-25-MOV-0026 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4682 | PS5-25-MOV-0026-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0026-CC02 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-MOV-0026 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4683 | PS5-25-MOV-0027-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0027-CC01 | I | Cable FROM PS5-25-BI-2103 TO PS5-25-MOV-0027 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4684 | PS5-25-MOV-0027-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0027-CC02 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-MOV-0027 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4685 | PS5-25-MOV-0028-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0028-CC01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0028 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00069-4686 | PS5-25-MXS-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MXS-0001-CJ01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00069-4687 | PS5-25-MXS-0008-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MXS-0008-CJ01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0008 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00069-4688 | PS5-25-MXS-0025-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MXS-0025-CJ01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0025 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00069-4689 | PS5-25-MXS-0028-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-MXS-0028-CJ01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0028 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00069-4696 | PS5-25-PDIT-0034A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PDIT-0034A |  | PS5-25-02 - Crude Oil Export Pump A
T-00069-4697 | PS5-25-PDIT-0034B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PDIT-0034B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PDIT-0034B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4698 | PS5-25-PDIT-0034C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PDIT-0034C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-PDIT-0034C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-4-0109 | 2026-07-22 | OPEN | G K RAO | PULLING
T-00069-4699 | PS5-25-PDIT-0050-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PDIT-0050-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-PDIT-0050 |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00069-4700 | PS5-25-PI-1102B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PI-1102B-CJ01 | I | Cable FROM PS5-25-PIT-1102 TO PS5-25-PI-1102B |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4701 | PS5-25-PI-1202B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PI-1202B-CJ01 | I | Cable FROM PS5-25-PIT-1202 TO PS5-25-PI-1202B |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4702 | PS5-25-PIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0001-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-PIT-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4703 | PS5-25-PIT-0003AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0003AA-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FCV-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4704 | PS5-25-PIT-0003BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0003BA-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FCV-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4705 | PS5-25-PIT-0003CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0003CA-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-FCV-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-4-0109 | 2026-07-22 | OPEN | G K RAO | PULLING
T-00069-4706 | PS5-25-PIT-0004AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0004AA-CJ01 | I | Cable FROM PS5-25-BI-1115 TO PS5-25-FCV-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00069-4707 | PS5-25-PIT-0004A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0004A-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-PIT-0004A |  | PS5-25-02 - Crude Oil Export Pump A
T-00069-4708 | PS5-25-PIT-0004B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0004B-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-PIT-0004B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4709 | PS5-25-PIT-0004C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0004C-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-PIT-0004C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4710 | PS5-25-PIT-0005A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0005A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PIT-0005A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4711 | PS5-25-PIT-0005B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0005B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PIT-0005B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4712 | PS5-25-PIT-0005C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0005C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-PIT-0005C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-4-0109 | 2026-07-22 | OPEN | G K RAO | PULLING
T-00069-4713 | PS5-25-PIT-0007A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0007A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PIT-0007A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4714 | PS5-25-PIT-0007B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0007B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PIT-0007B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4715 | PS5-25-PIT-0007C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0007C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-PIT-0007C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-4-0109 | 2026-07-22 | OPEN | G K RAO | PULLING
T-00069-4716 | PS5-25-PIT-0008A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0008A-CJ01 | I | Cable FROM PS5-25-BI-1301 TO PS5-25-PIT-0008A |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4717 | PS5-25-PIT-0008B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0008B-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-PIT-0008B |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4718 | PS5-25-PIT-0008C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0008C-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-PIT-0008C |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4719 | PS5-25-PIT-0013-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0013-CJ01 | I | Cable FROM PS5-25-BI-1115 TO PS5-25-PIT-0013 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4720 | PS5-25-PIT-0018-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0018-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PIT-0018 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4721 | PS5-25-PIT-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0022-CJ01 | I | Cable FROM PS5-25-BI-1301 TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4722 | PS5-25-PIT-0035A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0035A-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A
T-00069-4723 | PS5-25-PIT-0035B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0035B-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4724 | PS5-25-PIT-0035C-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4725 | PS5-25-PIT-0036A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0036A-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A
T-00069-4726 | PS5-25-PIT-0036B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0036B-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4727 | PS5-25-PIT-0036C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0036C-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4728 | PS5-25-PIT-0046-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0046-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00069-4730 | PS5-25-PIT-0053-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0053-CJ01 | I | Cable FROM PS5-25-BI-1115 TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4731 | PS5-25-PIT-0054A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0054A-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A
T-00069-4732 | PS5-25-PIT-0054B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0054B-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4733 | PS5-25-PIT-0054C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0054C-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4734 | PS5-25-PIT-0070-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0070-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-XV-0070 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4738 | PS5-25-PIT-1102-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-1102-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-PIT-1102 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4739 | PS5-25-PIT-1202-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-1202-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-PIT-1202 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4740 | PS5-25-SDV-0022-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0022-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4741 | PS5-25-SDV-0022-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-SDV-0022-HPU TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00069-4742 | PS5-25-SDV-0035A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0035A-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4743 | PS5-25-SDV-0035B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0035B-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4744 | PS5-25-SDV-0035C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0035C-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4745 | PS5-25-SDV-0036A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0036A-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4746 | PS5-25-SDV-0036B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0036B-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4747 | PS5-25-SDV-0036C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0036C-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4748 | PS5-25-SDV-0046-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0046-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4751 | PS5-25-SDV-0054A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0054A-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4752 | PS5-25-SDV-0054B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0054B-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4753 | PS5-25-SDV-0054C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0054C-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4755 | PS5-25-SXS-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-2302 TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00069-4756 | PS5-25-SXS-0035A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0035A-CJ01 | I | Cable FROM PS5-25-BI-2301 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4757 | PS5-25-SXS-0035B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0035B-CJ01 | I | Cable FROM PS5-25-BI-2301 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4758 | PS5-25-SXS-0035C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0035C-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4759 | PS5-25-SXS-0036A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0036A-CJ01 | I | Cable FROM PS5-25-BI-2301 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4760 | PS5-25-SXS-0036B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0036B-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4761 | PS5-25-SXS-0036C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0036C-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4762 | PS5-25-SXS-0046-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0046-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-4764 | PS5-25-SXS-0054A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-2301 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A
T-00069-4765 | PS5-25-SXS-0054B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0054B-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4766 | PS5-25-SXS-0054C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0054C-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4767 | PS5-25-SY-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0022-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4768 | PS5-25-SY-0035AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035AA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4769 | PS5-25-SY-0035AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035AB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A
T-00069-4770 | PS5-25-SY-0035BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035BA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4771 | PS5-25-SY-0035BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035BB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4772 | PS5-25-SY-0035CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035CA-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4773 | PS5-25-SY-0035CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035CB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4774 | PS5-25-SY-0036AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036AA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4775 | PS5-25-SY-0036AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036AB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A
T-00069-4776 | PS5-25-SY-0036BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036BA-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4777 | PS5-25-SY-0036BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036BB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4778 | PS5-25-SY-0036CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036CA-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4779 | PS5-25-SY-0036CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036CB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4780 | PS5-25-SY-0046A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0046A-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4781 | PS5-25-SY-0046B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0046B-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4783 | PS5-25-SY-0052B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0052B-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0052 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00069-4784 | PS5-25-SY-0054AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054AA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4785 | PS5-25-SY-0054AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054AB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4786 | PS5-25-SY-0054BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054BA-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4787 | PS5-25-SY-0054BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054BB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4788 | PS5-25-SY-0054CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054CA-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4789 | PS5-25-SY-0054CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054CB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C
T-00069-4790 | PS5-25-TIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0001-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-TIT-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4791 | PS5-25-TIT-0002A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0002A-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-TIT-0002A |  | PS5-25-02 - Crude Oil Export Pump A
T-00069-4792 | PS5-25-TIT-0002B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0002B-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-TIT-0002B |  | PS5-25-03 - Crude Oil Export Pump B
T-00069-4793 | PS5-25-TIT-0002C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0002C-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-TIT-0002C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4794 | PS5-25-TIT-0003A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0003A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-TIT-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4795 | PS5-25-TIT-0003B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0003B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-TIT-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4796 | PS5-25-TIT-0003C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0003C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-TIT-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-4-0109 | 2026-07-22 | OPEN | G K RAO | PULLING
T-00069-4797 | PS5-25-TIT-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0004-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-TIT-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4798 | PS5-25-TIT-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-1101-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-TIT-1101 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4799 | PS5-25-TIT-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-1201-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-TIT-1201 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4800 | PS5-25-XV-0053-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-XV-0053-CC01 | I | Cable FROM PS5-25-BI-2104 TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00069-4801 | PS5-25-XV-0053-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-XV-0053-HPU TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00069-4802 | PS5-25-XV-0070-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-XV-0070-CC01 | I | Cable FROM PS5-25-BI-2104 TO PS5-25-XV-0070 |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00069-4803 | PS5-25-XXS-0053-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-XXS-0053-CJ01 | I | Cable FROM PS5-25-BI-2105 TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00069-4804 | PS5-25-XXS-0070-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-XXS-0070-CJ01 | I | Cable FROM PS5-25-BI-2105 TO PS5-25-XV-0070 |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00069-4805 | PS5-25-XY-0053-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-XY-0053-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4806 | PS5-25-XY-0070-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-XY-0070-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-XV-0070 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4807 | PS5-25-ZIT-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ZIT-0001-CC01 | I | Cable FROM PS5-25-BI-1102 TO PS5-25-ZIT-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00069-4808 | PS5-25-ZIT-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ZIT-0002-CC01 | I | Cable FROM PS5-25-BI-1102 TO PS5-25-ZIT-0002 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00069-4809 | PS5-25-ZS-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ZS-1101-CJ01 | I | Cable FROM PS5-25-BI-2104 TO PS5-25-ZS-1101 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00069-4810 | PS5-25-ZS-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-25-ZS-1201-CJ01 | I | Cable FROM PS5-25-BI-2104 TO PS5-25-ZS-1201 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00069-4818 | PS5-28-HXA-1402-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-2115 TO PS5-28-HXA-1402 |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00069-4819 | PS5-28-HY-3901A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-HY-3901A-CJ01 | I | Cable FROM PS5-28-BI-1105 TO PS5-28-HY-3901A |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4820 | PS5-28-HY-3901B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-HY-3901B-CJ01 | I | Cable FROM PS5-28-BI-1105 TO PS5-28-HY-3901B |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4823 | PS5-28-LI-1101B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LI-1101B-CJ01 | I | Cable FROM PS5-28-LIT-1101 TO PS5-28-LI-1101B |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4824 | PS5-28-LI-1101C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LI-1101C-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-28-LI-1101C |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-04-0093 | 2026-07-13 | OPEN | G K RAO | PULLING
T-00069-4825 | PS5-28-LI-1402B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LI-1402B-CJ01 | I | Cable FROM PS5-28-LIT-1402 TO PS5-28-LI-1402B |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4826 | PS5-28-LIT-0002-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-0002-CJ01 | I | Cable FROM PS5-50-BI-1107 TO PS5-28-LIT-0002 |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4827 | PS5-28-LIT-0008-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-0008-CJ01 | I | Cable FROM PS5-50-BI-1107 TO PS5-28-LIT-0008 |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4828 | PS5-28-LIT-1101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1101-CJ01 | I | Cable FROM PS5-28-BI-1105 TO PS5-28-LIT-1101 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4829 | PS5-28-LIT-1102-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1102-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-LIT-1102 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4830 | PS5-28-LIT-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1201-CJ01 | I | Cable FROM PS5-28-BI-1106 TO PS5-28-LIT-1201 |  | PS5-28-06 - Relief Drum and Pump
T-00069-4831 | PS5-28-LIT-1202-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1202-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-LIT-1202 |  | PS5-28-06 - Relief Drum and Pump | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4832 | PS5-28-LIT-1301A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1301A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-28-LIT-1301A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4833 | PS5-28-LIT-1301B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1301B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-28-LIT-1301B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPP-RFI-68-64-04-0097 | 2026-07-16 | open | G K RAO | PULLING
T-00069-4834 | PS5-28-LIT-1301C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1301C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-28-LIT-1301C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPP-RFI-68-64-4-0109 | 2026-07-22 | OPEN | G K RAO | PULLING
T-00069-4835 | PS5-28-LIT-1401-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1401-CJ01 | I | Cable FROM PS5-28-BI-1307 TO PS5-28-LIT-1401 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4836 | PS5-28-LIT-1402-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1402-CJ01 | I | Cable FROM PS5-28-BI-1114 TO PS5-28-LIT-1402 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4837 | PS5-28-PIT-0015-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0015-CJ01 | I | Cable FROM PS5-28-BI-1105 TO PS5-28-PIT-0015 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4838 | PS5-28-PIT-0033-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0033-CJ01 | I | Cable FROM PS5-28-BI-1106 TO PS5-28-PIT-0033 |  | PS5-28-06 - Relief Drum and Pump
T-00069-4839 | PS5-28-PIT-0041-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0041-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-PIT-0041 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4840 | PS5-28-PIT-0045-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0045-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4841 | PS5-28-PIT-0053A-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-1302 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00069-4842 | PS5-28-PIT-0053B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0053B-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00069-4843 | PS5-28-PIT-0053C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0053C-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00069-4844 | PS5-28-PIT-3901A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-3901A-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-PIT-3901A |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4845 | PS5-28-PIT-3901B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-3901B-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-PIT-3901B |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4846 | PS5-28-SDV-0045-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SDV-0045-CC01 | I | Cable FROM PS5-28-BI-2304 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump
T-00069-4847 | PS5-28-SDV-0045-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-28-SDV-0045-HPU TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump
T-00069-4848 | PS5-28-SDV-0053A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SDV-0053A-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4849 | PS5-28-SDV-0053A-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-28-SDV-0053A-HPU TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00069-4850 | PS5-28-SDV-0053B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SDV-0053B-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00069-4851 | PS5-28-SDV-0053B-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-28-SDV-0053B-HPU TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00069-4852 | PS5-28-SDV-0053C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SDV-0053C-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00069-4853 | PS5-28-SDV-0053C-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-28-SDV-0053C-HPU TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00069-4854 | PS5-28-SXS-0045-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-2302 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump
T-00069-4855 | PS5-28-SXS-0053A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SXS-0053A-CJ01 | I | Cable FROM PS5-25-BI-2301 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4856 | PS5-28-SXS-0053B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SXS-0053B-CJ01 | I | Cable FROM PS5-25-BI-2301 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4857 | PS5-28-SXS-0053C-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SXS-0053C-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00069-4858 | PS5-28-SY-0045A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0045A-CJ01 | I | Cable FROM PS5-25-BI-2309 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4859 | PS5-28-SY-0045B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0045B-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4860 | PS5-28-SY-0053AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0053AA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4861 | PS5-28-SY-0053AB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0053AB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00069-4862 | PS5-28-SY-0053BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0053BA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4863 | PS5-28-SY-0053BB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0053BB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4864 | PS5-28-SY-0053CA-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-2316 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00069-4865 | PS5-28-SY-0053CB-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0053CB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00069-4866 | PS5-28-TIT-1104-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-1104-CJ01 | I | Cable FROM PS5-28-BI-1105 TO PS5-28-TIT-1104 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4867 | PS5-28-TIT-1105-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-1105-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-TIT-1105 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4868 | PS5-28-TIT-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-1201-CJ01 | I | Cable FROM PS5-28-BI-1106 TO PS5-28-TIT-1201 |  | PS5-28-06 - Relief Drum and Pump
T-00069-4869 | PS5-28-TIT-1401-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-1401-CJ01 | I | Cable FROM PS5-28-BI-1114 TO PS5-28-TIT-1401 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4870 | PS5-28-TIT-1402-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-1402-CJ01 | I | Cable FROM PS5-28-BI-1307 TO PS5-28-TIT-1402 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4871 | PS5-28-TIT-2101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-2101-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-TIT-2101 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4872 | PS5-28-TIT-2201-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-2201-CJ01 | I | Cable FROM PS5-28-BI-1307 TO PS5-28-TIT-2201 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-4874 | PS5-50-FIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-50-FIT-0001-CJ01 | I | Cable FROM PS5-50-BI-1107 TO PS5-50-FIT-0001 |  | PS5-50-03 - Water Pre-Treatment Package | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-4885 | PS5-53-LIT-4101-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-53-BI-1108 TO PS5-53-LIT-4101 |  | PS5-53-01 - Utility Water / Storage Tank
T-00069-4886 | PS5-53-LIT-4102-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-53-BI-1304 TO PS5-53-LIT-4102 |  | PS5-53-01 - Utility Water / Storage Tank
T-00069-4887 | PS5-53-PIT-0005-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-53-PIT-0005-CJ01 | I | Cable FROM PS5-53-BI-1108 TO PS5-53-PIT-0005 |  | PS5-53-02 - Water Distribution Pump A/B
T-00069-4888 | PS5-60-BE-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0001-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0001 |  | PS5-60-27 - Compressed Air Starting Skid | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4889 | PS5-60-BE-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0002-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0002 |  | PS5-60-26 - Instrument Air Compressor Skid | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4890 | PS5-60-BE-0004A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004A-CC01 | I | Cable FROM PS5-60-IN-0001A TO PS5-60-BE-0004A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4891 | PS5-60-BE-0004B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004B-CC01 | I | Cable FROM PS5-60-IN-0001B TO PS5-60-BE-0004B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4892 | PS5-60-BE-0004C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004C-CC01 | I | Cable FROM PS5-60-IN-0001C TO PS5-60-BE-0004C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4893 | PS5-60-BE-0004D-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004D-CC01 | I | Cable FROM PS5-60-IN-0001D TO PS5-60-BE-0004D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4894 | PS5-60-BE-0004E-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004E-CC01 | I | Cable FROM PS5-60-IN-0001E TO PS5-60-BE-0004E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4895 | PS5-60-BE-0004F-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004F-CC01 | I | Cable FROM PS5-60-IN-0001F TO PS5-60-BE-0004F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4896 | PS5-60-BE-0004G-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004G-CC01 | I | Cable FROM PS5-60-IN-0001G TO PS5-60-BE-0004G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4897 | PS5-60-BI-0001A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4898 | PS5-60-BI-0001A-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001A-CC03 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4899 | PS5-60-BI-0001B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4900 | PS5-60-BI-0001B-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001B-CC03 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4901 | PS5-60-BI-0001C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4902 | PS5-60-BI-0001C-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001C-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4903 | PS5-60-BI-0001D-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4904 | PS5-60-BI-0001D-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001D-CC03 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4905 | PS5-60-BI-0001E-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0001E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4906 | PS5-60-BI-0001E-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001E-CC03 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0001E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4907 | PS5-60-BI-0001F-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0001F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4908 | PS5-60-BI-0001F-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001F-CC03 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0001F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4909 | PS5-60-BI-0001G-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0001G |  | PS5-60-19 - Power Generation Package G | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4910 | PS5-60-BI-0001G-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001G-CC03 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0001G |  | PS5-60-19 - Power Generation Package G | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4911 | PS5-60-BI-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0002-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 |  | PS5-60-22 - Power Gen Master UCP
T-00069-4912 | PS5-60-BI-0002-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0002-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4913 | PS5-60-BI-0002-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0002-CC03 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 |  | PS5-60-22 - Power Gen Master UCP
T-00069-4914 | PS5-60-BI-0002-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0002-CC04 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 |  | PS5-60-22 - Power Gen Master UCP
T-00069-4915 | PS5-60-BI-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0003-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 |  | PS5-60-22 - Power Gen Master UCP | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4916 | PS5-60-BI-0003-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0003-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 |  | PS5-60-22 - Power Gen Master UCP | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4917 | PS5-60-BI-0004A-CCO1 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004A-CCO1 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0004A |  | PS5-60-01 - Power Generation Package A
T-00069-4918 | PS5-60-BI-0004B-CCO1 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004B-CCO1 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0004B |  | PS5-60-04 - Power Generation Package B
T-00069-4919 | PS5-60-BI-0004C-CCO1 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004C-CCO1 | I | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0004C |  | PS5-60-07 - Power Generation Package C
T-00069-4920 | PS5-60-BI-0004D-CCO1 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004D-CCO1 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0004D |  | PS5-60-10 - Power Generation Package D
T-00069-4921 | PS5-60-BI-0004E-CCO1 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004E-CCO1 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-BI-0004E |  | PS5-60-13 - Power Generation Package E
T-00069-4922 | PS5-60-BI-0004F-CCO1 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004F-CCO1 | I | Cable FROM PS5-60-IE-0001F TO PS5-60-BI-0004F |  | PS5-60-16 - Power Generation Package F
T-00069-4923 | PS5-60-BI-0004G-CCO1 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004G-CCO1 | I | Cable FROM PS5-60-IE-0001G TO PS5-60-BI-0004G |  | PS5-60-19 - Power Generation Package G
T-00069-4924 | PS5-60-BI-0005A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A |  | PS5-60-01 - Power Generation Package A
T-00069-4925 | PS5-60-BI-0005A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005A-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A |  | PS5-60-01 - Power Generation Package A
T-00069-4926 | PS5-60-BI-0005B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B |  | PS5-60-04 - Power Generation Package B
T-00069-4927 | PS5-60-BI-0005B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005B-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B |  | PS5-60-04 - Power Generation Package B
T-00069-4928 | PS5-60-BI-0005C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C |  | PS5-60-07 - Power Generation Package C
T-00069-4929 | PS5-60-BI-0005C-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005C-CC02 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C |  | PS5-60-07 - Power Generation Package C
T-00069-4930 | PS5-60-BI-0005D-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D |  | PS5-60-10 - Power Generation Package D
T-00069-4931 | PS5-60-BI-0005D-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005D-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D |  | PS5-60-10 - Power Generation Package D
T-00069-4932 | PS5-60-BI-0005E-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0005E |  | PS5-60-13 - Power Generation Package E
T-00069-4933 | PS5-60-BI-0005E-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005E-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0005E |  | PS5-60-13 - Power Generation Package E
T-00069-4934 | PS5-60-BI-0005F-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0005F |  | PS5-60-16 - Power Generation Package F
T-00069-4935 | PS5-60-BI-0005F-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005F-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0005F |  | PS5-60-16 - Power Generation Package F
T-00069-4936 | PS5-60-BI-0005G-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0005G |  | PS5-60-19 - Power Generation Package G
T-00069-4937 | PS5-60-BI-0005G-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005G-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0005G |  | PS5-60-19 - Power Generation Package G
T-00069-4938 | PS5-60-BI-0006A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0006A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4939 | PS5-60-BI-0006A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC02 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00069-4940 | PS5-60-BI-0006A-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC03 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00069-4941 | PS5-60-BI-0006A-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC04 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00069-4942 | PS5-60-BI-0006A-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC05 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4943 | PS5-60-BI-0006A-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC06 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00069-4944 | PS5-60-BI-0006B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0006B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4945 | PS5-60-BI-0006B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC02 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00069-4946 | PS5-60-BI-0006B-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC03 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00069-4947 | PS5-60-BI-0006B-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC04 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00069-4948 | PS5-60-BI-0006B-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC05 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4949 | PS5-60-BI-0006B-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC06 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00069-4950 | PS5-60-BI-0006C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0006C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4951 | PS5-60-BI-0006C-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC02 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00069-4952 | PS5-60-BI-0006C-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC03 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00069-4953 | PS5-60-BI-0006C-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC04 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00069-4954 | PS5-60-BI-0006C-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC05 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4955 | PS5-60-BI-0006C-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC06 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00069-4956 | PS5-60-BI-0006D-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0006D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4957 | PS5-60-BI-0006D-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC02 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00069-4958 | PS5-60-BI-0006D-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC03 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00069-4959 | PS5-60-BI-0006D-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC04 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00069-4960 | PS5-60-BI-0006D-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC05 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4961 | PS5-60-BI-0006D-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC06 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00069-4962 | PS5-60-BI-0006E-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0006E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4963 | PS5-60-BI-0006E-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC02 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00069-4964 | PS5-60-BI-0006E-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC03 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00069-4965 | PS5-60-BI-0006E-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC04 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00069-4966 | PS5-60-BI-0006E-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC05 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4967 | PS5-60-BI-0006E-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC06 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00069-4968 | PS5-60-BI-0006F-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0006F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4969 | PS5-60-BI-0006F-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC02 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00069-4970 | PS5-60-BI-0006F-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC03 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00069-4971 | PS5-60-BI-0006F-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC04 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00069-4972 | PS5-60-BI-0006F-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC05 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4973 | PS5-60-BI-0006F-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC06 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00069-4974 | PS5-60-BI-0006G-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0006G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4975 | PS5-60-BI-0006G-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC02 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00069-4976 | PS5-60-BI-0006G-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC03 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00069-4977 | PS5-60-BI-0006G-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC04 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00069-4978 | PS5-60-BI-0006G-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC05 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4979 | PS5-60-BI-0006G-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC06 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00069-4980 | PS5-60-BI-0008A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0008A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008A |  | PS5-60-01 - Power Generation Package A
T-00069-4981 | PS5-60-BI-0008A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0008A-CC02 | I | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008A |  | PS5-60-01 - Power Generation Package A
T-00069-4982 | PS5-60-BI-0008B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0008B-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008B |  | PS5-60-01 - Power Generation Package A
T-00069-4983 | PS5-60-BI-0008B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0008B-CC02 | I | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008B |  | PS5-60-01 - Power Generation Package A
T-00069-4984 | PS5-60-BI-0009A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0009A-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009A |  | PS5-60-04 - Power Generation Package B
T-00069-4985 | PS5-60-BI-0009A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0009A-CC02 | I | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009A |  | PS5-60-04 - Power Generation Package B
T-00069-4986 | PS5-60-BI-0009B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0009B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009B |  | PS5-60-04 - Power Generation Package B
T-00069-4987 | PS5-60-BI-0009B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0009B-CC02 | I | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4988 | PS5-60-BI-0010A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0010A-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010A |  | PS5-60-07 - Power Generation Package C
T-00069-4989 | PS5-60-BI-0010A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0010A-CC02 | I | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010A |  | PS5-60-07 - Power Generation Package C
T-00069-4990 | PS5-60-BI-0010B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0010B-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010B |  | PS5-60-07 - Power Generation Package C
T-00069-4991 | PS5-60-BI-0010B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0010B-CC02 | I | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010B |  | PS5-60-07 - Power Generation Package C | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4992 | PS5-60-BI-0011A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0011A-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011A |  | PS5-60-10 - Power Generation Package D
T-00069-4993 | PS5-60-BI-0011A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0011A-CC02 | I | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011A |  | PS5-60-10 - Power Generation Package D
T-00069-4994 | PS5-60-BI-0011B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0011B-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011B |  | PS5-60-10 - Power Generation Package D
T-00069-4995 | PS5-60-BI-0011B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0011B-CC02 | I | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011B |  | PS5-60-10 - Power Generation Package D | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4996 | PS5-60-BI-0012A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0012A-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0012A |  | PS5-60-13 - Power Generation Package E
T-00069-4997 | PS5-60-BI-0012A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0012A-CC02 | I | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0012A |  | PS5-60-13 - Power Generation Package E | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-4998 | PS5-60-BI-0012B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0012B-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0012B |  | PS5-60-13 - Power Generation Package E
T-00069-4999 | PS5-60-BI-0012B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0012B-CC02 | I | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0012B |  | PS5-60-13 - Power Generation Package E | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5000 | PS5-60-BI-0013A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0013A-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0013A |  | PS5-60-16 - Power Generation Package F
T-00069-5001 | PS5-60-BI-0013A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0013A-CC02 | I | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0013A |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5002 | PS5-60-BI-0013B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0013B-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0013B |  | PS5-60-16 - Power Generation Package F
T-00069-5003 | PS5-60-BI-0013B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0013B-CC02 | I | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0013B |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5004 | PS5-60-BI-0014A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0014A-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0014A |  | PS5-60-19 - Power Generation Package G
T-00069-5005 | PS5-60-BI-0014A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0014A-CC02 | I | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0014A |  | PS5-60-19 - Power Generation Package G | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5006 | PS5-60-BI-0014B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0014B-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0014B |  | PS5-60-19 - Power Generation Package G
T-00069-5007 | PS5-60-BI-0014B-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0014B |  | PS5-60-19 - Power Generation Package G
T-00069-5008 | PS5-60-BI-0016A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5009 | PS5-60-BI-0016A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016A-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-04-0117 | 2026-07-27 | Accepted with punch | G K RAO | PULLING | CPP-RFI-68-64-11-0118 | Accepted with punch | 2026-07-27 | G K RAO
T-00069-5010 | PS5-60-BI-0016A-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016A-CC03 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5011 | PS5-60-BI-0016A-CCO4 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016A-CCO4 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0016A |  | PS5-60-01 - Power Generation Package A
T-00069-5012 | PS5-60-BI-0016B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5013 | PS5-60-BI-0016B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016B-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B |  | PS5-60-04 - Power Generation Package B
T-00069-5014 | PS5-60-BI-0016B-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016B-CC03 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5015 | PS5-60-BI-0016B-CCO4 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016B-CCO4 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0016B |  | PS5-60-04 - Power Generation Package B
T-00069-5016 | PS5-60-BI-0016C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5017 | PS5-60-BI-0016C-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016C-CC02 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C |  | PS5-60-07 - Power Generation Package C
T-00069-5018 | PS5-60-BI-0016C-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016C-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5019 | PS5-60-BI-0016C-CCO4 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0016C |  | PS5-60-07 - Power Generation Package C
T-00069-5020 | PS5-60-BI-0016D-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5021 | PS5-60-BI-0016D-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016D-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D |  | PS5-60-10 - Power Generation Package D
T-00069-5022 | PS5-60-BI-0016D-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016D-CC03 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5023 | PS5-60-BI-0016D-CCO4 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0016D |  | PS5-60-10 - Power Generation Package D
T-00069-5024 | PS5-60-BI-0016E-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5025 | PS5-60-BI-0016E-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016E-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E |  | PS5-60-13 - Power Generation Package E
T-00069-5026 | PS5-60-BI-0016E-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016E-CC03 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5027 | PS5-60-BI-0016E-CCO4 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016E-CCO4 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-BI-0016E |  | PS5-60-13 - Power Generation Package E
T-00069-5028 | PS5-60-BI-0016F-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5029 | PS5-60-BI-0016F-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016F-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F |  | PS5-60-16 - Power Generation Package F
T-00069-5030 | PS5-60-BI-0016F-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016F-CC03 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5031 | PS5-60-BI-0016F-CCO4 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0001F TO PS5-60-BI-0016F |  | PS5-60-16 - Power Generation Package F
T-00069-5032 | PS5-60-BI-0016G-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G |  | PS5-60-19 - Power Generation Package G | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5033 | PS5-60-BI-0016G-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016G-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G |  | PS5-60-19 - Power Generation Package G
T-00069-5034 | PS5-60-BI-0016G-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016G-CC03 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5035 | PS5-60-BI-0016G-CCO4 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0001G TO PS5-60-BI-0016G |  | PS5-60-19 - Power Generation Package G
T-00069-5036 | PS5-60-BI-0017A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017A-CC02 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A
T-00069-5037 | PS5-60-BI-0017B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017B-CC02 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B
T-00069-5038 | PS5-60-BI-0017C-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017C-CC02 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00069-5039 | PS5-60-BI-0017D-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017D-CC02 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00069-5040 | PS5-60-BI-0017E-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017E-CC02 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0017E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00069-5041 | PS5-60-BI-0017F-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017F-CC02 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0017F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00069-5042 | PS5-60-BI-0017G-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017G-CC02 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0017G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00069-5043 | PS5-60-BI-0019A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5044 | PS5-60-BI-0019A-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5045 | PS5-60-BI-0019B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5046 | PS5-60-BI-0019B-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5047 | PS5-60-BI-0019C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5048 | PS5-60-BI-0019C-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5049 | PS5-60-BI-0019D-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5050 | PS5-60-BI-0019D-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019D-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5051 | PS5-60-BI-0019E-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0019E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5052 | PS5-60-BI-0019E-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019E-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0019E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5053 | PS5-60-BI-0019F-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0019F |  | PS5-60-16 - Power Generation Package F
T-00069-5054 | PS5-60-BI-0019F-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019F-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0019F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5055 | PS5-60-BI-0019G-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0019G |  | PS5-60-19 - Power Generation Package G
T-00069-5056 | PS5-60-BI-0019G-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019G-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0019G |  | PS5-60-19 - Power Generation Package G | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5057 | PS5-60-IE-0002B-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002B-CC05 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B
T-00069-5058 | PS5-60-IE-0002C-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002C-CC05 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5059 | PS5-60-IE-0002D-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002D-CC05 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5060 | PS5-60-IE-0002E-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002E-CC05 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5061 | PS5-60-IE-0002F-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002F-CC05 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5062 | PS5-60-IE-0002G-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002G-CC05 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5063 | PS5-60-IE-0003A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC01 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP)
T-00069-5064 | PS5-60-IE-0003A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC02 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-04-0117 | 2026-07-27 | Accepted with punch | G K RAO | PULLING | CPP-RFI-68-64-11-0118 | Accepted with punch | 2026-07-27 | G K RAO
T-00069-5065 | PS5-60-IE-0003A-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC03 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-04-0117 | 2026-07-27 | Accepted with punch | G K RAO | PULLING | CPP-RFI-68-64-11-0118 | Accepted with punch | 2026-07-27 | G K RAO
T-00069-5066 | PS5-60-IE-0003A-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC04 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-04-0117 | 2026-07-27 | Accepted with punch | G K RAO | PULLING | CPP-RFI-68-64-11-0118 | Accepted with punch | 2026-07-27 | G K RAO
T-00069-5067 | PS5-60-IE-0003A-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC05 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP)
T-00069-5068 | PS5-60-IE-0003A-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC06 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5069 | PS5-60-IE-0003A-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC07 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP)
T-00069-5070 | PS5-60-IE-0003A-CC08 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC08 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5071 | PS5-60-IE-0003A-CC09 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC09 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5072 | PS5-60-IE-0003A-CC10 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP)
T-00069-5073 | PS5-60-IE-0003A-CC11 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP)
T-00069-5074 | PS5-60-IE-0003A-CC15 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC15 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-04-0117 | 2026-07-27 | Accepted with punch | G K RAO | PULLING | CPP-RFI-68-64-11-0118 | Accepted with punch | 2026-07-27 | G K RAO
T-00069-5075 | PS5-60-IE-0003A-CC16 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC16 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5076 | PS5-60-IE-0003A-CC17 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC17 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5081 | PS5-60-IE-0003A-CC25 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC25 | I | Cable FROM PS5-60-TX-41100A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5082 | PS5-60-IE-0003A-CC26 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC26 | I | Cable FROM PS5-60-TX-41100B TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5083 | PS5-60-IE-0003B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC01 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00069-5084 | PS5-60-IE-0003B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC02 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00069-5085 | PS5-60-IE-0003B-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC03 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00069-5086 | PS5-60-IE-0003B-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC04 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00069-5087 | PS5-60-IE-0003B-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC05 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00069-5088 | PS5-60-IE-0003B-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC06 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00069-5089 | PS5-60-IE-0003B-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC07 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00069-5090 | PS5-60-IE-0003B-CC08 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC08 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5091 | PS5-60-IE-0003B-CC09 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC09 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5092 | PS5-60-IE-0003B-CC10 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00069-5093 | PS5-60-IE-0003B-CC11 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00069-5094 | PS5-60-IE-0003B-CC15 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC15 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5095 | PS5-60-IE-0003B-CC16 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC16 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5096 | PS5-60-IE-0003B-CC17 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC17 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5101 | PS5-60-IE-0003B-CC25 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC25 | I | Cable FROM PS5-60-TX-41200A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5102 | PS5-60-IE-0003B-CC26 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC26 | I | Cable FROM PS5-60-TX-41200B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5103 | PS5-60-IE-0003C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC01 | I | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00069-5104 | PS5-60-IE-0003C-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC02 | I | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00069-5105 | PS5-60-IE-0003C-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC03 | I | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00069-5106 | PS5-60-IE-0003C-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC04 | I | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00069-5107 | PS5-60-IE-0003C-CC05 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00069-5108 | PS5-60-IE-0003C-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC06 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00069-5109 | PS5-60-IE-0003C-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC07 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00069-5110 | PS5-60-IE-0003C-CC08 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC08 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5111 | PS5-60-IE-0003C-CC09 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC09 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5112 | PS5-60-IE-0003C-CC10 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00069-5113 | PS5-60-IE-0003C-CC11 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00069-5114 | PS5-60-IE-0003C-CC15 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC15 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00069-5115 | PS5-60-IE-0003C-CC16 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC16 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5116 | PS5-60-IE-0003C-CC17 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC17 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5121 | PS5-60-IE-0003C-CC25 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC25 | I | Cable FROM PS5-60-TX-41300A TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5122 | PS5-60-IE-0003C-CC26 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC26 | I | Cable FROM PS5-60-TX-41300B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5123 | PS5-60-IE-0003D-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC01 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00069-5124 | PS5-60-IE-0003D-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC02 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00069-5125 | PS5-60-IE-0003D-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC03 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00069-5126 | PS5-60-IE-0003D-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC04 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00069-5127 | PS5-60-IE-0003D-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC05 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00069-5128 | PS5-60-IE-0003D-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC06 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00069-5129 | PS5-60-IE-0003D-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC07 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00069-5130 | PS5-60-IE-0003D-CC08 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC08 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5131 | PS5-60-IE-0003D-CC09 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC09 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5132 | PS5-60-IE-0003D-CC10 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00069-5133 | PS5-60-IE-0003D-CC11 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00069-5134 | PS5-60-IE-0003D-CC15 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC15 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00069-5135 | PS5-60-IE-0003D-CC16 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC16 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5136 | PS5-60-IE-0003D-CC17 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC17 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5141 | PS5-60-IE-0003D-CC25 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC25 | I | Cable FROM PS5-60-TX-41400A TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5142 | PS5-60-IE-0003D-CC26 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC26 | I | Cable FROM PS5-60-TX-41400B TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5143 | PS5-60-IE-0003E-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC01 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00069-5144 | PS5-60-IE-0003E-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC02 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00069-5145 | PS5-60-IE-0003E-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC03 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00069-5146 | PS5-60-IE-0003E-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC04 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00069-5147 | PS5-60-IE-0003E-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC05 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003F |  | PS5-60-14 - Power Gen Package E (UCP)
T-00069-5148 | PS5-60-IE-0003E-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC06 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5149 | PS5-60-IE-0003E-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC07 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00069-5150 | PS5-60-IE-0003E-CC08 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC08 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5151 | PS5-60-IE-0003E-CC09 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC09 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5152 | PS5-60-IE-0003E-CC10 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00069-5153 | PS5-60-IE-0003E-CC11 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00069-5154 | PS5-60-IE-0003E-CC15 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC15 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00069-5155 | PS5-60-IE-0003E-CC16 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC16 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5156 | PS5-60-IE-0003E-CC17 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC17 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5161 | PS5-60-IE-0003E-CC25 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC25 | I | Cable FROM PS5-60-TX-41500A TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5162 | PS5-60-IE-0003E-CC26 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC26 | I | Cable FROM PS5-60-TX-41500B TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5163 | PS5-60-IE-0003F-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC01 | I | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5164 | PS5-60-IE-0003F-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC02 | I | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5165 | PS5-60-IE-0003F-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC03 | I | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5166 | PS5-60-IE-0003F-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC04 | I | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5167 | PS5-60-IE-0003F-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC05 | I | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0003G |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5168 | PS5-60-IE-0003F-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC06 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5169 | PS5-60-IE-0003F-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC07 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5170 | PS5-60-IE-0003F-CC08 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC08 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5171 | PS5-60-IE-0003F-CC09 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC09 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5172 | PS5-60-IE-0003F-CC10 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5173 | PS5-60-IE-0003F-CC11 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5174 | PS5-60-IE-0003F-CC15 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC15 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00069-5175 | PS5-60-IE-0003F-CC16 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC16 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5176 | PS5-60-IE-0003F-CC17 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC17 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5181 | PS5-60-IE-0003F-CC25 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC25 | I | Cable FROM PS5-60-TX-41600A TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5182 | PS5-60-IE-0003F-CC26 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC26 | I | Cable FROM PS5-60-TX-41600B TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5183 | PS5-60-IE-0003G-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC01 | I | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00069-5184 | PS5-60-IE-0003G-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC02 | I | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00069-5185 | PS5-60-IE-0003G-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC03 | I | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5186 | PS5-60-IE-0003G-CC04 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00069-5187 | PS5-60-IE-0003G-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC05 | I | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0003H |  | PS5-60-20 - Power Gen Package G (UCP)
T-00069-5188 | PS5-60-IE-0003G-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC06 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00069-5189 | PS5-60-IE-0003G-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC07 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00069-5190 | PS5-60-IE-0003G-CC08 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC08 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00069-5191 | PS5-60-IE-0003G-CC09 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC09 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00069-5192 | PS5-60-IE-0003G-CC10 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00069-5193 | PS5-60-IE-0003G-CC11 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00069-5194 | PS5-60-IE-0003G-CC15 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC15 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00069-5195 | PS5-60-IE-0003G-CC16 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC16 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5196 | PS5-60-IE-0003G-CC17 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC17 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5201 | PS5-60-IE-0003G-CC25 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC25 | I | Cable FROM PS5-60-TX-41700A TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5202 | PS5-60-IE-0003G-CC26 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC26 | I | Cable FROM PS5-60-TX-41700B TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5203 | PS5-60-IE-0004-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00069-5204 | PS5-60-IE-0004-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00069-5205 | PS5-60-IE-0004-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00069-5206 | PS5-60-IE-0004-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC04 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00069-5207 | PS5-60-IE-0004-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC05 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00069-5208 | PS5-60-IE-0004-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC06 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00069-5209 | PS5-60-IE-0004-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC07 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00069-5213 | PS5-60-IN-0001A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5214 | PS5-60-IN-0001A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001A-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A
T-00069-5215 | PS5-60-IN-0001A-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001A-CC03 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5216 | PS5-60-IN-0001A-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001A-CC04 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5217 | PS5-60-IN-0001B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5218 | PS5-60-IN-0001B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001B-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B
T-00069-5219 | PS5-60-IN-0001B-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001B-CC03 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5220 | PS5-60-IN-0001B-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001B-CC04 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5221 | PS5-60-IN-0001C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5222 | PS5-60-IN-0001C-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001C-CC02 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5223 | PS5-60-IN-0001C-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001C-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5224 | PS5-60-IN-0001C-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001C-CC04 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5225 | PS5-60-IN-0001D-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5226 | PS5-60-IN-0001D-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001D-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5227 | PS5-60-IN-0001D-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001D-CC03 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5228 | PS5-60-IN-0001D-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001D-CC04 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5229 | PS5-60-IN-0001E-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5230 | PS5-60-IN-0001E-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001E-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5231 | PS5-60-IN-0001E-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001E-CC03 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5232 | PS5-60-IN-0001E-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001E-CC04 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5233 | PS5-60-IN-0001F-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5234 | PS5-60-IN-0001F-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001F-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5235 | PS5-60-IN-0001F-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001F-CC03 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5236 | PS5-60-IN-0001F-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001F-CC04 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5237 | PS5-60-IN-0001G-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5238 | PS5-60-IN-0001G-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001G-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5239 | PS5-60-IN-0001G-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001G-CC03 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5240 | PS5-60-IN-0001G-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001G-CC04 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5241 | PS5-60-IN-0002A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00069-5242 | PS5-60-IN-0002A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00069-5243 | PS5-60-IN-0002A-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC03 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00069-5244 | PS5-60-IN-0002A-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC04 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00069-5245 | PS5-60-IN-0002A-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC05 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00069-5246 | PS5-60-IN-0002A-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC06 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5247 | PS5-60-IN-0002B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5248 | PS5-60-IN-0002B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00069-5249 | PS5-60-IN-0002B-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC03 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00069-5250 | PS5-60-IN-0002B-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC04 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5251 | PS5-60-IN-0002B-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC05 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00069-5252 | PS5-60-IN-0002B-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC06 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5253 | PS5-60-IN-0002C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5254 | PS5-60-IN-0002C-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC02 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00069-5255 | PS5-60-IN-0002C-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00069-5256 | PS5-60-IN-0002C-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC04 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5257 | PS5-60-IN-0002C-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC05 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00069-5258 | PS5-60-IN-0002C-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC06 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5259 | PS5-60-IN-0002D-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5260 | PS5-60-IN-0002D-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00069-5261 | PS5-60-IN-0002D-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC03 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00069-5262 | PS5-60-IN-0002D-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC04 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5263 | PS5-60-IN-0002D-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC05 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00069-5264 | PS5-60-IN-0002D-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC06 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5265 | PS5-60-IN-0002E-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5266 | PS5-60-IN-0002E-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00069-5267 | PS5-60-IN-0002E-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC03 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00069-5268 | PS5-60-IN-0002E-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC04 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5269 | PS5-60-IN-0002E-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC05 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00069-5270 | PS5-60-IN-0002E-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC06 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5271 | PS5-60-IN-0002F-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5272 | PS5-60-IN-0002F-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00069-5273 | PS5-60-IN-0002F-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC03 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00069-5274 | PS5-60-IN-0002F-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC04 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5275 | PS5-60-IN-0002F-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC05 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00069-5276 | PS5-60-IN-0002F-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC06 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5277 | PS5-60-IN-0002G-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5278 | PS5-60-IN-0002G-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00069-5279 | PS5-60-IN-0002G-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC03 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00069-5280 | PS5-60-IN-0002G-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC04 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5281 | PS5-60-IN-0002G-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC05 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00069-5282 | PS5-60-IN-0002G-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC06 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5283 | PS5-60-IN-0004A-CC11 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00069-5284 | PS5-60-LA-0002A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A
T-00069-5285 | PS5-60-LA-0002A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A
T-00069-5286 | PS5-60-LA-0002A-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC03 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A
T-00069-5287 | PS5-60-LA-0002A-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC04 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A
T-00069-5288 | PS5-60-LA-0002A-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC05 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A
T-00069-5289 | PS5-60-LA-0002A-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC06 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A
T-00069-5290 | PS5-60-LA-0002A-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC07 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A
T-00069-5291 | PS5-60-LA-0002A-CC08 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC08 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A
T-00069-5292 | PS5-60-LA-0002A-CC09 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC09 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A
T-00069-5293 | PS5-60-LA-0002B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002B-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00069-5294 | PS5-60-LA-0002B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002B-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00069-5295 | PS5-60-LA-0002B-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002B-CC03 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00069-5296 | PS5-60-LA-0002B-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002B-CC04 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00069-5297 | PS5-60-LA-0002B-CC05 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00069-5298 | PS5-60-LA-0002B-CC06 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00069-5299 | PS5-60-LA-0002C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5300 | PS5-60-LA-0002C-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5301 | PS5-60-LA-0002C-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC03 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5302 | PS5-60-LA-0002C-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC04 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5303 | PS5-60-LA-0002C-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC05 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5304 | PS5-60-LA-0002C-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC06 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5305 | PS5-60-LA-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0003-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 |  | PS5-60-22 - Power Gen Master UCP
T-00069-5306 | PS5-60-LIT-4301-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LIT-4301-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-60-LIT-4301 |  | PS5-60-24 - Cooling Water Tank & Pump | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5307 | PS5-60-LIT-4401-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-LIT-4401-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-60-LIT-4401 |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5308 | PS5-60-MOV-0005-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0005-CC01 | I | Cable FROM PS5-71-BI-2120 TO PS5-60-MOV-0005 |  | PS5-71-12 - CFO Service Tank
T-00069-5309 | PS5-60-MOV-0005-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0005-CC02 | I | Cable FROM PS5-71-BI-2124 TO PS5-60-MOV-0005 |  | PS5-71-12 - CFO Service Tank
T-00069-5310 | PS5-60-MOV-0006-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0006-CC01 | I | Cable FROM PS5-71-BI-2121 TO PS5-60-MOV-0006 |  | PS5-71-12 - CFO Service Tank
T-00069-5311 | PS5-60-MOV-0006-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0006-CC02 | I | Cable FROM PS5-71-BI-2125 TO PS5-60-MOV-0006 |  | PS5-71-12 - CFO Service Tank
T-00069-5312 | PS5-60-MOV-0011-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-2118 TO PS5-60-MOV-0011 |  | PS5-71-12 - CFO Service Tank
T-00069-5313 | PS5-60-MOV-0011-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0011-CC02 | I | Cable FROM PS5-71-BI-2122 TO PS5-60-MOV-0011 |  | PS5-71-12 - CFO Service Tank
T-00069-5314 | PS5-60-MOV-0012-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0012-CC01 | I | Cable FROM PS5-71-BI-2119 TO PS5-60-MOV-0012 |  | PS5-71-12 - CFO Service Tank
T-00069-5315 | PS5-60-MOV-0012-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0012-CC02 | I | Cable FROM PS5-71-BI-2123 TO PS5-60-MOV-0012 |  | PS5-71-12 - CFO Service Tank
T-00069-5316 | PS5-60-SEA-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5317 | PS5-60-SEA-0001-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-5318 | PS5-60-SEA-0001-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5319 | PS5-60-SEA-0001-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC04 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5320 | PS5-60-SEA-0001-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC05 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5321 | PS5-60-SEA-0001-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC06 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5322 | PS5-60-SEA-0001-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC07 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5323 | PS5-60-SEA-0001-CC10 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5324 | PS5-60-SEA-0001-CC11 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC11 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5325 | PS5-60-SEA-0001-CC12 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC12 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5326 | PS5-60-SEA-0001-CC13 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00069-5327 | PS5-60-SEA-0001-CC14 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC14 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5328 | PS5-60-SEA-0001-CC15 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC15 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5329 | PS5-60-SEA-0001-CC16 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC16 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5330 | PS5-60-SEA-0001-CC17 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC17 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5332 | PS5-60-SY-0007-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0007-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0007 |  | PS5-60-28 - Air Receiver A & Air Regulator A
T-00069-5333 | PS5-60-SY-0008-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0008-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0008 |  | PS5-60-29 - Air Receiver B & Air Regulator B
T-00069-5334 | PS5-60-SY-0009-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0009-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0009 |  | PS5-60-30 - Air Receiver C & Air Regulator C
T-00069-5335 | PS5-60-SY-0010-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0010-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0010 |  | PS5-60-31 - Air Receiver D & Air Regulator D
T-00069-5336 | PS5-60-SY-0011-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0011-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0011 |  | PS5-60-32 - Air Receiver E & Air Regulator E
T-00069-5337 | PS5-60-SY-0012-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0012-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0012 |  | PS5-60-33 - Air Receiver F & Air Regulator F | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5338 | PS5-60-SY-0013-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0013-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0013 |  | PS5-60-34 - Air Receiver G & Air Regulator G | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5339 | PS5-60-VS-9101A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-VS-9101A |  | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5340 | PS5-60-VS-9101B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-VS-9101B |  | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5341 | PS5-60-VS-9101C-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-VS-9101C |  | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5342 | PS5-60-VS-9101D-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-VS-9101D |  | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5343 | PS5-60-VS-9101E-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-VS-9101E |  | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5344 | PS5-60-VS-9101F-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-VS-9101F |  | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | Pulling
T-00069-5345 | PS5-60-VS-9101G-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-VS-9101G |  | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5346 | PS5-61-BI-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0001-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5347 | PS5-61-BI-0001-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0001-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5348 | PS5-61-BI-0001-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0001-CC03 | I | Cable FROM PS5-61-TE-0003A TO PS5-61-BI-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with Punch | Elizabeth | PULLING
T-00069-5349 | PS5-61-BI-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0002-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00069-5350 | PS5-61-BI-0002-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0002-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5351 | PS5-61-BI-0002-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0002-CC03 | I | Cable FROM PS5-61-TE-0003B TO PS5-61-BI-0002 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with Punch | Elizabeth | PULLING
T-00069-5352 | PS5-61-BI-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0003-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5353 | PS5-61-BI-0003-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0003-CC02 | I | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5354 | PS5-61-BI-0003-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0003-CC03 | I | Cable FROM PS5-61-TE-0003C TO PS5-61-BI-0003 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with Punch | Elizabeth | PULLING
T-00069-5355 | PS5-61-BI-0004-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0004-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5356 | PS5-61-BI-0004-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0004-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5357 | PS5-61-BI-0004-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0004-CC03 | I | Cable FROM PS5-61-TE-0003D TO PS5-61-BI-0004 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with Punch | Elizabeth | PULLING
T-00069-5358 | PS5-61-BI-0005-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0005-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-61-BI-0005 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5359 | PS5-61-BI-0005-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0005-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-61-BI-0005 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5360 | PS5-61-BI-0005-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0005-CC03 | I | Cable FROM PS5-61-TE-0003E TO PS5-61-BI-0005 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with Punch | Elizabeth | PULLING
T-00069-5361 | PS5-61-BI-0006-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0006-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-61-BI-0006 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5362 | PS5-61-BI-0006-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0006-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-61-BI-0006 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5363 | PS5-61-BI-0006-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0006-CC03 | I | Cable FROM PS5-61-TE-0003F TO PS5-61-BI-0006 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with Punch | Elizabeth | PULLING
T-00069-5364 | PS5-61-BI-0007-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0007-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-61-BI-0007 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5365 | PS5-61-BI-0007-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0007-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-61-BI-0007 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-64-04-0050 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00069-5366 | PS5-61-BI-0007-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0007-CC03 | I | Cable FROM PS5-61-TE-0003G TO PS5-61-BI-0007 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00069-5376 | PS5-71-BAV-0058-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BAV-0058-CC01 | I | Cable FROM PS5-71-BI-2113 TO PS5-71-BAV-0058 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5377 | PS5-71-BAV-0059-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BAV-0059-CC01 | I | Cable FROM PS5-71-BI-2113 TO PS5-71-BAV-0059 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5378 | PS5-71-BI-0001A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001A |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5379 | PS5-71-BI-0001B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001B |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5381 | PS5-71-BI-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0002 |  | PS5-71-18 - Diesel Separator Module
T-00069-5382 | PS5-71-BI-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0003-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5383 | PS5-71-BI-0003-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0003-CC02 | I | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5384 | PS5-71-BI-0003-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0003-CC03 | I | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5385 | PS5-71-BI-0003-CC04 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5386 | PS5-71-BI-0004-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5387 | PS5-71-BI-0005-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP)
T-00069-5388 | PS5-71-BI-0005-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0005-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0005 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5389 | PS5-71-BI-0006-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0006-CC01 | I | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00069-5390 | PS5-71-BI-0008A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0008A-CC01 | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5391 | PS5-71-BI-0008A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0008A-CC02 | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5392 | PS5-71-BI-0008B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5393 | PS5-71-BI-0008B-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5394 | PS5-71-BI-0009-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 |  | PS5-71-18 - Diesel Separator Module
T-00069-5395 | PS5-71-BI-0009-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0009-CC02 | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 |  | PS5-71-18 - Diesel Separator Module
T-00069-5396 | PS5-71-BI-0009-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0009-CC03 | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 |  | PS5-71-18 - Diesel Separator Module
T-00069-5397 | PS5-71-BI-0009-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0009-CC04 | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 |  | PS5-71-18 - Diesel Separator Module
T-00069-5398 | PS5-71-BI-0010-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0010-CC01 | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0010 |  | PS5-71-18 - Diesel Separator Module
T-00069-5399 | PS5-71-BI-0011A-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5400 | PS5-71-BI-0011A-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5401 | PS5-71-BI-0011A-CC03 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5402 | PS5-71-BI-0011A-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0011A-CC04 | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5403 | PS5-71-BI-0011A-CC05 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5404 | PS5-71-BI-0011B-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5405 | PS5-71-BI-0011B-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5406 | PS5-71-BI-0011B-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0011B-CC03 | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5407 | PS5-71-BI-0011B-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0011B-CC04 | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5408 | PS5-71-BI-0011B-CC05 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B |  | PS5-71-06 - Crude Fuel Separation Module
T-00069-5441 | PS5-71-FCV-0018-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-FCV-0018-HPU TO PS5-71-FCV-0018 |  | PS5-71-13 - CFO Service Pump A/B
T-00069-5442 | PS5-71-FCV-0019-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FCV-0019-CC01 | I | Cable FROM PS5-71-FCV-0019-HPU TO PS5-71-FCV-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00069-5443 | PS5-71-FCV-0020-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-FCV-0020-HPU TO PS5-71-FCV-0020 |  | PS5-71-05 - CFO Transfer Pump A/B
T-00069-5444 | PS5-71-FIT-0005-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0005-CJ01 | I | Cable FROM PS5-71-BI-1111 TO PS5-71-FIT-0005 |  | PS5-71-17 - Diesel Fuel Distribution Header | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5445 | PS5-71-FIT-0011A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0011A-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-FIT-0011A |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00069-5446 | PS5-71-FIT-0011B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0011B-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-FIT-0011B |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00069-5447 | PS5-71-FIT-0012-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1112 TO PS5-71-FIT-0012 |  | PS5-71-17 - Diesel Fuel Distribution Header
T-00069-5448 | PS5-71-FIT-0018-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0018-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-FIT-0018 |  | PS5-71-13 - CFO Service Pump A/B
T-00069-5449 | PS5-71-FIT-0019-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0019-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-FIT-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5450 | PS5-71-FIT-0020-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0020-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-FIT-0020 |  | PS5-71-05 - CFO Transfer Pump A/B
T-00069-5451 | PS5-71-FXS-0018-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FXS-0018-CJ01 | I | Cable FROM PS5-71-BI-2107 TO PS5-71-FCV-0018 |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5452 | PS5-71-FXS-0019-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FXS-0019-CJ01 | I | Cable FROM PS5-71-BI-2114 TO PS5-71-FCV-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5453 | PS5-71-FXS-0020-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FXS-0020-CJ01 | I | Cable FROM PS5-71-BI-2107 TO PS5-71-FCV-0020 |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5454 | PS5-71-FY-0018-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FY-0018-CJ01 | I | Cable FROM PS5-71-BI-1116 TO PS5-71-FCV-0018 |  | PS5-71-13 - CFO Service Pump A/B
T-00069-5455 | PS5-71-FY-0019-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FY-0019-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-71-FCV-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5456 | PS5-71-FY-0020-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-FY-0020-CJ01 | I | Cable FROM PS5-71-BI-1116 TO PS5-71-FCV-0020 |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5457 | PS5-71-IN-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5458 | PS5-71-IN-0001-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5459 | PS5-71-IN-0001-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC03 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5460 | PS5-71-IN-0001-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC04 | I | Cable FROM PS5-71-BI-0011A TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5461 | PS5-71-IN-0001-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC05 | I | Cable FROM PS5-71-BI-0011B TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5462 | PS5-71-IN-0001-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC06 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5463 | PS5-71-IN-0001-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC07 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5467 | PS5-71-IN-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0002-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5468 | PS5-71-IN-0002-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0002-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP)
T-00069-5469 | PS5-71-IN-0002-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0002-CC03 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5470 | PS5-71-IN-0002-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0002-CC04 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5474 | PS5-71-IN-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0003-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5475 | PS5-71-IN-0003-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0003-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-68-64-04-0080 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5476 | PS5-71-IN-0003-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0003-CC03 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5477 | PS5-71-IN-0003-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0003-CC04 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5481 | PS5-71-IN-0004A-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00069-5482 | PS5-71-IN-0004A-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00069-5483 | PS5-71-IN-0004A-CC03 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC03 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-04-0079 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5484 | PS5-71-IN-0004A-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC04 | I | Cable FROM PS5-71-BI-0011A TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5485 | PS5-71-IN-0004A-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC05 | I | Cable FROM PS5-71-BI-0011A TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5486 | PS5-71-IN-0004A-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC06 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5487 | PS5-71-IN-0004A-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC07 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5490 | PS5-71-IN-0004A-CC11 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00069-5492 | PS5-71-IN-0004A-CC13 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC13 | I | Cable FROM PS5-71-IN-0004B TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00069-5493 | PS5-71-IN-0004B-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00069-5494 | PS5-71-IN-0004B-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00069-5495 | PS5-71-IN-0004B-CC03 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00069-5496 | PS5-71-IN-0004B-CC04 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC04 | I | Cable FROM PS5-71-BI-0011B TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5497 | PS5-71-IN-0004B-CC05 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC05 | I | Cable FROM PS5-71-BI-0011B TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5498 | PS5-71-IN-0004B-CC06 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC06 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5499 | PS5-71-IN-0004B-CC07 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC07 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-04-0081 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00069-5502 | PS5-71-IN-0004B-CC11 | CJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC11 | I | Cable FROM PS5-71-IN-0001 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00069-5504 | PS5-71-LCV-4101-CC01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-LCV-4101-HPU TO PS5-71-LCV-4101 |  | PS5-71-04 - CFO Storage Tank
T-00069-5505 | PS5-71-LI-4201B-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-LIT-4201 TO PS5-71-LI-4201B |  | PS5-71-12 - CFO Service Tank
T-00069-5506 | PS5-71-LIT-1201-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-LIT-1201-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-71-LIT-1201 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5507 | PS5-71-LIT-1202-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-LIT-1202-CJ01 | I | Cable FROM PS5-28-BI-1307 TO PS5-71-LIT-1202 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5508 | PS5-71-LIT-4101-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1109 TO PS5-71-LIT-4101 |  | PS5-71-04 - CFO Storage Tank
T-00069-5509 | PS5-71-LIT-4102-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1305 TO PS5-71-LIT-4102 |  | PS5-71-04 - CFO Storage Tank
T-00069-5510 | PS5-71-LIT-4201-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1109 TO PS5-71-LIT-4201 |  | PS5-71-12 - CFO Service Tank
T-00069-5511 | PS5-71-LIT-4202-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1306 TO PS5-71-LIT-4202 |  | PS5-71-12 - CFO Service Tank
T-00069-5512 | PS5-71-LIT-4401-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-LIT-4401-CJ01 | I | Cable FROM PS5-71-BI-1111 TO PS5-71-LIT-4401 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5513 | PS5-71-LIT-4402-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-LIT-4402-CJ01 | I | Cable FROM PS5-71-BI-1308 TO PS5-71-LIT-4402 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5514 | PS5-71-LXS-4101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-LXS-4101-CJ01 | I | Cable FROM PS5-71-BI-2107 TO PS5-71-LCV-4101 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5515 | PS5-71-LY-4101-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-LY-4101-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-LCV-4101 |  | PS5-71-04 - CFO Storage Tank
T-00069-5516 | PS5-71-MOV-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0001-CC01 | I | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0001 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5517 | PS5-71-MOV-0001-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0001-CC02 | I | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0001 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5518 | PS5-71-MOV-0002-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0002-CC01 | I | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0002 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00069-5519 | PS5-71-MOV-0002-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0002-CC02 | I | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0002 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00069-5520 | PS5-71-MOV-0003-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0003-CC01 | I | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5521 | PS5-71-MOV-0003-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0003-CC02 | I | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5522 | PS5-71-MOV-0004-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0004-CC01 | I | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0004 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00069-5523 | PS5-71-MOV-0004-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0004-CC02 | I | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0004 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00069-5524 | PS5-71-MOV-0007-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0007-CC01 | I | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0007 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5525 | PS5-71-MOV-0007-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0007-CC02 | I | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0007 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5526 | PS5-71-MOV-0008-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0008-CC01 | I | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0008 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00069-5527 | PS5-71-MOV-0008-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0008-CC02 | I | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0008 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00069-5528 | PS5-71-MOV-0009-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0009-CC01 | I | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0009 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5529 | PS5-71-MOV-0009-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0009-CC02 | I | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0009 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00069-5530 | PS5-71-MOV-0010-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0010-CC01 | I | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0010 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00069-5531 | PS5-71-MOV-0010-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0010-CC02 | I | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0010 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00069-5532 | PS5-71-PDIT-0030-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PDIT-0030-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-PDIT-0030 |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00069-5533 | PS5-71-PDIT-0056A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PDIT-0056A-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PDIT-0056A |  | PS5-71-05 - CFO Transfer Pump A/B
T-00069-5534 | PS5-71-PDIT-0056B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PDIT-0056B-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PDIT-0056B |  | PS5-71-05 - CFO Transfer Pump A/B
T-00069-5535 | PS5-71-PIT-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0001-CJ01 | I | Cable FROM PS5-28-BI-1307 TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5536 | PS5-71-PIT-0014-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0014-CJ01 | I | Cable FROM PS5-71-BI-1111 TO PS5-71-PIT-0014 |  | PS5-71-17 - Diesel Fuel Distribution Header | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5537 | PS5-71-PIT-0018A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0018A-CJ01 | I | Cable FROM PS5-71-BI-1116 TO PS5-71-FCV-0018 |  | PS5-71-13 - CFO Service Pump A/B
T-00069-5538 | PS5-71-PIT-0019A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0019A-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-71-FCV-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5539 | PS5-71-PIT-0020A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0020A-CJ01 | I | Cable FROM PS5-71-BI-1116 TO PS5-71-FCV-0020 |  | PS5-71-05 - CFO Transfer Pump A/B
T-00069-5540 | PS5-71-PIT-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0022-CJ01 | I | Cable FROM PS5-71-BI-1305 TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5541 | PS5-71-PIT-0029-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0029-CJ01 | I | Cable FROM PS5-71-BI-1308 TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5542 | PS5-71-PIT-0039-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0039-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5543 | PS5-71-PIT-0089-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0089-CJ01 | I | Cable FROM PS5-71-BI-1117 TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank
T-00069-5544 | PS5-71-PIT-0090-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0090-CJ01 | I | Cable FROM PS5-71-BI-1117 TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank
T-00069-5545 | PS5-71-PIT-0091-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0091-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5546 | PS5-71-PIT-0092-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0092-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5547 | PS5-71-PIT-2402A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-2402A-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-PIT-2402A |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00069-5548 | PS5-71-PIT-2402B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-2402B-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-PIT-2402B |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00069-5549 | PS5-71-PIT-3301A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3301A-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-PIT-3301A |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5550 | PS5-71-PIT-3301B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3301B-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-PIT-3301B |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5551 | PS5-71-PIT-3302A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3302A-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PIT-3302A |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5552 | PS5-71-PIT-3302B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3302B-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PIT-3302B |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5553 | PS5-71-PIT-3401A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3401A-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-PIT-3401A |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5554 | PS5-71-PIT-3401B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3401B-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-PIT-3401B |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5555 | PS5-71-PIT-3402A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3402A-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PIT-3402A |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5556 | PS5-71-PIT-3402B-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3402B-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PIT-3402B |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5557 | PS5-71-PIT-4101A-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-4101A-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-LCV-4101 |  | PS5-71-04 - CFO Storage Tank
T-00069-5558 | PS5-71-SDV-0001-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SDV-0001-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank
T-00069-5559 | PS5-71-SDV-0001-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SDV-0001-CC02 | I | Cable FROM PS5-71-SDV-0001-HPU TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank
T-00069-5560 | PS5-71-SDV-0022-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SDV-0022-CC01 | I | Cable FROM PS5-71-BI-2306 TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank
T-00069-5561 | PS5-71-SDV-0022-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-SDV-0022-HPU TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank
T-00069-5562 | PS5-71-SDV-0029-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SDV-0029-CC01 | I | Cable FROM PS5-71-BI-2307 TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5563 | PS5-71-SDV-0029-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-SDV-0029-HPU TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00069-5564 | PS5-71-SDV-0039-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SDV-0039-CC01 | I | Cable FROM PS5-71-BI-2306 TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank
T-00069-5565 | PS5-71-SDV-0039-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-SDV-0039-HPU TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank
T-00069-5566 | PS5-71-SXS-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SXS-0001-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank
T-00069-5567 | PS5-71-SXS-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SXS-0022-CJ01 | I | Cable FROM PS5-71-BI-2314 TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5568 | PS5-71-SXS-0029-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SXS-0029-CJ01 | I | Cable FROM PS5-71-BI-2313 TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5569 | PS5-71-SXS-0039-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SXS-0039-CJ01 | I | Cable FROM PS5-71-BI-2314 TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5570 | PS5-71-SY-0001-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SY-0001-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank
T-00069-5571 | PS5-71-SY-0022-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SY-0022-CJ01 | I | Cable FROM PS5-71-BI-2310 TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5572 | PS5-71-SY-0029-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SY-0029-CJ01 | I | Cable FROM PS5-71-BI-2317 TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5573 | PS5-71-SY-0039-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-SY-0039-CJ01 | I | Cable FROM PS5-71-BI-2310 TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5574 | PS5-71-TIT-0003-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-0003-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-TIT-0003 |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00069-5575 | PS5-71-TIT-0004-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-0004-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-TIT-0004 |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00069-5576 | PS5-71-TIT-0006-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-0006-CJ01 | I | Cable FROM PS5-71-BI-1305 TO PS5-71-TIT-0006 |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5577 | PS5-71-TIT-0007-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-0007-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-TIT-0007 |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5578 | PS5-71-TIT-2204-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1306 TO PS5-71-TIT-2204 |  | PS5-71-12 - CFO Service Tank
T-00069-5579 | PS5-71-TIT-2301-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1305 TO PS5-71-TIT-2301 |  | PS5-71-04 - CFO Storage Tank
T-00069-5580 | PS5-71-TIT-2402AA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-2402AA-CJ01 | I | Cable FROM PS5-71-BI-1305 TO PS5-71-TIT-2402AA |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5581 | PS5-71-TIT-2402BA-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-2402BA-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-TIT-2402BA |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5584 | PS5-71-TIT-4102-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1109 TO PS5-71-TIT-4102 |  | PS5-71-04 - CFO Storage Tank
T-00069-5585 | PS5-71-TIT-4103-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1305 TO PS5-71-TIT-4103 |  | PS5-71-04 - CFO Storage Tank
T-00069-5586 | PS5-71-TIT-4202-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1109 TO PS5-71-TIT-4202 |  | PS5-71-12 - CFO Service Tank
T-00069-5587 | PS5-71-TIT-4203-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1306 TO PS5-71-TIT-4203 |  | PS5-71-12 - CFO Service Tank
T-00069-5588 | PS5-71-XV-0089-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XV-0089-CC01 | I | Cable FROM PS5-71-BI-2116 TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank
T-00069-5589 | PS5-71-XV-0089-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-XV-0089-HPU TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank
T-00069-5590 | PS5-71-XV-0090-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XV-0090-CC01 | I | Cable FROM PS5-71-BI-2116 TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank
T-00069-5591 | PS5-71-XV-0090-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-XV-0090-HPU TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank
T-00069-5592 | PS5-71-XV-0091-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XV-0091-CC01 | I | Cable FROM PS5-71-BI-2113 TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5593 | PS5-71-XV-0091-CC02 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-XV-0091-HPU TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module
T-00069-5594 | PS5-71-XV-0092-CC01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XV-0092-CC01 | I | Cable FROM PS5-71-BI-2113 TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5595 | PS5-71-XV-0092-CC02 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XV-0092-CC02 | I | Cable FROM PS5-71-XV-0092-HPU TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank
T-00069-5596 | PS5-71-XXS-0089-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XXS-0089-CJ01 | I | Cable FROM PS5-71-BI-2107 TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5597 | PS5-71-XXS-0090-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XXS-0090-CJ01 | I | Cable FROM PS5-71-BI-2107 TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5598 | PS5-71-XXS-0091-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XXS-0091-CJ01 | I | Cable FROM PS5-71-BI-2114 TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5599 | PS5-71-XXS-0092-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XXS-0092-CJ01 | I | Cable FROM PS5-71-BI-2114 TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5600 | PS5-71-XY-0089-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XY-0089-CJ01 | I | Cable FROM PS5-71-BI-2101 TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5601 | PS5-71-XY-0090-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XY-0090-CJ01 | I | Cable FROM PS5-71-BI-2101 TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-64-04-0052 | 2026-05-21 | Accepted with Punch | Elizabeth | PULLING
T-00069-5602 | PS5-71-XY-0091-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XY-0091-CJ01 | I | Cable FROM PS5-71-BI-2115 TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5603 | PS5-71-XY-0092-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-71-XY-0092-CJ01 | I | Cable FROM PS5-71-BI-2115 TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-04-0072 | 2026-06-23 | OPEN | Elizabeth | PULLING
T-00069-5606 | PS5-74-PIT-0002-CJ01 | CJX10 - Multi/Single-core instrument control cable | PS5-74-PIT-0002-CJ01 | I | Cable FROM PS5-50-BI-1107 TO PS5-74-PIT-0002 |  | PS5-74-04 - Nitrogen Distribution Header | CPP-RFI-68-64-04-0060 | 2026-06-06 | Accepted with Punch | Elizabeth | PULLING
T-00069-9408 | PS5-03-RMAC-1409-CJ01 | CJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0003 TO PS5-03-RMAC-1409 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00070-0051 | PS5-71-FO-0013B | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00070-0052 | PS5-28-FO-0009A | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00070-0053 | PS5-28-FO-0009B | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00070-0054 | PS5-28-FO-0003 | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-05 - HP Relief Header
T-00070-0055 | PS5-50-FE-0001 | CJX11 - Orifice plate | #N/A | I | Orifice Flow Element |  | PS5-50-03 - Water Pre-Treatment Package
T-00070-0056 | PS5-60-FO-0002 | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-60-24 - Cooling Water Tank & Pump
T-00070-0057 | PS5-28-FO-0005 | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-06 - Relief Drum and Pump
T-00070-0058 | PS5-60-FO-0001 | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump
T-00070-0059 | PS5-25-FO-0008 | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00070-0060 | PS5-71-FO-0013A | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00070-0061 | PS5-74-FO-0001 | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-74-04 - Nitrogen Distribution Header
T-00070-0062 | PS5-28-FO-0002A | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-08 - Open Drain Sump and Pumps
T-00070-0063 | PS5-28-FO-0002B | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-08 - Open Drain Sump and Pumps
T-00070-0064 | PS5-28-FO-0004 | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-16 - LP Relief Header
T-00070-0065 | PS5-28-FO-0006 | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-08 - Open Drain Sump and Pumps
T-00070-0066 | PS5-28-FO-0007 | CJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00071-0023 | PS5-09-LB-0006-CX01 | CJX12 - Optical fiber cable | #N/A | I | Cable FROM PS5-04-PNC-0001 TO PS5-09-LB-0006 |  | PS5-09-01 - HVAC for Office and Facilities building
T-00071-0024 | PS5-09-LB-0007-CX01 | CJX12 - Optical fiber cable | PS5-09-LB-0007-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-09-LB-0007 |  | PS5-09-04 - HVAC for Workshop & Warehouse | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00071-0025 | PS5-09-LB-0008-CX01 | CJX12 - Optical fiber cable | PS5-09-LB-0008-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00071-0026 | PS5-53-LA-0001-CX01 | CJX12 - Optical fiber cable | PS5-53-LA-0001-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-53-LA-0001 |  | PS5-53-04 - Water Treatment Purification Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00071-0027 | PS5-60-IE-0004-CX03 | CJX12 - Optical fiber cable | PS5-60-IE-0004-CX03 | I | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00071-0028 | PS5-60-IE-0004-CX04 | CJX12 - Optical fiber cable | PS5-60-IE-0004-CX04 | I | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00071-0029 | PS5-60-LA-0003-CX01 | CJX12 - Optical fiber cable | PS5-60-LA-0003-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 |  | PS5-60-22 - Power Gen Master UCP | CPP-68-64-04-0078 | 2026-07-04 | OPEN | Elizabeth | PULLING
T-00071-0030 | PS5-74-LB-5101-CX01 | CJX12 - Optical fiber cable | PS5-74-LB-5101-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-74-LB-5101 |  | PS5-74-02 - N2 Generation Skid (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00071-0031 | PS5-82-LA-0001-CX01 | CJX12 - Optical fiber cable | PS5-82-LA-0001-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-82-LA-0001 |  | PS5-82-03 - Sewage Treatment Plant Package (UCP) | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00071-0085 | PS5-75-LA-6200-CX01 | CJX12 - Optical fiber cable | PS5-75-LA-6200-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-75-LA-6200 |  | PS5-75-01 - DRA Injection Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00072-0165 | PS5-60-TW-0006G | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-76 - Engine G Cooling system
T-00072-0166 | PS5-71-TW-4203 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-12 - CFO Service Tank
T-00072-0167 | PS5-71-TW-0007 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00072-0168 | PS5-71-TW-0003 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00072-0169 | PS5-60-TW-0007C | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-72 - Engine C Cooling system
T-00072-0170 | PS5-71-TW-0004 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00072-0171 | PS5-60-TW-0005F | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-75 - Engine F Cooling system
T-00072-0172 | PS5-28-TW-1201 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-28-06 - Relief Drum and Pump
T-00072-0173 | PS5-60-TW-0007B | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-71 - Engine B Cooling system
T-00072-0174 | PS5-60-TW-0006C | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-72 - Engine C Cooling system
T-00072-0175 | PS5-60-TW-0008A | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-70 - Engine A Cooling system
T-00072-0176 | PS5-60-TW-0007D | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-73 - Engine D Cooling system
T-00072-0177 | PS5-60-TW-0008C | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-72 - Engine C Cooling system
T-00072-0178 | PS5-28-TW-1402 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00072-0179 | PS5-60-TW-0005G | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-76 - Engine G Cooling system
T-00072-0180 | PS5-28-TW-1104 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00072-0181 | PS5-60-TW-0008E | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-74 - Engine E Cooling system
T-00072-0182 | PS5-60-TW-0007A | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-70 - Engine A Cooling system
T-00072-0183 | PS5-60-TW-0006D | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-73 - Engine D Cooling system
T-00072-0184 | PS5-60-TW-0008B | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-71 - Engine B Cooling system
T-00072-0185 | PS5-60-TW-0007E | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-74 - Engine E Cooling system
T-00072-0186 | PS5-60-TW-0008D | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-73 - Engine D Cooling system
T-00072-0187 | PS5-25-TW-0003B | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-03 - Crude Oil Export Pump B
T-00072-0188 | PS5-71-TW-4202 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-12 - CFO Service Tank
T-00072-0189 | PS5-60-TW-0008F | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-75 - Engine F Cooling system
T-00072-0190 | PS5-60-TW-0006E | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-74 - Engine E Cooling system
T-00072-0191 | PS5-25-TW-0002A | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-02 - Crude Oil Export Pump A
T-00072-0192 | PS5-25-TW-0003C | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-04 - Crude Oil Export Pump C
T-00072-0193 | PS5-71-TW-0006 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00072-0194 | PS5-60-TW-0006B | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-71 - Engine B Cooling system
T-00072-0195 | PS5-25-TW-0003A | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-02 - Crude Oil Export Pump A
T-00072-0196 | PS5-71-TW-4103 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-04 - CFO Storage Tank
T-00072-0197 | PS5-28-TW-1105 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00072-0198 | PS5-60-TW-0006A | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-70 - Engine A Cooling system
T-00072-0199 | PS5-60-TW-0007F | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-75 - Engine F Cooling system
T-00072-0200 | PS5-25-TW-0002B | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-03 - Crude Oil Export Pump B
T-00072-0201 | PS5-25-TW-0001 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00072-0202 | PS5-25-TW-0004 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00072-0203 | PS5-25-TW-0002C | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-04 - Crude Oil Export Pump C
T-00072-0204 | PS5-71-TW-4102 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-04 - CFO Storage Tank
T-00072-0205 | PS5-74-TW-0001 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-74-04 - Nitrogen Distribution Header
T-00072-0206 | PS5-28-TW-1401 | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00072-0207 | PS5-60-TW-0005A | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-70 - Engine A Cooling system
T-00072-0208 | PS5-60-TW-0005B | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-71 - Engine B Cooling system
T-00072-0209 | PS5-60-TW-0005C | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-72 - Engine C Cooling system
T-00072-0210 | PS5-60-TW-0005D | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-73 - Engine D Cooling system
T-00072-0211 | PS5-60-TW-0005E | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-74 - Engine E Cooling system
T-00072-0212 | PS5-60-TW-0006F | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-75 - Engine F Cooling system
T-00072-0213 | PS5-60-TW-0007G | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-76 - Engine G Cooling system
T-00072-0214 | PS5-60-TW-0008G | CJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-76 - Engine G Cooling system
T-00075-0197 | PS5-25-PG-1101B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00075-0198 | PS5-28-PG-0001 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-08 - Open Drain Sump and Pumps
T-00075-0199 | PS5-28-PG-0071 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00075-0200 | PS5-60-TG-0005C | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-72 - Engine C Cooling system
T-00075-0201 | PS5-71-PG-0044 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-04 - CFO Storage Tank
T-00075-0202 | PS5-60-TG-0006F | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-75 - Engine F Cooling system
T-00075-0203 | PS5-28-PG-0067B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-17 - Reinjection Pump
T-00075-0204 | PS5-60-TG-0005E | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-74 - Engine E Cooling system
T-00075-0205 | PS5-60-TG-0008D | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-73 - Engine D Cooling system
T-00075-0206 | PS5-71-PG-0053B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-05 - CFO Transfer Pump A/B
T-00075-0207 | PS5-71-PG-0053A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-05 - CFO Transfer Pump A/B
T-00075-0208 | PS5-28-PG-0070C | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00075-0209 | PS5-71-PG-0050B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00075-0210 | PS5-71-PG-0050A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00075-0211 | PS5-60-TG-0005A | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-70 - Engine A Cooling system
T-00075-0212 | PS5-28-PG-0007A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-08 - Open Drain Sump and Pumps
T-00075-0213 | PS5-25-PG-1201A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00075-0214 | PS5-60-PG-0002F | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-60-33 - Air Receiver F & Air Regulator F
T-00075-0215 | PS5-60-TG-0007G | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-76 - Engine G Cooling system
T-00075-0216 | PS5-60-TG-0005F | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-75 - Engine F Cooling system
T-00075-0217 | PS5-60-TG-0006G | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-76 - Engine G Cooling system
T-00075-0218 | PS5-60-TG-0008A | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-70 - Engine A Cooling system
T-00075-0219 | PS5-25-PG-1101A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00075-0220 | PS5-60-PG-0027 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-60-24 - Cooling Water Tank & Pump
T-00075-0221 | PS5-60-PG-0002A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-60-28 - Air Receiver A & Air Regulator A
T-00075-0222 | PS5-28-PG-1401 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00075-0223 | PS5-53-PG-0022B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-53-02 - Water Distribution Pump A/B
T-00075-0224 | PS5-60-TG-0008C | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-72 - Engine C Cooling system
T-00075-0225 | PS5-60-PG-0002C | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-60-30 - Air Receiver C & Air Regulator C
T-00075-0226 | PS5-60-PG-0002E | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-60-32 - Air Receiver E & Air Regulator E
T-00075-0227 | PS5-71-PDG-0043A | CJX16 - Local gauge / indicator | #N/A | I | Diff Press Gauge |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00075-0228 | PS5-28-PG-0014A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00075-0229 | PS5-60-TG-0007D | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-73 - Engine D Cooling system
T-00075-0230 | PS5-74-TG-0001 | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-74-04 - Nitrogen Distribution Header
T-00075-0231 | PS5-53-PG-0022A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-53-02 - Water Distribution Pump A/B
T-00075-0232 | PS5-60-PG-0002B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-60-29 - Air Receiver B & Air Regulator B
T-00075-0233 | PS5-60-LG-0001 | CJX16 - Local gauge / indicator | #N/A | I | Magnetic Level Gauge |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump
T-00075-0234 | PS5-60-TG-0008E | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-74 - Engine E Cooling system
T-00075-0235 | PS5-71-PDG-0043B | CJX16 - Local gauge / indicator | #N/A | I | Diff Press Gauge |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00075-0236 | PS5-28-PG-1201 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-06 - Relief Drum and Pump
T-00075-0237 | PS5-60-PG-0002D | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-60-31 - Air Receiver D & Air Regulator D
T-00075-0238 | PS5-74-PG-0001 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-74-03 - Nitrogen Receiver
T-00075-0239 | PS5-60-TG-0007A | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-70 - Engine A Cooling system
T-00075-0240 | PS5-71-PG-0005 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station
T-00075-0241 | PS5-71-PDG-0049A | CJX16 - Local gauge / indicator | #N/A | I | Diff Press Gauge |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00075-0242 | PS5-60-TG-0008F | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-75 - Engine F Cooling system
T-00075-0243 | PS5-25-PG-1201B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00075-0244 | PS5-60-TG-0007C | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-72 - Engine C Cooling system
T-00075-0245 | PS5-28-PG-0007B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-08 - Open Drain Sump and Pumps
T-00075-0246 | PS5-71-PG-0059B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-13 - CFO Service Pump A/B
T-00075-0247 | PS5-71-PG-0059A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-13 - CFO Service Pump A/B
T-00075-0248 | PS5-28-PG-0014B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00075-0249 | PS5-71-PG-0006A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00075-0250 | PS5-60-TG-0005G | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-76 - Engine G Cooling system
T-00075-0251 | PS5-60-TG-0006D | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-73 - Engine D Cooling system
T-00075-0252 | PS5-60-TG-0007E | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-74 - Engine E Cooling system
T-00075-0253 | PS5-71-PG-0045 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-12 - CFO Service Tank
T-00075-0254 | PS5-71-PG-0007 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station
T-00075-0255 | PS5-71-PDG-0049B | CJX16 - Local gauge / indicator | #N/A | I | Diff Press Gauge |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00075-0256 | PS5-71-PG-0006B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00075-0257 | PS5-25-PG-0010 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00075-0258 | PS5-25-PG-0019 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00075-0259 | PS5-28-PG-0067A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-17 - Reinjection Pump
T-00075-0260 | PS5-28-PG-0070A | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00075-0261 | PS5-28-PG-0070B | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00075-0262 | PS5-28-PG-1101 | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00075-0263 | PS5-60-PG-0002G | CJX16 - Local gauge / indicator | #N/A | I | Pressure Gauge |  | PS5-60-34 - Air Receiver G & Air Regulator G
T-00075-0264 | PS5-60-TG-0005D | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-73 - Engine D Cooling system
T-00075-0265 | PS5-60-TG-0006A | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-70 - Engine A Cooling system
T-00075-0266 | PS5-60-TG-0006C | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-72 - Engine C Cooling system
T-00075-0267 | PS5-60-TG-0006E | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-74 - Engine E Cooling system
T-00075-0268 | PS5-60-TG-0007F | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-75 - Engine F Cooling system
T-00075-0269 | PS5-60-TG-0008G | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-76 - Engine G Cooling system
T-00075-0270 | PS5-60-TG-0006B | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-71 - Engine B Cooling system
T-00075-0271 | PS5-60-TG-0005B | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-71 - Engine B Cooling system
T-00075-0272 | PS5-60-TG-0007B | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-71 - Engine B Cooling system
T-00075-0273 | PS5-60-TG-0008B | CJX16 - Local gauge / indicator | #N/A | I | Temperature Gauge |  | PS5-60-71 - Engine B Cooling system
T-00075-0376 | PS5-09-PI-8401 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0377 | PS5-09-PI-8402 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0378 | PS5-09-PI-8403 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0379 | PS5-09-PI-8404 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0380 | PS5-09-PI-8405 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0381 | PS5-09-PI-8406 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0382 | PS5-09-PI-8407 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0383 | PS5-09-PI-8408 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0384 | PS5-09-PI-8409 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0385 | PS5-09-PI-8411 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0386 | PS5-09-PI-8412 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0387 | PS5-09-PI-8413 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0388 | PS5-09-PI-8414 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0389 | PS5-09-PI-8415 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0390 | PS5-09-PI-8416 | CJX16 - Local gauge / indicator | #N/A | I | PRESSURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0391 | PS5-09-TI-8401 | CJX16 - Local gauge / indicator | #N/A | I | TEMPERATURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0392 | PS5-09-TI-8402 | CJX16 - Local gauge / indicator | #N/A | I | TEMPERATURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0393 | PS5-09-TI-8403 | CJX16 - Local gauge / indicator | #N/A | I | TEMPERATURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0394 | PS5-09-TI-8404 | CJX16 - Local gauge / indicator | #N/A | I | TEMPERATURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0395 | PS5-09-TI-8405 | CJX16 - Local gauge / indicator | #N/A | I | TEMPERATURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0396 | PS5-09-TI-8406 | CJX16 - Local gauge / indicator | #N/A | I | TEMPERATURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0397 | PS5-09-TI-8407 | CJX16 - Local gauge / indicator | #N/A | I | TEMPERATURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0398 | PS5-09-TI-8408 | CJX16 - Local gauge / indicator | #N/A | I | TEMPERATURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0399 | PS5-09-TI-8409 | CJX16 - Local gauge / indicator | #N/A | I | TEMPERATURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00075-0400 | PS5-09-TI-8411 | CJX16 - Local gauge / indicator | #N/A | I | TEMPERATURE INDICATOR |  | PS5-09-03 - HVAC for Generator Building
T-00076-0013 | PS5-71-PSE-2401A | CJX20 - Bursting disc | #N/A | I | Bursting Disc |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00076-0014 | PS5-71-PSE-2401B | CJX20 - Bursting disc | #N/A | I | Bursting Disc |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00077-0236 | PS5-25-ESDV-0021 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Emergency Shut Down Valve |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00077-0237 | PS5-25-ESDV-0023 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Emergency Shut Down Valve |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00077-0238 | PS5-71-XV-0091 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | On / Off Valve |  | PS5-71-18 - Diesel Separator Module
T-00077-0239 | PS5-71-XV-0090 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | On / Off Valve |  | PS5-71-12 - CFO Service Tank
T-00077-0240 | PS5-25-SDV-0052 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00077-0241 | PS5-25-SDV-0054A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-02 - Crude Oil Export Pump A
T-00077-0242 | PS5-28-SDV-0053B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00077-0243 | PS5-71-SDV-0039 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-71-12 - CFO Service Tank
T-00077-0244 | PS5-71-SDV-0029 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00077-0245 | PS5-25-SDV-0036A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-02 - Crude Oil Export Pump A
T-00077-0246 | PS5-25-SDV-0036C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-04 - Crude Oil Export Pump C
T-00077-0247 | PS5-25-SDV-0035B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-03 - Crude Oil Export Pump B
T-00077-0248 | PS5-71-SDV-0022 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-71-04 - CFO Storage Tank
T-00077-0249 | PS5-25-SDV-0054C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-04 - Crude Oil Export Pump C
T-00077-0250 | PS5-28-SDV-0053C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00077-0251 | PS5-71-XV-0089 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | On / Off Valve |  | PS5-71-04 - CFO Storage Tank
T-00077-0252 | PS5-28-SDV-0045 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-28-17 - Reinjection Pump
T-00077-0253 | PS5-25-XV-0053 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | On / Off Valve |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00077-0254 | PS5-71-XV-0092 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | On / Off Valve |  | PS5-71-20 - Diesel Fuel Day Tank
T-00077-0255 | PS5-28-SDV-0053A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00077-0256 | PS5-71-SDV-0001 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-71-20 - Diesel Fuel Day Tank
T-00077-0257 | PS5-25-SDV-0022 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00077-0258 | PS5-25-SDV-0035A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-02 - Crude Oil Export Pump A
T-00077-0259 | PS5-25-SDV-0035C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-04 - Crude Oil Export Pump C
T-00077-0260 | PS5-25-SDV-0036B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-03 - Crude Oil Export Pump B
T-00077-0261 | PS5-25-SDV-0046 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00077-0262 | PS5-25-SDV-0054B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | Shutdown Valve |  | PS5-25-03 - Crude Oil Export Pump B
T-00077-0263 | PS5-25-XV-0070 | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | #N/A | I | On / Off Valve |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00078-0131 | PS5-25-MOV-0001 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00078-0132 | PS5-25-MOV-0008 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00078-0133 | PS5-25-MOV-0025 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00078-0134 | PS5-25-MOV-0028 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00078-0137 | PS5-25-MOV-0026 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00078-0138 | PS5-25-MOV-0027 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00078-0139 | PS5-60-MOV-0012 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-12 - CFO Service Tank
T-00078-0140 | PS5-71-MOV-0007 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00078-0141 | PS5-25-MOV-0003 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00078-0142 | PS5-75-MOV-0001 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-28-07 - Open Drains (OD2)
T-00078-0143 | PS5-71-MOV-0010 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00078-0144 | PS5-71-MOV-0003 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00078-0145 | PS5-25-MOV-0011 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00078-0146 | PS5-60-MOV-0005 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-12 - CFO Service Tank
T-00078-0147 | PS5-71-MOV-0004 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00078-0148 | PS5-25-MOV-0012 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00078-0149 | PS5-71-MOV-0001 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00078-0150 | PS5-60-MOV-0006 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-12 - CFO Service Tank
T-00078-0151 | PS5-71-MOV-0002 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00078-0152 | PS5-71-MOV-0008 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00078-0153 | PS5-71-MOV-0009 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00078-0154 | PS5-25-MOV-0002 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00078-0155 | PS5-60-MOV-0011 | CJX24 - Actuated on/off valve - Electrical type | #N/A | I | Motor Operated Valve |  | PS5-71-12 - CFO Service Tank
T-00079-0062 | PS5-01-FCV-0004B | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Flow Control Valve |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00079-0063 | PS5-25-FCV-0004 | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Flow Control Valve |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00079-0064 | PS5-01-FCV-0003A | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Flow Control Valve |  | PS5-01-02 - Fire Water Pump A
T-00079-0065 | PS5-01-FCV-0003B | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Flow Control Valve |  | PS5-01-03 - Fire Water Pump B
T-00079-0066 | PS5-71-FCV-0018 | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Flow Control Valve |  | PS5-71-13 - CFO Service Pump A/B
T-00079-0067 | PS5-25-FCV-0003B | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Flow Control Valve |  | PS5-25-03 - Crude Oil Export Pump B
T-00079-0068 | PS5-71-LCV-4101 | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Level Control Valve |  | PS5-71-04 - CFO Storage Tank
T-00079-0069 | PS5-71-FCV-0019 | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Flow Control Valve |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00079-0070 | PS5-71-FCV-0020 | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Flow Control Valve |  | PS5-71-05 - CFO Transfer Pump A/B
T-00079-0071 | PS5-01-FCV-0004A | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Flow Control Valve |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00079-0072 | PS5-25-FCV-0003A | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Flow Control Valve |  | PS5-25-02 - Crude Oil Export Pump A
T-00079-0073 | PS5-25-FCV-0003C | CJX27 - Control valve - Pneumatic / Hydraulic type | #N/A | I | Flow Control Valve |  | PS5-25-04 - Crude Oil Export Pump C
T-00080-0003 | PS5-09-TCV-8401 | CJX28 - Control valve - Electrical type | #N/A | I | CONTROL VALVE |  | PS5-09-03 - HVAC for Generator Building
T-00080-0004 | PS5-09-TCV-8402 | CJX28 - Control valve - Electrical type | #N/A | I | CONTROL VALVE |  | PS5-09-03 - HVAC for Generator Building
T-00082-0454 | PS5-01-BI-0001 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-05 - Foam Skid | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0455 | PS5-01-BI-0002 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0456 | PS5-01-BI-0003 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0457 | PS5-01-BI-0004 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0458 | PS5-01-BI-0005 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-05 - Foam Skid | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted | Elizabeth | Installation
T-00082-0459 | PS5-01-BI-0006 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-05 - Foam Skid | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0460 | PS5-01-BI-1117 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0461 | PS5-01-BI-1118 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0462 | PS5-01-BI-1501 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0463 | PS5-01-BI-1515 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0464 | PS5-01-BI-1520 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-05-0053 | 2026-05-30 | Accepted with Punch | Elizabeth | Installation
T-00082-0465 | PS5-01-BI-1571 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0466 | PS5-01-BI-2110 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0467 | PS5-01-BI-2520 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-05-0053 | 2026-05-30 | Accepted with Punch | Elizabeth | Installation
T-00082-0468 | PS5-01-BI-2571A | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0469 | PS5-01-BI-2571B | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0470 | PS5-03-BI-1502 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0471 | PS5-03-BI-1503 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0472 | PS5-03-BI-1506 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-05-0051 | 2026-05-21 | Accepted with Punch | Elizabeth | Installation
T-00082-0473 | PS5-03-BI-1507 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0474 | PS5-03-BI-1508 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0475 | PS5-03-BI-1509 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-05-0053 | 2026-05-30 | Accepted with Punch | Elizabeth | Installation
T-00082-0476 | PS5-03-BI-1510 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0477 | PS5-03-BI-1511 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-07 - FZ-07 - Pretreatment Area | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0478 | PS5-03-BI-1512 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-RFI-68-64-05-0065 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0479 | PS5-03-BI-1513 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-RFI-68-64-05-0065 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0480 | PS5-03-BI-1514 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CPP-RFI-68-64-05-0065 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0481 | PS5-03-BI-1516 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CPP-RFI-68-64-05-0065 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0482 | PS5-03-BI-2501 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-05-0064 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0483 | PS5-03-BI-2502 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-05-0064 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0484 | PS5-03-BI-2503 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0064 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0485 | PS5-03-BI-2504 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0486 | PS5-03-BI-2505 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0487 | PS5-03-BI-2506 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0065 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0488 | PS5-03-BI-2507 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-RFI-68-64-05-0065 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0489 | PS5-03-BI-2508 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CPP-RFI-68-64-05-0065 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0490 | PS5-03-BI-2509 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0491 | PS5-03-BI-2510 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-03 - FZ-03 - Buildings Area | CPP-RFI-68-64-05-0065 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0492 | PS5-03-BI-2511 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0493 | PS5-03-BI-2512 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0494 | PS5-03-BI-2514 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0065 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0495 | PS5-03-BI-2515 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0496 | PS5-05-BI-0002 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0497 | PS5-09-BI-2501 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-09-04 - HVAC for Workshop & Warehouse
T-00082-0498 | PS5-09-BI-2502 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-09-01 - HVAC for Office and Facilities building
T-00082-0499 | PS5-09-BI-2503 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-09-03 - HVAC for Generator Building
T-00082-0500 | PS5-25-BI-1101 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0501 | PS5-25-BI-1102 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0502 | PS5-25-BI-1103 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0503 | PS5-25-BI-1104 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0504 | PS5-25-BI-1115 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0505 | PS5-25-BI-1174A | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0506 | PS5-25-BI-1174B | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0507 | PS5-25-BI-1174C | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0508 | PS5-25-BI-1201 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0509 | PS5-25-BI-1274A | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0510 | PS5-25-BI-1274B | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0511 | PS5-25-BI-1274C | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0512 | PS5-25-BI-1301 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0513 | PS5-25-BI-1302 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0514 | PS5-25-BI-1310 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0515 | PS5-25-BI-2101 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0516 | PS5-25-BI-2102 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0517 | PS5-25-BI-2103 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0518 | PS5-25-BI-2104 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0519 | PS5-25-BI-2105 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0520 | PS5-25-BI-2106 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0053 | 2026-05-30 | Accepted with Punch | Elizabeth | Installation
T-00082-0521 | PS5-25-BI-2108 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0522 | PS5-25-BI-2109 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0523 | PS5-25-BI-2201 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0051 | 2026-05-21 | Accepted with Punch | Elizabeth | Installation
T-00082-0524 | PS5-25-BI-2203 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0051 | 2026-05-21 | Accepted with Punch | Elizabeth | Installation
T-00082-0525 | PS5-25-BI-2205 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-05-0051 | 2026-05-21 | Accepted with Punch | Elizabeth | Installation
T-00082-0526 | PS5-25-BI-2301 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0527 | PS5-25-BI-2302 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0528 | PS5-25-BI-2305 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0529 | PS5-25-BI-2308 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0053 | 2026-05-30 | Accepted with Punch | Elizabeth | Installation
T-00082-0530 | PS5-25-BI-2309 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0531 | PS5-25-BI-2312 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0532 | PS5-25-BI-2315 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0533 | PS5-25-BI-2316 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0534 | PS5-28-BI-1105 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0064 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0535 | PS5-28-BI-1106 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-28-06 - Relief Drum and Pump | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0536 | PS5-28-BI-1114 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0537 | PS5-28-BI-1303 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0538 | PS5-28-BI-1307 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0539 | PS5-28-BI-2304 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0540 | PS5-50-BI-1107 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0541 | PS5-53-BI-1108 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0542 | PS5-53-BI-1304 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-53-01 - Utility Water / Storage Tank | CPP-RFI-68-64-05-0064 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0543 | PS5-71-BI-1109 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0051 | 2026-05-21 | Accepted with Punch | Elizabeth | Installation
T-00082-0544 | PS5-71-BI-1110 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0545 | PS5-71-BI-1111 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0546 | PS5-71-BI-1112 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-71-17 - Diesel Fuel Distribution Header | CPP-RFI-68-64-05-0076 | 2026-06-26 | Accepted with Punch | Elizabeth | Installation
T-00082-0547 | PS5-71-BI-1113 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0548 | PS5-71-BI-1116 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0051 | 2026-05-21 | Accepted with Punch | Elizabeth | Installation
T-00082-0549 | PS5-71-BI-1117 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0550 | PS5-71-BI-1305 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0051 | 2026-05-21 | Accepted with Punch | Elizabeth | Installation
T-00082-0551 | PS5-71-BI-1306 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0051 | 2026-05-21 | Accepted with Punch | Elizabeth | Installation
T-00082-0552 | PS5-71-BI-1308 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0553 | PS5-71-BI-2101 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0554 | PS5-71-BI-2107 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0555 | PS5-71-BI-2113 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0556 | PS5-71-BI-2114 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0557 | PS5-71-BI-2115 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0558 | PS5-71-BI-2116 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0559 | PS5-71-BI-2118 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0053 | 2026-05-30 | Accepted with Punch | Elizabeth | Installation
T-00082-0560 | PS5-71-BI-2119 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0561 | PS5-71-BI-2120 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0562 | PS5-71-BI-2121 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0065 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0563 | PS5-71-BI-2122 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0053 | 2026-05-30 | Accepted with Punch | Elizabeth | Installation
T-00082-0564 | PS5-71-BI-2123 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0565 | PS5-71-BI-2124 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0566 | PS5-71-BI-2125 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0065 | 2026-06-18 | Accepted with Punch | Elizabeth | Installation
T-00082-0567 | PS5-71-BI-2306 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0051 | 2026-05-21 | Accepted with Punch | Elizabeth | Installation
T-00082-0568 | PS5-71-BI-2307 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0569 | PS5-71-BI-2310 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0062 | 2026-06-10 | Accepted | Elizabeth | Installation
T-00082-0570 | PS5-71-BI-2313 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-0571 | PS5-71-BI-2314 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-05-0058 | 2026-06-03 | Accepted | Elizabeth | Installation
T-00082-0572 | PS5-71-BI-2317 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-05-0057 | 2026-05-30 | Accepted | Elizabeth | Installation
T-00082-1230 | PS5-01-BI-0007 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-11 - Inergen for Power Gen Building
T-00082-1231 | PS5-01-BI-0008 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-11 - Inergen for Power Gen Building
T-00082-1232 | PS5-01-BI-0009 | CJX31 - Junction & marshalling box | #N/A | I | Junction Box |  | PS5-01-11 - Inergen for Power Gen Building
T-00082-1233 | PS5-01-NMR-61001 | CJX31 - Junction & marshalling box | #N/A | I | DISCHARGE PUSH BUTTON |  | PS5-01-11 - Inergen for Power Gen Building
T-00082-1234 | PS5-01-NMR-61002 | CJX31 - Junction & marshalling box | #N/A | I | DISCHARGE PUSH BUTTON |  | PS5-01-11 - Inergen for Power Gen Building
T-00082-1235 | PS5-01-NMR-61003 | CJX31 - Junction & marshalling box | #N/A | I | DISCHARGE PUSH BUTTON |  | PS5-01-11 - Inergen for Power Gen Building
T-00082-1236 | PS5-01-NMR-61004 | CJX31 - Junction & marshalling box | #N/A | I | DISCHARGE PUSH BUTTON |  | PS5-01-11 - Inergen for Power Gen Building
T-00082-1237 | PS5-01-NMRA-61001 | CJX31 - Junction & marshalling box | #N/A | I | ABORT DISCHARGE PUSH BUTTON |  | PS5-01-11 - Inergen for Power Gen Building
T-00082-1238 | PS5-01-NMRA-61002 | CJX31 - Junction & marshalling box | #N/A | I | ABORT DISCHARGE PUSH BUTTON |  | PS5-01-11 - Inergen for Power Gen Building
T-00082-1239 | PS5-01-NMRA-61003 | CJX31 - Junction & marshalling box | #N/A | I | ABORT DISCHARGE PUSH BUTTON |  | PS5-01-11 - Inergen for Power Gen Building
T-00082-1240 | PS5-01-NMRA-61004 | CJX31 - Junction & marshalling box | #N/A | I | ABORT DISCHARGE PUSH BUTTON |  | PS5-01-11 - Inergen for Power Gen Building
T-00083-0184 | PS5-03-GDLHP-0137 | CJX42 - Gas / smoke detector | #N/A | I | POINT TYPE LIQUID HYDROCARBON DETECTOR |  | PS5-03-01 - FZ-01 - Process Area
T-00083-0185 | PS5-03-GDLHP-0142 | CJX42 - Gas / smoke detector | #N/A | I | POINT TYPE LIQUID HYDROCARBON DETECTOR |  | PS5-03-01 - FZ-01 - Process Area
T-00083-0186 | PS5-03-GDLHP-0143 | CJX42 - Gas / smoke detector | #N/A | I | TRACE TAPE TYPE LIQUID HYDROCARBON LEAK DETECTOR |  | PS5-03-01 - FZ-01 - Process Area
T-00083-0187 | PS5-03-GDLHP-0144 | CJX42 - Gas / smoke detector | #N/A | I | TRACE TAPE TYPE LIQUID HYDROCARBON LEAK DETECTOR |  | PS5-03-01 - FZ-01 - Process Area
T-00083-0189 | PS5-03-GDLHP-0401 | CJX42 - Gas / smoke detector | #N/A | I | POINT TYPE LIQUID HYDROCARBON DETECTOR |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas
T-00083-0191 | PS5-03-RDH-0302 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-03 - FZ-03 - Buildings Area
T-00083-0192 | PS5-03-RDH-0303 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-03 - FZ-03 - Buildings Area
T-00083-0193 | PS5-03-RDH-0601 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0194 | PS5-03-RDH-0602 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0195 | PS5-03-RDH-0603 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0196 | PS5-03-RDH-0604 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0197 | PS5-03-RDH-0605 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0198 | PS5-03-RDH-0606 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0199 | PS5-03-RDH-0607 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0200 | PS5-03-RDH-0608 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0201 | PS5-03-RDH-0609 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0202 | PS5-03-RDH-0610 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0203 | PS5-03-RDH-0611 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0204 | PS5-03-RDH-0612 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0205 | PS5-03-RDH-0614 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0206 | PS5-03-RDH-0615 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0207 | PS5-03-RDH-0616 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0208 | PS5-03-RDH-0617 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0209 | PS5-03-RDH-0618 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0210 | PS5-03-RDH-0828 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00083-0211 | PS5-03-RDH-0829 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00083-0212 | PS5-03-RDH-0830 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00083-0213 | PS5-03-RDH-0831 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00083-0214 | PS5-03-RDH-0901 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0215 | PS5-03-RDH-0902 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0216 | PS5-03-RDH-0903 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0217 | PS5-03-RDH-0904 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0218 | PS5-03-RDH-0905 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0219 | PS5-03-RDH-0906 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0220 | PS5-03-RDH-0909 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0221 | PS5-03-RDH-0910 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0222 | PS5-03-RDH-0911 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0223 | PS5-03-RDH-0912 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0224 | PS5-03-RDH-1001 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0225 | PS5-03-RDH-1002 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0226 | PS5-03-RDH-1003 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0227 | PS5-03-RDH-1004 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0228 | PS5-03-RDH-1005 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0229 | PS5-03-RDH-1006 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0230 | PS5-03-RDH-1009 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0231 | PS5-03-RDH-1010 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0232 | PS5-03-RDH-1011 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0233 | PS5-03-RDH-1012 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0234 | PS5-03-RDH-1101 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0235 | PS5-03-RDH-1102 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0236 | PS5-03-RDH-1103 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0237 | PS5-03-RDH-1104 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0238 | PS5-03-RDH-1105 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0239 | PS5-03-RDH-1106 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0240 | PS5-03-RDH-1109 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0241 | PS5-03-RDH-1110 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0242 | PS5-03-RDH-1111 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0243 | PS5-03-RDH-1112 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0820 | PS5-03-GDIR-0901 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET A |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0821 | PS5-03-GDIR-0902 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET A |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0822 | PS5-03-GDIR-0903 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET A |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0823 | PS5-03-GDIR-0904 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET A |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0824 | PS5-03-GDIR-0906 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET B |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0825 | PS5-03-GDIR-0907 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET B |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0826 | PS5-03-GDIR-0908 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET B |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0827 | PS5-03-GDIR-0909 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET B |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00083-0828 | PS5-03-GDIR-1001 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET C |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0829 | PS5-03-GDIR-1002 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET C |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0830 | PS5-03-GDIR-1003 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET C |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0831 | PS5-03-GDIR-1004 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET C |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0832 | PS5-03-GDIR-1006 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET D |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0833 | PS5-03-GDIR-1007 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET D |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0834 | PS5-03-GDIR-1008 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET D |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0835 | PS5-03-GDIR-1009 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET D |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00083-0836 | PS5-03-GDIR-1101 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET E |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0837 | PS5-03-GDIR-1102 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET E |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0838 | PS5-03-GDIR-1103 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET E |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0839 | PS5-03-GDIR-1104 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET E |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0840 | PS5-03-GDIR-1106 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET F |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0841 | PS5-03-GDIR-1107 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET F |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0842 | PS5-03-GDIR-1108 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET F |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0843 | PS5-03-GDIR-1109 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET F |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00083-0844 | PS5-03-GDIR-1201 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET G |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00083-0845 | PS5-03-GDIR-1202 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET G |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00083-0846 | PS5-03-GDIR-1203 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET G |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00083-0847 | PS5-03-GDIR-1204 | CJX42 - Gas / smoke detector | #N/A | I | GAS DETECTOR - GENRATOR SET G |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00083-0848 | PS5-03-GDLHP-0146 | CJX42 - Gas / smoke detector | #N/A | I | POINT TYPE LIQUID HYDROCARBON DETECTOR |  | PS5-03-01 - FZ-01 - Process Area
T-00083-0849 | PS5-03-GDLHP-0147 | CJX42 - Gas / smoke detector | #N/A | I | POINT TYPE LIQUID HYDROCARBON DETECTOR |  | PS5-03-01 - FZ-01 - Process Area
T-00083-0850 | PS5-03-GDLHP-0149 | CJX42 - Gas / smoke detector | #N/A | I | POINT TYPE LIQUID HYDROCARBON DETECTOR |  | PS5-03-01 - FZ-01 - Process Area
T-00083-0851 | PS5-03-GDLHP-0150 | CJX42 - Gas / smoke detector | #N/A | I | POINT TYPE LIQUID HYDROCARBON DETECTOR |  | PS5-03-01 - FZ-01 - Process Area
T-00083-0852 | PS5-03-RDH-0619 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0853 | PS5-03-RDH-0620 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-06 - FZ-06 - Transformer Area
T-00083-0854 | PS5-03-RDH-1201 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00083-0855 | PS5-03-RDH-1202 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00083-0856 | PS5-03-RDH-1203 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00083-0857 | PS5-03-RDH-1204 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00083-0858 | PS5-03-RDH-1205 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00083-0859 | PS5-03-RDH-1302 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00083-0860 | PS5-03-RDH-1303 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00083-0861 | PS5-03-RDH-1304 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00083-0862 | PS5-03-RDH-1901 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room
T-00083-0863 | PS5-03-RDH-1902 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room
T-00083-0864 | PS5-03-RDH-1903 | CJX42 - Gas / smoke detector | #N/A | I | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) |  | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room
T-00083-0865 | PS5-03-RDOS-1401 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00083-0866 | PS5-03-RDOS-1402 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00083-0867 | PS5-03-RDOS-1403 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00083-0868 | PS5-03-RDOS-1404 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00083-0869 | PS5-03-RDOS-1405 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00083-0870 | PS5-03-RDOS-1406 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00083-0871 | PS5-03-RDOS-1407 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00083-0872 | PS5-03-RDOS-1408 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00083-0873 | PS5-03-RDOS-1501 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1
T-00083-0874 | PS5-03-RDOS-1502 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1
T-00083-0875 | PS5-03-RDOS-1503 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1
T-00083-0876 | PS5-03-RDOS-1601 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2
T-00083-0877 | PS5-03-RDOS-1602 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2
T-00083-0878 | PS5-03-RDOS-1603 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2
T-00083-0879 | PS5-03-RDOS-1701 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3
T-00083-0880 | PS5-03-RDOS-1702 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3
T-00083-0881 | PS5-03-RDOS-1703 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3
T-00083-0882 | PS5-03-RDOS-1801 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4
T-00083-0883 | PS5-03-RDOS-1802 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4
T-00083-0884 | PS5-03-RDOS-1803 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4
T-00083-0885 | PS5-03-RDOS-2101 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit
T-00083-0886 | PS5-03-RDOS-2102 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit
T-00083-0887 | PS5-03-RDOS-2103 | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit
T-00083-0888 | PS5-03-RDOS-G101A | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-22 - FZ-G1 - Guard House
T-00083-0889 | PS5-03-RDOS-G101B | CJX42 - Gas / smoke detector | #N/A | I | SMOKE DETECTOR |  | PS5-03-22 - FZ-G1 - Guard House
T-00083-1560 | PS5-03-RDHR-W101A | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1561 | PS5-03-RDHR-W101B | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1562 | PS5-03-RDHR-W101C | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1563 | PS5-03-RDHR-W101D | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1564 | PS5-03-RDHR-W101E | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1565 | PS5-03-RDHR-W101F | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1566 | PS5-03-RDHR-W101G | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1567 | PS5-03-RDHR-W101H | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1568 | PS5-03-RDHR-W101I | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1569 | PS5-03-RDHR-W601A | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1570 | PS5-03-RDHR-W601B | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1571 | PS5-03-RDHR-W601C | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1572 | PS5-03-RDHR-W601D | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1573 | PS5-03-RDHR-W601E | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1574 | PS5-03-RDHR-W601F | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1575 | PS5-03-RDHR-W601G | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1576 | PS5-03-RDHR-W601H | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1577 | PS5-03-RDHR-W601I | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1578 | PS5-03-RDHR-W601J | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1579 | PS5-03-RDHR-W601K | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1580 | PS5-03-RDHR-W601L | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1581 | PS5-03-RDHR-W601M | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1582 | PS5-03-RDHR-W601N | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1583 | PS5-03-RDHR-W601O | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1584 | PS5-03-RDHR-W601P | CJX42 - Gas / smoke detector | #N/A | I | Heat Detector |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1585 | PS5-03-RDOS-B101A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1586 | PS5-03-RDOS-B101B | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1587 | PS5-03-RDOS-B101C | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1588 | PS5-03-RDOS-B101D | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1589 | PS5-03-RDOS-B201A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1590 | PS5-03-RDOS-B201B | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1591 | PS5-03-RDOS-B201C | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1592 | PS5-03-RDOS-B201D | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1593 | PS5-03-RDOS-B201E | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1594 | PS5-03-RDOS-B301A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1595 | PS5-03-RDOS-B301B | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1596 | PS5-03-RDOS-B301C | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1597 | PS5-03-RDOS-B301D | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1598 | PS5-03-RDOS-B401A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1599 | PS5-03-RDOS-B401B | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1600 | PS5-03-RDOS-B401C | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1601 | PS5-03-RDOS-B401D | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1602 | PS5-03-RDOS-B501A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1603 | PS5-03-RDOS-B601A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1604 | PS5-03-RDOS-B701A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1605 | PS5-03-RDOS-B701B | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1606 | PS5-03-RDOS-B701C | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1607 | PS5-03-RDOS-B701D | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1608 | PS5-03-RDOS-B701E | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1609 | PS5-03-RDOS-B701F | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1610 | PS5-03-RDOS-B701G | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1611 | PS5-03-RDOS-B701H | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1612 | PS5-03-RDOS-B701I | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1613 | PS5-03-RDOS-B801A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1614 | PS5-03-RDOS-B801B | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1615 | PS5-03-RDOS-B901A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1616 | PS5-03-RDOS-B901B | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1617 | PS5-03-RDOS-B901C | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1618 | PS5-03-RDOS-B901D | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1619 | PS5-03-RDOS-B901E | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-24 - FZ - Office and Facilities Building
T-00083-1620 | PS5-03-RDOS-W201A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1621 | PS5-03-RDOS-W201B | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1622 | PS5-03-RDOS-W201C | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1623 | PS5-03-RDOS-W201D | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1624 | PS5-03-RDOS-W301A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1625 | PS5-03-RDOS-W401A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1626 | PS5-03-RDOS-W501A | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1627 | PS5-03-RDOS-W501B | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1628 | PS5-03-RDOS-W501C | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1629 | PS5-03-RDOS-W501D | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1630 | PS5-03-RDOS-W501E | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00083-1631 | PS5-03-RDOS-W501F | CJX42 - Gas / smoke detector | #N/A | I | Smoke Detector - Optical |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00084-0277 | PS5-03-RDIR-0104 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0278 | PS5-03-RDIR-0105 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0279 | PS5-03-RDIR-0106 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0280 | PS5-03-RDIR-0107 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0281 | PS5-03-RDIR-0108 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0282 | PS5-03-RDIR-0109 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0283 | PS5-03-RDIR-0110 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0284 | PS5-03-RDIR-0111 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0285 | PS5-03-RDIR-0112 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0286 | PS5-03-RDIR-0113 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0287 | PS5-03-RDIR-0114 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0288 | PS5-03-RDIR-0115 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0289 | PS5-03-RDIR-0116 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0290 | PS5-03-RDIR-0117 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0291 | PS5-03-RDIR-0118 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0292 | PS5-03-RDIR-0121 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0293 | PS5-03-RDIR-0122 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0294 | PS5-03-RDIR-0123 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0295 | PS5-03-RDIR-0124 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0296 | PS5-03-RDIR-0125 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0297 | PS5-03-RDIR-0126 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0298 | PS5-03-RDIR-0127 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0299 | PS5-03-RDIR-0128 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0300 | PS5-03-RDIR-0129 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0301 | PS5-03-RDIR-0130 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0302 | PS5-03-RDIR-0131 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0303 | PS5-03-RDIR-0132 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0304 | PS5-03-RDIR-0133 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0305 | PS5-03-RDIR-0137 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0306 | PS5-03-RDIR-0138 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0309 | PS5-03-RDIR-0403 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas
T-00084-0310 | PS5-03-RDIR-0404 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas
T-00084-0311 | PS5-03-RDIR-0405 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas
T-00084-0312 | PS5-03-RDIR-0406 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas
T-00084-0313 | PS5-03-RDIR-0409 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas
T-00084-0315 | PS5-03-RDIR-0411 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas
T-00084-0320 | PS5-03-RDIR-0819 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00084-0321 | PS5-03-RDIR-0820 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00084-0322 | PS5-03-RDIR-0832 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00084-0323 | PS5-03-RDIR-0833 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00084-0324 | PS5-03-RDUIR-0701 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00084-0325 | PS5-03-RDUIR-0702 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00084-0326 | PS5-03-RDUIR-0703 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00084-0327 | PS5-03-RDUIR-0704 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00084-0328 | PS5-03-RDUIR-0705 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00084-0329 | PS5-03-RDUIR-0907 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00084-0330 | PS5-03-RDUIR-0908 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00084-0331 | PS5-03-RDUIR-1007 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00084-0332 | PS5-03-RDUIR-1008 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00084-0333 | PS5-03-RDUIR-1107 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00084-0334 | PS5-03-RDUIR-1108 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00084-0349 | PS5-03-RDIR-0141 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0350 | PS5-03-RDIR-0142 | CJX43 - Fire detector | #N/A | I | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) |  | PS5-03-01 - FZ-01 - Process Area
T-00084-0351 | PS5-03-RDUIR-1207 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00084-0352 | PS5-03-RDUIR-1208 | CJX43 - Fire detector | #N/A | I | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00087-0102 | PS5-03-SEA-0002 | CJX48 - Indoor cabinet / panel | #N/A | I | FIRE ALARM CONTROL PANEL |  | PS5-03-22 - FZ-G1 - Guard House
T-00087-0103 | PS5-03-SEA-0003 | CJX48 - Indoor cabinet / panel | #N/A | I | FIRE ALARM CONTROL PANEL |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00087-0105 | PS5-60-SEA-0001 | CJX48 - Indoor cabinet / panel | #N/A | I | GAS DETECTION PANEL |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00087-0315 | PS5-03-MTX-0001 | CJX48 - Indoor cabinet / panel | #N/A | I | SIS/FGS Matrix Panel |  | PS5-04-02 - Office Building SIS/FGS System
T-00087-0492 | PS5-01-LB-0004 | CJX48 - Indoor cabinet / panel | #N/A | I | FIRE SUPPRESSION SKID CONTROL PANEL |  | PS5-01-11 - Inergen for Power Gen Building
T-00087-0500 | PS5-60-LA-0002A | CJX48 - Indoor cabinet / panel | #N/A | I | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM |  | PS5-60-01 - Power Generation Package A
T-00087-0501 | PS5-60-LA-0002B | CJX48 - Indoor cabinet / panel | #N/A | I | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-332-03-0406 | 2026-07-09 | Accepted with punch | Bertus Wikael | Installation
T-00087-0502 | PS5-60-LA-0002C | CJX48 - Indoor cabinet / panel | #N/A | I | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-332-03-0406 | 2026-07-09 | Accepted with punch | Bertus Wikael | Installation
T-00087-0516 | PS5-03-SEA-0005 | CJX48 - Indoor cabinet / panel | #N/A | I | FIRE ALARM CONTROL PANEL |  | PS5-03-24 - FZ - Office and Facilities Building
T-00087-0517 | PS5-03-SEA-0006 | CJX48 - Indoor cabinet / panel | #N/A | I | FIRE ALARM CONTROL PANEL |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00090-0009 | PS5-01-UK-6100 | CZX01I - Package | #N/A | I | DELUGE VALVE SKID |  | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100)
T-00090-0010 | PS5-01-UV-8700 | CZX01I - Package | #N/A | I | FOAM SKID |  | PS5-01-05 - Foam Skid
T-00090-0179 | PS5-60-UR-8100A | CZX01I - Package | #N/A | I | POWER GENERATION PACKAGE A |  | PS5-60-01 - Power Generation Package A
T-00090-0180 | PS5-60-UR-8100B | CZX01I - Package | #N/A | I | POWER GENERATION PACKAGE B |  | PS5-60-04 - Power Generation Package B
T-00090-0181 | PS5-60-UR-8100C | CZX01I - Package | #N/A | I | POWER GENERATION PACKAGE C |  | PS5-60-07 - Power Generation Package C
T-00090-0182 | PS5-60-UR-8100D | CZX01I - Package | #N/A | I | POWER GENERATION PACKAGE D |  | PS5-60-10 - Power Generation Package D
T-00090-0183 | PS5-60-UR-8100E | CZX01I - Package | #N/A | I | POWER GENERATION PACKAGE E |  | PS5-60-13 - Power Generation Package E
T-00090-0184 | PS5-60-UR-8100F | CZX01I - Package | #N/A | I | POWER GENERATION PACKAGE F |  | PS5-60-16 - Power Generation Package F
T-00090-0185 | PS5-60-UR-8100G | CZX01I - Package | #N/A | I | POWER GENERATION PACKAGE G |  | PS5-60-19 - Power Generation Package G
T-00090-0186 | PS5-05-UR-8100 | CZX01I - Package | #N/A | I | EMERGENCY DIESEL ENGINE GENERATOR PACKAGE |  | PS5-05-01 - Emergency Diesel Generator Package
T-00090-0187 | PS5-71-UZ-6200 | CZX01I - Package | #N/A | I | DIESEL FUEL DISPENSER STATION |  | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station
T-00090-0188 | PS5-60-UA-5100 | CZX01I - Package | #N/A | I | COMPRESSOR AIR STARTING SKID |  | PS5-60-27 - Compressed Air Starting Skid
T-00090-0189 | PS5-60-UO-81100A | CZX01I - Package | #N/A | I | LUBE OIL SEPARATOR MODULE |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A
T-00090-0190 | PS5-60-UO-81100B | CZX01I - Package | #N/A | I | LUBE OIL SEPARATOR MODULE |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B
T-00090-0191 | PS5-60-UO-81100C | CZX01I - Package | #N/A | I | LUBE OIL SEPARATOR MODULE |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C
T-00090-0192 | PS5-60-UO-81100D | CZX01I - Package | #N/A | I | LUBE OIL SEPARATOR MODULE |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D
T-00090-0193 | PS5-60-UO-81100E | CZX01I - Package | #N/A | I | LUBE OIL SEPARATOR MODULE |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E
T-00090-0194 | PS5-60-UO-81100F | CZX01I - Package | #N/A | I | LUBE OIL SEPARATOR MODULE |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F
T-00090-0195 | PS5-60-UO-81100G | CZX01I - Package | #N/A | I | LUBE OIL SEPARATOR MODULE |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G
T-00090-0196 | PS5-60-UZ-8200A | CZX01I - Package | #N/A | I | INJECTOR TIP COOLING MODULE |  | PS5-60-35 - Injector Tip Cooling Module A
T-00090-0197 | PS5-60-UZ-8200B | CZX01I - Package | #N/A | I | INJECTOR TIP COOLING MODULE |  | PS5-60-36 - Injector Tip Cooling Module B
T-00090-0198 | PS5-60-UZ-8200C | CZX01I - Package | #N/A | I | INJECTOR TIP COOLING MODULE |  | PS5-60-37 - Injector Tip Cooling Module C
T-00090-0199 | PS5-60-UZ-8200D | CZX01I - Package | #N/A | I | INJECTOR TIP COOLING MODULE |  | PS5-60-38 - Injector Tip Cooling Module D
T-00090-0200 | PS5-60-UZ-8200E | CZX01I - Package | #N/A | I | INJECTOR TIP COOLING MODULE |  | PS5-60-39 - Injector Tip Cooling Module E
T-00090-0201 | PS5-60-UZ-8200F | CZX01I - Package | #N/A | I | INJECTOR TIP COOLING MODULE |  | PS5-60-40 - Injector Tip Cooling Module F
T-00090-0202 | PS5-60-VS-9100A | CZX01I - Package | #N/A | I | OIL MIST SEPARATOR SKID |  | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A
T-00090-0203 | PS5-60-VS-9100B | CZX01I - Package | #N/A | I | OIL MIST SEPARATOR SKID |  | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B
T-00090-0204 | PS5-60-VS-9100C | CZX01I - Package | #N/A | I | OIL MIST SEPARATOR SKID |  | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C
T-00090-0205 | PS5-60-VS-9100D | CZX01I - Package | #N/A | I | OIL MIST SEPARATOR SKID |  | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D
T-00090-0206 | PS5-60-VS-9100E | CZX01I - Package | #N/A | I | OIL MIST SEPARATOR SKID |  | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E
T-00090-0207 | PS5-60-VS-9100F | CZX01I - Package | #N/A | I | OIL MIST SEPARATOR SKID |  | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F
T-00090-0208 | PS5-60-VS-9100G | CZX01I - Package | #N/A | I | OIL MIST SEPARATOR SKID |  | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G
T-00090-0209 | PS5-71-UZ-6500 | CZX01I - Package | #N/A | I | DIESEL FUEL SEPARATOR MODULE |  | PS5-71-18 - Diesel Separator Module
T-00090-0210 | PS5-71-UZ-6800A | CZX01I - Package | #N/A | I | CRUDE FUEL SEPARATOR MODULE A |  | PS5-71-06 - Crude Fuel Separation Module
T-00090-0211 | PS5-71-UZ-6800B | CZX01I - Package | #N/A | I | CRUDE FUEL SEPARATOR MODULE B |  | PS5-71-06 - Crude Fuel Separation Module
T-00090-0212 | PS5-01-UZ-6900 | CZX01I - Package | #N/A | I | WATER MIST FIRE PROTECTION PACKAGE |  | PS5-01-10 - Water Mist Package
T-00090-0213 | PS5-53-UT-8100 | CZX01I - Package | #N/A | I | WATER PRE-TREATMENT PACKAGE |  | PS5-50-03 - Water Pre-Treatment Package
T-00090-0214 | PS5-53-UT-8200 | CZX01I - Package | #N/A | I | WATER TREATMENT/ PURIFICATION PACKAGE |  | PS5-53-04 - Water Treatment Purification Package
T-00090-0215 | PS5-60-EA-2100A | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-70 - Engine A Cooling system
T-00090-0216 | PS5-60-EA-2100B | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-70 - Engine A Cooling system
T-00090-0217 | PS5-60-EA-21100A | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-01 - Power Generation Package A
T-00090-0218 | PS5-60-EA-21100B | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-04 - Power Generation Package B
T-00090-0219 | PS5-60-EA-21100C | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-07 - Power Generation Package C
T-00090-0220 | PS5-60-EA-21100D | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-10 - Power Generation Package D
T-00090-0221 | PS5-60-EA-21100E | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-13 - Power Generation Package E
T-00090-0222 | PS5-60-EA-21100F | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-16 - Power Generation Package F
T-00090-0223 | PS5-60-EA-21100G | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-19 - Power Generation Package G
T-00090-0224 | PS5-60-EA-21200A | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-01 - Power Generation Package A
T-00090-0225 | PS5-60-EA-21200B | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-04 - Power Generation Package B
T-00090-0226 | PS5-60-EA-21200C | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-07 - Power Generation Package C
T-00090-0227 | PS5-60-EA-21200D | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-10 - Power Generation Package D
T-00090-0228 | PS5-60-EA-21200E | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-13 - Power Generation Package E
T-00090-0229 | PS5-60-EA-21200F | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-16 - Power Generation Package F
T-00090-0230 | PS5-60-EA-21200G | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-19 - Power Generation Package G
T-00090-0231 | PS5-60-EA-2200A | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-71 - Engine B Cooling system
T-00090-0232 | PS5-60-EA-2200B | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-71 - Engine B Cooling system
T-00090-0233 | PS5-60-EA-2300A | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-72 - Engine C Cooling system
T-00090-0234 | PS5-60-EA-2300B | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-72 - Engine C Cooling system
T-00090-0235 | PS5-60-EA-2400A | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-73 - Engine D Cooling system
T-00090-0236 | PS5-60-EA-2400B | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-73 - Engine D Cooling system
T-00090-0237 | PS5-60-EA-2500A | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-74 - Engine E Cooling system
T-00090-0238 | PS5-60-EA-2500B | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-74 - Engine E Cooling system
T-00090-0239 | PS5-60-EA-2600A | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-75 - Engine F Cooling system
T-00090-0240 | PS5-60-EA-2600B | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-75 - Engine F Cooling system
T-00090-0241 | PS5-60-EA-2700A | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-76 - Engine G Cooling system
T-00090-0242 | PS5-60-EA-2700B | CZX01I - Package | #N/A | I | POWER GENERATION ENGINE RADIATOR |  | PS5-60-76 - Engine G Cooling system
T-00090-0243 | PS5-60-EA-2800A | CZX01I - Package | #N/A | I | RADIATOR |  | PS5-60-35 - Injector Tip Cooling Module A
T-00090-0244 | PS5-60-EA-2800B | CZX01I - Package | #N/A | I | RADIATOR |  | PS5-60-36 - Injector Tip Cooling Module B
T-00090-0245 | PS5-60-EA-2800C | CZX01I - Package | #N/A | I | RADIATOR |  | PS5-60-37 - Injector Tip Cooling Module C
T-00090-0246 | PS5-60-EA-2800D | CZX01I - Package | #N/A | I | RADIATOR |  | PS5-60-38 - Injector Tip Cooling Module D
T-00090-0247 | PS5-60-EA-2800E | CZX01I - Package | #N/A | I | RADIATOR |  | PS5-60-39 - Injector Tip Cooling Module E
T-00090-0248 | PS5-60-EA-2800F | CZX01I - Package | #N/A | I | RADIATOR |  | PS5-60-40 - Injector Tip Cooling Module F
T-00090-0249 | PS5-60-EA-2800G | CZX01I - Package | #N/A | I | RADIATOR |  | PS5-60-41 - Injector Tip Cooling Module G
T-00090-0250 | PS5-60-EA-2900A | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A
T-00090-0251 | PS5-60-EA-2900B | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B
T-00090-0252 | PS5-60-EA-2900C | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00090-0253 | PS5-60-EA-2900D | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00090-0254 | PS5-60-EA-2900E | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00090-0255 | PS5-60-EA-2900F | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00090-0256 | PS5-60-EA-2900G | CZX01I - Package | #N/A | I | COOLING SKID |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00090-0257 | PS5-60-TCV-0001A | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-70 - Engine A Cooling system
T-00090-0258 | PS5-60-TCV-0001B | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-71 - Engine B Cooling system
T-00090-0259 | PS5-60-TCV-0001C | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-72 - Engine C Cooling system
T-00090-0260 | PS5-60-TCV-0001D | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-73 - Engine D Cooling system
T-00090-0261 | PS5-60-TCV-0001E | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-74 - Engine E Cooling system
T-00090-0262 | PS5-60-TCV-0001F | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-75 - Engine F Cooling system
T-00090-0263 | PS5-60-TCV-0001G | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-76 - Engine G Cooling system
T-00090-0264 | PS5-60-TCV-0002A | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-70 - Engine A Cooling system
T-00090-0265 | PS5-60-TCV-0002B | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-71 - Engine B Cooling system
T-00090-0266 | PS5-60-TCV-0002C | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-72 - Engine C Cooling system
T-00090-0267 | PS5-60-TCV-0002D | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-73 - Engine D Cooling system
T-00090-0268 | PS5-60-TCV-0002E | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-74 - Engine E Cooling system
T-00090-0269 | PS5-60-TCV-0002F | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-75 - Engine F Cooling system
T-00090-0270 | PS5-60-TCV-0002G | CZX01I - Package | #N/A | I | THERMAL REGULATING VALVE SKID |  | PS5-60-76 - Engine G Cooling system
T-00090-0271 | PS5-60-UA-5200 | CZX01I - Package | #N/A | I | INSTRUMENT AIR COMPRESSOR MODULE |  | PS5-60-26 - Instrument Air Compressor Skid
T-00090-0272 | PS5-60-UR-8200A | CZX01I - Package | #N/A | I | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-01 - Power Generation Package A
T-00090-0273 | PS5-60-UR-8200B | CZX01I - Package | #N/A | I | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-04 - Power Generation Package B
T-00090-0274 | PS5-60-UR-8200C | CZX01I - Package | #N/A | I | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-07 - Power Generation Package C
T-00090-0275 | PS5-60-UR-8200D | CZX01I - Package | #N/A | I | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-10 - Power Generation Package D
T-00090-0276 | PS5-60-UR-8200E | CZX01I - Package | #N/A | I | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-13 - Power Generation Package E
T-00090-0277 | PS5-60-UR-8200F | CZX01I - Package | #N/A | I | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-16 - Power Generation Package F
T-00090-0278 | PS5-60-UR-8200G | CZX01I - Package | #N/A | I | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) |  | PS5-60-19 - Power Generation Package G
T-00090-0279 | PS5-60-UZ-8200G | CZX01I - Package | #N/A | I | INJECTOR TIP COOLING MODULE |  | PS5-60-41 - Injector Tip Cooling Module G
T-00090-0280 | PS5-60-UZ-8900A | CZX01I - Package | #N/A | I | FUEL CONDITIONING MODULE |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A
T-00090-0281 | PS5-60-UZ-8900B | CZX01I - Package | #N/A | I | FUEL CONDITIONING MODULE |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B
T-00090-0282 | PS5-60-UZ-8900C | CZX01I - Package | #N/A | I | FUEL CONDITIONING MODULE |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00090-0283 | PS5-60-UZ-8900D | CZX01I - Package | #N/A | I | FUEL CONDITIONING MODULE |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00090-0284 | PS5-60-UZ-8900E | CZX01I - Package | #N/A | I | FUEL CONDITIONING MODULE |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00090-0285 | PS5-60-UZ-8900F | CZX01I - Package | #N/A | I | FUEL CONDITIONING MODULE |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00090-0286 | PS5-60-UZ-8900G | CZX01I - Package | #N/A | I | FUEL CONDITIONING MODULE |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00090-0287 | PS5-71-UN-7200 | CZX01I - Package | #N/A | I | CRUDE FUEL OIL ALLOCATION METERING PACKAGE |  | PS5-71-02 - CFO Allocation Metering Package
T-00090-0288 | PS5-71-UZ-6400 | CZX01I - Package | #N/A | I | CRUDE FUEL OIL PRE-PRESSURE MODULE |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00090-0289 | PS5-71-UZ-6700 | CZX01I - Package | #N/A | I | DIESEL FUEL OIL PRE-PRESSURE MODULE |  | PS5-71-22 - Diesel Fuel Pre Pressure Module
T-00090-0290 | PS5-74-UB-5100 | CZX01I - Package | #N/A | I | NITROGEN GENERATION PACKAGE |  | PS5-74-01 - N2 Generation Skid
T-00090-0291 | PS5-75-UI-6100 | CZX01I - Package | #N/A | I | BIOCIDE INJECTION PACKAGE |  | PS5-75-02 - Biocide Injection Package
T-00090-0292 | PS5-75-UI-6200 | CZX01I - Package | #N/A | I | DRA PACKAGE |  | PS5-75-01 - DRA Injection Package
T-00090-0293 | PS5-75-UI-6300 | CZX01I - Package | #N/A | I | CORROSION INHIBITOR PACKAGE |  | PS5-75-03 - Corrosion Inhibitor Injection Package
T-00090-0294 | PS5-77-UZ-8200 | CZX01I - Package | #N/A | I | WATER DEIONIZATION PACKAGE |  | PS5-53-03 - Water Softener Package
T-00090-0295 | PS5-82-UZ-8100 | CZX01I - Package | #N/A | I | SEWAGE TREATMENT PLANT PACKAGE |  | PS5-82-02 - Sewage Treatment Plant Package
T-00090-0296 | PS5-60-PRV-0008A | CZX01I - Package | #N/A | I | AIR REGULATOR |  | PS5-60-28 - Air Receiver A & Air Regulator A
T-00090-0297 | PS5-60-PRV-0008B | CZX01I - Package | #N/A | I | AIR REGULATOR |  | PS5-60-29 - Air Receiver B & Air Regulator B
T-00090-0298 | PS5-60-PRV-0008C | CZX01I - Package | #N/A | I | AIR REGULATOR |  | PS5-60-30 - Air Receiver C & Air Regulator C
T-00090-0299 | PS5-60-PRV-0008D | CZX01I - Package | #N/A | I | AIR REGULATOR |  | PS5-60-31 - Air Receiver D & Air Regulator D
T-00090-0300 | PS5-60-PRV-0008E | CZX01I - Package | #N/A | I | AIR REGULATOR |  | PS5-60-32 - Air Receiver E & Air Regulator E
T-00090-0301 | PS5-60-PRV-0008F | CZX01I - Package | #N/A | I | AIR REGULATOR |  | PS5-60-33 - Air Receiver F & Air Regulator F
T-00090-0302 | PS5-60-PRV-0008G | CZX01I - Package | #N/A | I | AIR REGULATOR |  | PS5-60-34 - Air Receiver G & Air Regulator G
T-00090-0433 | PS5-01-UZ-610 | CZX01I - Package | #N/A | I | Fire suppression skid |  | PS5-01-11 - Inergen for Power Gen Building
T-00090-0436 | PS5-60-UR-8300A | CZX01I - Package | #N/A | I | POWER GENERATION - Cooler Module |  | PS5-60-35 - Injector Tip Cooling Module A
T-00090-0437 | PS5-60-UR-8300B | CZX01I - Package | #N/A | I | POWER GENERATION - Cooler Module |  | PS5-60-36 - Injector Tip Cooling Module B
T-00090-0438 | PS5-60-UR-8300C | CZX01I - Package | #N/A | I | POWER GENERATION - Cooler Module |  | PS5-60-37 - Injector Tip Cooling Module C
T-00090-0439 | PS5-60-UR-8300D | CZX01I - Package | #N/A | I | POWER GENERATION - Cooler Module |  | PS5-60-38 - Injector Tip Cooling Module D
T-00090-0440 | PS5-60-UR-8300E | CZX01I - Package | #N/A | I | POWER GENERATION - Cooler Module |  | PS5-60-39 - Injector Tip Cooling Module E
T-00090-0441 | PS5-60-UR-8300F | CZX01I - Package | #N/A | I | POWER GENERATION - Cooler Module |  | PS5-60-40 - Injector Tip Cooling Module F
T-00090-0442 | PS5-60-UR-8300G | CZX01I - Package | #N/A | I | POWER GENERATION - Cooler Module |  | PS5-60-41 - Injector Tip Cooling Module G
T-00090-0455 | PS5-03-SEA-0001 | CZX01I - Package | #N/A | I | FACP |  | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure
T-00163-0283 | PS5-08-01LS-0101 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 1 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0284 | PS5-08-01LS-0102 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 1 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0285 | PS5-08-01LS-0103 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 1 - Adressable weatherproof Horn Speaker (including LTD) |  | PS5-08-01 - PAGA
T-00163-0286 | PS5-08-01LS-0104 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 1 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0287 | PS5-08-01LS-0105 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 1 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0288 | PS5-08-01LS-0106 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 1 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0289 | PS5-08-01LS-0107 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 1 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0290 | PS5-08-01LS-0108 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 1 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0291 | PS5-08-01LS-0109 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 1 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0292 | PS5-08-01LS-0110 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 1 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0293 | PS5-08-01LS-0201 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 2 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0294 | PS5-08-01LS-0202 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 2 - Adressable weatherproof Horn Speaker (including LTD) |  | PS5-08-01 - PAGA
T-00163-0295 | PS5-08-01LS-0203 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 2 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0296 | PS5-08-01LS-0204 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 2 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0297 | PS5-08-01LS-0205 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 2 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0298 | PS5-08-01LS-0206 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 2 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0299 | PS5-08-01LS-0207 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 2 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0300 | PS5-08-01LS-0208 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 2 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0301 | PS5-08-01LS-0209 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 2 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0302 | PS5-08-01LS-0210 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 2 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0303 | PS5-08-01LS-0211 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 2 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0304 | PS5-08-01LS-0301 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 3 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) |  | PS5-08-01 - PAGA
T-00163-0305 | PS5-08-01LS-0302 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 3 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0306 | PS5-08-01LS-0303 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 3 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0307 | PS5-08-01LS-0304 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 3 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0308 | PS5-08-01LS-0305 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 3 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0309 | PS5-08-01LS-0306 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 3 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0310 | PS5-08-01LS-0307 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 3 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0311 | PS5-08-01LS-0308 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 3 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0312 | PS5-08-01LS-0309 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 3 - Adressable Safe area addressable ceiling-mounted speaker (including LTD) |  | PS5-08-01 - PAGA
T-00163-0313 | PS5-08-01LS-0310 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 3 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0322 | PS5-08-01LS-0401 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 4 - Adressable Hazardous area addressable wall-mounted speaker (Ex rated) |  | PS5-08-01 - PAGA
T-00163-0323 | PS5-08-01LS-0402 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 4 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0324 | PS5-08-01LS-0403 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 4 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0325 | PS5-08-01LS-0404 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 4 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0326 | PS5-08-01LS-0405 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 4 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0327 | PS5-08-01LS-0406 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 4 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0328 | PS5-08-01LS-0407 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 4 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0329 | PS5-08-01LS-0408 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 4 - Adressable Safe area addressable ceiling-mounted speaker (including LTD) |  | PS5-08-01 - PAGA
T-00163-0330 | PS5-08-01LS-0409 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 4 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0331 | PS5-08-01LS-0410 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 4 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0332 | PS5-08-01LS-0411 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 4 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0340 | PS5-08-01LS-0501 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0341 | PS5-08-01LS-0502 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0342 | PS5-08-01LS-0503 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0343 | PS5-08-01LS-0504 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0344 | PS5-08-01LS-0505 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0345 | PS5-08-01LS-0506 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0346 | PS5-08-01LS-0507 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0347 | PS5-08-01LS-0508 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0348 | PS5-08-01LS-0509 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0349 | PS5-08-01LS-0510 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0350 | PS5-08-01LS-0511 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0351 | PS5-08-01LS-0512 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker (Haz. Area) |  | PS5-08-01 - PAGA
T-00163-0352 | PS5-08-01LS-0517 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker (Haz. Area) |  | PS5-08-01 - PAGA
T-00163-0353 | PS5-08-01LS-0518 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0354 | PS5-08-01LS-0519 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker (Haz. Area) |  | PS5-08-01 - PAGA
T-00163-0355 | PS5-08-01LS-0520 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker (Haz. Area) |  | PS5-08-01 - PAGA
T-00163-0356 | PS5-08-01LS-0521 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker (Haz. Area) |  | PS5-08-01 - PAGA
T-00163-0357 | PS5-08-01LS-0522 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0358 | PS5-08-01LS-0523 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0359 | PS5-08-01LS-0524 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0360 | PS5-08-01LS-0525 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0361 | PS5-08-01LS-0526 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0362 | PS5-08-01LS-0527 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0363 | PS5-08-01LS-0528 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0364 | PS5-08-01LS-0529 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0365 | PS5-08-01LS-0530 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 5 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0366 | PS5-08-01LS-0601 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0367 | PS5-08-01LS-0602 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0368 | PS5-08-01LS-0603 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00227-0068 | PS5-61-ISR-0101 | TPX02 - Power transformer | #N/A | E | Shunt Reactor |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00227-0070 | PS5-61-IU-0010 | TPX02 - Power transformer | #N/A | E | LLHT Oil Transformer |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010)
T-00227-0071 | PS5-61-IU-0011 | TPX02 - Power transformer | #N/A | E | LLHT Oil Transformer |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011)
T-00227-0072 | PS5-63-IV-0010 | TPX02 - Power transformer | #N/A | E | Earthing Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00227-0073 | PS5-63-IV-0011 | TPX02 - Power transformer | #N/A | E | Earthing Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00227-0112 | PS5-61-IU-3100A | TPX02 - Power transformer | #N/A | E | VFD Transformer |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-332-16-0326 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00227-0113 | PS5-61-IU-3100B | TPX02 - Power transformer | #N/A | E | VFD Transformer |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-332-16-0326 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00227-0114 | PS5-61-IU-3100C | TPX02 - Power transformer | #N/A | E | VFD Transformer |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-332-16-0326 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00227-0133 | PS5-61-IU-0001A | TPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-01 - Power Generation Package A
T-00227-0134 | PS5-61-IU-0001B | TPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-04 - Power Generation Package B
T-00227-0135 | PS5-61-IU-0001C | TPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-07 - Power Generation Package C
T-00227-0136 | PS5-61-IU-0001D | TPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-10 - Power Generation Package D
T-00227-0137 | PS5-61-IU-0001E | TPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-13 - Power Generation Package E
T-00227-0138 | PS5-61-IU-0001F | TPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-16 - Power Generation Package F
T-00227-0139 | PS5-61-IU-0001G | TPX02 - Power transformer | #N/A | E | 11/33kV Transformer - 6.8 MVA |  | PS5-60-19 - Power Generation Package G
T-00228-0031 | PS5-61-IV-0001A | TPX03 - LV transformer | #N/A | E | Distribution Transformer |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-332-16-0332 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00228-0032 | PS5-61-IV-0001B | TPX03 - LV transformer | #N/A | E | Distribution Transformer |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-332-16-0396 | 2026-06-30 | Accepted with comment | Bertus Wikael | Testing
T-00228-0041 | PS5-61-IV-0002A | TPX03 - LV transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-332-16-0396 | 2026-06-30 | Accepted with comment | Bertus Wikael | Testing
T-00228-0042 | PS5-61-IV-0002B | TPX03 - LV transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-332-16-0396 | 2026-06-30 | Accepted with comment | Bertus Wikael | Testing
T-00228-0043 | PS5-61-IV-0007A | TPX03 - LV transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-332-16-0396 | 2026-06-30 | Accepted with comment | Bertus Wikael | Testing
T-00228-0044 | PS5-61-IV-0007B | TPX03 - LV transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-332-16-0396 | 2026-06-30 | Accepted with comment | Bertus Wikael | Testing
T-00228-0096 | PS5-79-IV-0001 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 1 |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | CPP-RFI-68-33/2-16-0327 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00228-0097 | PS5-79-IV-0002 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 2 |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | CPP-RFI-68-33/2-16-0327 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00228-0098 | PS5-79-IV-0003 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 3 |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | CPP-RFI-68-33/2-16-0327 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00228-0099 | PS5-79-IV-0004 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 4 |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | CPP-RFI-68-33/2-16-0327 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00228-0100 | PS5-79-IV-0005 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 5 |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | CPP-RFI-68-33/2-16-0327 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00228-0101 | PS5-79-IV-0006 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 6 |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | CPP-RFI-68-33/2-16-0327 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00228-0102 | PS5-79-IV-0007 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 7 |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | CPP-RFI-68-33/2-16-0327 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00228-0103 | PS5-79-IV-0008 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 8 |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | CPP-RFI-68-33/2-16-0327 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00228-0104 | PS5-79-IV-0009 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 9 |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | CPP-RFI-68-33/2-16-0327 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00228-0105 | PS5-79-IV-0010 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 10 |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | CPP-RFI-68-33/2-16-0327 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00228-0106 | PS5-79-IV-0011 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 11 |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | CPP-RFI-68-33/2-16-0327 | 2026-06-09 | Accepted | Bertus Wikael | Testing
T-00228-0107 | PS5-79-IV-0012 | TPX03 - LV transformer | #N/A | E | Feeder to EHT Transformer / DB 12 |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00228-0108 | PS5-87-IRF-0001 | TPX03 - LV transformer | #N/A | E | Transformer Rectifier Unit 1-for tank (PS5-53-TR-4100) |  | PS5-53-01 - Utility Water / Storage Tank
T-00228-0109 | PS5-87-IRF-0002 | TPX03 - LV transformer | #N/A | E | Transformer Rectifier Unit 2-for tank (PS5-71-TR-4100) |  | PS5-71-04 - CFO Storage Tank
T-00228-0110 | PS5-87-IRF-0003 | TPX03 - LV transformer | #N/A | E | Transformer Rectifier Unit 3-for tank (PS5-71-TR-4200) |  | PS5-71-12 - CFO Service Tank
T-00228-0111 | PS5-87-IRF-0004 | TPX03 - LV transformer | #N/A | E | Transformer Rectifier Unit 4-for tank ( PS5-71-TR-4400) |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00228-0153 | PS5-61-IV-0005A | TPX03 - LV transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00228-0154 | PS5-61-IV-0005B | TPX03 - LV transformer | #N/A | E | Distribution Transformer |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00230-0035 | PS5-61-IK-0003 | TPX05 - LV switchboard | #N/A | E | LV SWGR |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-332-13-0424 | 2026-07-19 | Accepted | Bertus Wikael | Testing | N/A | N/A | N/A
T-00230-0036 | PS5-61-IK-0006 | TPX05 - LV switchboard | #N/A | E | LV SWGR |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006)
T-00232-0952 | PS5-25-DM-3100A-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0953 | PS5-25-DM-3100A-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0954 | PS5-25-DM-3100A-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0955 | PS5-25-DM-3100A-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0956 | PS5-25-DM-3100A-CH05 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0957 | PS5-25-DM-3100A-CH06 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0958 | PS5-25-DM-3100B-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0959 | PS5-25-DM-3100B-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0960 | PS5-25-DM-3100B-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0961 | PS5-25-DM-3100B-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0962 | PS5-25-DM-3100B-CH05 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0963 | PS5-25-DM-3100B-CH06 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0964 | PS5-25-DM-3100C-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0965 | PS5-25-DM-3100C-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0966 | PS5-25-DM-3100C-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0967 | PS5-25-DM-3100C-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0968 | PS5-25-DM-3100C-CH05 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0969 | PS5-25-DM-3100C-CH06 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0208 | 2026-04-10 | Accepted | Elizabeth | TESTING
T-00232-0970 | PS5-60-IJ-0001A-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100A TO PS5-60-IJ-0001A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0175 | 2026-03-10 | Accepted | Ferdinand | TESTING
T-00232-0971 | PS5-60-IJ-0001B-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100B TO PS5-60-IJ-0001B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0175 | 2026-03-10 | Accepted | Ferdinand | TESTING
T-00232-0972 | PS5-60-IJ-0001C-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100C TO PS5-60-IJ-0001C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0175 | 2026-03-10 | Accepted | Ferdinand | TESTING
T-00232-0973 | PS5-60-IJ-0001D-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100D TO PS5-60-IJ-0001D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0175 | 2026-03-10 | Accepted | Ferdinand | TESTING
T-00232-0974 | PS5-60-IJ-0001E-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100E TO PS5-60-IJ-0001E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0175 | 2026-03-10 | Accepted | Ferdinand | TESTING
T-00232-0975 | PS5-60-IJ-0001F-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100F TO PS5-60-IJ-0001F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0175 | 2026-03-10 | Accepted | Ferdinand | TESTING
T-00232-0976 | PS5-60-IJ-0001G-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100G TO PS5-60-IJ-0001G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0175 | 2026-03-10 | Accepted | Ferdinand | TESTING
T-00232-0977 | PS5-61-IDH-3100A-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0978 | PS5-61-IDH-3100A-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0979 | PS5-61-IDH-3100A-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0980 | PS5-61-IDH-3100A-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0981 | PS5-61-IDH-3100A-CH05 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0982 | PS5-61-IDH-3100A-CH06 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0983 | PS5-61-IDH-3100A-CH07 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0984 | PS5-61-IDH-3100A-CH08 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0985 | PS5-61-IDH-3100A-CH09 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0986 | PS5-61-IDH-3100A-CH10 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0987 | PS5-61-IDH-3100A-CH11 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0988 | PS5-61-IDH-3100A-CH12 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0989 | PS5-61-IDH-3100B-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0990 | PS5-61-IDH-3100B-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0991 | PS5-61-IDH-3100B-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0992 | PS5-61-IDH-3100B-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0993 | PS5-61-IDH-3100B-CH05 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0994 | PS5-61-IDH-3100B-CH06 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0995 | PS5-61-IDH-3100B-CH07 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0996 | PS5-61-IDH-3100B-CH08 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0997 | PS5-61-IDH-3100B-CH09 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0998 | PS5-61-IDH-3100B-CH10 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-0999 | PS5-61-IDH-3100B-CH11 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1000 | PS5-61-IDH-3100B-CH12 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1001 | PS5-61-IDH-3100C-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1002 | PS5-61-IDH-3100C-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1003 | PS5-61-IDH-3100C-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1004 | PS5-61-IDH-3100C-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1005 | PS5-61-IDH-3100C-CH05 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1006 | PS5-61-IDH-3100C-CH06 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1007 | PS5-61-IDH-3100C-CH07 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1008 | PS5-61-IDH-3100C-CH08 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1009 | PS5-61-IDH-3100C-CH09 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1010 | PS5-61-IDH-3100C-CH10 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1011 | PS5-61-IDH-3100C-CH11 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1012 | PS5-61-IDH-3100C-CH12 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-03-28 | Accepted | Elizabeth | TESTING
T-00232-1013 | PS5-61-IJ-0001-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1014 | PS5-61-IJ-0001-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1015 | PS5-61-IJ-0001-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1016 | PS5-61-IJ-0001-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1017 | PS5-61-IJ-0001-CH05 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1018 | PS5-61-IJ-0001-CH06 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1019 | PS5-61-IJ-0001-CH07 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1020 | PS5-61-IJ-0001-CH08 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1021 | PS5-61-IJ-0001-CH09 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1022 | PS5-61-IJ-0001-CH10 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1023 | PS5-61-IJ-0001-CH11 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1024 | PS5-61-IJ-0001-CH12 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1025 | PS5-61-IJ-0001-CH13 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1026 | PS5-61-IJ-0001-CH14 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1027 | PS5-61-IJ-0001-CH15 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1028 | PS5-61-IJ-0001-CH16 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1029 | PS5-61-IJ-0001-CH17 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1030 | PS5-61-IJ-0001-CH18 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1031 | PS5-61-IJ-0001-CH19 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1032 | PS5-61-IJ-0001-CH20 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1033 | PS5-61-IJ-0001-CH21 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0199 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1034 | PS5-61-IJ-0010-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IJ-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-07-0201 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1035 | PS5-61-IJ-0010-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IJ-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-07-0201 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1036 | PS5-61-IJ-0010-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IJ-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-07-0201 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1037 | PS5-61-IJ-0011-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IJ-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-07-0201 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1038 | PS5-61-IJ-0011-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IJ-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-07-0201 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1039 | PS5-61-IJ-0011-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IJ-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-07-0201 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1040 | PS5-61-ISR-0101-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0101 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0197 | 2026-04-02 | Accepted | Ferdinand | Pulling
T-00232-1041 | PS5-61-ISR-0101-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0101 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-07-200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1042 | PS5-61-ISR-0101-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0101 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-07-200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1043 | PS5-61-ISR-0102-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0102 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-07-0200 | 2026-03-31 | Accepted | Ferdinand | TESTING
T-00232-1044 | PS5-61-ISR-0102-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0102 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-07-0200 | 2026-03-31 | Accepted | Ferdinand | TESTING
T-00232-1045 | PS5-61-ISR-0102-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-ISR-0102 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-07-0200 | 2026-03-31 | Accepted | Ferdinand | TESTING
T-00232-1046 | PS5-61-IU-0001A-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1047 | PS5-61-IU-0001A-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1048 | PS5-61-IU-0001A-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1049 | PS5-61-IU-0001B-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1050 | PS5-61-IU-0001B-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1051 | PS5-61-IU-0001B-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1052 | PS5-61-IU-0001C-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1053 | PS5-61-IU-0001C-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1054 | PS5-61-IU-0001C-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1055 | PS5-61-IU-0001D-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1056 | PS5-61-IU-0001D-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1057 | PS5-61-IU-0001D-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1058 | PS5-61-IU-0001E-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1059 | PS5-61-IU-0001E-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1060 | PS5-61-IU-0001E-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1061 | PS5-61-IU-0001F-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1062 | PS5-61-IU-0001F-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1063 | PS5-61-IU-0001F-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1064 | PS5-61-IU-0001G-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1065 | PS5-61-IU-0001G-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1066 | PS5-61-IU-0001G-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-169 | 2026-03-07 | Accepted | Elizabeth | TESTING
T-00232-1067 | PS5-61-IU-0010-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-07-200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1068 | PS5-61-IU-0010-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-07-200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1069 | PS5-61-IU-0010-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-07-200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1070 | PS5-61-IU-0011-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-07-200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1071 | PS5-61-IU-0011-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-07-200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1072 | PS5-61-IU-0011-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-07-200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1073 | PS5-61-IU-3100A-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0185 | 2026-03-22 | Accepted | Elizabeth | TESTING
T-00232-1074 | PS5-61-IU-3100A-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0185 | 2026-03-22 | Accepted | Elizabeth | TESTING
T-00232-1075 | PS5-61-IU-3100A-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0185 | 2026-03-22 | Accepted | Elizabeth | TESTING
T-00232-1076 | PS5-61-IU-3100A-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IV-0006A TO PS5-61-IU-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-33/1-07-0195 | 2026-04-02 | Accepted | Elizabeth | TESTING
T-00232-1077 | PS5-61-IU-3100B-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0185 | 2026-03-22 | Accepted | Elizabeth | TESTING
T-00232-1078 | PS5-61-IU-3100B-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0185 | 2026-03-22 | Accepted | Elizabeth | TESTING
T-00232-1079 | PS5-61-IU-3100B-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0185 | 2026-03-22 | Accepted | Elizabeth | TESTING
T-00232-1080 | PS5-61-IU-3100B-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IV-0006B TO PS5-61-IU-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-33/1-07-0195 | 2026-04-02 | Accepted | Elizabeth | TESTING
T-00232-1081 | PS5-61-IU-3100C-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0185 | 2026-03-22 | Accepted | Elizabeth | TESTING
T-00232-1082 | PS5-61-IU-3100C-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0185 | 2026-03-22 | Accepted | Elizabeth | TESTING
T-00232-1083 | PS5-61-IU-3100C-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IU-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0185 | 2026-03-22 | Accepted | Elizabeth | TESTING
T-00232-1084 | PS5-61-IU-3100C-CH04 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IV-0006C TO PS5-61-IU-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-33/1-07-0195 | 2026-04-02 | Accepted | Elizabeth | TESTING
T-00232-1085 | PS5-61-IV-0001A-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001A |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1086 | PS5-61-IV-0001A-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001A |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1087 | PS5-61-IV-0001A-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001A |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1088 | PS5-61-IV-0001B-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001B |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1089 | PS5-61-IV-0001B-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001B |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1090 | PS5-61-IV-0001B-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0001B |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1091 | PS5-61-IV-0002A-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002A |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1092 | PS5-61-IV-0002A-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002A |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1093 | PS5-61-IV-0002A-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002A |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1094 | PS5-61-IV-0002B-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002B |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1095 | PS5-61-IV-0002B-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002B |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1096 | PS5-61-IV-0002B-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0002B |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1097 | PS5-61-IV-0005A-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005A |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00232-1098 | PS5-61-IV-0005A-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005A |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00232-1099 | PS5-61-IV-0005A-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005A |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00232-1100 | PS5-61-IV-0005B-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005B |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00232-1101 | PS5-61-IV-0005B-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005B |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00232-1102 | PS5-61-IV-0005B-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0005B |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00232-1103 | PS5-61-IV-0007A-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007A |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1104 | PS5-61-IV-0007A-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007A |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1105 | PS5-61-IV-0007A-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007A |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1106 | PS5-61-IV-0007B-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007B |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1107 | PS5-61-IV-0007B-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007B |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1108 | PS5-61-IV-0007B-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IV-0007B |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0191 | 2026-03-23 | Accepted | Elizabeth | TESTING
T-00232-1109 | PS5-61-NER-0010-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-NER-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00232-1110 | PS5-61-NER-0011-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-NER-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00232-1111 | PS5-63-IV-0010-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0010 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1112 | PS5-63-IV-0010-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0010 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1113 | PS5-63-IV-0010-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0010 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1114 | PS5-63-IV-0011-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0011 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1115 | PS5-63-IV-0011-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0011 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1116 | PS5-63-IV-0011-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-63-IV-0011 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-07-0200 | 2026-04-02 | Accepted | Ferdinand | TESTING
T-00232-1117 | PS5-63-NER-0010-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-63-IV-0010 TO PS5-63-NER-0010 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-07-0209 | 2026-04-11 | Accepted | Bertus Wikael | TESTING
T-00232-1118 | PS5-63-NER-0011-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-63-IV-0011 TO PS5-63-NER-0011 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-07-0209 | 2026-04-11 | Accepted | Bertus Wikael | TESTING
T-00232-1119 | PS5-79-BH-0001-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0010 TO PS5-79-BH-0001 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00232-1120 | PS5-79-BH-0001-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0010 TO PS5-79-BH-0001 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00232-1121 | PS5-79-BH-0001-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0010 TO PS5-79-BH-0001 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
| PS5-28-DM-3900A-CL01 | TPX09 - LV power cable | #N/A | E | From PS5-61-IK-0001 to PS5-28-DM-3900A |  | PS5-28-17 | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
| PS5-28-HE-2200-CD01 | TPX09 - LV power cable | #N/A | E | From PS5-61-IK-0001 to PS5-28-HE-2200 |  | PS5-28-04 | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
| PS5-61-IDH-3100A-CL01 | TPX09 - LV power cable | #N/A | E | From PS5-06-IG-0001A to PS5-61-IDH-3100A |  | PS5-25-02 | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
| PS5-61-IDH-3100B-CL01 | TPX09 - LV power cable | #N/A | E | From PS5-06-IG-0001B to PS5-61-IDH-3100B |  | PS5-25-03 | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
| PS5-61-IDH-3100C-CL01 | TPX09 - LV power cable | #N/A | E | From PS5-06-IG-0001B to PS5-61-IDH-3100C |  | PS5-25-04 | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00232-1122 | PS5-79-BH-0002-CH01 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0011 TO PS5-79-BH-0002 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00232-1123 | PS5-79-BH-0002-CH02 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0011 TO PS5-79-BH-0002 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00232-1124 | PS5-79-BH-0002-CH03 | TPX08 - HV power cable | #N/A | E | Cable FROM PS5-61-IJ-0011 TO PS5-79-BH-0002 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-10060 | PS5-62-IE-0001-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10061 | PS5-62-IE-0001-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10062 | PS5-62-IE-0001-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10063 | PS5-62-IE-0001-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10064 | PS5-62-IE-0001-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10065 | PS5-62-IE-0001-CL51 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10066 | PS5-62-IE-0001-CL52 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10067 | PS5-62-IE-0001-CL53 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10068 | PS5-62-IE-0001-CL54 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10069 | PS5-62-IE-0001-CL55 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10070 | PS5-62-IE-0001-CL56 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10071 | PS5-62-IE-0001-CL57 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10072 | PS5-62-IE-0001-CL58 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10073 | PS5-62-IE-0001-CL59 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00233-10074 | PS5-62-IE-0002-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10075 | PS5-62-IE-0002-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10076 | PS5-62-IE-0002-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10077 | PS5-62-IE-0002-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10078 | PS5-62-IE-0002-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10079 | PS5-62-IE-0002-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10080 | PS5-62-IE-0002-CL52 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10081 | PS5-62-IE-0002-CL53 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10082 | PS5-62-IE-0002-CL54 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10083 | PS5-62-IE-0002-CL55 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10084 | PS5-62-IE-0002-CL56 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10085 | PS5-62-IE-0002-CL57 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10086 | PS5-62-IE-0002-CL58 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10087 | PS5-62-IE-0002-CL59 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10088 | PS5-62-IE-0002-CL60 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00233-10535 | PS5-06-GB-0003-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building
T-00233-10536 | PS5-60-IN-0002A-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00233-10537 | PS5-60-IN-0002B-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00233-10538 | PS5-60-IN-0002C-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00233-10539 | PS5-60-IN-0002D-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00233-10540 | PS5-60-IN-0002E-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00233-10541 | PS5-60-IN-0002F-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00233-10542 | PS5-60-IN-0002G-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
| PS5-61-IE-0002-CD01 | TPX | #N/A | E | Cable From PS5-61-IU-0010 to PS5-61-IE-0002 |  | PS5-61-08 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD04 | TPX | #N/A | E | Cable From PS5-61-IK-0003 to PS5-61-IJ-0001 |  | PS5-61-01 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD35 | TPX | #N/A | E | Cable From PS5-61-IU-0010 to PS5-61-IJ-0001 |  | PS5-61-02 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0010-CL01 | TPX | #N/A | E | Cable From PS5-61-NER-0010 to PS5-61-IJ-0010 |  | PS5-61-02 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0011-CL01 | TPX | #N/A | E | Cable From PS5-61-NER-0011 to PS5-61-IJ-0011 |  | PS5-61-03 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CG02 | TPX | #N/A | E | Cable From PS5-61-IV-0001A to |  | #N/A | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CG03 | TPX | #N/A | E | Cable From PS5-61-IV-0001B to |  | #N/A | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CG04 | TPX | #N/A | E | Cable From PS5-61-IV-0001B to |  | #N/A | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IU-0010-CL02 | TPX | #N/A | E | Cable From PS5-61-IG-0008 to |  | PS5-61-02 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0002-CD05 | TPX | #N/A | E | Cable From PS5-61-IU-0011 to |  | PS5-61-08 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD01 | TPX | #N/A | E | Cable From PS5-63-IV-0010 to |  | PS5-61-01 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD34 | TPX | #N/A | E | Cable From PS5-61-IV-0001B to |  | PS5-61-01 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD38 | TPX | #N/A | E | Cable From PS5-61-ISR-0102 to |  | PS5-61-01 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CL01 | TPX | #N/A | E | Cable From PS5-63-NER-0010 to |  | PS5-61-01 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CL02 | TPX | #N/A | E | Cable From PS5-63-NER-0011 to |  | PS5-61-01 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0002-CD04 | TPX | #N/A | E | Cable From PS5-61-IU-0011 to |  | PS5-61-08 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD39 | TPX | #N/A | E | Cable From PS5-61-IU-0010 to |  | PS5-61-02 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD40 | TPX | #N/A | E | Cable From PS5-61-IU-0011 to |  | PS5-61-03 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0002-CD03 | TPX | #N/A | E | Cable From PS5-61-IU-0010 to |  | PS5-61-08 | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
T-00233-10584 | PS5-05-BE-0001-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0256 | 2026-05-07 | Accepted | Bertus Wikael | Testing
T-00233-10585 | PS5-06-IG-0004A-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-IG-0004A |  | PS5-06-02 - AC UPS - Power Generator Building
T-00233-10586 | PS5-06-IG-0004B-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003B TO PS5-06-IG-0004B |  | PS5-06-02 - AC UPS - Power Generator Building
T-00233-10587 | PS5-25-DM-3100A-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-05-IG-0025-CD01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-05-IG-0026-CD01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-08-01FB-0913-CS02 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-08-01FB-1013-CS02 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-08-01FB-1101-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-08-52BT-0138-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-28-IES-3600A-CD01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-60-IE-0003E-CD06 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-60-IE-0003E-CD08 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD05 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-10588 | PS5-25-DM-3100A-CG02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-10589 | PS5-25-DM-3100B-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-10590 | PS5-25-DM-3100B-CG02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-10591 | PS5-25-DM-3100C-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-10592 | PS5-25-DM-3100C-CG02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0249 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-10593 | PS5-60-IH-0001A-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs
T-00233-10594 | PS5-60-IH-0001B-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs
T-00233-10595 | PS5-60-IH-0001C-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs
T-00233-10596 | PS5-60-IH-0001D-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs
T-00233-10597 | PS5-60-IH-0001E-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00233-10598 | PS5-60-IH-0001F-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00233-10599 | PS5-60-IH-0001G-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00233-10600 | PS5-60-IH-0002-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | Testing
T-00233-10601 | PS5-60-IH-0002-CG02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | Testing
T-00233-10602 | PS5-61-IH-0004-CG01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00233-10603 | PS5-61-IH-0004-CG02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00233-10604 | PS5-61-IH-0004-CG03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00233-10605 | PS5-61-IH-0004-CG04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00233-10616 | PS5-61-IK-0003-CG07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0247 | 2026-05-05 | Accepted | Bertus Wikael | TESTING
T-00233-10889 | PS5-28-DM-31100-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-28-ISO-2008 TO PS5-28-DM-31100 |  | PS5-28-10 - Oil Skimmer Package
T-00233-10890 | PS5-60-BE-0007A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-10891 | PS5-60-BE-0007A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-10892 | PS5-60-BE-0007B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-10893 | PS5-60-BE-0007B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-10894 | PS5-60-BE-0007C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-10895 | PS5-60-BE-0007C-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-10896 | PS5-60-BE-0007D-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-10897 | PS5-60-BE-0007D-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-10898 | PS5-60-BE-0007E-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-10899 | PS5-60-BE-0007E-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-10900 | PS5-60-BE-0007F-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-10901 | PS5-60-BE-0007F-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-10902 | PS5-60-BE-0007G-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-10903 | PS5-60-BE-0007G-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-10904 | PS5-60-ISO-62800A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-ISO-62800A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-10905 | PS5-60-ISO-62800C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-ISO-62800C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-10906 | PS5-60-ISO-62800E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-ISO-62800E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-10907 | PS5-60-ISO-62800G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-ISO-62800G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00233-4695 | PS5-01-BE-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-01-BE-0001 |  | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-4696 | PS5-01-FCV-0003A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-01-FCV-0003A |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-01-IE-0001A-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-01-IE-0001B-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-03-GDLHP-0137-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-03-GDLHP-0142-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-03-GDLHP-0143-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-03-GDLHP-0144-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-03-GDLHP-0146-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-03-GDLHP-0147-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-03-GDLHP-0149-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-03-GDLHP-0150-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-03-GDLHP-0401-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-05-IE-8100-CD22 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-05-IE-8100-CD24 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-06-GU-0003A-CD01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
T-00233-4697 | PS5-01-FCV-0003B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-01-FCV-0003B |  | PS5-01-03 - Fire Water Pump B | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
T-00233-4698 | PS5-01-FCV-0004A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-01-FCV-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
T-00233-4699 | PS5-01-FCV-0004B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-01-FCV-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
T-00233-4710 | PS5-01-IG-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-01-IG-0001 |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-4711 | PS5-01-LB-0004-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-01-LB-0004 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-4712 | PS5-01-LB-0004-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-01-LB-0004 |  | PS5-01-11 - Inergen for Power Gen Building
T-00233-4713 | PS5-01-LB-0004-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-01-LB-0004 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-4714 | PS5-01-MOV-8701-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-01-MOV-8701 |  | PS5-01-05 - Foam Skid | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-4724 | PS5-03-SEA-0002-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0006 TO PS5-03-SEA-0002 |  | PS5-03-22 - FZ-G1 - Guard House
T-00233-4725 | PS5-03-SEA-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-03-SEA-0003 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00233-4727 | PS5-05-BE-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-4728 | PS5-05-BE-0001-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-4729 | PS5-05-BE-0001-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
| PS5-08-01FB-1106-CS02 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0002-CD06 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
| PS5-61-IG-0016-CD01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
| PS5-61-IG-0016-CD01 |  | #N/A | E |  |  |  | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL35 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL36 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-4730 | PS5-05-BE-0001-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-4731 | PS5-05-BE-0001-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-4732 | PS5-05-BE-0001-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-4733 | PS5-05-BE-0001-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-4734 | PS5-05-BE-0001-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-4735 | PS5-05-BE-0001-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-4736 | PS5-05-BE-0001-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-4737 | PS5-05-BE-0001-CL11 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-DG-8100 TO PS5-05-BE-0001 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-4738 | PS5-05-IE-8100-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-4739 | PS5-05-IE-8100-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-4742 | PS5-05-IG-0009-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IG-0009 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
T-00233-4743 | PS5-05-IG-0009-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-05-IG-0009 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0278 | 2026-05-20 | Accepted | Bertus Wikael | Testing
T-00233-4744 | PS5-05-IG-0025-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IG-0025 |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
T-00233-4745 | PS5-05-IG-0026-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IG-0026 |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
T-00233-4746 | PS5-06-GB-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4747 | PS5-06-GB-0003-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4748 | PS5-06-GB-0003-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4749 | PS5-06-GB-0003-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4750 | PS5-06-GB-0003-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4751 | PS5-06-GB-0003-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-GB-0003 |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4752 | PS5-06-GU-0003A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-06-GU-0003A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4753 | PS5-06-GU-0003B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-06-GU-0003B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4754 | PS5-06-GU-0003C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-06-GU-0003C |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4756 | PS5-06-IG-0004A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-IG-0004A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4757 | PS5-06-IG-0004A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-IG-0004A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4758 | PS5-06-IG-0004A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-IG-0004A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4759 | PS5-06-IG-0004A-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003A TO PS5-06-IG-0004A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4761 | PS5-06-IG-0004B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003B TO PS5-06-IG-0004B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4762 | PS5-06-IG-0004B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003B TO PS5-06-IG-0004B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4763 | PS5-06-IG-0004B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003B TO PS5-06-IG-0004B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted | Ferdinand | Testing
T-00233-4764 | PS5-06-IG-0004B-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-GU-0003B TO PS5-06-IG-0004B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-33/1-07-0299 | 2026-05-25 | Accepted |  | Testing
T-00233-4808 | PS5-08-11CB-1501-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0006 TO PS5-08-11CB-1501 |  | PS5-08-11 - Corporate LAN (SIE) | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-4809 | PS5-08-11CB-1901-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-08-11CB-1901 |  | PS5-08-11 - Corporate LAN (SIE)
T-00233-4810 | PS5-08-11CB-1901-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-08-11CB-1901 |  | PS5-08-11 - Corporate LAN (SIE)
T-00233-4811 | PS5-08-11CB-1901-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-08-11CB-1901 |  | PS5-08-11 - Corporate LAN (SIE)
T-00233-4878 | PS5-09-LB-0008-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building
T-00233-4879 | PS5-09-LB-0008-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building
T-00233-4882 | PS5-25-DM-3100A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
T-00233-4883 | PS5-25-DM-3100A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0014 TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
| PS5-06-GU-0003B-CD01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
| PS5-08-01FB-1001-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
| PS5-08-03FB-0002-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
| PS5-08-03FB-0103-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
| PS5-08-12BT-0106-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
| PS5-08-52BT-0133-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
| PS5-08-12BT-0104-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
| PS5-08-12BT-0105-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
| PS5-08-15CP-0002-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
| PS5-08-52BT-0132-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
T-00233-4886 | PS5-25-DM-3100B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
T-00233-4887 | PS5-25-DM-3100B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0014 TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
T-00233-4890 | PS5-25-DM-3100C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
T-00233-4891 | PS5-25-DM-3100C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0014 TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0286 | 2026-05-12 | Accepted | Bertus Wikael | Testing
T-00233-4904 | PS5-25-ESDV-0021-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-4905 | PS5-25-ESDV-0023-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-ESDV-0023 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-4906 | PS5-25-FCV-0003A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-FCV-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-4907 | PS5-25-FCV-0003B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-FCV-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-4908 | PS5-25-FCV-0003C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-FCV-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-4909 | PS5-25-FCV-0004-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-FCV-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-4918 | PS5-25-MOV-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4919 | PS5-25-MOV-0002-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0002 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4920 | PS5-25-MOV-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0003 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4921 | PS5-25-MOV-0008-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-MOV-0008 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-4922 | PS5-25-MOV-0011-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0011 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4923 | PS5-25-MOV-0012-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0012 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4924 | PS5-25-MOV-0025-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0025 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-4925 | PS5-25-MOV-0026-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0026 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
| PS5-25-IES-6500A-CD01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
| PS5-25-IES-6500B-CD01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
| PS5-25-IES-6600A-CD01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
| PS5-25-IES-6600B-CD01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00233-4926 | PS5-25-MOV-0027-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-MOV-0027 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4927 | PS5-25-MOV-0028-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-MOV-0028 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4928 | PS5-25-SDV-0022-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4929 | PS5-25-SDV-0035A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4930 | PS5-25-SDV-0035B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4931 | PS5-25-SDV-0035C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4932 | PS5-25-SDV-0036A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4933 | PS5-25-SDV-0036B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4934 | PS5-25-SDV-0036C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0291 | 2026-05-16 | Accepted | Bertus Wikael | Testing
T-00233-4935 | PS5-25-SDV-0046-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-4936 | PS5-25-SDV-0052-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0052 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
T-00233-4937 | PS5-25-SDV-0054A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-4938 | PS5-25-SDV-0054B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
| PS5-05-IE-8100-CD09 | TPX10 - Multicore electrical control cable | #N/A | E | Cable From PS5-61-IE-0002 to PS5-05-IE-8100 |  | PS5-05-02 | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
| PS5-08-52BT-0135-CS01 | TPX09 - LV power cable | #N/A | E | Cable From PS5-08-11CB-1901 to PS5-08-52BT-0135 |  | PS5-08-52 | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
| PS5-08-52BT-0140-CS01 | TPX09 - LV power cable | #N/A | E | Cable From PS5-08-11CB-1901 to PS5-08-52BT-0140 |  | PS5-08-52 | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD06 | TPX10 - Multicore electrical control cable | #N/A | E | Cable From PS5-61-IK-0006 to PS5-61-IJ-0001 |  | PS5-61-01 | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-4939 | PS5-25-SDV-0054C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-4941 | PS5-25-XV-0053-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00233-4942 | PS5-25-XV-0070-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-25-XV-0070 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-4944 | PS5-28-BE-0002A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-28-BE-0002A |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-331-07-0253 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-08-52BT-0134-CS01 | TPX | #N/A | E | From PS5-08-11CB-1901 to PS5-08-52BT-0134 |  | PS5-08-52 | CPP-RFI-68-331-07-0253 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-28-DM-3400-CL01 | TPX | #N/A | E | From PS5-61-IK-0001 to PS5-28-DM-3400 |  | PS5-28-03 | CPP-RFI-68-331-07-0253 | 2026-05-07 | Accepted | Bertus Wikael | Testing
T-00233-4946 | PS5-28-BE-0002B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-28-BE-0002B |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-331-07-0253 | 2026-05-07 | Accepted | Bertus Wikael | Testing
T-00233-4962 | PS5-28-HE-2100-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-28-HE-2100 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-331-07-0253 | 2026-05-07 | Accepted | Bertus Wikael | Testing
T-00233-4964 | PS5-28-HE-2200-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-28-HE-2200 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-4966 | PS5-28-LB-8200-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-28-LB-8200 |  | PS5-28-11 - Open Drain Interceptor | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-BE-0002A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-BE-0002B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-DM-3300-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-DM-3500-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-DM-3600A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-DM-3600B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-DM-3600B-CL02 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-DM-3700B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-DM-3800A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-DM-3800B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-DM-3800C-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-HE-2100-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-HE-2100-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-HE-2200-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-IES-2008-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-IES-3300-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-IES-3400-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-IES-3500-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-IES-3600B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-IES-3800A-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-IES-3800B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-IES-3800C-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-IES-3900A-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
| PS5-28-IES-3900B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-28-ISO-2008-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-4967 | PS5-28-SDV-0045-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-4968 | PS5-28-SDV-0053A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
| PS5-08-52BT-0136-CS01 | TPX09 - LV power cable | #N/A | E |  |  | PS5-08-52 | CPP-RFI-68-331-07-0254 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-28-IES-3700A-CD01 | TPX09 - LV power cable | #N/A | E |  |  | PS5-28-04 | CPP-RFI-68-331-07-0254 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IDH-3100B-CD02 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-IDH-3100B-CD02 | CPP-RFI-68-331-07-0254 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IG-0043-CL01 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-IG-0043-CL01 | CPP-RFI-68-331-07-0254 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-ISR-0101-CL01 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-ISR-0101-CL01 | CPP-RFI-68-331-07-0254 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-ISR-0102-CL01 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-ISR-0102-CL01 | CPP-RFI-68-331-07-0254 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IU-0010-CL01 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-IU-0010-CL01 | CPP-RFI-68-331-07-0254 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IU-0011-CL01 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-IU-0011-CL01 | CPP-RFI-68-331-07-0254 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-61-IU-0011-CL02 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-IU-0011-CL02 | CPP-RFI-68-331-07-0254 | 2026-05-07 | Accepted | Bertus Wikael | Testing
| PS5-71-HE-2200-CD01 | TPX09 - LV power cable | #N/A | E |  |  | PS5-71-HE-2200-CD01 | CPP-RFI-68-331-07-0254 | 2026-05-07 | Accepted | Bertus Wikael | Testing
T-00233-4969 | PS5-28-SDV-0053B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPP-RFI-68-331-07-0254 | 2026-05-07 | Accepted | Bertus Wikael | Testing
T-00233-4970 | PS5-28-SDV-0053C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPP-RFI-68-331-07-0253 | 2026-05-07 | Accepted | Bertus Wikael | Testing
T-00233-4978 | PS5-60-BE-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 |  | PS5-60-27 - Compressed Air Starting Skid | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-4979 | PS5-60-BE-0001-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 |  | PS5-60-27 - Compressed Air Starting Skid | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-4981 | PS5-60-BE-0001-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0001 |  | PS5-60-27 - Compressed Air Starting Skid | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-4982 | PS5-60-BE-0002-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 |  | PS5-60-26 - Instrument Air Compressor Skid | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-4983 | PS5-60-BE-0002-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 |  | PS5-60-26 - Instrument Air Compressor Skid | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-4984 | PS5-60-BE-0002-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 |  | PS5-60-26 - Instrument Air Compressor Skid | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-4986 | PS5-60-BE-0002-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0002 |  | PS5-60-26 - Instrument Air Compressor Skid | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-4987 | PS5-60-BE-0003A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | Testing
T-00233-4988 | PS5-60-BE-0003B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | Testing
T-00233-4989 | PS5-60-BE-0003C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0003C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-4990 | PS5-60-BE-0003D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
T-00233-4991 | PS5-60-BE-0003E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0003E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-4992 | PS5-60-BE-0003F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0003F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-4993 | PS5-60-BE-0003G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0003G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0427 | 2026-07-21 | Accepted | Bertus Wikael | Testing
T-00233-4994 | PS5-60-BE-0004A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0004A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
T-00233-4995 | PS5-60-BE-0004B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0004B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
T-00233-4996 | PS5-60-BE-0004C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0004C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-4997 | PS5-60-BE-0004D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0004D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
T-00233-4998 | PS5-60-BE-0004E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0004E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-4999 | PS5-60-BE-0004F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0004F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5000 | PS5-60-BE-0004G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0004G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-RFI-68-33/1-07-0427 | 2026-07-21 | Accepted | Bertus Wikael | Testing
T-00233-5001 | PS5-60-BE-0005A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0005A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5002 | PS5-60-BE-0005B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0005B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5003 | PS5-60-BE-0005C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0005C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5004 | PS5-60-BE-0005D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0005D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | Testing
T-00233-5005 | PS5-60-BE-0005E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0005E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5006 | PS5-60-BE-0005F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0005F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5007 | PS5-60-BE-0005G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0005G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00233-5008 | PS5-60-BE-0011A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5009 | PS5-60-BE-0011A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5010 | PS5-60-BE-0011A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5011 | PS5-60-BE-0011A-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5012 | PS5-60-BE-0011A-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5013 | PS5-60-BE-0011A-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5014 | PS5-60-BE-0011B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5015 | PS5-60-BE-0011B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5016 | PS5-60-BE-0011B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5017 | PS5-60-BE-0011B-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5018 | PS5-60-BE-0011B-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5019 | PS5-60-BE-0011B-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5020 | PS5-60-BE-0012A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5021 | PS5-60-BE-0012A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5022 | PS5-60-BE-0012A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5023 | PS5-60-BE-0012A-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5024 | PS5-60-BE-0012A-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5025 | PS5-60-BE-0012A-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5026 | PS5-60-BE-0012B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5027 | PS5-60-BE-0012B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5028 | PS5-60-BE-0012B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5029 | PS5-60-BE-0012B-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5030 | PS5-60-BE-0012B-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5031 | PS5-60-BE-0012B-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0433 | ACCEPTED WITH COMMENT | 2026-07-23 | Bertus Wikael
T-00233-5032 | PS5-60-BE-0013A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C
T-00233-5033 | PS5-60-BE-0013A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5034 | PS5-60-BE-0013A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5035 | PS5-60-BE-0013A-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5036 | PS5-60-BE-0013A-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5037 | PS5-60-BE-0013A-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5038 | PS5-60-BE-0013B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5039 | PS5-60-BE-0013B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5040 | PS5-60-BE-0013B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5041 | PS5-60-BE-0013B-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5042 | PS5-60-BE-0013B-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5043 | PS5-60-BE-0013B-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5044 | PS5-60-BE-0014A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0421 | 2026-07-18 | OPEN | Bertus Wikael | Testing
T-00233-5045 | PS5-60-BE-0014A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5046 | PS5-60-BE-0014A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5047 | PS5-60-BE-0014A-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5048 | PS5-60-BE-0014A-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5049 | PS5-60-BE-0014A-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5050 | PS5-60-BE-0014B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5051 | PS5-60-BE-0014B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5052 | PS5-60-BE-0014B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5053 | PS5-60-BE-0014B-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5054 | PS5-60-BE-0014B-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5055 | PS5-60-BE-0014B-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5056 | PS5-60-BE-0015A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5057 | PS5-60-BE-0015A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5058 | PS5-60-BE-0015A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5059 | PS5-60-BE-0015A-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5060 | PS5-60-BE-0015A-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5061 | PS5-60-BE-0015A-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5062 | PS5-60-BE-0015B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5063 | PS5-60-BE-0015B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0421 | 2026-07-18 | OPEN | Bertus Wikael | Testing
T-00233-5064 | PS5-60-BE-0015B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5065 | PS5-60-BE-0015B-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5066 | PS5-60-BE-0015B-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5067 | PS5-60-BE-0015B-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5068 | PS5-60-BE-0016A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5069 | PS5-60-BE-0016A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5070 | PS5-60-BE-0016A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5071 | PS5-60-BE-0016A-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5072 | PS5-60-BE-0016A-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5073 | PS5-60-BE-0016A-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5074 | PS5-60-BE-0016B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5075 | PS5-60-BE-0016B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5076 | PS5-60-BE-0016B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5077 | PS5-60-BE-0016B-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5078 | PS5-60-BE-0016B-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5079 | PS5-60-BE-0016B-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5080 | PS5-60-BE-0017A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5081 | PS5-60-BE-0017A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5082 | PS5-60-BE-0017A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5083 | PS5-60-BE-0017A-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G
T-00233-5084 | PS5-60-BE-0017A-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0416 | 2026-07-15 | Waiting for Signature | Ferdinand | Testing
T-00233-5085 | PS5-60-BE-0017A-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5086 | PS5-60-BE-0017B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5087 | PS5-60-BE-0017B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5088 | PS5-60-BE-0017B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5089 | PS5-60-BE-0017B-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5090 | PS5-60-BE-0017B-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0421 | 2026-07-18 | OPEN | Bertus Wikael | Testing
T-00233-5091 | PS5-60-BE-0017B-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0421 | 2026-07-18 | OPEN | Bertus Wikael | Testing
T-00233-5092 | PS5-60-BE-0021A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021A |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
T-00233-5093 | PS5-60-BE-0021B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021B |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5094 | PS5-60-BE-0024A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A |  | PS5-60-35 - Injector Tip Cooling Module A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5095 | PS5-60-BE-0024A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A |  | PS5-60-35 - Injector Tip Cooling Module A | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5096 | PS5-60-BE-0024B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B |  | PS5-60-36 - Injector Tip Cooling Module B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5097 | PS5-60-BE-0024B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B |  | PS5-60-36 - Injector Tip Cooling Module B | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5098 | PS5-60-BE-0024C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C |  | PS5-60-37 - Injector Tip Cooling Module C | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5099 | PS5-60-BE-0024C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C |  | PS5-60-37 - Injector Tip Cooling Module C | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5100 | PS5-60-BE-0024D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D |  | PS5-60-38 - Injector Tip Cooling Module D | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5101 | PS5-60-BE-0024D-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D |  | PS5-60-38 - Injector Tip Cooling Module D | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5102 | PS5-60-BE-0024E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0024E |  | PS5-60-39 - Injector Tip Cooling Module E | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5103 | PS5-60-BE-0024E-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0024E |  | PS5-60-39 - Injector Tip Cooling Module E | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5104 | PS5-60-BE-0024F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0024F |  | PS5-60-40 - Injector Tip Cooling Module F | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5105 | PS5-60-BE-0024F-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0024F |  | PS5-60-40 - Injector Tip Cooling Module F | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5106 | PS5-60-BE-0024G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0024G |  | PS5-60-41 - Injector Tip Cooling Module G | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5107 | PS5-60-BE-0024G-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0024G |  | PS5-60-41 - Injector Tip Cooling Module G | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-5108 | PS5-60-BE-0025A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0025A |  | PS5-60-35 - Injector Tip Cooling Module A | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | Testing
T-00233-5109 | PS5-60-BE-0025B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0025B |  | PS5-60-36 - Injector Tip Cooling Module B | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | Testing
T-00233-5110 | PS5-60-BE-0025C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0025C |  | PS5-60-37 - Injector Tip Cooling Module C | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5111 | PS5-60-BE-0025D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0025D |  | PS5-60-38 - Injector Tip Cooling Module D | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5112 | PS5-60-BE-0025E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0025E |  | PS5-60-39 - Injector Tip Cooling Module E | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5113 | PS5-60-BE-0025F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0025F |  | PS5-60-40 - Injector Tip Cooling Module F | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00233-5114 | PS5-60-BE-0025G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0025G |  | PS5-60-41 - Injector Tip Cooling Module G | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5115 | PS5-60-BE-0026A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A |  | PS5-60-70 - Engine A Cooling system | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5116 | PS5-60-BE-0026A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A |  | PS5-60-70 - Engine A Cooling system | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5117 | PS5-60-BE-0026B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B |  | PS5-60-71 - Engine B Cooling system | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5118 | PS5-60-BE-0026B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B |  | PS5-60-71 - Engine B Cooling system | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5119 | PS5-60-BE-0026C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C |  | PS5-60-72 - Engine C Cooling system | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5120 | PS5-60-BE-0026C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C |  | PS5-60-72 - Engine C Cooling system | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5121 | PS5-60-BE-0026D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D |  | PS5-60-73 - Engine D Cooling system | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5122 | PS5-60-BE-0026D-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D |  | PS5-60-73 - Engine D Cooling system | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5123 | PS5-60-BE-0026E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0026E |  | PS5-60-74 - Engine E Cooling system | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5124 | PS5-60-BE-0026E-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0026E |  | PS5-60-74 - Engine E Cooling system | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5125 | PS5-60-BE-0026F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0026F |  | PS5-60-75 - Engine F Cooling system | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5126 | PS5-60-BE-0026F-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0026F |  | PS5-60-75 - Engine F Cooling system | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-5127 | PS5-60-BE-0026G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0026G |  | PS5-60-76 - Engine G Cooling system | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5128 | PS5-60-BE-0026G-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0026G |  | PS5-60-76 - Engine G Cooling system | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5129 | PS5-60-BI-0005A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0005A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
| PS5-08-01FB-0902-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
| PS5-08-01FB-0904-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
| PS5-08-01FB-1007-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
| PS5-08-01FB-1010-CS01 | TPX09 - LV power cable | #N/A | E
| PS5-08-01FB-1105-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-5130 | PS5-60-BI-0005B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0005B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-5131 | PS5-60-BI-0005C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0005C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-5132 | PS5-60-BI-0005D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0005D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-5133 | PS5-60-BI-0005E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0005E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-5134 | PS5-60-BI-0005F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0005F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-5135 | PS5-60-BI-0005G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0005G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-5136 | PS5-60-BI-0015A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
T-00233-5137 | PS5-60-BI-0015A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5138 | PS5-60-BI-0015A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5139 | PS5-60-BI-0015B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
T-00233-5140 | PS5-60-BI-0015B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5141 | PS5-60-BI-0015B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5142 | PS5-60-BI-0015C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5143 | PS5-60-BI-0015C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5144 | PS5-60-BI-0015C-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5145 | PS5-60-BI-0015D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
T-00233-5146 | PS5-60-BI-0015D-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5147 | PS5-60-BI-0015D-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | testing
T-00233-5148 | PS5-60-BI-0015E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5149 | PS5-60-BI-0015E-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5150 | PS5-60-BI-0015E-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5151 | PS5-60-BI-0015F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5152 | PS5-60-BI-0015F-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5153 | PS5-60-BI-0015F-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5154 | PS5-60-BI-0015G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G |  | PS5-60-19 - Power Generation Package G
T-00233-5155 | PS5-60-BI-0015G-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-5156 | PS5-60-BI-0015G-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-5157 | PS5-60-DD-62800A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-DD-62800A |  | PS5-60-01 - Power Generation Package A
T-00233-5159 | PS5-60-DD-62800C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-DD-62800C |  | PS5-60-07 - Power Generation Package C
T-00233-5161 | PS5-60-DD-62800E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-DD-62800E |  | PS5-60-13 - Power Generation Package E
T-00233-5163 | PS5-60-DD-62800G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-DD-62800G |  | PS5-60-19 - Power Generation Package G
T-00233-5166 | PS5-60-IE-0002A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5167 | PS5-60-IE-0002A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5168 | PS5-60-IE-0002A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5169 | PS5-60-IE-0002B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
| PS5-08-52BT-0131-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0002-CD43 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0002-CD44 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD61 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD62 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD63 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD64 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD65 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD67 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0003-CD02 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0003-CD03 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0003-CD04 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD66 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0276 | 2026-05-19 | Accepted | Bertus Wikael | Testing
T-00233-5170 | PS5-60-IE-0002B-CL02 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
T-00233-5171 | PS5-60-IE-0002B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5172 | PS5-60-IE-0002C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00233-5173 | PS5-60-IE-0002C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5174 | PS5-60-IE-0002C-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0421 | 2026-07-18 | OPEN | Bertus Wikael | Testing
T-00233-5175 | PS5-60-IE-0002D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5176 | PS5-60-IE-0002D-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5177 | PS5-60-IE-0002D-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D
T-00233-5178 | PS5-60-IE-0002E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5179 | PS5-60-IE-0002E-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5180 | PS5-60-IE-0002E-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E
T-00233-5181 | PS5-60-IE-0002F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5182 | PS5-60-IE-0002F-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0421 | 2026-07-18 | OPEN | Bertus Wikael | Testing
T-00233-5183 | PS5-60-IE-0002F-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F
T-00233-5184 | PS5-60-IE-0002G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-5185 | PS5-60-IE-0002G-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5186 | PS5-60-IE-0002G-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G
T-00233-5187 | PS5-60-IE-0003A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5188 | PS5-60-IE-0003A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5189 | PS5-60-IE-0003B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5190 | PS5-60-IE-0003B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5191 | PS5-60-IE-0003C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5192 | PS5-60-IE-0003C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00233-5193 | PS5-60-IE-0003D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00233-5194 | PS5-60-IE-0003D-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5195 | PS5-60-IE-0003E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5196 | PS5-60-IE-0003E-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5197 | PS5-60-IE-0003F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5198 | PS5-60-IE-0003F-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5199 | PS5-60-IE-0003G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5200 | PS5-60-IE-0003G-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5201 | PS5-60-IE-0004-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5202 | PS5-60-IE-0004-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5204 | PS5-60-IH-0001A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00233-5205 | PS5-60-IH-0001A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00233-5206 | PS5-60-IH-0001A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00233-5207 | PS5-60-IH-0001A-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00233-5208 | PS5-60-IH-0001A-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5209 | PS5-60-IH-0001A-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5211 | PS5-60-IH-0001B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00233-5212 | PS5-60-IH-0001B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00233-5213 | PS5-60-IH-0001B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00233-5214 | PS5-60-IH-0001B-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing | CPP-RFI-68-331-06-0435 | ACCEPTED WITH COMMENT | 2026-07-29 | Bertus Wikael
T-00233-5215 | PS5-60-IH-0001B-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5216 | PS5-60-IH-0001B-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5218 | PS5-60-IH-0001C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5219 | PS5-60-IH-0001C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5220 | PS5-60-IH-0001C-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5221 | PS5-60-IH-0001C-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5222 | PS5-60-IH-0001C-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0427 | 2026-07-21 | Accepted | Bertus Wikael | Testing
T-00233-5223 | PS5-60-IH-0001C-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5225 | PS5-60-IH-0001D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5226 | PS5-60-IH-0001D-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5227 | PS5-60-IH-0001D-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5228 | PS5-60-IH-0001D-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0411 | 2026-07-13 | Accepted | Bertus Wikael | Testing
T-00233-5229 | PS5-60-IH-0001D-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5230 | PS5-60-IH-0001D-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5232 | PS5-60-IH-0001E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5233 | PS5-60-IH-0001E-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5234 | PS5-60-IH-0001E-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5235 | PS5-60-IH-0001E-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00233-5236 | PS5-60-IH-0001E-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5237 | PS5-60-IH-0001E-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5239 | PS5-60-IH-0001F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00233-5240 | PS5-60-IH-0001F-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00233-5241 | PS5-60-IH-0001F-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00233-5242 | PS5-60-IH-0001F-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00233-5243 | PS5-60-IH-0001F-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00233-5244 | PS5-60-IH-0001F-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5246 | PS5-60-IH-0001G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00233-5247 | PS5-60-IH-0001G-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00233-5248 | PS5-60-IH-0001G-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00233-5249 | PS5-60-IH-0001G-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-5250 | PS5-60-IH-0001G-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5251 | PS5-60-IH-0001G-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00233-5254 | PS5-60-IH-0002-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5255 | PS5-60-IH-0002-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5256 | PS5-60-IH-0002-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5257 | PS5-60-IH-0002-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5258 | PS5-60-IH-0002-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5259 | PS5-60-IH-0002-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5260 | PS5-60-IH-0002-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5261 | PS5-60-IH-0002-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5262 | PS5-60-IH-0002-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5263 | PS5-60-IH-0002-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5264 | PS5-60-IN-0001A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5265 | PS5-60-IN-0001B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5266 | PS5-60-IN-0001C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5267 | PS5-60-IN-0001D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5268 | PS5-60-IN-0001E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5269 | PS5-60-IN-0001F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5270 | PS5-60-IN-0001G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5271 | PS5-60-IN-0002A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5272 | PS5-60-IN-0002A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5273 | PS5-60-IN-0002A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5274 | PS5-60-IN-0002B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5275 | PS5-60-IN-0002B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5276 | PS5-60-IN-0002B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5277 | PS5-60-IN-0002C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00233-5278 | PS5-60-IN-0002C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00233-5279 | PS5-60-IN-0002C-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00233-5280 | PS5-60-IN-0002D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5281 | PS5-60-IN-0002D-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5282 | PS5-60-IN-0002D-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5283 | PS5-60-IN-0002E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00233-5284 | PS5-60-IN-0002E-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5285 | PS5-60-IN-0002E-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5286 | PS5-60-IN-0002F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00233-5287 | PS5-60-IN-0002F-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5288 | PS5-60-IN-0002F-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPP-RFI-68-33/1-07-0421 | 2026-07-18 | OPEN | Bertus Wikael | Testing
T-00233-5289 | PS5-60-IN-0002G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00233-5290 | PS5-60-IN-0002G-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPP-RFI-68-33/1-07-0421 | 2026-07-18 | OPEN | Bertus Wikael | Testing
T-00233-5291 | PS5-60-IN-0002G-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5292 | PS5-60-IWK-0001A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001A |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
T-00233-5293 | PS5-60-IWK-0001A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001A |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
T-00233-5294 | PS5-60-IWK-0001B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001B |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5295 | PS5-60-IWK-0001B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001B |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5296 | PS5-60-IWK-0001C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001C |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5297 | PS5-60-IWK-0001C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001C |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5298 | PS5-60-LA-0002A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5299 | PS5-60-LA-0002A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5300 | PS5-60-LA-0002B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5301 | PS5-60-LA-0002B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5302 | PS5-60-LA-0002C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5303 | PS5-60-LA-0002C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5304 | PS5-60-LA-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0003 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5305 | PS5-60-LA-0003-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0003 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5306 | PS5-60-MOV-0005-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-60-MOV-0005 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing
| PS5-08-01FB-0913-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00233-5307 | PS5-60-MOV-0006-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-60-MOV-0006 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00233-5308 | PS5-60-MOV-0011-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-60-MOV-0011 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00233-5309 | PS5-60-MOV-0012-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-60-MOV-0012 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00233-5310 | PS5-60-SEA-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5311 | PS5-60-SEA-0001-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5312 | PS5-60-VS-9100A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-60-VS-9100A |  | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5313 | PS5-60-VS-9100B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-60-VS-9100B |  | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5314 | PS5-60-VS-9100C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-60-VS-9100C |  | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5315 | PS5-60-VS-9100D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-60-VS-9100D |  | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5316 | PS5-60-VS-9100E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-60-VS-9100E |  | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5317 | PS5-60-VS-9100F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-60-VS-9100F |  | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-5318 | PS5-60-VS-9100G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-60-VS-9100G |  | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
| PS5-05-IG-0004-CL01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-05-IG-0006-CL01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-50-IE-0001-CL01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-50-IE-0002-CL01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
T-00233-5319 | PS5-61-BI-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001A TO PS5-61-BI-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL44 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-5320 | PS5-61-BI-0002-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001B TO PS5-61-BI-0002 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-5321 | PS5-61-BI-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001C TO PS5-61-BI-0003 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
T-00233-5322 | PS5-61-BI-0004-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001D TO PS5-61-BI-0004 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
T-00233-5323 | PS5-61-BI-0005-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001E TO PS5-61-BI-0005 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
T-00233-5324 | PS5-61-BI-0006-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001F TO PS5-61-BI-0006 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
T-00233-5325 | PS5-61-BI-0007-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0001G TO PS5-61-BI-0007 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5335 | PS5-61-IG-0015-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IG-0015 |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5336 | PS5-61-IG-0016-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IG-0016 |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00233-5343 | PS5-61-IH-0004-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5344 | PS5-61-IH-0004-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5345 | PS5-61-IH-0004-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5346 | PS5-61-IH-0004-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5347 | PS5-61-IH-0004-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5348 | PS5-61-IH-0004-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5349 | PS5-61-IH-0004-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-5350 | PS5-61-IH-0004-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5351 | PS5-61-IH-0004-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5352 | PS5-61-IH-0004-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5353 | PS5-61-IH-0004-CL11 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5354 | PS5-61-IH-0004-CL12 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5355 | PS5-61-IH-0004-CL13 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5356 | PS5-61-IH-0004-CL14 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5357 | PS5-61-IH-0004-CL15 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00233-5358 | PS5-61-IH-0004-CL16 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00233-5359 | PS5-61-IH-0004-CL17 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5360 | PS5-61-IH-0004-CL18 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00233-5361 | PS5-61-IH-0004-CL19 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00233-5362 | PS5-61-IH-0004-CL20 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00233-5363 | PS5-61-IH-0004-CL21 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00233-5364 | PS5-61-IH-0004-CL22 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5425 | PS5-61-IK-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-5426 | PS5-61-IK-0003-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-5427 | PS5-61-IK-0003-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003)
T-00233-5428 | PS5-61-IK-0003-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5429 | PS5-61-IK-0003-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5430 | PS5-61-IK-0003-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5431 | PS5-61-IK-0003-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0257 | 2026-05-09 | Accepted | Ferdinand | TESTING
T-00233-5432 | PS5-61-IK-0003-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0257 | 2026-05-09 | Accepted | Ferdinand | TESTING
T-00233-5433 | PS5-61-IK-0003-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0257 | 2026-05-09 | Accepted | Ferdinand | TESTING
T-00233-5434 | PS5-61-IK-0003-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0257 | 2026-05-09 | Accepted | Ferdinand | TESTING
T-00233-5435 | PS5-61-IK-0003-CL11 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0257 | 2026-05-09 | Accepted | Ferdinand | TESTING
T-00233-5436 | PS5-61-IK-0003-CL12 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0257 | 2026-05-09 | Accepted | Ferdinand | TESTING
T-00233-5437 | PS5-61-IK-0003-CL13 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5438 | PS5-61-IK-0003-CL14 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5439 | PS5-61-IK-0003-CL15 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003)
T-00233-5440 | PS5-61-IK-0003-CL16 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5441 | PS5-61-IK-0003-CL17 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5442 | PS5-61-IK-0003-CL18 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5443 | PS5-61-IK-0003-CL19 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5444 | PS5-61-IK-0003-CL20 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5445 | PS5-61-IK-0003-CL21 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5446 | PS5-61-IK-0003-CL22 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5447 | PS5-61-IK-0003-CL23 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5448 | PS5-61-IK-0003-CL24 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5449 | PS5-61-IK-0003-CL25 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
T-00233-5450 | PS5-61-IK-0003-CL26 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
T-00233-5451 | PS5-61-IK-0003-CL27 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
T-00233-5452 | PS5-61-IK-0003-CL28 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
T-00233-5453 | PS5-61-IK-0003-CL29 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
T-00233-5454 | PS5-61-IK-0003-CL30 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5455 | PS5-61-IK-0003-CL31 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5456 | PS5-61-IK-0003-CL32 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5457 | PS5-61-IK-0003-CL33 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5458 | PS5-61-IK-0003-CL34 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5459 | PS5-61-IK-0003-CL35 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IV-0001A-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IV-0001B-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IV-0006B-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5460 | PS5-61-IK-0003-CL36 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5461 | PS5-61-IK-0003-CL37 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL19 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL20 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL21 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL22 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL23 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL24 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL25 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL26 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL27 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL28 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL29 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL30 | TPX09 - LV power cable | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5462 | PS5-61-IK-0003-CL38 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5463 | PS5-61-IK-0003-CL39 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5464 | PS5-61-IK-0003-CL40 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5465 | PS5-61-IK-0003-CL41 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL02 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL03 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL04 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL05 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL06 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL07 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL08 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| 8PS5-61-IK-0001-CL09 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL10 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL11 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL12 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL13 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL14 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL15 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL16 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL17 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
| PS5-61-IK-0001-CL18 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5466 | PS5-61-IK-0003-CL42 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5467 | PS5-61-IK-0003-CL43 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5468 | PS5-61-IK-0003-CL44 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
T-00233-5469 | PS5-61-IK-0003-CL45 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5470 | PS5-61-IK-0003-CL46 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5471 | PS5-61-IK-0003-CL47 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5472 | PS5-61-IK-0003-CL48 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5473 | PS5-61-IK-0003-CL49 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5474 | PS5-61-IK-0003-CL50 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5475 | PS5-61-IK-0003-CL51 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5476 | PS5-61-IK-0003-CL52 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5477 | PS5-61-IK-0003-CL53 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5478 | PS5-61-IK-0003-CL54 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0251 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5479 | PS5-61-IK-0003-CL55 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0253 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5480 | PS5-61-IK-0003-CL56 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0253 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-25-UD-3100A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IDH-3100A-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IDH-3100A-CD02 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IDH-3100B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IDH-3100C-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IDH-3100C-CD02 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IG-0012A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IG-0012B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IG-0012C-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD24 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD25 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IJ-0001-CD26 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IV-0006A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
| PS5-61-IV-0006C-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
T-00233-5481 | PS5-61-IK-0003-CL57 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
T-00233-5482 | PS5-61-IK-0003-CL58 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
T-00233-5483 | PS5-61-IK-0003-CL59 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
T-00233-5484 | PS5-61-IK-0003-CL60 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-BE-0001 TO PS5-61-IK-0003 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-331-07-0292 | 2026-05-19 | Accepted | Bertus Wikael | Testing
T-00233-5485 | PS5-61-IK-0003-CL61 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
T-00233-5486 | PS5-61-IK-0003-CL62 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5487 | PS5-05-IG-0002-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IG-0002 |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00233-5492 | PS5-61-IK-0006-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5493 | PS5-61-IK-0006-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5494 | PS5-61-IK-0006-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5495 | PS5-61-IK-0006-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5496 | PS5-61-IK-0006-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5497 | PS5-61-IK-0006-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5498 | PS5-61-IK-0006-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5499 | PS5-61-IK-0006-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5500 | PS5-61-IK-0006-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0257 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5501 | PS5-61-IK-0006-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5502 | PS5-61-IK-0006-CL11 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5503 | PS5-61-IK-0006-CL12 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5504 | PS5-61-IK-0006-CL13 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5505 | PS5-61-IK-0006-CL14 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5506 | PS5-61-IK-0006-CL15 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5507 | PS5-61-IK-0006-CL16 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5508 | PS5-61-IK-0006-CL17 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5509 | PS5-61-IK-0006-CL18 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5510 | PS5-61-IK-0006-CL19 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-07-0247 | 2026-05-14 | Accepted | Bertus Wikael | TESTING
T-00233-5511 | PS5-61-IK-0006-CL20 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-07-0247 | 2026-05-14 | Accepted | Bertus Wikael | TESTING
T-00233-5512 | PS5-61-IK-0006-CL21 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-07-0247 | 2026-05-14 | Accepted | Bertus Wikael | TESTING
T-00233-5513 | PS5-61-IK-0006-CL22 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-07-0247 | 2026-05-14 | Accepted | Bertus Wikael | TESTING
T-00233-5514 | PS5-61-IK-0006-CL23 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
T-00233-5515 | PS5-61-IK-0006-CL24 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
T-00233-5516 | PS5-61-IK-0006-CL25 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IG-0006-CD01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IG-0006-CL01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IG-0007-CD01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IG-0007-CL01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IG-0042-CD01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IG-0042-CL01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IG-0043-CD01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IJ-0001-CD27 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IJ-0001-CD28 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IJ-0001-CD29 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IJ-0001-CD30 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IJ-0001-CD36 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IJ-0001-CD41 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IK-0001-CL31 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IK-0001-CL32 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IK-0001-CL37 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IK-0001-CL38 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IK-0001-CL39 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IK-0001-CL40 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IK-0001-CL41 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IK-0001-CL42 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-61-IK-0001-CL43 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-DM-3300-CL01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003A-CD06 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
| PS5-60-IE-0003A-CD08 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
| PS5-60-IE-0003A-CD12 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
| PS5-60-IE-0003B-CD06 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003B-CD08 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003B-CD12 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003C-CD06 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003C-CD08 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003C-CD12 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003D-CD06 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003D-CD08 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003D-CD12 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003E-CD12 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003F-CD06 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003F-CD08 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003G-CD08 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0003G-CD12 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0004-CD01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IE-0004-CD02 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
| PS5-60-IES-3300-CD01 | TPX09 - LV power cable | #N/A |  |  |  |  | CPP-RFI-68-33/1-07-0271 | 2026-05-16 | Accepted | Ferdinand | Testing
T-00233-5517 | PS5-61-IK-0006-CL26 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-5518 | PS5-61-IK-0006-CL27 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-5519 | PS5-61-IK-0006-CL28 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-07-0268 | 2026-05-09 | Accepted | Bertus Wikael | Testing
T-00233-5520 | PS5-61-IK-0006-CL29 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-5521 | PS5-61-IK-0006-CL30 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0419 | 2026-07-16 | Accepted | Bertus Wikael | TESTING
T-00233-5522 | PS5-61-IK-0006-CL31 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-5523 | PS5-61-IK-0006-CL32 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-5524 | PS5-61-IK-0006-CL33 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-07-0249 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5525 | PS5-61-IK-0006-CL34 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-07-0249 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5532 | PS5-61-IU-3100A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-61-IU-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
T-00233-5533 | PS5-61-IU-3100B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-61-IU-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
T-00233-5534 | PS5-61-IU-3100C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-61-IU-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
T-00233-5537 | PS5-61-IV-0002A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IV-0002A |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5538 | PS5-61-IV-0002B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IV-0002B |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5542 | PS5-61-IV-0007A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IV-0007A |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5543 | PS5-61-IV-0007B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0016 TO PS5-61-IV-0007B |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-07-0265 | 2026-05-14 | Accepted | Ferdinand | TESTING
T-00233-5546 | PS5-62-IE-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0004 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00233-5547 | PS5-62-IE-0002-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-5561 | PS5-71-FCV-0018-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-FCV-0018 |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
T-00233-5562 | PS5-71-FCV-0019-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-FCV-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-5563 | PS5-71-FCV-0020-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-FCV-0020 |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-5567 | PS5-71-HE-2200-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-71-HE-2200 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
| PS5-28-DM-3600A-CL02 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
| PS5-28-IES-3700B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
| PS5-05-IG-0004-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
| PS5-05-IG-0006-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
| PS5-28-DM-3900B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
| PS5-53-IN-0001-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
| PS5-60-IE-0003G-CD06 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
| PS5-61-IG-0014-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
| PS5-61-IG-0014-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
| PS5-61-IG-0015-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
| PS5-62-IE-0002-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
T-00233-5569 | PS5-71-HE-2300-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-71-HE-2300 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-33/1-07-0307 | 30-May-2026 | Accepted | Ferdinand | TESTING
T-00233-5570 | PS5-71-HE-2400A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IE-0001 TO PS5-71-HE-2400A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-331-07-0247 | 2026-05-05 | Accepted | Bertus Wikael | TESTING
T-00233-5571 | PS5-71-HE-2400A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IE-0001 TO PS5-71-HE-2400A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-331-07-0247 | 2026-05-05 | Accepted | Bertus Wikael | TESTING
T-00233-5572 | PS5-71-HE-2400A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IE-0001 TO PS5-71-HE-2400A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5573 | PS5-71-HE-2400A-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IE-0001 TO PS5-71-HE-2400A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5574 | PS5-71-HE-2400B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IE-0002 TO PS5-71-HE-2400B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5575 | PS5-71-HE-2400B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IE-0002 TO PS5-71-HE-2400B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5576 | PS5-71-HE-2400B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IE-0002 TO PS5-71-HE-2400B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5577 | PS5-71-HE-2400B-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IE-0002 TO PS5-71-HE-2400B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5578 | PS5-71-IN-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-5579 | PS5-71-IN-0001-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-5580 | PS5-71-IN-0001-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-5581 | PS5-71-IN-0002-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5582 | PS5-71-IN-0002-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5583 | PS5-71-IN-0002-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-5584 | PS5-71-IN-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5585 | PS5-71-IN-0003-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-5586 | PS5-71-IN-0003-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-331-07-0310 | 2026-06-04 | Accepted | Ferdinand | TESTING
T-00233-5587 | PS5-71-IN-0004A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5588 | PS5-71-IN-0004A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-331-07-0408 | 2026-07-09 | Accepted | Bertus Wikael | Testing
T-00233-5589 | PS5-71-IN-0004A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-5590 | PS5-71-IN-0004B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5591 | PS5-71-IN-0004B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-5592 | PS5-71-IN-0004B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-5593 | PS5-71-LCV-4101-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-LCV-4101 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-5594 | PS5-71-MOV-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0001 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5595 | PS5-71-MOV-0002-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0002 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00233-5596 | PS5-71-MOV-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5597 | PS5-71-MOV-0004-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0004 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
T-00233-5598 | PS5-71-MOV-0007-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0007 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00233-5599 | PS5-71-MOV-0008-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0008 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00233-5600 | PS5-71-MOV-0009-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0009 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5601 | PS5-71-MOV-0010-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0010 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5602 | PS5-71-SDV-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-5603 | PS5-71-SDV-0022-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank
T-00233-5604 | PS5-71-SDV-0029-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5605 | PS5-71-SDV-0039-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-5606 | PS5-71-UZ-6200-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0014 TO PS5-71-UZ-6200 |  | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5607 | PS5-71-XV-0089-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-5608 | PS5-71-XV-0090-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-5609 | PS5-71-XV-0091-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
T-00233-5610 | PS5-71-XV-0092-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0042 TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
| PS5-71-DM-3100A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-71-DM-3100B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-71-DM-3200-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-71-DM-3300A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-71-DM-3300B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-71-DM-3400A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-71-DM-3400B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-71-DM-3500A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
| PS5-71-DM-3500B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
| PS5-71-FIT-0011B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-71-HE-2200-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-71-HE-2300-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-71-IES-3100A-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
| PS5-71-IES-3100B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
| PS5-71-IES-3200-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
| PS5-71-IES-3300A-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
| PS5-71-IES-3300B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
| PS5-71-IES-3400A-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
| PS5-71-IES-3400B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
| PS5-71-IES-3500A-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
| PS5-71-IES-3500B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00233-5612 | PS5-74-LB-5101-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004A TO PS5-74-LB-5101 |  | PS5-74-02 - N2 Generation Skid (UCP) | CPP-RFI-68-331-07-0261 | 2026-05-14 | Accepted | Bertus Wikael | Testing
T-00233-5613 | PS5-74-LB-5101-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0004B TO PS5-74-LB-5101 |  | PS5-74-02 - N2 Generation Skid (UCP) | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-74-IG-5101-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-75-DM-3100B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-75-DM-3200B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-75-IES-3100B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-75-ISO-0001-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-75-ISO-0002-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-79-IV-0001-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-79-IV-0002-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-79-IV-0003-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-79-IV-0004-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-79-IV-0005-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-79-IV-0006-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-79-IV-0007-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-79-IV-0008-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-79-IV-0009-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
| PS5-79-IV-0010-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0303 | 27-May-2026 | Accepted | Ferdinand | Testing
T-00233-5620 | PS5-75-MOV-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0043 TO PS5-75-MOV-0001 |  | PS5-28-07 - Open Drains (OD2) | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
T-00233-5621 | PS5-75-UI-6200-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0001A TO PS5-75-UI-6200 |  | PS5-75-01 - DRA Injection Package
T-00233-5622 | PS5-75-UI-6200-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-06-IG-0001B TO PS5-75-UI-6200 |  | PS5-75-01 - DRA Injection Package
T-00233-5623 | PS5-78-JC-9100A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-78-JC-9100A |  | PS5-78-01 - Lifting and handling equipment
T-00233-5624 | PS5-78-JC-9100B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-78-JC-9100B |  | PS5-78-01 - Lifting and handling equipment | CPP-RFI-68-33/1-07-0427 | 2026-07-21 | Accepted | Bertus Wikael | Testing
T-00233-5625 | PS5-78-JC-9100C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-78-JC-9100C |  | PS5-78-01 - Lifting and handling equipment | CPP-RFI-68-33/1-07-0427 | 2026-07-21 | Accepted | Bertus Wikael | Testing
T-00233-5626 | PS5-78-JC-9100D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-78-JC-9100D |  | PS5-78-01 - Lifting and handling equipment | CPP-RFI-68-33/1-07-0427 | 2026-07-21 | Accepted | Bertus Wikael | Testing
T-00233-5640 | PS5-87-IRF-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-87-IRF-0001 |  | PS5-53-01 - Utility Water / Storage Tank | CPP-RFI-68-331-07-0267 | 2026-05-13 | Accepted | Bertus Wikael | Testing
T-00233-5641 | PS5-87-IRF-0002-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-87-IRF-0002 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5642 | PS5-87-IRF-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0006 TO PS5-87-IRF-0003 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-5643 | PS5-87-IRF-0004-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IG-0007 TO PS5-87-IRF-0004 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-33/1-07-0290 | 2026-05-21 | Accepted | Ferdinand | Testing
T-00233-8829 | PS5-79-IG-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0001 TO PS5-79-IG-0001 |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00233-8830 | PS5-79-IG-0002-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0002 TO PS5-79-IG-0002 |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00233-8831 | PS5-79-IG-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0003 TO PS5-79-IG-0003 |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00233-8832 | PS5-79-IG-0004-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0004 TO PS5-79-IG-0004 |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00233-8833 | PS5-79-IG-0005-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0005 TO PS5-79-IG-0005 |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00233-8834 | PS5-79-IG-0006-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0006 TO PS5-79-IG-0006 |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00233-8835 | PS5-79-IG-0007-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0007 TO PS5-79-IG-0007 |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00233-8836 | PS5-79-IG-0008-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0008 TO PS5-79-IG-0008 |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00233-8837 | PS5-79-IG-0009-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0009 TO PS5-79-IG-0009 |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00233-8838 | PS5-79-IG-0010-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0010 TO PS5-79-IG-0010 |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00233-8839 | PS5-79-IG-0011-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0011 TO PS5-79-IG-0011 |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00233-8840 | PS5-79-IG-0012-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-79-IV-0012 TO PS5-79-IG-0012 |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00233-9120 | PS5-02-SWSI-0001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-02-SWSI-0001 |  | PS5-02-01 - Miscellaneous Safety equipment | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
| PS5-61-IJ-0001-CD37 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
| PS5-08-52BT-0137-CS01 | TPX09 - LV power cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0321 |  | Accepted | Ferdinand | testing
T-00233-9121 | PS5-02-SWSI-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0006 TO PS5-02-SWSI-0003 |  | PS5-02-01 - Miscellaneous Safety equipment | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00233-9122 | PS5-06-GU-0005-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0007 TO PS5-06-GU-0005 |  | PS5-06-04 - AC UPS - Guard House
T-00233-9128 | PS5-09-LB-7001-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-05-IG-0007 TO PS5-09-LB-7001 |  | PS5-09-02 - HVAC for Guard House
T-00233-9131 | PS5-60-BE-0007A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-9132 | PS5-60-BE-0007B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00233-9133 | PS5-60-BE-0007C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-9134 | PS5-60-BE-0007D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00233-9135 | PS5-60-BE-0007E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-9136 | PS5-60-BE-0007F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-9137 | PS5-60-BE-0007G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-9138 | PS5-60-BE-0027A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0027A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9139 | PS5-60-BE-0027B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0027B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
T-00233-9140 | PS5-60-BE-0027C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0027C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00233-9141 | PS5-60-BE-0027D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0027D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00233-9142 | PS5-60-BE-0027E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0027E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00233-9143 | PS5-60-BE-0027F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0027F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00233-9144 | PS5-60-BE-0027G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0027G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00233-9145 | PS5-60-BE-0028A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0028A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9146 | PS5-60-BE-0028B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0028B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9147 | PS5-60-BE-0028C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0028C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00233-9148 | PS5-60-BE-0028D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0028D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D
T-00233-9149 | PS5-60-BE-0028E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0028E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-9150 | PS5-60-BE-0028F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0028F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-9151 | PS5-60-BE-0028G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0028G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-9152 | PS5-60-BI-0006A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9153 | PS5-60-BI-0006A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00233-9154 | PS5-60-BI-0006A-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9155 | PS5-60-BI-0006A-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9156 | PS5-60-BI-0006A-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9157 | PS5-60-BI-0006A-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9158 | PS5-60-BI-0006A-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9159 | PS5-60-BI-0006A-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9160 | PS5-60-BI-0006A-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9161 | PS5-60-BI-0006A-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9162 | PS5-60-BI-0006A-CL11 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9163 | PS5-60-BI-0006B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9164 | PS5-60-BI-0006B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9165 | PS5-60-BI-0006B-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9166 | PS5-60-BI-0006B-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9167 | PS5-60-BI-0006B-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9168 | PS5-60-BI-0006B-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9169 | PS5-60-BI-0006B-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9170 | PS5-60-BI-0006B-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9171 | PS5-60-BI-0006B-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9172 | PS5-60-BI-0006B-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9173 | PS5-60-BI-0006B-CL11 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9174 | PS5-60-BI-0006C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-9175 | PS5-60-BI-0006C-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00233-9176 | PS5-60-BI-0006C-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-9177 | PS5-60-BI-0006C-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-9178 | PS5-60-BI-0006C-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-9179 | PS5-60-BI-0006C-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9180 | PS5-60-BI-0006C-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9181 | PS5-60-BI-0006C-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9182 | PS5-60-BI-0006C-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9183 | PS5-60-BI-0006C-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9184 | PS5-60-BI-0006C-CL11 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C
T-00233-9185 | PS5-60-BI-0006D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-9186 | PS5-60-BI-0006D-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-9187 | PS5-60-BI-0006D-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9188 | PS5-60-BI-0006D-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9189 | PS5-60-BI-0006D-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9190 | PS5-60-BI-0006D-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9191 | PS5-60-BI-0006D-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9192 | PS5-60-BI-0006D-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9193 | PS5-60-BI-0006D-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9194 | PS5-60-BI-0006D-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
T-00233-9195 | PS5-60-BI-0006D-CL11 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-9196 | PS5-60-BI-0006E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-9197 | PS5-60-BI-0006E-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00233-9198 | PS5-60-BI-0006E-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPP-RFI-68-33/1-07-0427 | 2026-07-21 | Accepted | Bertus Wikael | Testing
T-00233-9199 | PS5-60-BI-0006E-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00233-9200 | PS5-60-BI-0006E-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00233-9201 | PS5-60-BI-0006E-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00233-9202 | PS5-60-BI-0006E-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00233-9203 | PS5-60-BI-0006E-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPP-RFI-68-33/1-07-0420 | 2026-07-17 | Accepted | Bertus Wikael | TESTING
T-00233-9204 | PS5-60-BI-0006E-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00233-9205 | PS5-60-BI-0006E-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00233-9206 | PS5-60-BI-0006E-CL11 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-9207 | PS5-60-BI-0006F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00233-9208 | PS5-60-BI-0006F-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00233-9209 | PS5-60-BI-0006F-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00233-9210 | PS5-60-BI-0006F-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-9211 | PS5-60-BI-0006F-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00233-9212 | PS5-60-BI-0006F-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00233-9213 | PS5-60-BI-0006F-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00233-9214 | PS5-60-BI-0006F-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00233-9215 | PS5-60-BI-0006F-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00233-9216 | PS5-60-BI-0006F-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00233-9217 | PS5-60-BI-0006F-CL11 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-9218 | PS5-60-BI-0006G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00233-9219 | PS5-60-BI-0006G-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00233-9220 | PS5-60-BI-0006G-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00233-9221 | PS5-60-BI-0006G-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00233-9222 | PS5-60-BI-0006G-CL05 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00233-9223 | PS5-60-BI-0006G-CL06 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00233-9224 | PS5-60-BI-0006G-CL07 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00233-9225 | PS5-60-BI-0006G-CL08 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00233-9226 | PS5-60-BI-0006G-CL09 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00233-9227 | PS5-60-BI-0006G-CL10 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00233-9228 | PS5-60-BI-0006G-CL11 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-9229 | PS5-60-BI-0017A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9230 | PS5-60-BI-0017B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9231 | PS5-60-BI-0017C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-9232 | PS5-60-BI-0017D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-9233 | PS5-60-BI-0017E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0017E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-9234 | PS5-60-BI-0017F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0017F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00233-9235 | PS5-60-BI-0017G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0017G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPP-RFI-68-33/1-07-0412 | 2026-07-14 | Acceptable | Ferdinand | Testing
T-00233-9236 | PS5-60-EA-2900A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002A TO PS5-60-EA-2900A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
T-00233-9237 | PS5-60-EA-2900B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002B TO PS5-60-EA-2900B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
T-00233-9238 | PS5-60-EA-2900C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002C TO PS5-60-EA-2900C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-9239 | PS5-60-EA-2900D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002D TO PS5-60-EA-2900D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-9240 | PS5-60-EA-2900E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002E TO PS5-60-EA-2900E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-9241 | PS5-60-EA-2900F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002F TO PS5-60-EA-2900F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
| PS5-08-01FB-0905-CS01 | TPX09 | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
| PS5-08-01FB-0908-CS01 | TPX09 | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
| PS5-08-01FB-1006-CS01 | TPX09 | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
| PS5-08-01FB-1008-CS01 | TPX09 | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
| PS5-08-01FB-1013-CS01 | TPX09 | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
| PS5-08-12BT-1904-CS01 | TPX09 | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
| PS5-60-IE-0004-CD14 | TPX09 | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
| PS5-60-IE-0004-CD15 | TPX09 | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
| PS5-60-IE-0004-CD16 | TPX09 | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0405 | 09-July-2026 | Signed | Ferdinand | Testing
T-00233-9242 | PS5-60-EA-2900G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-60-IN-0002G TO PS5-60-EA-2900G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00233-9243 | PS5-61-IK-0005-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-61-IK-0005 |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00233-9244 | PS5-71-BE-0004-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-331-07-0400 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00233-9245 | PS5-71-BE-0004-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00233-9246 | PS5-71-BE-0004-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-331-07-0400 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00233-9247 | PS5-71-BI-0003-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-331-07-0400 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00233-9248 | PS5-71-BI-0003-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-33/1-07-0410 | 2026-07-11 | Accepted | Bertus Wikael | Testing
T-00233-9249 | PS5-71-BI-0003-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-9250 | PS5-71-BI-0003-CL04 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
| PS5-08-01FB-0906-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
| PS5-08-01FB-0909-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
| PS5-08-01FB-0910-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
| PS5-08-01FB-0911-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
| PS5-08-01FB-0912-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
| PS5-08-01FB-1002-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
| PS5-08-01FB-1003-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
| PS5-08-01FB-1004-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
| PS5-08-01FB-1005-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
| PS5-08-12BT-1903-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0409 | 11-July-2026 | Acceptable | Ferdinand | Testing
T-00233-9251 | PS5-71-BI-0004-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00233-9252 | PS5-71-BI-0005-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9253 | PS5-71-BI-0005-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9254 | PS5-71-BI-0005-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00233-9255 | PS5-71-BI-0006-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-33/1-07-0378 | 24-June-2026 | Acceptable | Ferdinand | Testing
T-00233-9680 | PS5-09-AHU-8111A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8111A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9681 | PS5-09-AHU-8111B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8111B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9682 | PS5-09-AHU-8211A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8211A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9683 | PS5-09-AHU-8211B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8211B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9684 | PS5-09-AHU-8311A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8311A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9685 | PS5-09-AHU-8311A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8311A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9686 | PS5-09-AHU-8311B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8311B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9687 | PS5-09-AHU-8311B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8311B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9688 | PS5-09-AHU-8321A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8321A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9689 | PS5-09-AHU-8321A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8321A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9690 | PS5-09-AHU-8321B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8321B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9691 | PS5-09-AHU-8321B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8321B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9692 | PS5-09-AHU-8331A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8331A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9693 | PS5-09-AHU-8331A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8331A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9694 | PS5-09-AHU-8331B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8331B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9695 | PS5-09-AHU-8331B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8331B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9696 | PS5-09-AHU-8341-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8341 |  | PS5-09-03 - HVAC for Generator Building
T-00233-9697 | PS5-09-AHU-8341-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8341 |  | PS5-09-03 - HVAC for Generator Building
T-00233-9698 | PS5-09-AHU-8411A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9699 | PS5-09-AHU-8411A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9700 | PS5-09-AHU-8411B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9701 | PS5-09-AHU-8411B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-AHU-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9702 | PS5-09-FCU-8442A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9703 | PS5-09-FCU-8442B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9704 | PS5-09-FCU-8442C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442C |  | PS5-09-03 - HVAC for Generator Building
T-00233-9705 | PS5-09-FCU-8442D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442D |  | PS5-09-03 - HVAC for Generator Building
T-00233-9706 | PS5-09-FCU-8442E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442E |  | PS5-09-03 - HVAC for Generator Building
T-00233-9707 | PS5-09-FCU-8442F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442F |  | PS5-09-03 - HVAC for Generator Building
T-00233-9708 | PS5-09-FCU-8442G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442G |  | PS5-09-03 - HVAC for Generator Building
T-00233-9709 | PS5-09-FCU-8442H-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-FCU-8442H |  | PS5-09-03 - HVAC for Generator Building
T-00233-9710 | PS5-09-LB-0008-CL03 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building
T-00233-9711 | PS5-09-PA-84500A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-PA-84500A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9712 | PS5-09-PA-84500B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-PA-84500B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9713 | PS5-09-QX-8451A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-QX-8451A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9714 | PS5-09-QX-8451A-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-QX-8451A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9715 | PS5-09-QX-8451B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-QX-8451B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9716 | PS5-09-QX-8451B-CL02 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-QX-8451B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9717 | PS5-09-RF-81200A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-81200A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9718 | PS5-09-RF-81200B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-81200B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9719 | PS5-09-RF-81200C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-81200C |  | PS5-09-03 - HVAC for Generator Building
T-00233-9720 | PS5-09-RF-82200A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-82200A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9721 | PS5-09-RF-82200B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-82200B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9722 | PS5-09-RF-82200C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-82200C |  | PS5-09-03 - HVAC for Generator Building
T-00233-9723 | PS5-09-RF-82200D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-82200D |  | PS5-09-03 - HVAC for Generator Building
T-00233-9724 | PS5-09-RF-83500A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9725 | PS5-09-RF-83500B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9726 | PS5-09-RF-83500C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500C |  | PS5-09-03 - HVAC for Generator Building
T-00233-9727 | PS5-09-RF-83500D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500D |  | PS5-09-03 - HVAC for Generator Building
T-00233-9728 | PS5-09-RF-83500E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500E |  | PS5-09-03 - HVAC for Generator Building
T-00233-9729 | PS5-09-RF-83500F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500F |  | PS5-09-03 - HVAC for Generator Building
T-00233-9730 | PS5-09-RF-83500G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500G |  | PS5-09-03 - HVAC for Generator Building
T-00233-9731 | PS5-09-RF-83500H-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500H |  | PS5-09-03 - HVAC for Generator Building
T-00233-9732 | PS5-09-RF-83500J-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500J |  | PS5-09-03 - HVAC for Generator Building
T-00233-9733 | PS5-09-RF-83500K-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500K |  | PS5-09-03 - HVAC for Generator Building
T-00233-9734 | PS5-09-RF-83500L-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500L |  | PS5-09-03 - HVAC for Generator Building
T-00233-9735 | PS5-09-RF-83500M-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500M |  | PS5-09-03 - HVAC for Generator Building
T-00233-9736 | PS5-09-RF-83500N-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500N |  | PS5-09-03 - HVAC for Generator Building
T-00233-9737 | PS5-09-RF-83500P-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-RF-83500P |  | PS5-09-03 - HVAC for Generator Building
T-00233-9738 | PS5-09-RF-83600A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9739 | PS5-09-RF-83600B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9740 | PS5-09-RF-83600C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600C |  | PS5-09-03 - HVAC for Generator Building
T-00233-9741 | PS5-09-RF-83600D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600D |  | PS5-09-03 - HVAC for Generator Building
T-00233-9742 | PS5-09-RF-83600E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600E |  | PS5-09-03 - HVAC for Generator Building
T-00233-9743 | PS5-09-RF-83600F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600F |  | PS5-09-03 - HVAC for Generator Building
T-00233-9744 | PS5-09-RF-83600G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600G |  | PS5-09-03 - HVAC for Generator Building
T-00233-9745 | PS5-09-RF-83600H-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600H |  | PS5-09-03 - HVAC for Generator Building
T-00233-9746 | PS5-09-RF-83600J-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600J |  | PS5-09-03 - HVAC for Generator Building
T-00233-9747 | PS5-09-RF-83600K-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600K |  | PS5-09-03 - HVAC for Generator Building
T-00233-9748 | PS5-09-RF-83600L-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600L |  | PS5-09-03 - HVAC for Generator Building
T-00233-9749 | PS5-09-RF-83600M-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600M |  | PS5-09-03 - HVAC for Generator Building
T-00233-9750 | PS5-09-RF-83600N-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600N |  | PS5-09-03 - HVAC for Generator Building
T-00233-9751 | PS5-09-RF-83600P-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-RF-83600P |  | PS5-09-03 - HVAC for Generator Building
T-00233-9752 | PS5-09-RF-83700A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9753 | PS5-09-RF-83700B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9754 | PS5-09-RF-83700C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700C |  | PS5-09-03 - HVAC for Generator Building
T-00233-9755 | PS5-09-RF-83700D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700D |  | PS5-09-03 - HVAC for Generator Building
T-00233-9756 | PS5-09-RF-83700E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700E |  | PS5-09-03 - HVAC for Generator Building
T-00233-9757 | PS5-09-RF-83700F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700F |  | PS5-09-03 - HVAC for Generator Building
T-00233-9758 | PS5-09-RF-83700G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700G |  | PS5-09-03 - HVAC for Generator Building
T-00233-9759 | PS5-09-RF-83700H-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700H |  | PS5-09-03 - HVAC for Generator Building
T-00233-9760 | PS5-09-RF-83700J-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700J |  | PS5-09-03 - HVAC for Generator Building
T-00233-9761 | PS5-09-RF-83700K-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700K |  | PS5-09-03 - HVAC for Generator Building
T-00233-9762 | PS5-09-RF-83700L-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700L |  | PS5-09-03 - HVAC for Generator Building
T-00233-9763 | PS5-09-RF-83700M-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700M |  | PS5-09-03 - HVAC for Generator Building
T-00233-9764 | PS5-09-RF-83700N-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700N |  | PS5-09-03 - HVAC for Generator Building
T-00233-9765 | PS5-09-RF-83700P-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-RF-83700P |  | PS5-09-03 - HVAC for Generator Building
T-00233-9766 | PS5-09-RF-83800A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9767 | PS5-09-RF-83800B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9768 | PS5-09-RF-83800C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800C |  | PS5-09-03 - HVAC for Generator Building
T-00233-9769 | PS5-09-RF-83800D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800D |  | PS5-09-03 - HVAC for Generator Building
T-00233-9770 | PS5-09-RF-83800E-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800E |  | PS5-09-03 - HVAC for Generator Building
T-00233-9771 | PS5-09-RF-83800F-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800F |  | PS5-09-03 - HVAC for Generator Building
T-00233-9772 | PS5-09-RF-83800G-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-RF-83800G |  | PS5-09-03 - HVAC for Generator Building
T-00233-9773 | PS5-09-RF-84200A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-84200A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9774 | PS5-09-RF-84200B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-RF-84200B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9775 | PS5-09-UZ-84600-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-09-IH-0004 TO PS5-09-UZ-84600 |  | PS5-09-03 - HVAC for Generator Building
T-00233-9776 | PS5-61-IH-0004A-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-61-IH-0004A |  | PS5-09-03 - HVAC for Generator Building
T-00233-9777 | PS5-61-IH-0004B-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-61-IH-0004B |  | PS5-09-03 - HVAC for Generator Building
T-00233-9778 | PS5-61-IH-0004C-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-61-IH-0004C |  | PS5-09-03 - HVAC for Generator Building
T-00233-9779 | PS5-61-IH-0004D-CL01 | TPX09 - LV power cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-61-IH-0004D |  | PS5-09-03 - HVAC for Generator Building
T-00234-2028 | PS5-05-IE-8100-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2029 | PS5-05-IE-8100-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2030 | PS5-05-IE-8100-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2031 | PS5-05-IE-8100-CD04 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2032 | PS5-05-IE-8100-CD05 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2033 | PS5-05-IE-8100-CD06 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0002-CD48 | TPX10 - Multicore electrical control cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0002-CD49 | TPX10 - Multicore electrical control cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0002-CD50 | TPX10 - Multicore electrical control cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0003-CD11 | TPX10 - Multicore electrical control cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0003-CD12 | TPX10 - Multicore electrical control cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
| PS5-61-IE-0003-CD13 | TPX10 - Multicore electrical control cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
| PS5-05-BE-0001-CL12 | TPX10 - Multicore electrical control cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2034 | PS5-05-IE-8100-CD07 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2035 | PS5-05-IE-8100-CD08 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0392 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2037 | PS5-05-IE-8100-CD10 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0392 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2038 | PS5-05-IE-8100-CD11 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2039 | PS5-05-IE-8100-CD12 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0392 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2040 | PS5-05-IE-8100-CD13 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0392 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2041 | PS5-05-IE-8100-CD14 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0392 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2042 | PS5-05-IE-8100-CD15 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0392 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2043 | PS5-05-IE-8100-CD16 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0392 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2044 | PS5-05-IE-8100-CD17 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0392 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2045 | PS5-05-IE-8100-CD18 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2046 | PS5-05-IE-8100-CD19 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2047 | PS5-05-IE-8100-CD20 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2048 | PS5-05-IE-8100-CD21 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-33/1-07-0392 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2052 | PS5-05-IE-8100-CD25 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-07-0313 | 2026-06-04 | Accepted | Bertus Wikael | Testing
| PS5-06-IG-0004B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable From PS5-61-IE-0002 to PS5-06-IG-0004B |  | PS5-06-02 | CPP-RFI-68-331-07-0247 | 2026-05-05 | Accepted | Bertus Wikael | TESTING
| PS5-61-IJ-0001-CD07 | TPX10 - Multicore electrical control cable | #N/A | E | Cable From PS5-61-IK-0006 to PS5-61-IJ-0001 |  | PS5-61-01 | CPP-RFI-68-331-07-0247 | 2026-05-05 | Accepted | Bertus Wikael | TESTING
T-00234-2061 | PS5-25-DM-3100A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-DM-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0247 | 2026-05-05 | Accepted | Bertus Wikael | TESTING
T-00234-2062 | PS5-25-DM-3100B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-DM-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0247 | 2026-05-05 | Accepted | Bertus Wikael | TESTING
T-00234-2063 | PS5-25-DM-3100C-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-DM-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0247 | 2026-05-05 | Accepted | Bertus Wikael | TESTING
T-00234-2067 | PS5-25-IES-3100A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-25-IES-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING
| PS5-25-HE-2300-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING
| PS5-25-IES-3200A-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
| PS5-25-IES-3200B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
| PS5-25-IES-3300A-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
| PS5-25-IES-3300B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
| PS5-25-IES-3400A-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
| PS5-25-IES-3400B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
| PS5-25-IES-6400A-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
| PS5-25-IES-6400B-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
| PS5-25-HE-2200-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING
| PS5-25-HE-2300-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING
T-00234-2068 | PS5-25-IES-3100B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-25-IES-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING
T-00234-2069 | PS5-25-IES-3100C-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-25-IES-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0287 | 2026-05-15 | Accepted | Bertus Wikael | TESTING
T-00234-2097 | PS5-50-IE-0001-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-50-IE-0001 |  | PS5-50-01 - Water Well Submersible Pumps (3100)
T-00234-2098 | PS5-50-IE-0002-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-50-IE-0002 |  | PS5-50-02 - Water Well Submersible Pumps (3200)
T-00234-2101 | PS5-60-IE-0002A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00234-2102 | PS5-60-IE-0002A-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00234-2103 | PS5-60-IE-0002A-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00234-2104 | PS5-60-IE-0002B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00234-2105 | PS5-60-IE-0002B-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00234-2106 | PS5-60-IE-0002B-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00234-2107 | PS5-60-IE-0002C-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0400 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00234-2108 | PS5-60-IE-0002C-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0400 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00234-2109 | PS5-60-IE-0002C-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0400 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00234-2110 | PS5-60-IE-0002D-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-331-07-0400 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00234-2111 | PS5-60-IE-0002D-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-331-07-0400 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00234-2112 | PS5-60-IE-0002D-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-331-07-0422 | 2026-07-18 | Waiting for Signature | Ferdinand | Testing
T-00234-2113 | PS5-60-IE-0002E-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0421 | 2026-07-18 | OPEN | Bertus Wikael | Testing
T-00234-2114 | PS5-60-IE-0002E-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0421 | 2026-07-18 | OPEN | Bertus Wikael | Testing
T-00234-2115 | PS5-60-IE-0002E-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0421 | 2026-07-18 | OPEN | Bertus Wikael | Testing
T-00234-2116 | PS5-60-IE-0002F-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00234-2117 | PS5-60-IE-0002F-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00234-2118 | PS5-60-IE-0002F-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00234-2119 | PS5-60-IE-0002G-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00234-2120 | PS5-60-IE-0002G-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00234-2121 | PS5-60-IE-0002G-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0415 | 2026-07-15 | ACCEPTED | Bertus Wikael | Testing
T-00234-2123 | PS5-60-IE-0003A-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00234-2124 | PS5-60-IE-0003A-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00234-2125 | PS5-60-IE-0003A-CD04 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0005A TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00234-2126 | PS5-60-IE-0003A-CD05 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00234-2135 | PS5-60-IE-0003A-CD14 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00234-2136 | PS5-60-IE-0003A-CD15 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00234-2138 | PS5-60-IE-0003B-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00234-2139 | PS5-60-IE-0003B-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
| PS5-08-01FB-1102-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
| PS5-08-01FB-1103-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
| PS5-08-01FB-1106-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
| PS5-08-03FB-1903-CS01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00234-2140 | PS5-60-IE-0003B-CD04 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0005B TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00234-2141 | PS5-60-IE-0003B-CD05 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00234-2150 | PS5-60-IE-0003B-CD14 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0348 | 2026-06-17 | Accepted | Bertus Wikael | testing
T-00234-2151 | PS5-60-IE-0003B-CD15 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00234-2153 | PS5-60-IE-0003C-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00234-2154 | PS5-60-IE-0003C-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00234-2155 | PS5-60-IE-0003C-CD04 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0005C TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2156 | PS5-60-IE-0003C-CD05 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00234-2165 | PS5-60-IE-0003C-CD14 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00234-2166 | PS5-60-IE-0003C-CD15 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C
T-00234-2168 | PS5-60-IE-0003D-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
T-00234-2169 | PS5-60-IE-0003D-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00234-2170 | PS5-60-IE-0003D-CD04 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0005D TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00234-2171 | PS5-60-IE-0003D-CD05 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
T-00234-2180 | PS5-60-IE-0003D-CD14 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-07-0330 | 12-June-2026 | Accepted | Ferdinand | TESTING
|  |  | #N/A | E
T-00234-2181 | PS5-60-IE-0003D-CD15 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D
T-00234-2183 | PS5-60-IE-0003E-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00234-2184 | PS5-60-IE-0003E-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00234-2185 | PS5-60-IE-0003E-CD04 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0005E TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2186 | PS5-60-IE-0003E-CD05 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00234-2195 | PS5-60-IE-0003E-CD14 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00234-2196 | PS5-60-IE-0003E-CD15 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-07-0426 | 21-July-2026 | Accepted | Ferdinand | Testing
T-00234-2198 | PS5-60-IE-0003F-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00234-2199 | PS5-60-IE-0003F-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00234-2200 | PS5-60-IE-0003F-CD04 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0005F TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2201 | PS5-60-IE-0003F-CD05 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F
T-00234-2210 | PS5-60-IE-0003F-CD14 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F
T-00234-2211 | PS5-60-IE-0003F-CD15 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00234-2213 | PS5-60-IE-0003G-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00234-2214 | PS5-60-IE-0003G-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00234-2215 | PS5-60-IE-0003G-CD04 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0005G TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-07-0388 | 2026-06-30 | Accepted | Bertus Wikael | Testing
T-00234-2216 | PS5-60-IE-0003G-CD05 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00234-2225 | PS5-60-IE-0003G-CD14 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00234-2226 | PS5-60-IE-0003G-CD15 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-331-07-0423 | 2026-07-18 | Accepted | Bertus Wikael | Testing
T-00234-2233 | PS5-61-IDH-3100A-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IU-3100A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
T-00234-2236 | PS5-61-IDH-3100B-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IU-3100B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
T-00234-2239 | PS5-61-IDH-3100C-CD03 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IU-3100C TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
T-00234-2288 | PS5-62-IE-0001-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-62-IE-0002 TO PS5-62-IE-0001 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPP-RFI-68-331-07-0248 | 2026-05-05 | Accepted | Bertus Wikael | Testing
T-00234-3288 | PS5-79-IG-0001-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0001 TO PS5-79-IG-0001 |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00234-3289 | PS5-79-IG-0002-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0002 TO PS5-79-IG-0002 |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00234-3290 | PS5-79-IG-0003-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0003 TO PS5-79-IG-0003 |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00234-3291 | PS5-79-IG-0004-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0004 TO PS5-79-IG-0004 |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00234-3292 | PS5-79-IG-0005-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0005 TO PS5-79-IG-0005 |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00234-3293 | PS5-79-IG-0006-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0006 TO PS5-79-IG-0006 |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00234-3294 | PS5-79-IG-0007-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0007 TO PS5-79-IG-0007 |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00234-3295 | PS5-79-IG-0008-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0008 TO PS5-79-IG-0008 |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00234-3296 | PS5-79-IG-0009-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0009 TO PS5-79-IG-0009 |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00234-3297 | PS5-79-IG-0010-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0010 TO PS5-79-IG-0010 |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00234-3298 | PS5-79-IG-0011-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0011 TO PS5-79-IG-0011 |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00234-3299 | PS5-79-IG-0012-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-79-IV-0012 TO PS5-79-IG-0012 |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00234-3399 | PS5-06-GU-0003A-CD02 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-06-GB-0003 TO PS5-06-GU-0003A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-331-07-0369 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
T-00234-3634 | PS5-09-IES-8101A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8101A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3635 | PS5-09-IES-8101B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8101B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3636 | PS5-09-IES-8102A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8102A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3637 | PS5-09-IES-8102B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8102B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3638 | PS5-09-IES-8102C-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8102C |  | PS5-09-03 - HVAC for Generator Building
T-00234-3639 | PS5-09-IES-8201A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8201A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3640 | PS5-09-IES-8201B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8201B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3641 | PS5-09-IES-8202A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8202A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3642 | PS5-09-IES-8202B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8202B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3643 | PS5-09-IES-8202C-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8202C |  | PS5-09-03 - HVAC for Generator Building
T-00234-3644 | PS5-09-IES-8202D-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8202D |  | PS5-09-03 - HVAC for Generator Building
T-00234-3645 | PS5-09-IES-8301A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8301A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3646 | PS5-09-IES-8301B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8301B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3647 | PS5-09-IES-8302A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8302A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3648 | PS5-09-IES-8302B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8302B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3649 | PS5-09-IES-8304A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8304A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3650 | PS5-09-IES-8304B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8304B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3651 | PS5-09-IES-8305A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8305A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3652 | PS5-09-IES-8305B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8305B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3653 | PS5-09-IES-8307A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8307A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3654 | PS5-09-IES-8307B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8307B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3655 | PS5-09-IES-8308A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8308A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3656 | PS5-09-IES-8308B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8308B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3657 | PS5-09-IES-8311A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8311A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3658 | PS5-09-IES-8311B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8311B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3659 | PS5-09-IES-8313-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-IES-8313 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3660 | PS5-09-IES-8314-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004A TO PS5-09-IES-8314 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3661 | PS5-09-IES-8315-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8315 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3662 | PS5-09-IES-8316-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-IES-8316 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3663 | PS5-09-IES-8317-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004B TO PS5-09-IES-8317 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3664 | PS5-09-IES-8318-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8318 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3665 | PS5-09-IES-8319-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-IES-8319 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3666 | PS5-09-IES-8321-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004C TO PS5-09-IES-8321 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3667 | PS5-09-IES-8322-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8322 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3668 | PS5-09-IES-8323-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-IES-8323 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3669 | PS5-09-IES-8324-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004D TO PS5-09-IES-8324 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3670 | PS5-09-IES-8325-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8325 |  | PS5-09-03 - HVAC for Generator Building
T-00234-3671 | PS5-09-IES-8401A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8401A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3672 | PS5-09-IES-8401B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8401B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3673 | PS5-09-IES-8403A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8403A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3674 | PS5-09-IES-8403B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8403B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3675 | PS5-09-IES-8404A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8404A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3676 | PS5-09-IES-8404B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8404B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3677 | PS5-09-IES-8405A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8405A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3678 | PS5-09-IES-8405B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8405B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3679 | PS5-09-IES-8406A-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406A |  | PS5-09-03 - HVAC for Generator Building
T-00234-3680 | PS5-09-IES-8406B-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406B |  | PS5-09-03 - HVAC for Generator Building
T-00234-3681 | PS5-09-IES-8406C-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406C |  | PS5-09-03 - HVAC for Generator Building
T-00234-3682 | PS5-09-IES-8406D-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406D |  | PS5-09-03 - HVAC for Generator Building
T-00234-3683 | PS5-09-IES-8406E-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406E |  | PS5-09-03 - HVAC for Generator Building
T-00234-3684 | PS5-09-IES-8406F-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406F |  | PS5-09-03 - HVAC for Generator Building
T-00234-3685 | PS5-09-IES-8406G-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406G |  | PS5-09-03 - HVAC for Generator Building
T-00234-3686 | PS5-09-IES-8406H-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8406H |  | PS5-09-03 - HVAC for Generator Building
T-00234-3687 | PS5-09-IES-8407-CD01 | TPX10 - Multicore electrical control cable | #N/A | E | Cable FROM PS5-61-IH-0004 TO PS5-09-IES-8407 |  | PS5-09-03 - HVAC for Generator Building
| PS5-01-BI-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0001-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-BI-0001 | PS5-01-05 - Foam Skid | PS5-01-05 - Foam Skid | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-01-BI-0002-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0002-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-BI-0002 | PS5-01-10 - Water Mist Package | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-01-BI-0003-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0003-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-01-BI-0003 | PS5-01-10 - Water Mist Package | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-01-BI-0004-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0004-CC01 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-BI-0004 | PS5-01-10 - Water Mist Package | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-01-BI-0005-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0005-CC01 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-BI-0005 | PS5-01-05 - Foam Skid | PS5-01-05 - Foam Skid | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-01-BI-0006-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0006-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-01-BI-0006 | PS5-01-05 - Foam Skid | PS5-01-05 - Foam Skid | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-01-BI-1117-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1117-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-01-BI-1117 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-01-BI-1118-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1118-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-01-BI-1118 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-01-BI-1501-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1501-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-01-BI-1501 | PS5-01-07 - Fire Water Ring Main & Distribution | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
| PS5-01-BI-1515-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1515-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-01-BI-1515 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-01-BI-1520-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1520-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-01-BI-1520 | PS5-01-10 - Water Mist Package | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-01-BI-1571-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1571-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-01-BI-1571 | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-01-BI-2110-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-2110-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-01-BI-2110 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-01-BI-2520-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-2520-CC01 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-BI-2520 | PS5-01-10 - Water Mist Package | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-01-BI-2571A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-2571A-CC01 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-BI-2571A | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-01-BI-2571B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-2571B-CC01 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-BI-2571B | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPP-RFI-68-64-12-0055 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0002A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0002A-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-IE-0002A | PS5-01-01 - Fire Water Jockey Pump A/B | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-64-12-0055 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0002A-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0002A-CC02 | I | Cable FROM PS5-03-SFMC-0013 TO PS5-01-IE-0002A | PS5-01-01 - Fire Water Jockey Pump A/B | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-64-12-0055 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0002B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0002B-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-IE-0002B | PS5-01-01 - Fire Water Jockey Pump A/B | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-64-12-0055 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0002B-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0002B-CC02 | I | Cable FROM PS5-03-SFMC-0013 TO PS5-01-IE-0002B | PS5-01-01 - Fire Water Jockey Pump A/B | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-64-12-0055 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0009A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0009A-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-IE-0009A | PS5-01-02 - Fire Water Pump A | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-64-12-0055 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0009A-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-IE-0009A | PS5-01-02 - Fire Water Pump A | PS5-01-02 - Fire Water Pump A
| PS5-01-IE-0009B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0009B-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-IE-0009B | PS5-01-03 - Fire Water Pump B | PS5-01-03 - Fire Water Pump B | CPP-RFI-68-64-12-0055 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0009B-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-IE-0009B | PS5-01-03 - Fire Water Pump B | PS5-01-03 - Fire Water Pump B
| PS5-01-LB-0004-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-LB-0004-CC01 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-01-LB-0004 | PS5-01-11 - Inergen for Power Gen Building | PS5-01-11 - Inergen for Power Gen Building |  | 2026-04-16
| PS5-01-LB-0004-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-LB-0004-CC02 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-LB-0004 | PS5-01-11 - Inergen for Power Gen Building | PS5-01-11 - Inergen for Power Gen Building |  | 2026-04-16
| PS5-01-LB-0004-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-LB-0004-CC03 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-01-LB-0004 | PS5-01-11 - Inergen for Power Gen Building | PS5-01-11 - Inergen for Power Gen Building |  | 2026-04-16
| PS5-01-LIT-4201-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-LIT-4201-CJ01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-01-LIT-4201 | PS5-01-10 - Water Mist Package | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-01-PIT-0014-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-PIT-0014-CJ01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-01-PIT-0014 | PS5-01-07 - Fire Water Ring Main & Distribution | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-01-PIT-0015-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-PIT-0015-CJ01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-01-PIT-0015 | PS5-01-07 - Fire Water Ring Main & Distribution | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-01-PIT-0016-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-PIT-0016-CJ01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-01-PIT-0016 | PS5-01-07 - Fire Water Ring Main & Distribution | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-01-PIT-0017-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-PIT-0017-CJ01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-01-PIT-0017 | PS5-01-07 - Fire Water Ring Main & Distribution | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1502-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1502-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1502 | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1503-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1503-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1503 | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1506-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1506-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1506 | PS5-03-01 - FZ-01 - Process Area | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1507-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1507-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1507 | PS5-03-01 - FZ-01 - Process Area | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0045 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1508-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1508-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1508 | PS5-03-01 - FZ-01 - Process Area | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1509-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1509-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1509 | PS5-03-01 - FZ-01 - Process Area | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1510-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1510-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1510 | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1511-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1511-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1511 | PS5-03-07 - FZ-07 - Pretreatment Area | PS5-03-07 - FZ-07 - Pretreatment Area | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1512-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1512-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1512 | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1513-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1513-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1513 | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | 2026-04-24
| PS5-03-BI-1514-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1514-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1514 | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | 2026-04-24
| PS5-03-BI-1516-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1516-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1516 | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | 2026-05-20
| PS5-03-BI-2501-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2501-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2501 | PS5-03-06 - FZ-06 - Transformer Area | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2502-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2502-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2502 | PS5-03-06 - FZ-06 - Transformer Area | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2503-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2503-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2503 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2504-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2504-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2504 | PS5-03-01 - FZ-01 - Process Area | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2505-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2505-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2505 | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2506-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2506-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2506 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2507-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2507-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2507 | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | 2026-04-16
| PS5-03-BI-2508-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2508-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2508 | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CPP-RFI-68-64-12-0056 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2509-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2509-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2509 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2510-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2510 | PS5-03-03 - FZ-03 - Buildings Area | PS5-03-03 - FZ-03 - Buildings Area
| PS5-03-BI-2511-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2511-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2511 | PS5-03-01 - FZ-01 - Process Area | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2512-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2512-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2512 | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2514-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2514-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2514 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-03-BI-2515-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2515-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2515 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-03-HS-7002-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-HS-7002-CJ01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-03-HS-7002 | PS5-03-03 - FZ-03 - Buildings Area | PS5-03-03 - FZ-03 - Buildings Area | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-03-MTX-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0001 TO PS5-03-MTX-0001 | PS5-04-02 - Office Building SIS/FGS System | PS5-04-02 - Office Building SIS/FGS System
| PS5-03-MTX-0001-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0001 TO PS5-03-MTX-0001 | PS5-04-02 - Office Building SIS/FGS System | PS5-04-02 - Office Building SIS/FGS System
| PS5-03-MTX-0001-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0004 TO PS5-03-MTX-0001 | PS5-04-02 - Office Building SIS/FGS System | PS5-04-02 - Office Building SIS/FGS System
| PS5-03-MTX-0001-CC04 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0005 TO PS5-03-MTX-0001 | PS5-04-02 - Office Building SIS/FGS System | PS5-04-02 - Office Building SIS/FGS System
| PS5-03-MTX-0001-CC05 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-MTX-0001 | PS5-04-02 - Office Building SIS/FGS System | PS5-04-02 - Office Building SIS/FGS System
| PS5-03-MTX-0001-CC06 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0011 TO PS5-03-MTX-0001 | PS5-04-02 - Office Building SIS/FGS System | PS5-04-02 - Office Building SIS/FGS System
| PS5-03-MTX-0001-CC07 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0011 TO PS5-03-MTX-0001 | PS5-04-02 - Office Building SIS/FGS System | PS5-04-02 - Office Building SIS/FGS System
| PS5-03-MTX-0001-CC08 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0012 TO PS5-03-MTX-0001 | PS5-04-02 - Office Building SIS/FGS System | PS5-04-02 - Office Building SIS/FGS System
| PS5-03-NMR-0801-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-NMR-0801-CJ01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-NMR-0801 | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-03-NMR-0802-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-NMR-0802-CJ01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-NMR-0802 | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0056 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-03-NMR-0803-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-NMR-0803-CJ01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-NMR-0803 | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-03-NMR-0804-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-NMR-0804-CJ01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-NMR-0804 | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-03-RMAC-0120-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-RMAC-0120-CJ01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-RMAC-0120 | PS5-03-01 - FZ-01 - Process Area | PS5-03-01 - FZ-01 - Process Area |  | 2026-04-16
| PS5-03-RMAC-0824-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-RMAC-0824-CJ01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-RMAC-0824 | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-03-SEA-0002-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0002-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-SEA-0002 | PS5-03-22 - FZ-G1 - Guard House | PS5-03-22 - FZ-G1 - Guard House | CPP-RFI-68-64-12-0055 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-03-SEA-0002-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0002-CJ01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-03-SEA-0002 | PS5-03-22 - FZ-G1 - Guard House | PS5-03-22 - FZ-G1 - Guard House |  | 2026-04-16
| PS5-03-SEA-0003-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0003-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-SEA-0003 | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-03-SEA-0003-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0003-CJ01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-03-SEA-0003 | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-03-SEA-0005-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-SEA-0005 | PS5-03-24 - FZ - Office and Facilities Building | PS5-03-24 - FZ - Office and Facilities Building
| PS5-03-SEA-0005-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0004 TO PS5-03-SEA-0005 | PS5-03-24 - FZ - Office and Facilities Building | PS5-03-24 - FZ - Office and Facilities Building
| PS5-03-SEA-0006-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0006-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-SEA-0006 | PS5-03-25 - FZ - Workshop & Warehouse | PS5-03-25 - FZ - Workshop & Warehouse |  | 2026-05-06
| PS5-03-SEA-0006-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0006-CJ01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-03-SEA-0006 | PS5-03-25 - FZ - Workshop & Warehouse | PS5-03-25 - FZ - Workshop & Warehouse |  | 2026-04-16
| PS5-05-BI-0002-CC11 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-05-BI-0002-CC11 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-05-BI-0002 | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-05-BI-0002-CC12 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-05-BI-0002-CC12 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-05-BI-0002 | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-05-IE-8100-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-05-IE-8100-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-05-IE-8100 | PS5-05-02 - Emergency Diesel Generator Package (UCP) | PS5-05-02 - Emergency Diesel Generator Package (UCP) |  | 2026-05-20
| PS5-05-IE-8100-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-05-IE-8100-CC02 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-05-IE-8100 | PS5-05-02 - Emergency Diesel Generator Package (UCP) | PS5-05-02 - Emergency Diesel Generator Package (UCP) |  | 2026-04-16
| PS5-06-GU-0003A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-06-GU-0003A-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-06-GU-0003A | PS5-06-02 - AC UPS - Power Generator Building | PS5-06-02 - AC UPS - Power Generator Building |  | 2026-04-16
| PS5-06-GU-0003B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-06-GU-0003B-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-06-GU-0003B | PS5-06-02 - AC UPS - Power Generator Building | PS5-06-02 - AC UPS - Power Generator Building |  | 2026-04-16
| PS5-09-BI-2501-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-BI-2501-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-09-BI-2501 | PS5-09-04 - HVAC for Workshop & Warehouse | PS5-09-04 - HVAC for Workshop & Warehouse |  | 2026-04-16
| PS5-09-BI-2502-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-BI-2502 | PS5-09-01 - HVAC for Office and Facilities building | PS5-09-01 - HVAC for Office and Facilities building
| PS5-09-BI-2503-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-BI-2503-CC01 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-BI-2503 | PS5-09-03 - HVAC for Generator Building | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-09-LB-0006-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0013 TO PS5-09-LB-0006 | PS5-09-01 - HVAC for Office and Facilities building | PS5-09-01 - HVAC for Office and Facilities building
| PS5-09-LB-0006-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0006 | PS5-09-01 - HVAC for Office and Facilities building | PS5-09-01 - HVAC for Office and Facilities building
| PS5-09-LB-0006-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0003 TO PS5-09-LB-0006 | PS5-09-01 - HVAC for Office and Facilities building | PS5-09-01 - HVAC for Office and Facilities building
| PS5-09-LB-0006-CC04 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0006 | PS5-09-01 - HVAC for Office and Facilities building | PS5-09-01 - HVAC for Office and Facilities building
| PS5-09-LB-0007-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0007-CC01 | I | Cable FROM PS5-03-SFMC-0013 TO PS5-09-LB-0007 | PS5-09-04 - HVAC for Workshop & Warehouse | PS5-09-04 - HVAC for Workshop & Warehouse |  | 2026-04-16
| PS5-09-LB-0007-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0007-CC02 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0007 | PS5-09-04 - HVAC for Workshop & Warehouse | PS5-09-04 - HVAC for Workshop & Warehouse |  | 2026-05-06
| PS5-09-LB-0007-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0007-CC03 | I | Cable FROM PS5-04-PMC-0005 TO PS5-09-LB-0007 | PS5-09-04 - HVAC for Workshop & Warehouse | PS5-09-04 - HVAC for Workshop & Warehouse |  | 2026-04-16
| PS5-09-LB-0007-CC04 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0007-CC04 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0007 | PS5-09-04 - HVAC for Workshop & Warehouse | PS5-09-04 - HVAC for Workshop & Warehouse |  | 2026-04-16
| PS5-09-LB-0008-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC01 | I | Cable FROM PS5-03-SFMC-0013 TO PS5-09-LB-0008 | PS5-09-03 - HVAC for Generator Building | PS5-09-03 - HVAC for Generator Building |  | 2026-05-06
| PS5-09-LB-0008-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC02 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0008 | PS5-09-03 - HVAC for Generator Building | PS5-09-03 - HVAC for Generator Building |  | 2026-05-06
| PS5-09-LB-0008-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC03 | I | Cable FROM PS5-04-PMC-0005 TO PS5-09-LB-0008 | PS5-09-03 - HVAC for Generator Building | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-09-LB-0008-CC04 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC04 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0008 | PS5-09-03 - HVAC for Generator Building | PS5-09-03 - HVAC for Generator Building |  | 2026-04-16
| PS5-09-LB-0008-CC05 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC05 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-09-LB-0008 | PS5-09-03 - HVAC for Generator Building | PS5-09-03 - HVAC for Generator Building |  | 2026-04-16
| PS5-09-LB-0008-CC06 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC06 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-09-LB-0008 | PS5-09-03 - HVAC for Generator Building | PS5-09-03 - HVAC for Generator Building |  | 2026-05-06
| PS5-09-LB-0008-CC07 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC07 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-09-LB-0008 | PS5-09-03 - HVAC for Generator Building | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-12-0056 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-09-LB-0008-CC08 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC08 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0008 | PS5-09-03 - HVAC for Generator Building | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-12-0056 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1101-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1101-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1101 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1102-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1102-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1102 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1103-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1103-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1103 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1104-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1104-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1104 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1115-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1115-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1115 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1174A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1174A-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1174A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1174B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1174B-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1174B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1174C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1174C-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1174C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1201-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1201-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-1201 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1274A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1274A-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1274A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1274B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1274B-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1274B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1274C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1274C-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-1274C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1301-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1301-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1301 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1302-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1302-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1302 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1310-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1310-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1310 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-25-BI-1801A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1801A-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1801A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0046 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1801B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1801B-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1801B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1801C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1801C-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1801C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1802A-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1802A-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1802A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1802B-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1802B-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1802B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1802C-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1802C-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1802C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803A-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803A-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803A-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803B-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803B-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803B-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803C-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803C-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803C-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2101-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2101-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-25-BI-2101 | PS5-25-01 - Export Pipeline Pig Receiver | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2102-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2102-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-25-BI-2102 | PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2103-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2103-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2103 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0046 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2104-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2104-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-25-BI-2104 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2105-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2105-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2105 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2106-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2106-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2106 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2108-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2108-CC01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-25-BI-2108 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2109-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2109-CC01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-25-BI-2109 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0046 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2201-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2201-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-2201 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2203-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2203-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-2203 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0046 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2205-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2205-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-2205 | PS5-25-01 - Export Pipeline Pig Receiver | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2301-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2301-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2301 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2302-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2302-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-25-BI-2302 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0046 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2305-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2305-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2305 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2308-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2308-CC01 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-25-BI-2308 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2309-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2309-CC01 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-25-BI-2309 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2312-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2312-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2312 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2315-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2315-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2315 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2316-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2316-CC01 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-25-BI-2316 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-MXS-3101AA-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101AA-CJ01 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-61-IDH-3100A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-25-MXS-3101AB-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101AB-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-61-IDH-3100A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A |  | 2026-04-16
| PS5-25-MXS-3101BA-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101BA-CJ01 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-61-IDH-3100B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-25-MXS-3101BB-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101BB-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-61-IDH-3100B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B |  | 2026-04-16
| PS5-25-MXS-3101CA-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101CA-CJ01 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-61-IDH-3100C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-25-MXS-3101CB-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101CB-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-61-IDH-3100C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C |  | 2026-04-16 | Accepted
| PS5-25-PIT-0052-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-PIT-0052-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-SDV-0052 | PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-PIT-0071A-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-PIT-0071A-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-PIT-0071A | PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-PIT-0071B-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-PIT-0071B-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-PIT-0071B | PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-PIT-0071C-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-PIT-0071C-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-PIT-0071C | PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-SDV-0052-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-SDV-0052-CC01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-SDV-0052 | PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-25-SDV-0052-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-SDV-0052-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-SDV-0052 | PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07 - Export Pipeline Pig Launcher
| PS5-25-SHSR-0052-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-SHSR-0052-CJ01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-25-SDV-0052 | PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-25-SXS-0052-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-SXS-0052-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-SDV-0052 | PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07 - Export Pipeline Pig Launcher
| PS5-25-SY-0052A-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-SY-0052A-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-SDV-0052 | PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07 - Export Pipeline Pig Launcher
| PS5-28-BI-1105-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-1105-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-28-BI-1105 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-28-BI-1106-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-1106-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-28-BI-1106 | PS5-28-06 - Relief Drum and Pump | PS5-28-06 - Relief Drum and Pump | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-28-BI-1114-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-1114-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-28-BI-1114 | PS5-28-04 - Closed Drain Drum and Pump 02 | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-28-BI-1303-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-1303-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-28-BI-1303 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-28-BI-1307-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-1307-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-28-BI-1307 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-28-BI-2304-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-2304-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-28-BI-2304 | PS5-28-17 - Reinjection Pump | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-28-HXA-1101-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-HXA-1101-CJ01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-28-HXA-1101 | PS5-28-03 - Closed Drain Drum and Pump 01 | PS5-28-03 - Closed Drain Drum and Pump 01 |  | 2026-04-16
| PS5-28-LB-8200-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-LB-8200-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-28-LB-8200 | PS5-28-11 - Open Drain Interceptor | PS5-28-11 - Open Drain Interceptor | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-28-LB-8200-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-LB-8200-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-28-LB-8200 | PS5-28-11 - Open Drain Interceptor | PS5-28-11 - Open Drain Interceptor | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-50-BI-1107-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-50-BI-1107-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-50-BI-1107 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-50-IE-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-50-IE-0001-CC01 | I | Cable FROM PS5-04-PMC-0008 TO PS5-50-IE-0001 | PS5-50-01 - Water Well Submersible Pumps (3100) | PS5-50-01 - Water Well Submersible Pumps (3100) | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-50-IE-0001-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-50-IE-0001-CC02 | I | Cable FROM PS5-04-PMC-0007 TO PS5-50-IE-0001 | PS5-50-01 - Water Well Submersible Pumps (3100) | PS5-50-01 - Water Well Submersible Pumps (3100) | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-50-IE-0002-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-50-IE-0002-CC01 | I | Cable FROM PS5-04-PMC-0008 TO PS5-50-IE-0002 | PS5-50-02 - Water Well Submersible Pumps (3200) | PS5-50-02 - Water Well Submersible Pumps (3200) | CPP-RFI-68-64-12-0055 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-50-IE-0002-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-50-IE-0002-CC02 | I | Cable FROM PS5-04-PMC-0007 TO PS5-50-IE-0002 | PS5-50-02 - Water Well Submersible Pumps (3200) | PS5-50-02 - Water Well Submersible Pumps (3200) | CPP-RFI-68-64-12-0055 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-50-LIT-0001-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0001 TO PS5-50-LIT-0001 | PS5-50-01 - Water Well Submersible Pumps (3100) | PS5-50-01 - Water Well Submersible Pumps (3100) |  | 2026-04-16
| PS5-50-LIT-0002-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0001 TO PS5-50-LIT-0002 | PS5-50-02 - Water Well Submersible Pumps (3200) | PS5-50-02 - Water Well Submersible Pumps (3200)
| PS5-53-BI-1108-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-53-BI-1108-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-53-BI-1108 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-53-BI-1304-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-53-BI-1304-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-53-BI-1304 | PS5-53-01 - Utility Water / Storage Tank | PS5-53-01 - Utility Water / Storage Tank | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-53-LA-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-53-LA-0001-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-53-LA-0001 | PS5-53-04 - Water Treatment Purification Package | PS5-53-04 - Water Treatment Purification Package | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-53-LA-0001-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-53-LA-0001-CC02 | I | Cable FROM PS5-04-PMC-0002 TO PS5-53-LA-0001 | PS5-53-04 - Water Treatment Purification Package | PS5-53-04 - Water Treatment Purification Package | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003A-CC21 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003A-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003A | PS5-60-02 - Power Gen Package A (UCP) | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-60-IE-0003A-CC22 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003A-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003A | PS5-60-02 - Power Gen Package A (UCP) | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-60-IE-0003A-CC23 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003A-CC23 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003A | PS5-60-02 - Power Gen Package A (UCP) | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-60-IE-0003A-CC24 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003A-CC24 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003A | PS5-60-02 - Power Gen Package A (UCP) | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-60-IE-0003B-CC21 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003B-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003B | PS5-60-05 - Power Gen Package B (UCP) | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-60-IE-0003B-CC22 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003B-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003B | PS5-60-05 - Power Gen Package B (UCP) | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-60-IE-0003B-CC23 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003B-CC23 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003B | PS5-60-05 - Power Gen Package B (UCP) | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-60-IE-0003B-CC24 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003B-CC24 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003B | PS5-60-05 - Power Gen Package B (UCP) | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-60-IE-0003C-CC21 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003C-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003C | PS5-60-08 - Power Gen Package C (UCP) | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003C-CC22 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003C-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003C | PS5-60-08 - Power Gen Package C (UCP) | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003C-CC23 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003C-CC23 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003C | PS5-60-08 - Power Gen Package C (UCP) | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003C-CC24 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003C-CC24 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-60-IE-0003C | PS5-60-08 - Power Gen Package C (UCP) | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003D-CC21 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003D-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003D | PS5-60-11 - Power Gen Package D (UCP) | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003D-CC22 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003D-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003D | PS5-60-11 - Power Gen Package D (UCP) | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003D-CC23 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003D-CC23 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003D | PS5-60-11 - Power Gen Package D (UCP) | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003D-CC24 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003D-CC24 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003D | PS5-60-11 - Power Gen Package D (UCP) | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0056 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003E-CC21 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003E-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003E | PS5-60-14 - Power Gen Package E (UCP) | PS5-60-14 - Power Gen Package E (UCP) |  | 2026-05-06
| PS5-60-IE-0003E-CC22 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003E-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003E | PS5-60-14 - Power Gen Package E (UCP) | PS5-60-14 - Power Gen Package E (UCP) |  | 2026-05-20
| PS5-60-IE-0003E-CC23 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003E-CC23 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003E | PS5-60-14 - Power Gen Package E (UCP) | PS5-60-14 - Power Gen Package E (UCP) | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003E-CC24 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003E-CC24 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003E | PS5-60-14 - Power Gen Package E (UCP) | PS5-60-14 - Power Gen Package E (UCP) | CPP-RFI-68-64-12-0056 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003F-CC21 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003F-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003F | PS5-60-17 - Power Gen Package F (UCP) | PS5-60-17 - Power Gen Package F (UCP) |  | 2026-05-06 | Accepted
| PS5-60-IE-0003F-CC22 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003F-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003F | PS5-60-17 - Power Gen Package F (UCP) | PS5-60-17 - Power Gen Package F (UCP) | CPP-RFI-68-64-12-0056 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003F-CC23 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003F-CC23 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-60-IE-0003F | PS5-60-17 - Power Gen Package F (UCP) | PS5-60-17 - Power Gen Package F (UCP) | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003F-CC24 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003F-CC24 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-60-IE-0003F | PS5-60-17 - Power Gen Package F (UCP) | PS5-60-17 - Power Gen Package F (UCP) | CPP-RFI-68-64-12-0056 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003G-CC21 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003G-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003G | PS5-60-20 - Power Gen Package G (UCP) | PS5-60-20 - Power Gen Package G (UCP) | CPP-RFI-68-64-12-0056 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003G-CC22 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003G-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003G | PS5-60-20 - Power Gen Package G (UCP) | PS5-60-20 - Power Gen Package G (UCP) | CPP-RFI-68-64-12-0056 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003G-CC23 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003G-CC23 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-60-IE-0003G | PS5-60-20 - Power Gen Package G (UCP) | PS5-60-20 - Power Gen Package G (UCP) |  | 2026-04-16
| PS5-60-IE-0003G-CC24 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003G-CC24 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-60-IE-0003G | PS5-60-20 - Power Gen Package G (UCP) | PS5-60-20 - Power Gen Package G (UCP) |  | 2026-04-16
| PS5-60-IE-0004-CC08 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0004-CC08 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0004 | PS5-60-22 - Power Gen Master UCP | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-60-IE-0004-CC11 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0004-CC11 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-60-IE-0004 | PS5-60-22 - Power Gen Master UCP | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0004-CC12 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0004-CC12 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0004 | PS5-60-22 - Power Gen Master UCP | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-60-SEA-0001-CC18 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-SEA-0001-CC18 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-60-SEA-0001 | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100A-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-61-IDH-3100A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100A-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100A-CC02 | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100A-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100A-CC03 | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100B-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-61-IDH-3100B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100B-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100B-CC02 | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0056 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100B-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100B-CC03 | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0056 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100C-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-61-IDH-3100C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0056 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100C-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100C-CC02 | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0056 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100C-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C |  | 2026-04-16
| PS5-71-BI-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-0001-CC01 | I | Cable FROM PS5-26-LA-0001 TO PS5-71-BI-0001 | PS5-71-02 - CFO Allocation Metering Package | PS5-71-02 - CFO Allocation Metering Package |  | 2026-04-16
| PS5-71-BI-0021-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-26-LA-0001 TO PS5-71-BI-0021 | PS5-71-02 - CFO Allocation Metering Package | PS5-71-02 - CFO Allocation Metering Package |  | 2026-04-16
| PS5-71-BI-0021-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-0021-CC02 | I | Cable FROM PS5-26-LA-0001 TO PS5-71-BI-0021 | PS5-71-02 - CFO Allocation Metering Package | PS5-71-02 - CFO Allocation Metering Package |  | 2026-04-16
| PS5-71-BI-1109-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1109-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1109 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1110-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1110-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-71-BI-1110 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1111-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1111-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1111 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1112-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1112-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1112 | PS5-71-17 - Diesel Fuel Distribution Header | PS5-71-17 - Diesel Fuel Distribution Header | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1113-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1113-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1113 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1116-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1116-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1116 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1117-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1117-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-71-BI-1117 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1201-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2101 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB |  | 2026-04-16
| PS5-71-BI-1305-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1305-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-71-BI-1305 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1306-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1306-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-71-BI-1306 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1308-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1308-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-71-BI-1308 | PS5-71-15 - Diesel Fuel Storage Tank | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-12-0063 | 2026-04-24 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2107-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2107-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2107 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0048 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2113-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2113-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-71-BI-2113 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2114-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2114-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2114 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2115-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2115-CC01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2115 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2116-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2116-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-71-BI-2116 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2118-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2118-CC01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2118 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0055 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2119-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2119-CC01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2119 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0055 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2120-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2120-CC01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2120 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0055 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2121-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2121-CC01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2121 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0055 | 2026-05-06 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2122-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2122-CC01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2122 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2123-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2123-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2123 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0111 | 2026-07-23 | Accepted | Elizabeth | Testing
| PS5-71-BI-2124-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2124-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2124 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2125-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2125-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2125 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2306-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2306-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2306 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-05-09 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2307-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2307-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2307 | PS5-71-15 - Diesel Fuel Storage Tank | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2310-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2310-CC01 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-71-BI-2310 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-05-09 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2313-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2313-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2313 | PS5-71-15 - Diesel Fuel Storage Tank | PS5-71-15 - Diesel Fuel Storage Tank
| PS5-71-BI-2314-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2314-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2314 | PS5-91-01 - Multicore cables & JB | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-12-0045 | 2026-05-09 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2317-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2317-CC01 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-71-BI-2317 | PS5-71-15 - Diesel Fuel Storage Tank | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0001-CC08 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0001-CC08 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0001 | PS5-71-19 - Diesel Separator Module (UCP) | PS5-71-19 - Diesel Separator Module (UCP) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0001-CC09 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0001-CC09 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-IN-0001 | PS5-71-19 - Diesel Separator Module (UCP) | PS5-71-19 - Diesel Separator Module (UCP) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0001-CC10 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0001-CC10 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-71-IN-0001 | PS5-71-19 - Diesel Separator Module (UCP) | PS5-71-19 - Diesel Separator Module (UCP) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0002-CC05 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0002-CC05 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0002 | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | 2026-04-17
| PS5-71-IN-0002-CC06 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0002-CC06 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-IN-0002 | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | 2026-04-17
| PS5-71-IN-0002-CC07 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0002-CC07 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-71-IN-0002 | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | 2026-04-17
| PS5-71-IN-0003-CC05 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0003-CC05 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0003 | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0003-CC06 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0003-CC06 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-IN-0003 | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0003-CC07 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0003-CC07 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-71-IN-0003 | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0004A-CC08 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004A-CC08 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0004A | PS5-71-07 - Crude Fuel Separation Module (UCP) | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0004A-CC09 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004A-CC09 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-71-IN-0004A | PS5-71-07 - Crude Fuel Separation Module (UCP) | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0004A-CC12 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004A-CC12 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-71-IN-0004A | PS5-71-07 - Crude Fuel Separation Module (UCP) | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0004B-CC08 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004B-CC08 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0004B | PS5-71-07 - Crude Fuel Separation Module (UCP) | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0004B-CC09 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004B-CC09 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-71-IN-0004B | PS5-71-07 - Crude Fuel Separation Module (UCP) | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0004B-CC12 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004B-CC12 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-71-IN-0004B | PS5-71-07 - Crude Fuel Separation Module (UCP) | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
| PS5-71-TIT-2403A-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-TIT-2403A-CJ01 | I | Cable FROM PS5-71-IE-0001 TO PS5-71-TIT-2403A | PS5-71-01 - CFO Storage Tank Feed Heater | PS5-71-01 - CFO Storage Tank Feed Heater |  | 2026-04-16
| PS5-71-TIT-2403B-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-TIT-2403B-CJ01 | I | Cable FROM PS5-71-IE-0002 TO PS5-71-TIT-2403B | PS5-71-01 - CFO Storage Tank Feed Heater | PS5-71-01 - CFO Storage Tank Feed Heater |  | 2026-04-16
| PS5-74-LB-5101-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-74-LB-5101-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-74-LB-5101 | PS5-74-02 - N2 Generation Skid (UCP) | PS5-74-02 - N2 Generation Skid (UCP) | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-74-LB-5101-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-74-LB-5101-CJ01 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-74-LB-5101 | PS5-74-02 - N2 Generation Skid (UCP) | PS5-74-02 - N2 Generation Skid (UCP) | CPP-RFI-68-64-12-0063 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-75-BI-1177-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-1177-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-75-BI-1177 | PS5-75-02 - Biocide Injection Package | PS5-75-02 - Biocide Injection Package | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-75-BI-1178-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-1178-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-75-BI-1178 | PS5-75-03 - Corrosion Inhibitor Injection Package | PS5-75-03 - Corrosion Inhibitor Injection Package | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-75-BI-1371-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-1371-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-75-BI-1371 | PS5-75-02 - Biocide Injection Package | PS5-75-02 - Biocide Injection Package | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-75-BI-1372-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-1372-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-75-BI-1372 | PS5-75-03 - Corrosion Inhibitor Injection Package | PS5-75-03 - Corrosion Inhibitor Injection Package | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-75-BI-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-0001-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-75-BI-0001 | PS5-75-01 - DRA Injection Package | PS5-75-01 - DRA Injection Package | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-75-BI-0002-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-0002-CC01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-75-BI-0002 | PS5-75-01 - DRA Injection Package | PS5-75-01 - DRA Injection Package | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-75-BI-0002-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-0002-CC02 | I | Cable FROM PS5-04-PMC-0006 TO PS5-75-BI-0002 | PS5-75-01 - DRA Injection Package | PS5-75-01 - DRA Injection Package | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-75-BI-0002-CC03 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-0002-CC03 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-75-BI-0002 | PS5-75-01 - DRA Injection Package | PS5-75-01 - DRA Injection Package | CPP-RFI-68-64-12-0056 | 2026-05-20 | Accepted | Elizabeth | TESTING
| PS5-75-MOV-0001-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-MOV-0001-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-75-MOV-0001 | PS5-28-07 - Open Drains (OD2) | PS5-28-07 - Open Drains (OD2) | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-75-MOV-0001-CC02 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-MOV-0001-CC02 | I | Cable FROM PS5-04-PMC-0003 TO PS5-75-MOV-0001 | PS5-28-07 - Open Drains (OD2) | PS5-28-07 - Open Drains (OD2) | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0001-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0001-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0001 | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0002-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0002-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0002 | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) |  | 2026-04-16
| PS5-79-IG-0003-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0003-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0003 | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0004-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0004-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0004 | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0005-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0005-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0005 | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0006-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0006-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0006 | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0007-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0007-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0007 | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0008-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0008-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0008 | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0009-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0009-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0009 | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | CPP-RFI-68-64-12-0055 | 2026-04-16 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0010-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0010-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0010 | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0011-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0011-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0011 | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0012-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0012-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0012 | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-83-EHO-0001A-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001A-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-83-EHO-0001A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-83-EHO-0001A-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001A-CJ01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-83-EHO-0001A | PS5-25-02 - Crude Oil Export Pump A | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-83-EHO-0001B-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001B-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-83-EHO-0001B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-83-EHO-0001B-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001B-CJ01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-83-EHO-0001B | PS5-25-03 - Crude Oil Export Pump B | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-83-EHO-0001C-CC01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001C-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-83-EHO-0001C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
| PS5-83-EHO-0001C-CJ01 | TJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001C-CJ01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-83-EHO-0001C | PS5-25-04 - Crude Oil Export Pump C | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0073 | 2026-06-23 | Accepted | Elizabeth | TESTING
T-00235-0013 | PS5-25-DM-3100A | TPX12 - Motor HV | #N/A | E | CRUDE OIL EXPORT PUMP A MOTOR |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-18-0364 | 2026-06-18 | Accepted | Bertus Wikael | TESTING
T-00235-0014 | PS5-25-DM-3100B | TPX12 - Motor HV | #N/A | E | CRUDE OIL EXPORT PUMP B MOTOR |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-18-0364 | 2026-06-18 | Accepted | Bertus Wikael | TESTING
T-00235-0015 | PS5-25-DM-3100C | TPX12 - Motor HV | #N/A | E | CRUDE OIL EXPORT PUMP C MOTOR |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-18-0364 | 2026-06-18 | Accepted | Bertus Wikael | TESTING
T-00236-0155 | PS5-28-DM-3300 | TPX13 - Motor LV | #N/A | E | Relief Drum Pump Motor |  | PS5-28-06 - Relief Drum and Pump
T-00236-0156 | PS5-28-DM-3400 | TPX13 - Motor LV | #N/A | E | Closed Drain Drum 01 Pump Motor |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00236-0157 | PS5-28-DM-3500 | TPX13 - Motor LV | #N/A | E | Oily Water Sump Pump Motor |  | PS5-28-08 - Open Drain Sump and Pumps
T-00236-0158 | PS5-28-DM-3600A | TPX13 - Motor LV | #N/A | E | Open Drain Sump Pump Motor A |  | PS5-28-08 - Open Drain Sump and Pumps
T-00236-0159 | PS5-28-DM-3600B | TPX13 - Motor LV | #N/A | E | Open Drain Sump Pump Motor B |  | PS5-28-08 - Open Drain Sump and Pumps
T-00236-0160 | PS5-28-DM-3700A | TPX13 - Motor LV | #N/A | E | Closed Drain Drum 02 Pump Motor A |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00236-0161 | PS5-28-DM-3700B | TPX13 - Motor LV | #N/A | E | Closed Drain Drum 02 Pump Motor B |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00236-0162 | PS5-28-DM-3800A | TPX13 - Motor LV | #N/A | E | Seal Oil Drain Drum Pump Motor A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00236-0163 | PS5-28-DM-3800B | TPX13 - Motor LV | #N/A | E | Seal Oil Drain Drum Pump Motor B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00236-0164 | PS5-28-DM-3800C | TPX13 - Motor LV | #N/A | E | Seal Oil Drain Drum Pump Motor C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00236-0165 | PS5-28-DM-3900A | TPX13 - Motor LV | #N/A | E | Reinjection Pump Motor A |  | PS5-28-17 - Reinjection Pump
T-00236-0166 | PS5-28-DM-3900B | TPX13 - Motor LV | #N/A | E | Reinjection Pump Motor B |  | PS5-28-17 - Reinjection Pump
T-00236-0167 | PS5-53-DM-3100A | TPX13 - Motor LV | #N/A | E | Water Distribution Pump Motor A |  | PS5-53-02 - Water Distribution Pump A/B
T-00236-0168 | PS5-53-DM-3100B | TPX13 - Motor LV | #N/A | E | Water Distribution Pump Motor B |  | PS5-53-02 - Water Distribution Pump A/B
T-00236-0169 | PS5-60-DM-3300 | TPX13 - Motor LV | #N/A | E | Cooling Water Pump Motor |  | PS5-60-24 - Cooling Water Tank & Pump
T-00236-0170 | PS5-60-DM-3400 | TPX13 - Motor LV | #N/A | E | Cooling Water Return Pump Motor |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump
T-00236-0171 | PS5-71-DM-3100A | TPX13 - Motor LV | #N/A | E | Diesel Fuel Supply Pump Motor A |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00236-0172 | PS5-71-DM-3100B | TPX13 - Motor LV | #N/A | E | Diesel Fuel Supply Pump Motor B |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00236-0173 | PS5-71-DM-3200 | TPX13 - Motor LV | #N/A | E | Diesel Fuel Make-Up Pump Motor |  | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station
T-00236-0174 | PS5-71-DM-3300A | TPX13 - Motor LV | #N/A | E | Crude Fuel Oil Transfer Pump Motor A |  | PS5-71-05 - CFO Transfer Pump A/B
T-00236-0175 | PS5-71-DM-3300B | TPX13 - Motor LV | #N/A | E | Crude Fuel Oil Transfer Pump Motor B |  | PS5-71-05 - CFO Transfer Pump A/B
T-00236-0176 | PS5-71-DM-3400A | TPX13 - Motor LV | #N/A | E | Crude Fuel Oil Service Pump Motor A |  | PS5-71-13 - CFO Service Pump A/B
T-00236-0177 | PS5-71-DM-3400B | TPX13 - Motor LV | #N/A | E | Crude Fuel Oil Service Pump Motor B |  | PS5-71-13 - CFO Service Pump A/B
T-00236-0178 | PS5-71-DM-3500A | TPX13 - Motor LV | #N/A | E | Diesel Transfer Pump Motor A |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00236-0179 | PS5-71-DM-3500B | TPX13 - Motor LV | #N/A | E | Diesel Transfer Pump Motor B |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00236-0286 | PS5-28-DM-31100 | TPX13 - Motor LV | #N/A | E | OIL SKIMMER MOTOR |  | PS5-28-10 - Oil Skimmer Package
T-00238-0457 | PS5-60-IE-0003A | TPX15 - Distribution board/console/control panel | #N/A | E | GCP G-1 (A) |  | PS5-60-02 - Power Gen Package A (UCP)
T-00238-0458 | PS5-60-IE-0003B | TPX15 - Distribution board/console/control panel | #N/A | E | GCP G-2 (B) |  | PS5-60-05 - Power Gen Package B (UCP)
T-00238-0459 | PS5-60-IE-0003C | TPX15 - Distribution board/console/control panel | #N/A | E | GCP G-3 (C) |  | PS5-60-08 - Power Gen Package C (UCP)
T-00238-0460 | PS5-60-IE-0003D | TPX15 - Distribution board/console/control panel | #N/A | E | GCP G-4 (D) |  | PS5-60-11 - Power Gen Package D (UCP)
T-00238-0461 | PS5-60-IE-0003E | TPX15 - Distribution board/console/control panel | #N/A | E | GCP G-5 (E) |  | PS5-60-14 - Power Gen Package E (UCP)
T-00238-0462 | PS5-60-IE-0003F | TPX15 - Distribution board/console/control panel | #N/A | E | GCP G-6 (F) |  | PS5-60-17 - Power Gen Package F (UCP)
T-00238-0463 | PS5-60-IE-0003G | TPX15 - Distribution board/console/control panel | #N/A | E | GCP G-7 (G) |  | PS5-60-20 - Power Gen Package G (UCP)
T-00238-0464 | PS5-60-IE-0004 | TPX15 - Distribution board/console/control panel | #N/A | E | MCP- MASTER CONTROL PANEL |  | PS5-60-22 - Power Gen Master UCP
T-00238-0465 | PS5-60-IH-0001A | TPX15 - Distribution board/console/control panel | #N/A | E | GENSET MCC -1 - G1 (A) |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-332-13-0424 | 2026-07-19 | Accepted | Bertus Wikael | Testing | N/A | N/A | N/A
T-00238-0466 | PS5-60-IH-0001B | TPX15 - Distribution board/console/control panel | #N/A | E | GENSET MCC -2 - G2 (B) |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-332-13-0424 | 2026-07-19 | Accepted | Bertus Wikael | Testing | N/A | N/A | N/A
T-00238-0467 | PS5-60-IH-0001C | TPX15 - Distribution board/console/control panel | #N/A | E | GENSET MCC -3 - G3 (C) |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-332-13-0424 | 2026-07-19 | Accepted | Bertus Wikael | Testing | N/A | N/A | N/A
T-00238-0468 | PS5-60-IH-0001D | TPX15 - Distribution board/console/control panel | #N/A | E | GENSET MCC -4 - G4 (D) |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | CPP-RFI-68-332-13-0424 | 2026-07-19 | Accepted | Bertus Wikael | Testing | N/A | N/A | N/A
T-00238-0469 | PS5-60-IH-0001E | TPX15 - Distribution board/console/control panel | #N/A | E | GENSET MCC -5 - G5 (E) |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | CPP-RFI-68-332-13-0424 | 2026-07-19 | Accepted | Bertus Wikael | Testing | N/A | N/A | N/A
T-00238-0470 | PS5-60-IH-0001F | TPX15 - Distribution board/console/control panel | #N/A | E | GENSET MCC -6 - G6 (F) |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | CPP-RFI-68-332-13-0424 | 2026-07-19 | Accepted | Bertus Wikael | Testing | N/A | N/A | N/A
T-00238-0471 | PS5-60-IH-0001G | TPX15 - Distribution board/console/control panel | #N/A | E | GENSET MCC -7 - G7 (G) |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | CPP-RFI-68-332-13-0424 | 2026-07-19 | Accepted | Bertus Wikael | Testing | N/A | N/A | N/A
T-00238-0472 | PS5-60-IH-0002 | TPX15 - Distribution board/console/control panel | #N/A | E | COMMON / TREATMENT MCC |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-332-13-0424 | 2026-07-19 | Accepted | Bertus Wikael | Testing | N/A | N/A | N/A
T-00238-0473 | PS5-60-IE-0002A | TPX15 - Distribution board/console/control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-01 - Power Generation Package A
T-00238-0474 | PS5-60-IE-0002B | TPX15 - Distribution board/console/control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-04 - Power Generation Package B
T-00238-0475 | PS5-60-IE-0002C | TPX15 - Distribution board/console/control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-07 - Power Generation Package C
T-00238-0476 | PS5-60-IE-0002D | TPX15 - Distribution board/console/control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-10 - Power Generation Package D
T-00238-0477 | PS5-60-IE-0002E | TPX15 - Distribution board/console/control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-13 - Power Generation Package E
T-00238-0478 | PS5-60-IE-0002F | TPX15 - Distribution board/console/control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-16 - Power Generation Package F
T-00238-0479 | PS5-60-IE-0002G | TPX15 - Distribution board/console/control panel | #N/A | E | LOCAL DISPLAY PANEL LDP GENERATOR SET |  | PS5-60-19 - Power Generation Package G
T-00238-0542 | PS5-01-IE-0001A | TPX15 - Distribution board/console/control panel | #N/A | E | Foam Package (PS5-01-UV-8700 Pump Control Panel A) |  | PS5-01-05 - Foam Skid
T-00238-0543 | PS5-01-IE-0001B | TPX15 - Distribution board/console/control panel | #N/A | E | Foam Package (PS5-01-UV-8700 Pump Control Panel B) |  | PS5-01-05 - Foam Skid
T-00238-0544 | PS5-01-IE-0002A | TPX15 - Distribution board/console/control panel | #N/A | E | Fire Water Jockey Pump Control Panel A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00238-0545 | PS5-01-IE-0002B | TPX15 - Distribution board/console/control panel | #N/A | E | Fire Water Jockey Pump Control Panel B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00238-0546 | PS5-01-IE-0009A | TPX15 - Distribution board/console/control panel | #N/A | E | Fire Water starter pump Local Control Panel A |  | PS5-01-02 - Fire Water Pump A
T-00238-0547 | PS5-01-IE-0009B | TPX15 - Distribution board/console/control panel | #N/A | E | Fire Water starter pump Local Control Panel B |  | PS5-01-03 - Fire Water Pump B
T-00238-0549 | PS5-05-IE-8100 | TPX15 - Distribution board/console/control panel | #N/A | E | Unit Control Panel for Emergency Diesel Generator |  | PS5-05-02 - Emergency Diesel Generator Package (UCP)
T-00238-0550 | PS5-50-IE-0001 | TPX15 - Distribution board/console/control panel | #N/A | E | Water Well Submersible Pump Control Panel A |  | PS5-50-01 - Water Well Submersible Pumps (3100)
T-00238-0551 | PS5-50-IE-0002 | TPX15 - Distribution board/console/control panel | #N/A | E | Water Well Submersible Pump Control Panel B |  | PS5-50-02 - Water Well Submersible Pumps (3200)
T-00238-0552 | PS5-60-IN-0002A | TPX15 - Distribution board/console/control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00238-0553 | PS5-60-IN-0002B | TPX15 - Distribution board/console/control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00238-0554 | PS5-60-IN-0002C | TPX15 - Distribution board/console/control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00238-0555 | PS5-60-IN-0002D | TPX15 - Distribution board/console/control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00238-0556 | PS5-60-IN-0002E | TPX15 - Distribution board/console/control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00238-0557 | PS5-60-IN-0002F | TPX15 - Distribution board/console/control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00238-0558 | PS5-60-IN-0002G | TPX15 - Distribution board/console/control panel | #N/A | E | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00238-0559 | PS5-61-IH-0004 | TPX15 - Distribution board/console/control panel | #N/A | E | HVAC MCC |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-332-13-0445 | 2026-07-30 | OPEN | Bertus Wikael | TESTING
T-00238-0560 | PS5-61-IH-0004A | TPX15 - Distribution board/console/control panel | #N/A | E | LOCAL STARTER PANEL FOR GENRATOR BAY 1 EXHAUST FANS |  | PS5-09-03 - HVAC for Generator Building
T-00238-0561 | PS5-61-IH-0004B | TPX15 - Distribution board/console/control panel | #N/A | E | LOCAL STARTER PANEL FOR GENRATOR BAY 2 EXHAUST FANS |  | PS5-09-03 - HVAC for Generator Building
s | PS5-62-IE-0001 | TPX15 - Distribution board/console/control panel | #N/A | E | Lighting Control panel 1 - Pump Station 5 |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPP-RFI-68-332-17-0342 | 2026-06-15 | Accepted | Bertus Wikael | Testing
T-00238-0563 | PS5-62-IE-0002 | TPX15 - Distribution board/console/control panel | #N/A | E | Lighting Control panel 2 - Pump Station 5 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPP-RFI-68-332-17-0342 | 2026-06-15 | Accepted | Bertus Wikael | Testing
T-00238-0564 | PS5-71-IN-0001 | TPX15 - Distribution board/console/control panel | #N/A | E | DFO- SEPARATOR CONTROL PANEL |  | PS5-71-19 - Diesel Separator Module (UCP)
T-00238-0565 | PS5-71-IN-0002 | TPX15 - Distribution board/console/control panel | #N/A | E | CRO-PRE PRESSURECONTROL PANEL |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP)
T-00238-0566 | PS5-71-IN-0003 | TPX15 - Distribution board/console/control panel | #N/A | E | DFO- PRE PRESSURE CONTROL PANEL |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP)
T-00238-0567 | PS5-71-IN-0004A | TPX15 - Distribution board/console/control panel | #N/A | E | CRO- SEPARATOR CONTROL PANEL-1 |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00238-0568 | PS5-71-IN-0004B | TPX15 - Distribution board/console/control panel | #N/A | E | CRO- SEPARATOR CONTROL PANEL-2 |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00238-0714 | PS5-01-IG-0001 | TPX15 - Distribution board/console/control panel | #N/A | E | Water Mist System Main Distribution Board |  | PS5-01-10 - Water Mist Package
T-00238-0715 | PS5-05-IG-0002 | TPX15 - Distribution board/console/control panel | #N/A | E | Indoor Emergency L&SP DB Office and Facilities Building |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00238-0716 | PS5-05-IG-0004 | TPX15 - Distribution board/console/control panel | #N/A | E | Outdoor Emergency Lighting Distribution Board PS-5 |  | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | CPP-RFI-68-332-17-0342 | 2026-06-15 | Accepted | Bertus Wikael | Testing
T-00238-0717 | PS5-05-IG-0006 | TPX15 - Distribution board/console/control panel | #N/A | E | Outdoor Emergency Lighting Distribution Board PS-5 |  | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | CPP-RFI-68-332-17-0342 | 2026-06-15 | Accepted | Bertus Wikael | Testing
T-00238-0718 | PS5-05-IG-0007 | TPX15 - Distribution board/console/control panel | #N/A | E | Indoor Emergency L&SP DB - Guard House |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00238-0719 | PS5-05-IG-0025 | TPX15 - Distribution board/console/control panel | #N/A | E | CRO Generator Building Emergency Lighting Distribution Board PS-5 |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00238-0720 | PS5-05-IG-0026 | TPX15 - Distribution board/console/control panel | #N/A | E | Generator Electrical Building Emergency Lighting Distribution Board PS-5 |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00238-0721 | PS5-06-IG-0004A | TPX15 - Distribution board/console/control panel | #N/A | E | AC UPS DB - Generator Electrical Bldng |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-332-13-0445 | 2026-07-30 | OPEN | Bertus Wikael | TESTING
T-00238-0722 | PS5-06-IG-0004B | TPX15 - Distribution board/console/control panel | #N/A | E | AC UPS DB - Generator Electrical Bldng |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-332-13-0445 | 2026-07-30 | OPEN | Bertus Wikael | TESTING
T-00238-0723 | PS5-61-IG-0006 | TPX15 - Distribution board/console/control panel | #N/A | E | Outdoor Normal Lighting Distribution Board PS-5 |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | CPP-RFI-68-332-17-0342 | 2026-06-15 | Accepted | Bertus Wikael | Testing
T-00238-0724 | PS5-61-IG-0007 | TPX15 - Distribution board/console/control panel | #N/A | E | Outdoor Normal Lighting Distribution Board PS-5 |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | CPP-RFI-68-332-17-0342 | 2026-06-15 | Accepted | Bertus Wikael | Testing
T-00238-0725 | PS5-61-IG-0014 | TPX15 - Distribution board/console/control panel | #N/A | E | Outdoor Power Distribution Board PS-5 |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | CPP-RFI-68-332-17-0342 | 2026-06-15 | Accepted | Bertus Wikael | Testing
T-00238-0726 | PS5-61-IG-0015 | TPX15 - Distribution board/console/control panel | #N/A | E | CRO Generator Building Normal L&SP Distribution Board PS-5 |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00238-0727 | PS5-61-IG-0016 | TPX15 - Distribution board/console/control panel | #N/A | E | Generator Electrical Building Normal L&SP Distribution Board PS-5 |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00238-0728 | PS5-61-IG-0042 | TPX15 - Distribution board/console/control panel | #N/A | E | Outdoor valves Distribution Board PS-5 |  | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | CPP-RFI-68-332-17-0342 | 2026-06-15 | Accepted | Bertus Wikael | Testing
T-00238-0729 | PS5-61-IG-0043 | TPX15 - Distribution board/console/control panel | #N/A | E | Outdoor valves Distribution Board PS-5 |  | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | CPP-RFI-68-332-17-0342 | 2026-06-15 | Accepted | Bertus Wikael | Testing
T-00238-0730 | PS5-74-IG-5101 | TPX15 - Distribution board/console/control panel | #N/A | E | Nitrogen Generation Skid Power Distribution Panel |  | PS5-74-01 - N2 Generation Skid
T-00238-0731 | PS5-79-IG-0001 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 1 |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | CPP-RFI-68-332-17-0335 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00238-0732 | PS5-79-IG-0002 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 2 |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | CPP-RFI-68-332-17-0335 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00238-0733 | PS5-79-IG-0003 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 3 |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | CPP-RFI-68-332-17-0335 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00238-0734 | PS5-79-IG-0004 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 4 |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | CPP-RFI-68-332-17-0335 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00238-0735 | PS5-79-IG-0005 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 5 |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | CPP-RFI-68-332-17-0335 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00238-0736 | PS5-79-IG-0006 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 6 |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | CPP-RFI-68-332-17-0335 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00238-0737 | PS5-79-IG-0007 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 7 |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | CPP-RFI-68-332-17-0335 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00238-0738 | PS5-79-IG-0008 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 8 |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | CPP-RFI-68-332-17-0335 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00238-0739 | PS5-79-IG-0009 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 9 |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | CPP-RFI-68-332-17-0335 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00238-0740 | PS5-79-IG-0010 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 10 |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | CPP-RFI-68-332-17-0335 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00238-0741 | PS5-79-IG-0011 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 11 |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | CPP-RFI-68-332-17-0335 | 2026-06-11 | Accepted | Bertus Wikael | TESTING
T-00238-0742 | PS5-79-IG-0012 | TPX15 - Distribution board/console/control panel | #N/A | E | EHT Distribution Board 12 |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00238-0819 | PS5-09-LB-0008 | TPX15 - Distribution board/console/control panel | #N/A | E | HUCP |  | PS5-09-03 - HVAC for Generator Building
T-00238-0820 | PS5-61-IH-0004C | TPX15 - Distribution board/console/control panel | #N/A | E | LOCAL STARTER PANEL FOR GENRATOR BAY 3 EXHAUST FANS |  | PS5-09-03 - HVAC for Generator Building
T-00238-0821 | PS5-61-IH-0004D | TPX15 - Distribution board/console/control panel | #N/A | E | LOCAL STARTER PANEL FOR GENRATOR BAY 4 EXHAUST FANS |  | PS5-09-03 - HVAC for Generator Building
T-00238-0858 | PS5-09-LB-7001 | TPX15 - Distribution board/console/control panel | #N/A | E | HVAC UCP - Guard House |  | PS5-09-02 - HVAC for Guard House
T-00239-0234 | PS5-06-GU-0003A | TPX16 - Charger / inverter | #N/A | E | AC UPS Generator Building |  | PS5-06-02 - AC UPS - Power Generator Building
T-00239-0235 | PS5-06-GU-0003B | TPX16 - Charger / inverter | #N/A | E | AC UPS Generator Building |  | PS5-06-02 - AC UPS - Power Generator Building
T-00239-0236 | PS5-06-GU-0003C | TPX16 - Charger / inverter | #N/A | E | AC UPS Generator Building - BYPASS |  | PS5-06-02 - AC UPS - Power Generator Building
T-00240-1264 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1265 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1266 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1267 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1268 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1269 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1270 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1271 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1272 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1273 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1274 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1275 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1276 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002
T-00240-1277 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00240-1278 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00240-1279 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00240-1280 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00240-1281 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00240-1282 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00240-1283 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00240-1284 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00240-1285 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00240-1286 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00240-1287 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025
T-00240-1288 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00240-1289 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00240-1290 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00240-1291 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00240-1292 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00240-1293 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026
T-00240-1294 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1295 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1296 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1297 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1298 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1299 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1300 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1301 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1302 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1303 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1304 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1305 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00240-1306 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00240-1307 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00240-1308 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00240-1309 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00240-1310 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00240-1311 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00240-1312 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00240-1313 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00240-1314 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006
T-00240-1315 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00240-1316 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00240-1317 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00240-1318 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00240-1319 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00240-1320 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00240-1321 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00240-1322 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00240-1323 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00240-1324 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007
T-00240-1325 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010
T-00240-1326 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010
T-00240-1327 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010
T-00240-1328 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1329 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1330 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1331 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1332 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1333 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1334 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1335 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1336 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1337 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1338 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1339 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1340 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1341 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00240-1342 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00240-1343 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00240-1344 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00240-1345 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00240-1346 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00240-1347 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111
T-00240-1348 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112
T-00240-1349 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1350 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1351 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1352 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1353 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1354 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1355 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1356 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1357 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1358 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1359 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1360 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1361 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1362 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1363 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001
T-00240-1364 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1365 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1366 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1367 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1368 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1369 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1370 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1371 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1372 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1373 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1374 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1375 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1376 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1377 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1378 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00240-1379 |  | TPX18 - Lighting circuits | #N/A | E |  |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002
T-00241-0165 | PS5-25-UD-3100A | TPX19 - Power socket outlet | #N/A | E | 5 pin 32A plug and socket for Oil Purifier Control Panel(Portable Load) |  | PS5-25-02 - Crude Oil Export Pump A
T-00241-0166 | PS5-28-ISO-2008 | TPX19 - Power socket outlet | #N/A | E | Socket Outlet 63A for mobile oil skimmer (PS5-28-UZ-8100) |  | PS5-28-10 - Oil Skimmer Package
T-00241-0438 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00241-0439 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00241-0440 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00241-0441 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00241-0442 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007
T-00241-0443 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-06-05 - AC UPS - Workshop & Warehouse
T-00241-0444 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-06-05 - AC UPS - Workshop & Warehouse
T-00241-0445 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-06-05 - AC UPS - Workshop & Warehouse
T-00241-0446 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00241-0447 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00241-0448 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00241-0449 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00241-0450 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00241-0451 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00241-0452 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00241-0453 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00241-0454 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00241-0455 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00241-0456 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002
T-00241-0457 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010
T-00241-0458 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010
T-00241-0459 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00241-0460 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00241-0461 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00241-0462 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00241-0463 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00241-0464 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00241-0465 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00241-0466 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014
T-00241-0467 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00241-0468 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00241-0469 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015
T-00241-0470 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00241-0471 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016
T-00241-0472 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111
T-00241-0473 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111
T-00241-0474 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112
T-00241-0475 |  | TPX19 - Power socket outlet | #N/A | E |  |  | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112
T-00242-0044 | PS5-28-HE-2100 | TPX20 - Heater | #N/A | E | CLOSED DRAIN DRUM HEATER 01 |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00242-0045 | PS5-28-HE-2200 | TPX20 - Heater | #N/A | E | CLOSED DRAIN DRUM HEATER 02 |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00242-0046 | PS5-71-HE-2200 | TPX20 - Heater | #N/A | E | CRUDE FUEL OIL SERVICE TANK HEATER |  | PS5-71-12 - CFO Service Tank
T-00242-0047 | PS5-71-HE-2300 | TPX20 - Heater | #N/A | E | CRUDE FUEL OIL STORAGE TANK HEATER |  | PS5-71-04 - CFO Storage Tank
T-00242-0048 | PS5-71-HE-2400A | TPX20 - Heater | #N/A | E | CRUDE FUEL OIL STORAGE TANK FEED HEATER |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00242-0049 | PS5-71-HE-2400B | TPX20 - Heater | #N/A | E | CRUDE FUEL OIL STORAGE TANK FEED HEATER |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00242-0068 | PS5-25-HE-2100 | TPX20 - Heater | #N/A | E | Crude Oil Export Pump Motor A - Lube Oil System Oil Reservoir Heater |  | PS5-25-02 - Crude Oil Export Pump A
T-00242-0069 | PS5-25-HE-2200 | TPX20 - Heater | #N/A | E | Crude Oil Export Pump Motor B - Lube Oil System Oil Reservoir Heater |  | PS5-25-03 - Crude Oil Export Pump B
T-00242-0070 | PS5-25-HE-2300 | TPX20 - Heater | #N/A | E | Crude Oil Export Pump Motor C - Lube Oil System Oil Reservoir Heater |  | PS5-25-04 - Crude Oil Export Pump C
T-00243-0041 | PS5-61-NER-0010 | TPX21 - Neutral earthing resistor | #N/A | E | LLHT Transformer NER |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010)
T-00243-0042 | PS5-61-NER-0011 | TPX21 - Neutral earthing resistor | #N/A | E | LLHT Transformer NER |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011)
T-00243-0043 | PS5-63-NER-0010 | TPX21 - Neutral earthing resistor | #N/A | E | Earthing Transformer NER |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00243-0044 | PS5-63-NER-0011 | TPX21 - Neutral earthing resistor | #N/A | E | Earthing Transformer NER |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00243-0059 | PS5-60-IJ-0001A | TPX21 - Neutral earthing resistor | #N/A | E | Neutral Grounding resistor for Generator set 1 (A) |  | PS5-60-01 - Power Generation Package A
T-00243-0060 | PS5-60-IJ-0001B | TPX21 - Neutral earthing resistor | #N/A | E | Neutral Grounding resistor for Generator set 2 (B) |  | PS5-60-04 - Power Generation Package B
T-00243-0061 | PS5-60-IJ-0001C | TPX21 - Neutral earthing resistor | #N/A | E | Neutral Grounding resistor for Generator set 3 (C) |  | PS5-60-07 - Power Generation Package C
T-00243-0062 | PS5-60-IJ-0001D | TPX21 - Neutral earthing resistor | #N/A | E | Neutral Grounding resistor for Generator set 4 (D) |  | PS5-60-10 - Power Generation Package D
T-00243-0063 | PS5-60-IJ-0001E | TPX21 - Neutral earthing resistor | #N/A | E | Neutral Grounding resistor for Generator set 5 (E) |  | PS5-60-13 - Power Generation Package E
T-00243-0064 | PS5-60-IJ-0001F | TPX21 - Neutral earthing resistor | #N/A | E | Neutral Grounding resistor for Generator set 6 (F) |  | PS5-60-16 - Power Generation Package F
T-00243-0065 | PS5-60-IJ-0001G | TPX21 - Neutral earthing resistor | #N/A | E | Neutral Grounding resistor for Generator set 7 (G) |  | PS5-60-19 - Power Generation Package G
T-00244-1357 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1358 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1359 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1360 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1361 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1362 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1363 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1364 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1365 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1366 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1367 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1368 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1369 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1370 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1371 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1372 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1373 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1374 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1375 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1376 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1377 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1378 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1379 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1380 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1381 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1382 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1383 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1384 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1385 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001)
T-00244-1386 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1387 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1388 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1389 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1390 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1391 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1392 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1393 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1394 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1395 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1396 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1397 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1398 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1399 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1400 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1401 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1402 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1403 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1404 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1405 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1406 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1407 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1408 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1409 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1410 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1411 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1412 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1413 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1414 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1415 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002)
T-00244-1416 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1417 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1418 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1419 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1420 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1421 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1422 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1423 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1424 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1425 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1426 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1427 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1428 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1429 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1430 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1431 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1432 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1433 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1434 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1435 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1436 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1437 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1438 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1439 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1440 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1441 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1442 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1443 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1444 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003)
T-00244-1445 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1446 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1447 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1448 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1449 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1450 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1451 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1452 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1453 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1454 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1455 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1456 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1457 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1458 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1459 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1460 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1461 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1462 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1463 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1464 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1465 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1466 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1467 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1468 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1469 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1470 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1471 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004)
T-00244-1472 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1473 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1474 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1475 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1476 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1477 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1478 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1479 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1480 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1481 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1482 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1483 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1484 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1485 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1486 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1487 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1488 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1489 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1490 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1491 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1492 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1493 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1494 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1495 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1496 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1497 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1498 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1499 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005)
T-00244-1500 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1501 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1502 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1503 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1504 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1505 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1506 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1507 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1508 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1509 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1510 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1511 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1512 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1513 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1514 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1515 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1516 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1517 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1518 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1519 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1520 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1521 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1522 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1523 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1524 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1525 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1526 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1527 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1528 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1529 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1530 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1531 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006)
T-00244-1532 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1533 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1534 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1535 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1536 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1537 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1538 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1539 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1540 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1541 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1542 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1543 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1544 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1545 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1546 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1547 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1548 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1549 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1550 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1551 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1552 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1553 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1554 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1555 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1556 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1557 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1558 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1559 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1560 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1561 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1562 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1563 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007)
T-00244-1564 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1565 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1566 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1567 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1568 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1569 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1570 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1571 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1572 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1573 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1574 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1575 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1576 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1577 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1578 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1579 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1580 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1581 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1582 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1583 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1584 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1585 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1586 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1587 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1588 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1589 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1590 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1591 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1592 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1593 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1594 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1595 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008)
T-00244-1596 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1597 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1598 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1599 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1600 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1601 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1602 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1603 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1604 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1605 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1606 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1607 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1608 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1609 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1610 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1611 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1612 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1613 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1614 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1615 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1616 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1617 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1618 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1619 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1620 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1621 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1622 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1623 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1624 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1625 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1626 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1627 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009)
T-00244-1628 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1629 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1630 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1631 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1632 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1633 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1634 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1635 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1636 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1637 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1638 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1639 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1640 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1641 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1642 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1643 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1644 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1645 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1646 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1647 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1648 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1649 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1650 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1651 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1652 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1653 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1654 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1655 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1656 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1657 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010)
T-00244-1658 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1659 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1660 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1661 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1662 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1663 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1664 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1665 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1666 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1667 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1668 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1669 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1670 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1671 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1672 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1673 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1674 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1675 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1676 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1677 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1678 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1679 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1680 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1681 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1682 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1683 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1684 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1685 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1686 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1687 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011)
T-00244-1688 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1689 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1690 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1691 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1692 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1693 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1694 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1695 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1696 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1697 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1698 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1699 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1700 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1701 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1702 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1703 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1704 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1705 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1706 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1707 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1708 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1709 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1710 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1711 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1712 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1713 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1714 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1715 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1716 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1717 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1718 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1719 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1720 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1721 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00244-1722 |  | TPX22 - Tape Trace Heating | #N/A | E |  |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012)
T-00247-0134 | PS5 - CFO AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0135 | PS5 - CHEMICAL AND WASTE STORAGE AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0136 | PS5 - CLOSED DRAIN DRUM AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0137 | PS5 - DIESEL FUEL STORAGE AND PUMP AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0138 | PS5 - EXPORT PUMP VSD AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0139 | PS5 - EXPORT LOADING PUMP AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0140 | PS5 - FENCE EAST AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0141 | PS5 - FENCE SOUTH WEST AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0142 | PS5 - FENCE WEST AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0143 | PS5 - FENCE SOUTH EAST AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0144 | PS5 - LAUNCHER/RECEIVER AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0145 | PS5 - OBSERVATION BASIN AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0146 | PS5 - POWER DISTRIBUTION AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0147 | PS5 - POWER GENERATION BUILDING AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0148 | PS5 - POWER GENERATION COOLING TOWER AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0149 | PS5 - TURNSTILE GATE AND OFFICE BUILDING AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0150 | PS5 - UTILITY AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0151 | PS5 - UTILITY/FIRE WATER STORAGE TANK AREA_Earthing | TPX26 - Earthing system | #N/A | E | Earthing |  | PS5-63-01 - Electrical Earthing
T-00247-0152 | PS5-82-OB-0001_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Office and Facilities building |  | PS5-63-02 - Electrical Earthing - Office and Facilities building
T-00247-0153 | PS5-82-OB-0005_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Guard House |  | PS5-63-06 - Electrical Earthing - Guard House
T-00247-0154 | PS5-82-OB-0009A_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Guard Hut A |  | PS5-63-05 - Electrical Earthing - Guard Hut A & B
T-00247-0155 | PS5-82-OB-0009B_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Guard Hut B |  | PS5-63-05 - Electrical Earthing - Guard Hut A & B
T-00247-0157 | PS5-84-OB-0001_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Workshop & Warehouse |  | PS5-63-07 - Electrical Earthing - Workshop & Warehouse
T-00247-0158 | PS5-84-OB-0003_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Hazardous Waste Shelter |  | PS5-63-01 - Electrical Earthing
T-00247-0159 | PS5-84-OB-0004_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Non-Hazardous Waste Shelter |  | PS5-63-01 - Electrical Earthing
T-00247-0160 | PS5-84-OB-0005_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Generator Electrical Building |  | PS5-63-03 - Electrical Earthing - Generator Building
T-00247-0161 | PS5-84-OB-0006_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Chemical Storage Shelter |  | PS5-63-01 - Electrical Earthing
T-00247-0162 | PS5-84-OB-0007_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Chemical Waste Storage Shelter |  | PS5-63-01 - Electrical Earthing
T-00247-0163 | PS5-86-OB-0001_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Closed Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00247-0164 | PS5-86-OB-0002_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Relief Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00247-0165 | PS5-86-OB-0003_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Fire Water Pump Shelter |  | PS5-63-01 - Electrical Earthing
T-00247-0166 | PS5-86-OB-0004_Earthing | TPX26 - Earthing system | #N/A | E | Earthing for Closed Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00248-0052 | PS5 - RECEIVER AND LAUNCHER AREA_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning |  | PS5-63-01 - Electrical Earthing
T-00248-0053 | PS5-82-OB-0001_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Office and Facilities building |  | PS5-63-02 - Electrical Earthing - Office and Facilities building
T-00248-0054 | PS5-82-OB-0005_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Guard House |  | PS5-63-06 - Electrical Earthing - Guard House
T-00248-0055 | PS5-82-OB-0009A_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Guard Hut A |  | PS5-63-05 - Electrical Earthing - Guard Hut A & B
T-00248-0056 | PS5-82-OB-0009B_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Guard Hut B |  | PS5-63-05 - Electrical Earthing - Guard Hut A & B
T-00248-0057 | PS5-84-OB-0001_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Workshop & Warehouse |  | PS5-63-07 - Electrical Earthing - Workshop & Warehouse
T-00248-0058 | PS5-84-OB-0003_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Hazardous Waste Shelter |  | PS5-63-01 - Electrical Earthing
T-00248-0059 | PS5-84-OB-0005_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Generator Electrical Building |  | PS5-63-03 - Electrical Earthing - Generator Building
T-00248-0060 | PS5-84-OB-0006_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Chemical Storage Shelter |  | PS5-63-01 - Electrical Earthing
T-00248-0061 | PS5-84-OB-0007_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Chemical Waste Storage Shelter |  | PS5-63-01 - Electrical Earthing
T-00248-0062 | PS5-86-OB-0001_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Closed Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00248-0063 | PS5-86-OB-0002_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Relief Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00248-0064 | PS5-86-OB-0003_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Fire Water Pump Shelter |  | PS5-63-01 - Electrical Earthing
T-00248-0065 | PS5-86-OB-0004_Lightning | TPX28 - Lightning protection system | #N/A | E | Lightning for Closed Drain Drum Shelter |  | PS5-63-01 - Electrical Earthing
T-00249-0008 | PS5-53-TR-4100 | TPX33 - Cathodic protection | #N/A | E | UTILITY WATER / FIRE WATER STORAGE TANK |  | PS5-53-01 - Utility Water / Storage Tank
T-00249-0009 | PS5-71-TR-4100 | TPX33 - Cathodic protection | #N/A | E | CRUDE FUEL OIL STORAGE TANK |  | PS5-71-04 - CFO Storage Tank
T-00249-0010 | PS5-71-TR-4200 | TPX33 - Cathodic protection | #N/A | E | CRUDE FUEL OIL SERVICE TANK |  | PS5-71-12 - CFO Service Tank
T-00249-0011 | PS5-71-TR-4400 | TPX33 - Cathodic protection | #N/A | E | DIESEL FUEL STORAGE TANK |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00251-0115 | PS5-25-PSV-1103 | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00251-0116 | PS5-28-PSV-0064C | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00251-0117 | PS5-25-PSV-1203 | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00251-0118 | PS5-28-PRV-0047B | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00251-0119 | PS5-74-PSV-0003 | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-74-03 - Nitrogen Receiver
T-00251-0120 | PS5-28-PRV-0040 | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00251-0121 | PS5-50-PSV-0004A | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-50-01 - Water Well Submersible Pumps (3100)
T-00251-0122 | PS5-71-PSV-2403A | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00251-0123 | PS5-28-PSV-3901B | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-17 - Reinjection Pump
T-00251-0124 | PS5-28-PRV-0047A | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00251-0125 | PS5-71-PVSV-4202 | TJX03 - Relief valve | #N/A | I | Pressure / Vacuum Safety Valve |  | PS5-71-12 - CFO Service Tank
T-00251-0126 | PS5-71-PVSV-4102 | TJX03 - Relief valve | #N/A | I | Pressure / Vacuum Safety Valve |  | PS5-71-04 - CFO Storage Tank
T-00251-0127 | PS5-28-PRV-0046A | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00251-0128 | PS5-28-PRV-0008 | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00251-0129 | PS5-28-PSV-0064A | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00251-0130 | PS5-28-PRV-0054 | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00251-0131 | PS5-28-PSV-0044 | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00251-0132 | PS5-71-PRV-0016 | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-71-04 - CFO Storage Tank
T-00251-0133 | PS5-28-PRV-0046B | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00251-0134 | PS5-71-PRV-0015 | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-71-04 - CFO Storage Tank
T-00251-0135 | PS5-71-PRV-0018 | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-71-12 - CFO Service Tank
T-00251-0136 | PS5-71-PRV-0041 | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-71-12 - CFO Service Tank
T-00251-0137 | PS5-71-PSV-2403B | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00251-0138 | PS5-28-PRV-0046C | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00251-0139 | PS5-28-PRV-0047C | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00251-0140 | PS5-28-PRV-0055 | TJX03 - Relief valve | #N/A | I | Self-Actuating / Regulating Press Valve |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00251-0141 | PS5-28-PSV-0061 | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00251-0142 | PS5-28-PSV-0064B | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00251-0143 | PS5-28-PSV-3901A | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-28-17 - Reinjection Pump
T-00251-0144 | PS5-50-PSV-0004B | TJX03 - Relief valve | #N/A | I | Pressure Safety Relief Valve |  | PS5-50-02 - Water Well Submersible Pumps (3200)
T-00254-10862 | PS5-03-RAB-B402-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0005 TO PS5-03-RAB-B402 |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10863 | PS5-03-RAB-B902-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0005 TO PS5-03-RAB-B902 |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10864 | PS5-03-RAB-W502-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0006 TO PS5-03-RAB-W502 |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10865 | PS5-03-RDHR-W101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W201A TO PS5-03-RDHR-W101A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10866 | PS5-03-RDHR-W101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101A TO PS5-03-RDHR-W101B |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10867 | PS5-03-RDHR-W101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101B TO PS5-03-RDHR-W101C |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10868 | PS5-03-RDHR-W101D-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101E TO PS5-03-RDHR-W101D |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10869 | PS5-03-RDHR-W101E-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101F TO PS5-03-RDHR-W101E |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10870 | PS5-03-RDHR-W101F-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101C TO PS5-03-RDHR-W101F |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10871 | PS5-03-RDHR-W101G-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101D TO PS5-03-RDHR-W101G |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10872 | PS5-03-RDHR-W101H-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101G TO PS5-03-RDHR-W101H |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10873 | PS5-03-RDHR-W101I-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W101H TO PS5-03-RDHR-W101I |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10874 | PS5-03-RDHR-W601A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601B TO PS5-03-RDHR-W601A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10875 | PS5-03-RDHR-W601B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601C TO PS5-03-RDHR-W601B |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10876 | PS5-03-RDHR-W601C-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601D TO PS5-03-RDHR-W601C |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10877 | PS5-03-RDHR-W601D-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601E TO PS5-03-RDHR-W601D |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10878 | PS5-03-RDHR-W601E-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601F TO PS5-03-RDHR-W601E |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10879 | PS5-03-RDHR-W601F-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601G TO PS5-03-RDHR-W601F |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10880 | PS5-03-RDHR-W601G-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601H TO PS5-03-RDHR-W601G |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10881 | PS5-03-RDHR-W601H-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601I TO PS5-03-RDHR-W601H |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10882 | PS5-03-RDHR-W601I-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601J TO PS5-03-RDHR-W601I |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10883 | PS5-03-RDHR-W601J-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601K TO PS5-03-RDHR-W601J |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10884 | PS5-03-RDHR-W601K-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601L TO PS5-03-RDHR-W601K |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10885 | PS5-03-RDHR-W601L-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601M TO PS5-03-RDHR-W601L |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10886 | PS5-03-RDHR-W601M-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601N TO PS5-03-RDHR-W601M |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10887 | PS5-03-RDHR-W601N-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601O TO PS5-03-RDHR-W601N |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10888 | PS5-03-RDHR-W601O-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDHR-W601P TO PS5-03-RDHR-W601O |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10889 | PS5-03-RDHR-W601P-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-W501 TO PS5-03-RDHR-W601P |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10890 | PS5-03-RDOS-B101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B101B TO PS5-03-RDOS-B101A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10891 | PS5-03-RDOS-B101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B101C TO PS5-03-RDOS-B101B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10892 | PS5-03-RDOS-B101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B101D TO PS5-03-RDOS-B101C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10893 | PS5-03-RDOS-B101D-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B401A TO PS5-03-RDOS-B101D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10894 | PS5-03-RDOS-B201A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B201B TO PS5-03-RDOS-B201A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10895 | PS5-03-RDOS-B201B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B201C TO PS5-03-RDOS-B201B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10896 | PS5-03-RDOS-B201C-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B201D TO PS5-03-RDOS-B201C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10897 | PS5-03-RDOS-B201D-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B201E TO PS5-03-RDOS-B201D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10898 | PS5-03-RDOS-B201E-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0005 TO PS5-03-RDOS-B201E |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10899 | PS5-03-RDOS-B301A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B101A TO PS5-03-RDOS-B301A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10900 | PS5-03-RDOS-B301B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B301A TO PS5-03-RDOS-B301B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10901 | PS5-03-RDOS-B301C-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B301B TO PS5-03-RDOS-B301C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10902 | PS5-03-RDOS-B301D-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B801A TO PS5-03-RDOS-B301D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10903 | PS5-03-RDOS-B401A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B401B TO PS5-03-RDOS-B401A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10904 | PS5-03-RDOS-B401B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B401C TO PS5-03-RDOS-B401B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10905 | PS5-03-RDOS-B401C-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-B401 TO PS5-03-RDOS-B401C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10906 | PS5-03-RDOS-B401D-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B501A TO PS5-03-RDOS-B401D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10907 | PS5-03-RDOS-B501A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B601A TO PS5-03-RDOS-B501A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10908 | PS5-03-RDOS-B601A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-B901 TO PS5-03-RDOS-B601A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10909 | PS5-03-RDOS-B701A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B901A TO PS5-03-RDOS-B701A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10910 | PS5-03-RDOS-B701B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701C TO PS5-03-RDOS-B701B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10911 | PS5-03-RDOS-B701C-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701D TO PS5-03-RDOS-B701C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10912 | PS5-03-RDOS-B701D-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701E TO PS5-03-RDOS-B701D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10913 | PS5-03-RDOS-B701E-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701F TO PS5-03-RDOS-B701E |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10914 | PS5-03-RDOS-B701F-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701G TO PS5-03-RDOS-B701F |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10915 | PS5-03-RDOS-B701G-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701I TO PS5-03-RDOS-B701G |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10916 | PS5-03-RDOS-B701H-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B301D TO PS5-03-RDOS-B701H |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10917 | PS5-03-RDOS-B701I-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701H TO PS5-03-RDOS-B701I |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10918 | PS5-03-RDOS-B801A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B801B TO PS5-03-RDOS-B801A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10919 | PS5-03-RDOS-B801B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B701A TO PS5-03-RDOS-B801B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10920 | PS5-03-RDOS-B901A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B901B TO PS5-03-RDOS-B901A |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10921 | PS5-03-RDOS-B901B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B901C TO PS5-03-RDOS-B901B |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10922 | PS5-03-RDOS-B901C-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B901D TO PS5-03-RDOS-B901C |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10923 | PS5-03-RDOS-B901D-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B901E TO PS5-03-RDOS-B901D |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10924 | PS5-03-RDOS-B901E-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0005 TO PS5-03-RDOS-B901E |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10925 | PS5-03-RDOS-W201A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W201B TO PS5-03-RDOS-W201A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10926 | PS5-03-RDOS-W201B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W301A TO PS5-03-RDOS-W201B |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10927 | PS5-03-RDOS-W201C-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W201D TO PS5-03-RDOS-W201C |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10928 | PS5-03-RDOS-W201D-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501A TO PS5-03-RDOS-W201D |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10929 | PS5-03-RDOS-W301A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W401A TO PS5-03-RDOS-W301A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10930 | PS5-03-RDOS-W401A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W201C TO PS5-03-RDOS-W401A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10931 | PS5-03-RDOS-W501A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501B TO PS5-03-RDOS-W501A |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10932 | PS5-03-RDOS-W501B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501C TO PS5-03-RDOS-W501B |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10933 | PS5-03-RDOS-W501C-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501D TO PS5-03-RDOS-W501C |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10934 | PS5-03-RDOS-W501D-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501E TO PS5-03-RDOS-W501D |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10935 | PS5-03-RDOS-W501E-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-W501F TO PS5-03-RDOS-W501E |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10936 | PS5-03-RDOS-W501F-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0006 TO PS5-03-RDOS-W501F |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-10937 | PS5-03-RMAC-B401-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-B401D TO PS5-03-RMAC-B401 |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10938 | PS5-03-RMAC-B901-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0005 TO PS5-03-RMAC-B901 |  | PS5-03-24 - FZ - Office and Facilities Building
T-00254-10939 | PS5-03-RMAC-W501-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0006 TO PS5-03-RMAC-W501 |  | PS5-03-25 - FZ - Workshop & Warehouse
T-00254-11586 | PS5-09-AH-8401-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11587 | PS5-09-AH-8401-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11588 | PS5-09-AH-8402-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11589 | PS5-09-AH-8402-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11590 | PS5-09-AH-8403-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11591 | PS5-09-AH-8403-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AH-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11592 | PS5-09-AS-8111A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8111A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11593 | PS5-09-AS-8111A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8111A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11594 | PS5-09-AS-8111B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8111B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11595 | PS5-09-AS-8111B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8111B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11596 | PS5-09-AS-8211A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8211A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11597 | PS5-09-AS-8211A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8211A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11598 | PS5-09-AS-8211B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8211B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11599 | PS5-09-AS-8211B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8211B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11600 | PS5-09-AS-8311A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11601 | PS5-09-AS-8311A-A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11602 | PS5-09-AS-8311B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11603 | PS5-09-AS-8311B-B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11604 | PS5-09-AS-8311C-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11605 | PS5-09-AS-8311C-A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11606 | PS5-09-AS-8311D-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311D |  | PS5-09-03 - HVAC for Generator Building
T-00254-11607 | PS5-09-AS-8311D-B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8311D |  | PS5-09-03 - HVAC for Generator Building
T-00254-11608 | PS5-09-AS-8321A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11609 | PS5-09-AS-8321A-A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11610 | PS5-09-AS-8321B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11611 | PS5-09-AS-8321B-B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11612 | PS5-09-AS-8321C-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11613 | PS5-09-AS-8321C-A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11614 | PS5-09-AS-8321D-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321D |  | PS5-09-03 - HVAC for Generator Building
T-00254-11615 | PS5-09-AS-8321D-B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8321D |  | PS5-09-03 - HVAC for Generator Building
T-00254-11616 | PS5-09-AS-8331A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11617 | PS5-09-AS-8331A-A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11618 | PS5-09-AS-8331B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11619 | PS5-09-AS-8331B-B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11620 | PS5-09-AS-8331C-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11621 | PS5-09-AS-8331C-A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11622 | PS5-09-AS-8331D-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331D |  | PS5-09-03 - HVAC for Generator Building
T-00254-11623 | PS5-09-AS-8331D-B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8331D |  | PS5-09-03 - HVAC for Generator Building
T-00254-11624 | PS5-09-AS-8341A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8341A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11625 | PS5-09-AS-8341A-A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8341A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11626 | PS5-09-AS-8341B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8341B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11627 | PS5-09-AS-8341B-B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8341B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11628 | PS5-09-AS-8411A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11629 | PS5-09-AS-8411A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11630 | PS5-09-AS-8411B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11631 | PS5-09-AS-8411B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11632 | PS5-09-AS-8412A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8412A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11633 | PS5-09-AS-8412A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8412A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11634 | PS5-09-AS-8412B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8412B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11635 | PS5-09-AS-8412B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8412B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11636 | PS5-09-AS-8421A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8421A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11637 | PS5-09-AS-8421A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8421A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11638 | PS5-09-AS-8421B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8421B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11639 | PS5-09-AS-8421B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8421B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11640 | PS5-09-AS-8432A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8432A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11641 | PS5-09-AS-8432A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8432A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11642 | PS5-09-AS-8432B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8432B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11643 | PS5-09-AS-8432B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-AS-8432B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11644 | PS5-09-BI-8111A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8111A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11645 | PS5-09-BI-8111B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8111B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11646 | PS5-09-BI-8211A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8211A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11647 | PS5-09-BI-8211B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8211B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11648 | PS5-09-BI-8311A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8311A-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11649 | PS5-09-BI-8311A-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8311A-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11650 | PS5-09-BI-8311B-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8311B-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11651 | PS5-09-BI-8311B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8311B-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11652 | PS5-09-BI-8321A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8321A-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11653 | PS5-09-BI-8321A-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8321A-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11654 | PS5-09-BI-8321B-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8321B-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11655 | PS5-09-BI-8321B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8321B-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11656 | PS5-09-BI-8331A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8331A-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11657 | PS5-09-BI-8331A-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8331A-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11658 | PS5-09-BI-8331B-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8331B-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11659 | PS5-09-BI-8331B-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8331B-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11660 | PS5-09-BI-8341A-A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8341A-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11661 | PS5-09-BI-8341A-B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8341A-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11662 | PS5-09-BI-8411A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11663 | PS5-09-BI-8411B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-BI-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11664 | PS5-09-FCU-8442A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11665 | PS5-09-FCU-8442A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11666 | PS5-09-FCU-8442B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11667 | PS5-09-FCU-8442B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11668 | PS5-09-FCU-8442C-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11669 | PS5-09-FCU-8442C-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11670 | PS5-09-FCU-8442D-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442D |  | PS5-09-03 - HVAC for Generator Building
T-00254-11671 | PS5-09-FCU-8442D-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442D |  | PS5-09-03 - HVAC for Generator Building
T-00254-11672 | PS5-09-FCU-8442E-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442E |  | PS5-09-03 - HVAC for Generator Building
T-00254-11673 | PS5-09-FCU-8442E-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442E |  | PS5-09-03 - HVAC for Generator Building
T-00254-11674 | PS5-09-FCU-8442F-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442F |  | PS5-09-03 - HVAC for Generator Building
T-00254-11675 | PS5-09-FCU-8442F-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442F |  | PS5-09-03 - HVAC for Generator Building
T-00254-11676 | PS5-09-FCU-8442G-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442G |  | PS5-09-03 - HVAC for Generator Building
T-00254-11677 | PS5-09-FCU-8442G-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442G |  | PS5-09-03 - HVAC for Generator Building
T-00254-11678 | PS5-09-FCU-8442H-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442H |  | PS5-09-03 - HVAC for Generator Building
T-00254-11679 | PS5-09-FCU-8442H-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FCU-8442H |  | PS5-09-03 - HVAC for Generator Building
T-00254-11680 | PS5-09-FD-0019-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0019 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11681 | PS5-09-FD-0019-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0019 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11682 | PS5-09-FD-0019-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0019 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11683 | PS5-09-FD-0021-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0021 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11684 | PS5-09-FD-0021-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0021 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11685 | PS5-09-FD-0021-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0021 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11686 | PS5-09-FD-0024-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0024 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11687 | PS5-09-FD-0024-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0024 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11688 | PS5-09-FD-0024-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0024 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11689 | PS5-09-FD-0025-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0025 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11690 | PS5-09-FD-0025-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0025 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11691 | PS5-09-FD-0025-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0025 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11692 | PS5-09-FD-0026-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0026 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11693 | PS5-09-FD-0026-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0026 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11694 | PS5-09-FD-0026-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0026 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11695 | PS5-09-FD-0027-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0027 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11696 | PS5-09-FD-0027-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0027 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11697 | PS5-09-FD-0027-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0027 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11698 | PS5-09-FD-0028-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0028 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11699 | PS5-09-FD-0028-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0028 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11700 | PS5-09-FD-0028-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0028 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11701 | PS5-09-FD-0029-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0029 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11702 | PS5-09-FD-0029-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0029 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11703 | PS5-09-FD-0029-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0029 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11704 | PS5-09-FD-0030-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0030 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11705 | PS5-09-FD-0030-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0030 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11706 | PS5-09-FD-0030-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0030 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11707 | PS5-09-FD-0031-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0031 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11708 | PS5-09-FD-0031-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0031 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11709 | PS5-09-FD-0031-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0031 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11710 | PS5-09-FD-0032-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0032 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11711 | PS5-09-FD-0032-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0032 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11712 | PS5-09-FD-0032-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0032 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11713 | PS5-09-FD-0033-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-BI-2503 TO PS5-09-FD-0033 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11714 | PS5-09-FD-0033-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0033 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11715 | PS5-09-FD-0033-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-FD-0033 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11716 | PS5-09-HE-8401A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-61-IH-0004 TO PS5-09-HE-8401A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11717 | PS5-09-HE-8401B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-61-IH-0004 TO PS5-09-HE-8401B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11718 | PS5-09-LB-8111A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8111A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11719 | PS5-09-LB-8111B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8111B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11720 | PS5-09-LB-8211A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8211A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11721 | PS5-09-LB-8211B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8211B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11722 | PS5-09-LB-8311A-A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8311A-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11723 | PS5-09-LB-8311A-B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8311B-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11724 | PS5-09-LB-8311B-A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8311B-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11725 | PS5-09-LB-8311B-B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8321A-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11726 | PS5-09-LB-8321A-A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8321A-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11727 | PS5-09-LB-8321A-B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8321B-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11728 | PS5-09-LB-8321B-A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8321B-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11729 | PS5-09-LB-8321B-B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8331A-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11730 | PS5-09-LB-8331A-A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8331A-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11731 | PS5-09-LB-8331A-B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8331B-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11732 | PS5-09-LB-8331B-A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8331B-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11733 | PS5-09-LB-8331B-B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8341A-A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11734 | PS5-09-LB-8341A-A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8341A-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11735 | PS5-09-LB-8341A-B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8341A-B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11736 | PS5-09-LB-8411A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8411A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11737 | PS5-09-LB-8411B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8411B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11738 | PS5-09-LB-8442A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11739 | PS5-09-LB-8442B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11740 | PS5-09-LB-8442C-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11741 | PS5-09-LB-8442D-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442D |  | PS5-09-03 - HVAC for Generator Building
T-00254-11742 | PS5-09-LB-8442E-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442E |  | PS5-09-03 - HVAC for Generator Building
T-00254-11743 | PS5-09-LB-8442F-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442F |  | PS5-09-03 - HVAC for Generator Building
T-00254-11744 | PS5-09-LB-8442G-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442G |  | PS5-09-03 - HVAC for Generator Building
T-00254-11745 | PS5-09-LB-8442H-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8442H |  | PS5-09-03 - HVAC for Generator Building
T-00254-11746 | PS5-09-LB-8451A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11747 | PS5-09-LB-8451A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11748 | PS5-09-LB-8451B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11749 | PS5-09-LB-8451B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11750 | PS5-09-PDIT-8207-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PDIT-8207 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11751 | PS5-09-PDIT-8407-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PDIT-8407 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11752 | PS5-09-PDIT-8408-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PDIT-8408 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11753 | PS5-09-PDIT-8409-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PDIT-8409 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11754 | PS5-09-PDIT-8411-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PDIT-8411 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11755 | PS5-09-PIT-8401-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PIT-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11756 | PS5-09-PIT-8402-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PIT-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11757 | PS5-09-PIT-8403-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PIT-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11758 | PS5-09-PIT-8404-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-PIT-8404 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11759 | PS5-09-TCV-8401-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TCV-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11760 | PS5-09-TCV-8401-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TCV-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11761 | PS5-09-TCV-8402-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TCV-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11762 | PS5-09-TCV-8402-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TCV-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11763 | PS5-09-TIT-8101-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8101 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11764 | PS5-09-TIT-8201-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8201 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11765 | PS5-09-TIT-8301-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8301 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11766 | PS5-09-TIT-8302-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8302 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11767 | PS5-09-TIT-8303-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8303 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11768 | PS5-09-TIT-8304-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8304 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11769 | PS5-09-TIT-8401-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11770 | PS5-09-TIT-8402-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11771 | PS5-09-TIT-8403-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11772 | PS5-09-TIT-8404-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8404 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11773 | PS5-09-TIT-8405-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8405 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11774 | PS5-09-TIT-8406-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8406 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11775 | PS5-09-TIT-8407-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8407 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11776 | PS5-09-TIT-8408-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-TIT-8408 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11777 | PS5-09-UZ-84600-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-UZ-84600 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11778 | PS5-09-UZ-84600-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-UZ-84600 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11779 | PS5-09-XV-8401-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11780 | PS5-09-XV-8401-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8401 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11781 | PS5-09-XV-8402-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11782 | PS5-09-XV-8402-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8402 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11783 | PS5-09-XV-8403-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11784 | PS5-09-XV-8403-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8403 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11785 | PS5-09-XV-8404-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8404 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11786 | PS5-09-XV-8404-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8404 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11787 | PS5-09-XV-8413-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8413 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11788 | PS5-09-XV-8413-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8413 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11789 | PS5-09-XV-8414-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8414 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11790 | PS5-09-XV-8414-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-09-XV-8414 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11791 | PS5-61-IH-0004A-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11792 | PS5-61-IH-0004A-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11793 | PS5-61-IH-0004A-CU03 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11794 | PS5-61-IH-0004A-CU04 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004A |  | PS5-09-03 - HVAC for Generator Building
T-00254-11795 | PS5-61-IH-0004B-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11796 | PS5-61-IH-0004B-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11797 | PS5-61-IH-0004B-CU03 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11798 | PS5-61-IH-0004B-CU04 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004B |  | PS5-09-03 - HVAC for Generator Building
T-00254-11799 | PS5-61-IH-0004C-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11800 | PS5-61-IH-0004C-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11801 | PS5-61-IH-0004C-CU03 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11802 | PS5-61-IH-0004C-CU04 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004C |  | PS5-09-03 - HVAC for Generator Building
T-00254-11803 | PS5-61-IH-0004-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11804 | PS5-61-IH-0004-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11805 | PS5-61-IH-0004-CU03 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11806 | PS5-61-IH-0004-CU04 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11807 | PS5-61-IH-0004-CU05 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11808 | PS5-61-IH-0004-CU06 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11809 | PS5-61-IH-0004-CU07 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11810 | PS5-61-IH-0004-CU08 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11811 | PS5-61-IH-0004-CU09 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11812 | PS5-61-IH-0004-CU10 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11813 | PS5-61-IH-0004-CU11 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11814 | PS5-61-IH-0004-CU12 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11815 | PS5-61-IH-0004-CU13 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11816 | PS5-61-IH-0004-CU14 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11817 | PS5-61-IH-0004-CU15 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11818 | PS5-61-IH-0004-CU16 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11819 | PS5-61-IH-0004-CU17 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11820 | PS5-61-IH-0004-CU18 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11821 | PS5-61-IH-0004-CU19 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11822 | PS5-61-IH-0004-CU20 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11823 | PS5-61-IH-0004-CU21 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11824 | PS5-61-IH-0004-CU22 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11825 | PS5-61-IH-0004-CU23 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11826 | PS5-61-IH-0004-CU24 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11827 | PS5-61-IH-0004-CU25 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11828 | PS5-61-IH-0004-CU26 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11829 | PS5-61-IH-0004-CU27 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11830 | PS5-61-IH-0004-CU28 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11831 | PS5-61-IH-0004-CU29 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004 |  | PS5-09-03 - HVAC for Generator Building
T-00254-11832 | PS5-61-IH-0004D-CU01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004D |  | PS5-09-03 - HVAC for Generator Building
T-00254-11833 | PS5-61-IH-0004D-CU02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-09-LB-0008 TO PS5-61-IH-0004D |  | PS5-09-03 - HVAC for Generator Building
T-00254-4222 | PS5-01-BI-0007-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-BI-0007 |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4223 | PS5-01-BI-0008-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-BI-0008 |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4224 | PS5-01-BI-0009-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-BI-0009 |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4235 | PS5-01-FCV-0003A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-FCV-0003A-HPU TO PS5-01-FCV-0003A |  | PS5-01-02 - Fire Water Pump A
T-00254-4236 | PS5-01-FCV-0003B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-FCV-0003B-HPU TO PS5-01-FCV-0003B |  | PS5-01-03 - Fire Water Pump B
T-00254-4237 | PS5-01-FCV-0004A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-FCV-0004A-HPU TO PS5-01-FCV-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4238 | PS5-01-FCV-0004B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-FCV-0004B-HPU TO PS5-01-FCV-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4239 | PS5-01-FIT-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FIT-0003A-CJ01 | I | Cable FROM PS5-01-BI-1117 TO PS5-01-FIT-0003A |  | PS5-01-02 - Fire Water Pump A
T-00254-4240 | PS5-01-FIT-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FIT-0003B-CJ01 | I | Cable FROM PS5-01-BI-1117 TO PS5-01-FIT-0003B |  | PS5-01-03 - Fire Water Pump B
T-00254-4241 | PS5-01-FIT-0004A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FIT-0004A-CJ01 | I | Cable FROM PS5-01-BI-1117 TO PS5-01-FIT-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4242 | PS5-01-FIT-0004B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FIT-0004B-CJ01 | I | Cable FROM PS5-01-BI-1117 TO PS5-01-FIT-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4243 | PS5-01-FXS-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FXS-0003A-CJ01 | I | Cable FROM PS5-01-BI-2110 TO PS5-01-FCV-0003A |  | PS5-01-02 - Fire Water Pump A
T-00254-4244 | PS5-01-FXS-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FXS-0003B-CJ01 | I | Cable FROM PS5-01-BI-2110 TO PS5-01-FCV-0003B |  | PS5-01-03 - Fire Water Pump B
T-00254-4245 | PS5-01-FXS-0004A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FXS-0004A-CJ01 | I | Cable FROM PS5-01-BI-2110 TO PS5-01-FCV-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4246 | PS5-01-FXS-0004B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FXS-0004B-CJ01 | I | Cable FROM PS5-01-BI-2110 TO PS5-01-FCV-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4247 | PS5-01-FY-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FY-0003A-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0003A |  | PS5-01-02 - Fire Water Pump A
T-00254-4248 | PS5-01-FY-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FY-0003B-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0003B |  | PS5-01-03 - Fire Water Pump B
T-00254-4249 | PS5-01-FY-0004A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FY-0004A-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4250 | PS5-01-FY-0004B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-FY-0004B-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4251 | PS5-01-HS-3108AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-IE-0009A TO PS5-03-MTX-0001 |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-64-12-0087
T-00254-4252 | PS5-01-HS-3108BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-IE-0009B TO PS5-03-MTX-0001 |  | PS5-01-03 - Fire Water Pump B | CPP-RFI-68-64-12-0087
T-00254-4264 | PS5-01-LB-6101A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-LB-6101A |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-12-0087
T-00254-4265 | PS5-01-LB-6102A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-LB-6102A |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-12-0087
T-00254-4266 | PS5-01-LB-6103A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-LB-6103A |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-12-0087
T-00254-4267 | PS5-01-LB-6104A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-LB-6104A |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-12-0087
T-00254-4268 | PS5-01-LIT-4101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-LIT-4101A-CJ01 | I | Cable FROM PS5-01-IE-0009A TO PS5-01-LIT-4101A |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-64-12-0087
T-00254-4269 | PS5-01-LIT-4101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-LIT-4101B-CJ01 | I | Cable FROM PS5-01-IE-0009B TO PS5-01-LIT-4101A |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-64-12-0087
T-00254-4271 | PS5-01-NMR-61001-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMR-61001 |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4272 | PS5-01-NMR-61002-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMR-61002 |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4273 | PS5-01-NMR-61003-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMR-61003 |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4274 | PS5-01-NMR-61004-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMR-61004 |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4275 | PS5-01-NMRA-61001-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMRA-61001 |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4276 | PS5-01-NMRA-61002-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMRA-61002 |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4277 | PS5-01-NMRA-61003-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMRA-61003 |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4278 | PS5-01-NMRA-61004-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-NMRA-61004 |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4279 | PS5-01-PDIT-0011A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PDIT-0011A-CJ01 | I | Cable FROM PS5-01-BI-1515 TO PS5-01-PDIT-0011A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4280 | PS5-01-PDIT-0011B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PDIT-0011B-CJ01 | I | Cable FROM PS5-01-BI-1515 TO PS5-01-PDIT-0011B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4281 | PS5-01-PDIT-0012A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PDIT-0012A-CJ01 | I | Cable FROM PS5-01-BI-1515 TO PS5-01-PDIT-0012A |  | PS5-01-02 - Fire Water Pump A
T-00254-4282 | PS5-01-PDIT-0012B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PDIT-0012B-CJ01 | I | Cable FROM PS5-01-BI-1515 TO PS5-01-PDIT-0012B |  | PS5-01-03 - Fire Water Pump B
T-00254-4283 | PS5-01-PIT-0003AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-0003AA-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0003A |  | PS5-01-02 - Fire Water Pump A
T-00254-4284 | PS5-01-PIT-0003BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-0003BA-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0003B |  | PS5-01-03 - Fire Water Pump B
T-00254-4285 | PS5-01-PIT-0004AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-0004AA-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4286 | PS5-01-PIT-0004BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-0004BA-CJ01 | I | Cable FROM PS5-01-BI-1118 TO PS5-01-FCV-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00254-4287 | PS5-01-PIT-0010-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-0010-CJ01 | I | Cable FROM PS5-01-BI-1501 TO PS5-01-PIT-0010 |  | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4288 | PS5-01-PIT-0013-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-BI-1515 TO PS5-01-PIT-0013 |  | PS5-01-07 - Fire Water Ring Main & Distribution
T-00254-4293 | PS5-01-PIT-8101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101A-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101A |  | PS5-01-10 - Water Mist Package
T-00254-4294 | PS5-01-PIT-8101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101B-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101B |  | PS5-01-10 - Water Mist Package
T-00254-4295 | PS5-01-PIT-8101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101C-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101C |  | PS5-01-10 - Water Mist Package
T-00254-4296 | PS5-01-PIT-8101D-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101D-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101D |  | PS5-01-10 - Water Mist Package
T-00254-4297 | PS5-01-PIT-8101E-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101E-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101E |  | PS5-01-10 - Water Mist Package
T-00254-4298 | PS5-01-PIT-8101F-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101F-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101F |  | PS5-01-10 - Water Mist Package
T-00254-4299 | PS5-01-PIT-8101G-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101G-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101G |  | PS5-01-10 - Water Mist Package
T-00254-4300 | PS5-01-PIT-8101H-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-PIT-8101H-CJ01 | I | Cable FROM PS5-01-BI-1520 TO PS5-01-PIT-8101H |  | PS5-01-10 - Water Mist Package
T-00254-4301 | PS5-01-RAB-61001A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61001A |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4302 | PS5-01-RAB-61001B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61001B |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4303 | PS5-01-RAB-61002A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61002A |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4304 | PS5-01-RAB-61002B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61002B |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4305 | PS5-01-RAB-61003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61003A |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4306 | PS5-01-RAB-61003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61003B |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4307 | PS5-01-RAB-61004A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61004A |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4308 | PS5-01-RAB-61004B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-01-LB-0004 TO PS5-01-RAB-61004B |  | PS5-01-11 - Inergen for Power Gen Building
T-00254-4309 | PS5-01-SY-8101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101A-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101A |  | PS5-01-10 - Water Mist Package
T-00254-4310 | PS5-01-SY-8101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101B-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101B |  | PS5-01-10 - Water Mist Package
T-00254-4311 | PS5-01-SY-8101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101C-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101C |  | PS5-01-10 - Water Mist Package
T-00254-4312 | PS5-01-SY-8101D-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101D-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101D |  | PS5-01-10 - Water Mist Package
T-00254-4313 | PS5-01-SY-8101E-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101E-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101E |  | PS5-01-10 - Water Mist Package
T-00254-4314 | PS5-01-SY-8101F-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101F-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101F |  | PS5-01-10 - Water Mist Package
T-00254-4315 | PS5-01-SY-8101G-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101G-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101G |  | PS5-01-10 - Water Mist Package
T-00254-4316 | PS5-01-SY-8101H-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-01-SY-8101H-CJ01 | I | Cable FROM PS5-01-BI-2520 TO PS5-01-SY-8101H |  | PS5-01-10 - Water Mist Package
T-00254-4343 | PS5-03-GDIR-0901-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0901-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0901 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4344 | PS5-03-GDIR-0902-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0902-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0902 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4345 | PS5-03-GDIR-0903-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0903-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0903 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4346 | PS5-03-GDIR-0904-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0904-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0904 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4347 | PS5-03-GDIR-0906-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0906-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0906 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4348 | PS5-03-GDIR-0907-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0907-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0907 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4349 | PS5-03-GDIR-0907-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0907-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0908 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4350 | PS5-03-GDIR-0909-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-0909-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-0909 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4351 | PS5-03-GDIR-1001-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1001-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1001 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4352 | PS5-03-GDIR-1002-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1002-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1002 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4353 | PS5-03-GDIR-1003-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1003-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1003 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4354 | PS5-03-GDIR-1004-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1004-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1004 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4355 | PS5-03-GDIR-1006-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1006-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1006 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4356 | PS5-03-GDIR-1007-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1007-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1007 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4357 | PS5-03-GDIR-1008-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1008-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1008 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4358 | PS5-03-GDIR-1009-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1009-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1009 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4359 | PS5-03-GDIR-1101-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1101-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1101 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4360 | PS5-03-GDIR-1102-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1102-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1102 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4361 | PS5-03-GDIR-1103-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1103-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1103 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4362 | PS5-03-GDIR-1104-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1104-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1104 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4363 | PS5-03-GDIR-1106-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1106-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1106 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4364 | PS5-03-GDIR-1107-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1107-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1107 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4365 | PS5-03-GDIR-1108-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1108-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1108 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4366 | PS5-03-GDIR-1109-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1109-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1109 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4367 | PS5-03-GDIR-1201-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1201-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1201 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00254-4368 | PS5-03-GDIR-1202-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1202-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1202 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00254-4369 | PS5-03-GDIR-1203-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1203-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1203 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00254-4370 | PS5-03-GDIR-1204-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDIR-1204-CC01 | I | Cable FROM PS5-60-SEA-0001 TO PS5-03-GDIR-1204 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4371 | PS5-03-GDLHP-0137-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0137-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0137 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4372 | PS5-03-GDLHP-0142-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0142-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0142 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4373 | PS5-03-GDLHP-0143-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0143-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0143 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4374 | PS5-03-GDLHP-0144-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0144-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0144 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4375 | PS5-03-GDLHP-0146-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0146-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0146 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4376 | PS5-03-GDLHP-0147-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0147-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0147 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4377 | PS5-03-GDLHP-0149-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0149-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0149 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4378 | PS5-03-GDLHP-0150-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0150-CJ01 | I | Cable FROM PS5-03-BI-2511 TO PS5-03-GDLHP-0150 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4379 | PS5-03-GDLHP-0401-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-GDLHP-0401-CJ01 | I | Cable FROM PS5-03-BI-2512 TO PS5-03-GDLHP-0401 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4393 | PS5-03-RDH-0302-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-2510 TO PS5-03-RDH-0302 |  | PS5-03-03 - FZ-03 - Buildings Area
T-00254-4394 | PS5-03-RDH-0303-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-2510 TO PS5-03-RDH-0303 |  | PS5-03-03 - FZ-03 - Buildings Area
T-00254-4395 | PS5-03-RDH-0601-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0601-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0601 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4396 | PS5-03-RDH-0602-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0602-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0602 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4397 | PS5-03-RDH-0603-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0603-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0603 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4398 | PS5-03-RDH-0604-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0604-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0604 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4399 | PS5-03-RDH-0605-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0605-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0605 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4400 | PS5-03-RDH-0606-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0606-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0606 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4401 | PS5-03-RDH-0607-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0607-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0607 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00254-4402 | PS5-03-RDH-0608-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0608-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0608 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00254-4403 | PS5-03-RDH-0609-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0609-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0609 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00254-4404 | PS5-03-RDH-0610-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0610-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0610 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00254-4405 | PS5-03-RDH-0611-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0611-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0611 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00254-4406 | PS5-03-RDH-0612-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0612-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0612 |  | PS5-03-06 - FZ-06 - Transformer Area
T-00254-4407 | PS5-03-RDH-0614-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0614-CJ01 | I | Cable FROM PS5-03-BI-2501 TO PS5-03-RDH-0614 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4408 | PS5-03-RDH-0615-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0615-CJ01 | I | Cable FROM PS5-03-BI-2501 TO PS5-03-RDH-0615 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4409 | PS5-03-RDH-0616-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0616-CJ01 | I | Cable FROM PS5-03-BI-2501 TO PS5-03-RDH-0616 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4410 | PS5-03-RDH-0617-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0617-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0617 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4411 | PS5-03-RDH-0618-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0618-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0618 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4412 | PS5-03-RDH-0620-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0620-CJ01 | I | Cable FROM PS5-03-BI-2502 TO PS5-03-RDH-0620 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4413 | PS5-03-RDH-0828-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0828-CJ01 | I | Cable FROM PS5-03-BI-2505 TO PS5-03-RDH-0828 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00254-4414 | PS5-03-RDH-0829-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0829-CJ01 | I | Cable FROM PS5-03-BI-2505 TO PS5-03-RDH-0829 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00254-4415 | PS5-03-RDH-0830-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0830-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0830 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4416 | PS5-03-RDH-0831-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0831-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RDH-0831 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4417 | PS5-03-RDH-0901-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0901-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0901 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4418 | PS5-03-RDH-0902-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0902-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0902 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4419 | PS5-03-RDH-0903-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0903-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0903 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4420 | PS5-03-RDH-0904-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0904-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0904 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4421 | PS5-03-RDH-0905-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0905-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0905 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4422 | PS5-03-RDH-0906-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0906-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0906 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4423 | PS5-03-RDH-0909-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0909-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0909 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4424 | PS5-03-RDH-0910-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0910-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0910 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4425 | PS5-03-RDH-0911-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0911-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0911 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4426 | PS5-03-RDH-0912-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-0912-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RDH-0912 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4427 | PS5-03-RDH-1001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1001-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1001 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4428 | PS5-03-RDH-1002-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1002-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1002 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4429 | PS5-03-RDH-1003-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1003-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1003 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4430 | PS5-03-RDH-1004-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1004-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1004 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4431 | PS5-03-RDH-1005-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1005-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1005 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4432 | PS5-03-RDH-1006-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1006-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1006 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4433 | PS5-03-RDH-1009-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1009-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1009 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4434 | PS5-03-RDH-1010-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1010-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1010 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4435 | PS5-03-RDH-1011-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1011-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1011 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4436 | PS5-03-RDH-1012-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1012-CJ01 | I | Cable FROM PS5-03-BI-2507 TO PS5-03-RDH-1012 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4437 | PS5-03-RDH-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1101-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1101 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4438 | PS5-03-RDH-1102-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1102-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1102 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4439 | PS5-03-RDH-1103-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1103-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1103 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4440 | PS5-03-RDH-1104-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1104-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1104 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4441 | PS5-03-RDH-1105-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1105-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1105 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4442 | PS5-03-RDH-1106-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1106-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1106 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4443 | PS5-03-RDH-1109-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1109-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1109 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4444 | PS5-03-RDH-1110-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1110-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1110 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4445 | PS5-03-RDH-1111-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1111-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1111 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4446 | PS5-03-RDH-1112-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1112-CJ01 | I | Cable FROM PS5-03-BI-2508 TO PS5-03-RDH-1112 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4447 | PS5-03-RDH-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1201-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RDH-1201 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00254-4448 | PS5-03-RDH-1202-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1202-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RDH-1202 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00254-4449 | PS5-03-RDH-1203-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1203-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RDH-1203 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00254-4450 | PS5-03-RDH-1204-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1204-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RDH-1204 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00254-4451 | PS5-03-RDH-1205-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1205-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RDH-1205 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00254-4452 | PS5-03-RDH-1302-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1302-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RDH-1302 |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00254-4453 | PS5-03-RDH-1303-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1303-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RDH-1303 |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00254-4454 | PS5-03-RDH-1304-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDH-1304-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RDH-1304 |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00254-4455 | PS5-03-RDH-1901-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDH-1903 TO PS5-03-RDH-1901 |  | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room
T-00254-4456 | PS5-03-RDH-1903-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-1410 TO PS5-03-RDH-1903 |  | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room
T-00254-4457 | PS5-03-RDIR-0104-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0104-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0104 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0092 | 2026-07-10 | Accepted | G K RAO | TESTING
T-00254-4458 | PS5-03-RDIR-0105-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0105-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0105 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0092 | 2026-07-10 | Accepted | G K RAO | TESTING
T-00254-4459 | PS5-03-RDIR-0106-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0106-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0106 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0092 | 2026-07-10 | Accepted | G K RAO | TESTING
T-00254-4460 | PS5-03-RDIR-0107-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0107 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4461 | PS5-03-RDIR-0108-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0108-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0108 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4462 | PS5-03-RDIR-0109-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0109-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0109 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4463 | PS5-03-RDIR-0110-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0110-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0110 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4464 | PS5-03-RDIR-0111-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0111-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0111 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4465 | PS5-03-RDIR-0112-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0112-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0112 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4466 | PS5-03-RDIR-0113-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0113-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0113 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4467 | PS5-03-RDIR-0114-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0114-CJ01 | I | Cable FROM PS5-03-BI-1509 TO PS5-03-RDIR-0114 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4468 | PS5-03-RDIR-0115-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0115-CJ01 | I | Cable FROM PS5-03-BI-1509 TO PS5-03-RDIR-0115 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4469 | PS5-03-RDIR-0116-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0116-CJ01 | I | Cable FROM PS5-03-BI-1509 TO PS5-03-RDIR-0116 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4470 | PS5-03-RDIR-0117-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0117-CJ01 | I | Cable FROM PS5-03-BI-1509 TO PS5-03-RDIR-0117 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4471 | PS5-03-RDIR-0118-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0118-CJ01 | I | Cable FROM PS5-03-BI-1509 TO PS5-03-RDIR-0118 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4472 | PS5-03-RDIR-0121-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0121-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0121 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4473 | PS5-03-RDIR-0122-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0122-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0122 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4474 | PS5-03-RDIR-0123-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0123-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0123 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4475 | PS5-03-RDIR-0124-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0124 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4476 | PS5-03-RDIR-0125-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0125-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0125 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4477 | PS5-03-RDIR-0126-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0126-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0126 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4478 | PS5-03-RDIR-0127-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0127-CJ01 | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0127 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4479 | PS5-03-RDIR-0128-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0128 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4480 | PS5-03-RDIR-0129-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0129 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4481 | PS5-03-RDIR-0130-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0130 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4482 | PS5-03-RDIR-0131-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0131 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4483 | PS5-03-RDIR-0132-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0132 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4484 | PS5-03-RDIR-0133-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1506 TO PS5-03-RDIR-0133 |  | PS5-03-01 - FZ-01 - Process Area
T-00254-4485 | PS5-03-RDIR-0137-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0137-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0137 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0092 | 2026-07-10 | Accepted | G K RAO | TESTING
T-00254-4486 | PS5-03-RDIR-0138-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0138-CJ01 | I | Cable FROM PS5-03-BI-1508 TO PS5-03-RDIR-0138 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0090 | 2026-07-07 | Accepted | G K RAO | TESTING
T-00254-4487 | PS5-03-RDIR-0141-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0141-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0141 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0092 | 2026-07-10 | Accepted | G K RAO | TESTING
T-00254-4488 | PS5-03-RDIR-0142-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0142-CJ01 | I | Cable FROM PS5-03-BI-1507 TO PS5-03-RDIR-0142 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0092 | 2026-07-10 | Accepted | G K RAO | TESTING
T-00254-4489 | PS5-03-RDIR-0403-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0403-CJ01 | I | Cable FROM PS5-03-BI-1503 TO PS5-03-RDIR-0403 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4490 | PS5-03-RDIR-0404-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0404-CJ01 | I | Cable FROM PS5-03-BI-1503 TO PS5-03-RDIR-0404 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4491 | PS5-03-RDIR-0405-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0405-CJ01 | I | Cable FROM PS5-03-BI-1502 TO PS5-03-RDIR-0405 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-12-0092 | 2026-07-10 | Accepted | G K RAO | TESTING
T-00254-4492 | PS5-03-RDIR-0406-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1502 TO PS5-03-RDIR-0406 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas
T-00254-4493 | PS5-03-RDIR-0409-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0409-CJ01 | I | Cable FROM PS5-03-BI-1503 TO PS5-03-RDIR-0409 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-12-0092 | 2026-07-10 | Accepted | G K RAO | TESTING
T-00254-4494 | PS5-03-RDIR-0411-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0411-CJ01 | I | Cable FROM PS5-03-BI-1503 TO PS5-03-RDIR-0411 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4495 | PS5-03-RDIR-0819-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0819-CJ01 | I | Cable FROM PS5-03-BI-1510 TO PS5-03-RDIR-0819 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4496 | PS5-03-RDIR-0820-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0820-CJ01 | I | Cable FROM PS5-03-BI-1510 TO PS5-03-RDIR-0820 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4497 | PS5-03-RDIR-0832-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDIR-0832-CJ01 | I | Cable FROM PS5-03-BI-1510 TO PS5-03-RDIR-0832 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4498 | PS5-03-RDIR-0833-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-1510 TO PS5-03-RDIR-0833 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00254-4499 | PS5-03-RDOS-1401-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-1411 TO PS5-03-RDOS-1401 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-4500 | PS5-03-RDOS-1402-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1401 TO PS5-03-RDOS-1402 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-4501 | PS5-03-RDOS-1403-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1402 TO PS5-03-RDOS-1403 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-4502 | PS5-03-RDOS-1404-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1403 TO PS5-03-RDOS-1404 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-4503 | PS5-03-RDOS-1405-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1404 TO PS5-03-RDOS-1405 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-4504 | PS5-03-RDOS-1406-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1503 TO PS5-03-RDOS-1406 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-4505 | PS5-03-RDOS-1407-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1405 TO PS5-03-RDOS-1407 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-4506 | PS5-03-RDOS-1408-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1407 TO PS5-03-RDOS-1408 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-4507 | PS5-03-RDOS-1501-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1603 TO PS5-03-RDOS-1501 |  | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1
T-00254-4508 | PS5-03-RDOS-1502-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1501 TO PS5-03-RDOS-1502 |  | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1
T-00254-4509 | PS5-03-RDOS-1503-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1502 TO PS5-03-RDOS-1503 |  | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1
T-00254-4510 | PS5-03-RDOS-1601-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1702 TO PS5-03-RDOS-1601 |  | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2
T-00254-4511 | PS5-03-RDOS-1602-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1601 TO PS5-03-RDOS-1602 |  | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2
T-00254-4512 | PS5-03-RDOS-1603-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1602 TO PS5-03-RDOS-1603 |  | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2
T-00254-4513 | PS5-03-RDOS-1701-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1803 TO PS5-03-RDOS-1701 |  | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3
T-00254-4514 | PS5-03-RDOS-1702-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1701 TO PS5-03-RDOS-1702 |  | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3
T-00254-4515 | PS5-03-RDOS-1801-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDH-1901 TO PS5-03-RDOS-1801 |  | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4
T-00254-4516 | PS5-03-RDOS-1802-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1801 TO PS5-03-RDOS-1802 |  | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4
T-00254-4517 | PS5-03-RDOS-1803-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1802 TO PS5-03-RDOS-1803 |  | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4
T-00254-4518 | PS5-03-RDOS-2101-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RMAC-1409 TO PS5-03-RDOS-2101 |  | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit
T-00254-4519 | PS5-03-RDOS-2102-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-2101 TO PS5-03-RDOS-2102 |  | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit
T-00254-4520 | PS5-03-RDOS-2103-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-2102 TO PS5-03-RDOS-2103 |  | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit
T-00254-4521 | PS5-03-RDOS-G101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-G101B TO PS5-03-RDOS-G101A |  | PS5-03-22 - FZ-G1 - Guard House
T-00254-4522 | PS5-03-RDOS-G101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0002 TO PS5-03-RDOS-G101B |  | PS5-03-22 - FZ-G1 - Guard House
T-00254-4523 | PS5-03-RDUIR-0701-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0701-CJ01 | I | Cable FROM PS5-03-BI-1511 TO PS5-03-RDUIR-0701 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00254-4524 | PS5-03-RDUIR-0702-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0702-CJ01 | I | Cable FROM PS5-03-BI-1511 TO PS5-03-RDUIR-0702 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00254-4525 | PS5-03-RDUIR-0703-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0703-CJ01 | I | Cable FROM PS5-03-BI-1511 TO PS5-03-RDUIR-0703 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00254-4526 | PS5-03-RDUIR-0704-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0704-CJ01 | I | Cable FROM PS5-03-BI-1511 TO PS5-03-RDUIR-0704 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00254-4527 | PS5-03-RDUIR-0705-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0705-CJ01 | I | Cable FROM PS5-03-BI-1511 TO PS5-03-RDUIR-0705 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00254-4528 | PS5-03-RDUIR-0907-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0907-CJ01 | I | Cable FROM PS5-03-BI-1512 TO PS5-03-RDUIR-0907 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4529 | PS5-03-RDUIR-0908-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-0908-CJ01 | I | Cable FROM PS5-03-BI-1512 TO PS5-03-RDUIR-0908 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1
T-00254-4530 | PS5-03-RDUIR-1007-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1007-CJ01 | I | Cable FROM PS5-03-BI-1513 TO PS5-03-RDUIR-1007 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4531 | PS5-03-RDUIR-1008-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1008-CJ01 | I | Cable FROM PS5-03-BI-1513 TO PS5-03-RDUIR-1008 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2
T-00254-4532 | PS5-03-RDUIR-1107-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1107-CJ01 | I | Cable FROM PS5-03-BI-1514 TO PS5-03-RDUIR-1107 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4533 | PS5-03-RDUIR-1108-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1108-CJ01 | I | Cable FROM PS5-03-BI-1514 TO PS5-03-RDUIR-1108 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3
T-00254-4534 | PS5-03-RDUIR-1207-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1207-CJ01 | I | Cable FROM PS5-03-BI-1516 TO PS5-03-RDUIR-1207 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00254-4535 | PS5-03-RDUIR-1208-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RDUIR-1208-CJ01 | I | Cable FROM PS5-03-BI-1516 TO PS5-03-RDUIR-1208 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4
T-00254-4536 | PS5-03-RMAC-0101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0101-CJ01 | I | Cable FROM PS5-03-BI-2504 TO PS5-03-RMAC-0101 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4537 | PS5-03-RMAC-0102-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0102-CJ01 | I | Cable FROM PS5-03-BI-2504 TO PS5-03-RMAC-0102 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4538 | PS5-03-RMAC-0103-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0103-CJ01 | I | Cable FROM PS5-03-BI-2504 TO PS5-03-RMAC-0103 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4540 | PS5-03-RMAC-0301-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-2509 TO PS5-03-RMAC-0301 |  | PS5-03-03 - FZ-03 - Buildings Area
T-00254-4541 | PS5-03-RMAC-0304-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-BI-2509 TO PS5-03-RMAC-0304 |  | PS5-03-03 - FZ-03 - Buildings Area
T-00254-4542 | PS5-03-RMAC-0401-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0401-CJ01 | I | Cable FROM PS5-03-BI-2509 TO PS5-03-RMAC-0401 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4543 | PS5-03-RMAC-0402-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0402-CJ01 | I | Cable FROM PS5-03-BI-2509 TO PS5-03-RMAC-0402 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4544 | PS5-03-RMAC-0613-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0613-CJ01 | I | Cable FROM PS5-03-BI-2503 TO PS5-03-RMAC-0613 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4545 | PS5-03-RMAC-0706-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0706-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RMAC-0706 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00254-4546 | PS5-03-RMAC-0707-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0707-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RMAC-0707 |  | PS5-03-07 - FZ-07 - Pretreatment Area
T-00254-4548 | PS5-03-RMAC-0825-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0825-CJ01 | I | Cable FROM PS5-03-BI-2506 TO PS5-03-RMAC-0825 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00254-4549 | PS5-03-RMAC-0827-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0827-CJ01 | I | Cable FROM PS5-03-BI-2505 TO PS5-03-RMAC-0827 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00254-4550 | PS5-03-RMAC-0834-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-0834-CJ01 | I | Cable FROM PS5-03-BI-2514 TO PS5-03-RMAC-0834 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External
T-00254-4551 | PS5-03-RMAC-1301-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-RMAC-1301-CJ01 | I | Cable FROM PS5-03-BI-2515 TO PS5-03-RMAC-1301 |  | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room
T-00254-4552 | PS5-03-RMAC-1410-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-2103 TO PS5-03-RMAC-1410 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-4553 | PS5-03-RMAC-1411-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-RDOS-1406 TO PS5-03-RMAC-1411 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-4554 | PS5-03-SEA-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-03-SEA-0001-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4563 | PS5-05-BI-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4564 | PS5-05-BI-0002-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC02 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4565 | PS5-05-BI-0002-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC03 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4566 | PS5-05-BI-0002-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC04 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4567 | PS5-05-BI-0002-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC05 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4568 | PS5-05-BI-0002-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CC06 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4571 | PS5-05-BI-0002-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CJ01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING
T-00254-4572 | PS5-05-BI-0002-CJ02 | TJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CJ02 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING
T-00254-4573 | PS5-05-BI-0002-CJ03 | TJX10 - Multi/Single-core instrument control cable | PS5-05-BI-0002-CJ03 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4574 | PS5-05-GC-8100-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-05-GC-8100-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4577 | PS5-05-IE-8101-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-05-IE-8101-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4578 | PS5-05-IG-0009-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-05-IG-0009-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4579 | PS5-05-IG-0009-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-05-IG-0009-CC02 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4580 | PS5-05-IG-0009-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-05-IG-0009-CJ01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4581 | PS5-05-LIT-4101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-05-LIT-4101-CJ01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4582 | PS5-05-UH-8100-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-05-UH-8100-CC01 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4583 | PS5-05-UH-8100-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-05-UH-8100-CC02 | I | Cable FROM PS5-05-IE-8100 TO PS5-05-BI-0002 |  | PS5-05-01 - Emergency Diesel Generator Package | CPP-RFI-68-64-12-0107 | 2026-07-22 | Accepted | Elizabeth | TESTING |  |  |  | Elizabeth
T-00254-4623 | PS5-25-BI-1802A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-BI-1802A-CC01 | I | Cable FROM PS5-61-IDH-3100A TO PS5-25-BI-1802A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0055 | 2026-05-09 | Accepted with Punch | Elizabeth | TESTING
T-00254-4625 | PS5-25-BI-1802B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-BI-1802B-CC01 | I | Cable FROM PS5-61-IDH-3100B TO PS5-25-BI-1802B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0055 | 2026-05-09 | Accepted with Punch | Elizabeth | TESTING
T-00254-4627 | PS5-25-BI-1802C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-BI-1802C-CC01 | I | Cable FROM PS5-61-IDH-3100C TO PS5-25-BI-1802C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0055 | 2026-05-09 | Accepted with Punch | Elizabeth | TESTING
T-00254-4654 | PS5-25-ESDV-0021-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0021-CC01 | I | Cable FROM PS5-25-BI-1201 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4655 | PS5-25-ESDV-0021-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0021-CC02 | I | Cable FROM PS5-25-BI-2201 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4656 | PS5-25-ESDV-0021-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0021-CC03 | I | Cable FROM PS5-25-BI-2203 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4657 | PS5-25-ESDV-0023-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0023-CC01 | I | Cable FROM PS5-25-BI-1201 TO PS5-25-ESDV-0023 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4658 | PS5-25-ESDV-0023-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0023-CC02 | I | Cable FROM PS5-25-BI-2201 TO PS5-25-ESDV-0023 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4659 | PS5-25-ESDV-0023-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ESDV-0023-CC03 | I | Cable FROM PS5-25-BI-2203 TO PS5-25-ESDV-0023 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4660 | PS5-25-ESY-0021A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ESY-0021A-CJ01 | I | Cable FROM PS5-25-BI-2205 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4661 | PS5-25-ESY-0021B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ESY-0021B-CJ01 | I | Cable FROM PS5-25-BI-2309 TO PS5-25-ESDV-0021 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4662 | PS5-25-ESY-0023B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ESY-0023B-CJ01 | I | Cable FROM PS5-25-BI-2309 TO PS5-25-ESDV-0023 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4663 | PS5-25-FCV-0003A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-FCV-0003A-HPU TO PS5-25-FCV-0003A |  | PS5-25-02 - Crude Oil Export Pump A
T-00254-4664 | PS5-25-FCV-0003B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-FCV-0003B-HPU TO PS5-25-FCV-0003B |  | PS5-25-03 - Crude Oil Export Pump B
T-00254-4665 | PS5-25-FCV-0003C-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-FCV-0003C-HPU TO PS5-25-FCV-0003C |  | PS5-25-04 - Crude Oil Export Pump C
T-00254-4666 | PS5-25-FCV-0004-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-FCV-0004-HPU TO PS5-25-FCV-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00254-4667 | PS5-25-FIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FIT-0001-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-FIT-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4668 | PS5-25-FIT-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FIT-0003A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FIT-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4669 | PS5-25-FIT-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FIT-0003B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FIT-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4670 | PS5-25-FIT-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FIT-0003C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-FIT-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0108 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4671 | PS5-25-FIT-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FIT-0004-CJ01 | I | Cable FROM PS5-25-BI-1115 TO PS5-25-FIT-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4672 | PS5-25-FXS-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FXS-0003A-CJ01 | I | Cable FROM PS5-25-BI-2106 TO PS5-25-FCV-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4673 | PS5-25-FXS-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FXS-0003B-CJ01 | I | Cable FROM PS5-25-BI-2106 TO PS5-25-FCV-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4674 | PS5-25-FXS-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FXS-0003C-CJ01 | I | Cable FROM PS5-25-BI-2106 TO PS5-25-FCV-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4675 | PS5-25-FXS-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FXS-0004-CJ01 | I | Cable FROM PS5-25-BI-2105 TO PS5-25-FCV-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4676 | PS5-25-FY-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FY-0003A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FCV-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4677 | PS5-25-FY-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FY-0003B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FCV-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4678 | PS5-25-FY-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FY-0003C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-FCV-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0108 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4679 | PS5-25-FY-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-FY-0004-CJ01 | I | Cable FROM PS5-25-BI-1115 TO PS5-25-FCV-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4680 | PS5-25-HS-8101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8101A-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8101A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4681 | PS5-25-HS-8101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8101B-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8101B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4682 | PS5-25-HS-8101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8101C-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8101C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4683 | PS5-25-HS-8102A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8102A-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8102A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4684 | PS5-25-HS-8102B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8102B-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8102B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4685 | PS5-25-HS-8102C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-HS-8102C-CJ01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-HS-8102C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4686 | PS5-25-MOV-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0001-CC01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00254-4687 | PS5-25-MOV-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0002-CC01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0002 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4688 | PS5-25-MOV-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0003-CC01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0003 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4689 | PS5-25-MOV-0008-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0008-CC01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0008 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4690 | PS5-25-MOV-0011-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0011-CC01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0011 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4691 | PS5-25-MOV-0012-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0012-CC01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0012 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4692 | PS5-25-MOV-0025-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0025-CC01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0025 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4693 | PS5-25-MOV-0026-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0026-CC01 | I | Cable FROM PS5-25-BI-2103 TO PS5-25-MOV-0026 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4694 | PS5-25-MOV-0026-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0026-CC02 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-MOV-0026 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4695 | PS5-25-MOV-0027-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0027-CC01 | I | Cable FROM PS5-25-BI-2103 TO PS5-25-MOV-0027 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4696 | PS5-25-MOV-0027-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0027-CC02 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-MOV-0027 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4697 | PS5-25-MOV-0028-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MOV-0028-CC01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0028 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4698 | PS5-25-MXS-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MXS-0001-CJ01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00254-4699 | PS5-25-MXS-0008-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MXS-0008-CJ01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0008 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4700 | PS5-25-MXS-0025-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MXS-0025-CJ01 | I | Cable FROM PS5-25-BI-2101 TO PS5-25-MOV-0025 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4701 | PS5-25-MXS-0028-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-MXS-0028-CJ01 | I | Cable FROM PS5-25-BI-2102 TO PS5-25-MOV-0028 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00254-4708 | PS5-25-PDIT-0034A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PDIT-0034A |  | PS5-25-02 - Crude Oil Export Pump A
T-00254-4709 | PS5-25-PDIT-0034B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PDIT-0034B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PDIT-0034B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4710 | PS5-25-PDIT-0034C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PDIT-0034C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-PDIT-0034C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0108 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4711 | PS5-25-PDIT-0050-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PDIT-0050-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-PDIT-0050 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4712 | PS5-25-PI-1102B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PI-1102B-CJ01 | I | Cable FROM PS5-25-PIT-1102 TO PS5-25-PI-1102B |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4713 | PS5-25-PI-1202B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PI-1202B-CJ01 | I | Cable FROM PS5-25-PIT-1202 TO PS5-25-PI-1202B |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4714 | PS5-25-PIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0001-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-PIT-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4715 | PS5-25-PIT-0003AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0003AA-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FCV-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4716 | PS5-25-PIT-0003BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0003BA-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-FCV-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4717 | PS5-25-PIT-0003CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0003CA-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-FCV-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0108 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4718 | PS5-25-PIT-0004AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0004AA-CJ01 | I | Cable FROM PS5-25-BI-1115 TO PS5-25-FCV-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00254-4719 | PS5-25-PIT-0004A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0004A-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-PIT-0004A |  | PS5-25-02 - Crude Oil Export Pump A
T-00254-4720 | PS5-25-PIT-0004B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0004B-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-PIT-0004B |  | PS5-25-03 - Crude Oil Export Pump B
T-00254-4721 | PS5-25-PIT-0004C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0004C-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-PIT-0004C |  | PS5-25-04 - Crude Oil Export Pump C
T-00254-4722 | PS5-25-PIT-0005A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0005A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PIT-0005A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4723 | PS5-25-PIT-0005B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0005B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PIT-0005B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4724 | PS5-25-PIT-0005C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0005C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-PIT-0005C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0108 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4725 | PS5-25-PIT-0007A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0007A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PIT-0007A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4726 | PS5-25-PIT-0007B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0007B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PIT-0007B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4727 | PS5-25-PIT-0007C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0007C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-PIT-0007C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0108 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4728 | PS5-25-PIT-0008A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0008A-CJ01 | I | Cable FROM PS5-25-BI-1301 TO PS5-25-PIT-0008A |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4729 | PS5-25-PIT-0008B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0008B-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-PIT-0008B |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00254-4730 | PS5-25-PIT-0008C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0008C-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-PIT-0008C |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00254-4731 | PS5-25-PIT-0013-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0013-CJ01 | I | Cable FROM PS5-25-BI-1115 TO PS5-25-PIT-0013 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4732 | PS5-25-PIT-0018-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0018-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-PIT-0018 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4733 | PS5-25-PIT-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0022-CJ01 | I | Cable FROM PS5-25-BI-1301 TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4734 | PS5-25-PIT-0035A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0035A-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A
T-00254-4735 | PS5-25-PIT-0035B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0035B-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B
T-00254-4736 | PS5-25-PIT-0035C-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C
T-00254-4737 | PS5-25-PIT-0036A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0036A-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A
T-00254-4738 | PS5-25-PIT-0036B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0036B-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B
T-00254-4739 | PS5-25-PIT-0036C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0036C-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C
T-00254-4740 | PS5-25-PIT-0046-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0046-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00254-4742 | PS5-25-PIT-0053-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0053-CJ01 | I | Cable FROM PS5-25-BI-1115 TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4743 | PS5-25-PIT-0054A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0054A-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A
T-00254-4744 | PS5-25-PIT-0054B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0054B-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4745 | PS5-25-PIT-0054C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0054C-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4746 | PS5-25-PIT-0070-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-0070-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-XV-0070 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4750 | PS5-25-PIT-1102-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-1102-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-PIT-1102 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4751 | PS5-25-PIT-1202-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-PIT-1202-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-PIT-1202 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4752 | PS5-25-SDV-0022-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0022-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4753 | PS5-25-SDV-0022-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-SDV-0022-HPU TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00254-4754 | PS5-25-SDV-0035A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0035A-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4755 | PS5-25-SDV-0035B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0035B-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4756 | PS5-25-SDV-0035C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0035C-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4757 | PS5-25-SDV-0036A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0036A-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4758 | PS5-25-SDV-0036B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0036B-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-4759 | PS5-25-SDV-0036C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0036C-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-4760 | PS5-25-SDV-0046-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0046-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4763 | PS5-25-SDV-0054A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0054A-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4764 | PS5-25-SDV-0054B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0054B-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4765 | PS5-25-SDV-0054C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SDV-0054C-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-4767 | PS5-25-SXS-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-2302 TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00254-4768 | PS5-25-SXS-0035A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0035A-CJ01 | I | Cable FROM PS5-25-BI-2301 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4769 | PS5-25-SXS-0035B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0035B-CJ01 | I | Cable FROM PS5-25-BI-2301 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4770 | PS5-25-SXS-0035C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0035C-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4771 | PS5-25-SXS-0036A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0036A-CJ01 | I | Cable FROM PS5-25-BI-2301 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4772 | PS5-25-SXS-0036B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0036B-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4773 | PS5-25-SXS-0036C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0036C-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4774 | PS5-25-SXS-0046-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0046-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-4776 | PS5-25-SXS-0054A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-2301 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A
T-00254-4777 | PS5-25-SXS-0054B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0054B-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B
T-00254-4778 | PS5-25-SXS-0054C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SXS-0054C-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4779 | PS5-25-SY-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0022-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0022 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4780 | PS5-25-SY-0035AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035AA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4781 | PS5-25-SY-0035AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035AB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-SDV-0035A |  | PS5-25-02 - Crude Oil Export Pump A
T-00254-4782 | PS5-25-SY-0035BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035BA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4783 | PS5-25-SY-0035BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035BB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-SDV-0035B |  | PS5-25-03 - Crude Oil Export Pump B
T-00254-4784 | PS5-25-SY-0035CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035CA-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C
T-00254-4785 | PS5-25-SY-0035CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0035CB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-25-SDV-0035C |  | PS5-25-04 - Crude Oil Export Pump C
T-00254-4786 | PS5-25-SY-0036AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036AA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4787 | PS5-25-SY-0036AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036AB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-SDV-0036A |  | PS5-25-02 - Crude Oil Export Pump A
T-00254-4788 | PS5-25-SY-0036BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036BA-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B
T-00254-4789 | PS5-25-SY-0036BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036BB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-25-SDV-0036B |  | PS5-25-03 - Crude Oil Export Pump B
T-00254-4790 | PS5-25-SY-0036CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036CA-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-4791 | PS5-25-SY-0036CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0036CB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-25-SDV-0036C |  | PS5-25-04 - Crude Oil Export Pump C
T-00254-4792 | PS5-25-SY-0046A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0046A-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4793 | PS5-25-SY-0046B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0046B-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-SDV-0046 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4795 | PS5-25-SY-0052B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0052B-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0052 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-4796 | PS5-25-SY-0054AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054AA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4797 | PS5-25-SY-0054AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054AB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-SDV-0054A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4798 | PS5-25-SY-0054BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054BA-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B
T-00254-4799 | PS5-25-SY-0054BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054BB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-25-SDV-0054B |  | PS5-25-03 - Crude Oil Export Pump B
T-00254-4800 | PS5-25-SY-0054CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054CA-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C
T-00254-4801 | PS5-25-SY-0054CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-SY-0054CB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-25-SDV-0054C |  | PS5-25-04 - Crude Oil Export Pump C
T-00254-4802 | PS5-25-TIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0001-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-TIT-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4803 | PS5-25-TIT-0002A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0002A-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-TIT-0002A |  | PS5-25-02 - Crude Oil Export Pump A
T-00254-4804 | PS5-25-TIT-0002B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0002B-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-25-TIT-0002B |  | PS5-25-03 - Crude Oil Export Pump B
T-00254-4805 | PS5-25-TIT-0002C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0002C-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-25-TIT-0002C |  | PS5-25-04 - Crude Oil Export Pump C
T-00254-4806 | PS5-25-TIT-0003A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0003A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-TIT-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4807 | PS5-25-TIT-0003B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0003B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-25-TIT-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4808 | PS5-25-TIT-0003C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0003C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-25-TIT-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-12-0108 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4809 | PS5-25-TIT-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-0004-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-TIT-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4810 | PS5-25-TIT-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-1101-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-TIT-1101 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4811 | PS5-25-TIT-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-TIT-1201-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-25-TIT-1201 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4812 | PS5-25-XV-0053-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-XV-0053-CC01 | I | Cable FROM PS5-25-BI-2104 TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00254-4813 | PS5-25-XV-0053-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-XV-0053-HPU TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00254-4814 | PS5-25-XV-0070-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-XV-0070-CC01 | I | Cable FROM PS5-25-BI-2104 TO PS5-25-XV-0070 |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00254-4815 | PS5-25-XXS-0053-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-XXS-0053-CJ01 | I | Cable FROM PS5-25-BI-2105 TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4816 | PS5-25-XXS-0070-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-XXS-0070-CJ01 | I | Cable FROM PS5-25-BI-2105 TO PS5-25-XV-0070 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4817 | PS5-25-XY-0053-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-XY-0053-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-XV-0053 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4818 | PS5-25-XY-0070-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-XY-0070-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-25-XV-0070 |  | PS5-25-05 - Crude Oil Export Pumps Bypass | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4819 | PS5-25-ZIT-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ZIT-0001-CC01 | I | Cable FROM PS5-25-BI-1102 TO PS5-25-ZIT-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00254-4820 | PS5-25-ZIT-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ZIT-0002-CC01 | I | Cable FROM PS5-25-BI-1102 TO PS5-25-ZIT-0002 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00254-4821 | PS5-25-ZS-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ZS-1101-CJ01 | I | Cable FROM PS5-25-BI-2104 TO PS5-25-ZS-1101 |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00254-4822 | PS5-25-ZS-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-25-ZS-1201-CJ01 | I | Cable FROM PS5-25-BI-2104 TO PS5-25-ZS-1201 |  | PS5-25-07 - Export Pipeline Pig Launcher
T-00254-4830 | PS5-28-HXA-1402-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-2115 TO PS5-28-HXA-1402 |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00254-4831 | PS5-28-HY-3901A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-HY-3901A-CJ01 | I | Cable FROM PS5-28-BI-1105 TO PS5-28-HY-3901A |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4832 | PS5-28-HY-3901B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-HY-3901B-CJ01 | I | Cable FROM PS5-28-BI-1105 TO PS5-28-HY-3901B |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4835 | PS5-28-LI-1101B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LI-1101B-CJ01 | I | Cable FROM PS5-28-LIT-1101 TO PS5-28-LI-1101B |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4836 | PS5-28-LI-1101C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LI-1101C-CJ01 | I | Cable FROM PS5-25-BI-1101 TO PS5-28-LI-1101C |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-12-0094 | 2026-07-13 | Accepted | G K RAO | TESTING
T-00254-4837 | PS5-28-LI-1402B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LI-1402B-CJ01 | I | Cable FROM PS5-28-LIT-1402 TO PS5-28-LI-1402B |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4838 | PS5-28-LIT-0002-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-0002-CJ01 | I | Cable FROM PS5-50-BI-1107 TO PS5-28-LIT-0002 |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4839 | PS5-28-LIT-0008-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-0008-CJ01 | I | Cable FROM PS5-50-BI-1107 TO PS5-28-LIT-0008 |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4840 | PS5-28-LIT-1101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1101-CJ01 | I | Cable FROM PS5-28-BI-1105 TO PS5-28-LIT-1101 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4841 | PS5-28-LIT-1102-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1102-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-LIT-1102 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4842 | PS5-28-LIT-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1201-CJ01 | I | Cable FROM PS5-28-BI-1106 TO PS5-28-LIT-1201 |  | PS5-28-06 - Relief Drum and Pump
T-00254-4843 | PS5-28-LIT-1202-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1202-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-LIT-1202 |  | PS5-28-06 - Relief Drum and Pump | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4844 | PS5-28-LIT-1301A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1301A-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-28-LIT-1301A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4845 | PS5-28-LIT-1301B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1301B-CJ01 | I | Cable FROM PS5-25-BI-1103 TO PS5-28-LIT-1301B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPP-RFI-68-64-12-0098 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-4846 | PS5-28-LIT-1301C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1301C-CJ01 | I | Cable FROM PS5-25-BI-1104 TO PS5-28-LIT-1301C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPP-RFI-68-64-12-0108 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4847 | PS5-28-LIT-1401-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1401-CJ01 | I | Cable FROM PS5-28-BI-1307 TO PS5-28-LIT-1401 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4848 | PS5-28-LIT-1402-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-LIT-1402-CJ01 | I | Cable FROM PS5-28-BI-1114 TO PS5-28-LIT-1402 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4849 | PS5-28-PIT-0015-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0015-CJ01 | I | Cable FROM PS5-28-BI-1105 TO PS5-28-PIT-0015 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4850 | PS5-28-PIT-0033-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0033-CJ01 | I | Cable FROM PS5-28-BI-1106 TO PS5-28-PIT-0033 |  | PS5-28-06 - Relief Drum and Pump
T-00254-4851 | PS5-28-PIT-0041-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0041-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-PIT-0041 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4852 | PS5-28-PIT-0045-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0045-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4853 | PS5-28-PIT-0053A-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-1302 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00254-4854 | PS5-28-PIT-0053B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0053B-CJ01 | I | Cable FROM PS5-25-BI-1302 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00254-4855 | PS5-28-PIT-0053C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-0053C-CJ01 | I | Cable FROM PS5-25-BI-1310 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4856 | PS5-28-PIT-3901A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-3901A-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-PIT-3901A |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4857 | PS5-28-PIT-3901B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-PIT-3901B-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-PIT-3901B |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4858 | PS5-28-SDV-0045-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SDV-0045-CC01 | I | Cable FROM PS5-28-BI-2304 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump
T-00254-4859 | PS5-28-SDV-0045-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-28-SDV-0045-HPU TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump
T-00254-4860 | PS5-28-SDV-0053A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SDV-0053A-CC01 | I | Cable FROM PS5-25-BI-2305 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4861 | PS5-28-SDV-0053A-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-28-SDV-0053A-HPU TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00254-4862 | PS5-28-SDV-0053B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SDV-0053B-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00254-4863 | PS5-28-SDV-0053B-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-28-SDV-0053B-HPU TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00254-4864 | PS5-28-SDV-0053C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SDV-0053C-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00254-4865 | PS5-28-SDV-0053C-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-28-SDV-0053C-HPU TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00254-4866 | PS5-28-SXS-0045-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-2302 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump
T-00254-4867 | PS5-28-SXS-0053A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SXS-0053A-CJ01 | I | Cable FROM PS5-25-BI-2301 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00254-4868 | PS5-28-SXS-0053B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SXS-0053B-CJ01 | I | Cable FROM PS5-25-BI-2301 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B
T-00254-4869 | PS5-28-SXS-0053C-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SXS-0053C-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4870 | PS5-28-SY-0045A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0045A-CJ01 | I | Cable FROM PS5-25-BI-2309 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4871 | PS5-28-SY-0045B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0045B-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-28-SDV-0045 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4872 | PS5-28-SY-0053AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0053AA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4873 | PS5-28-SY-0053AB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0053AB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-28-SDV-0053A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A
T-00254-4874 | PS5-28-SY-0053BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0053BA-CJ01 | I | Cable FROM PS5-25-BI-2308 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4875 | PS5-28-SY-0053BB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0053BB-CJ01 | I | Cable FROM PS5-25-BI-2109 TO PS5-28-SDV-0053B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4876 | PS5-28-SY-0053CA-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-25-BI-2316 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C
T-00254-4877 | PS5-28-SY-0053CB-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-SY-0053CB-CJ01 | I | Cable FROM PS5-25-BI-2108 TO PS5-28-SDV-0053C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPP-RFI-68-64-12-0114 | 25-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4878 | PS5-28-TIT-1104-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-1104-CJ01 | I | Cable FROM PS5-28-BI-1105 TO PS5-28-TIT-1104 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4879 | PS5-28-TIT-1105-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-1105-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-TIT-1105 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4880 | PS5-28-TIT-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-1201-CJ01 | I | Cable FROM PS5-28-BI-1106 TO PS5-28-TIT-1201 |  | PS5-28-06 - Relief Drum and Pump
T-00254-4881 | PS5-28-TIT-1401-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-1401-CJ01 | I | Cable FROM PS5-28-BI-1114 TO PS5-28-TIT-1401 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4882 | PS5-28-TIT-1402-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-1402-CJ01 | I | Cable FROM PS5-28-BI-1307 TO PS5-28-TIT-1402 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4883 | PS5-28-TIT-2101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-2101-CJ01 | I | Cable FROM PS5-28-BI-1303 TO PS5-28-TIT-2101 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4884 | PS5-28-TIT-2201-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-28-TIT-2201-CJ01 | I | Cable FROM PS5-28-BI-1307 TO PS5-28-TIT-2201 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-4886 | PS5-50-FIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-50-FIT-0001-CJ01 | I | Cable FROM PS5-50-BI-1107 TO PS5-50-FIT-0001 |  | PS5-50-03 - Water Pre-Treatment Package | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-4897 | PS5-53-LIT-4101-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-53-BI-1108 TO PS5-53-LIT-4101 |  | PS5-53-01 - Utility Water / Storage Tank
T-00254-4898 | PS5-53-LIT-4102-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-53-BI-1304 TO PS5-53-LIT-4102 |  | PS5-53-01 - Utility Water / Storage Tank
T-00254-4899 | PS5-53-PIT-0005-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-53-PIT-0005-CJ01 | I | Cable FROM PS5-53-BI-1108 TO PS5-53-PIT-0005 |  | PS5-53-02 - Water Distribution Pump A/B
T-00254-4900 | PS5-60-BE-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0001-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0001 |  | PS5-60-27 - Compressed Air Starting Skid | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4901 | PS5-60-BE-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0002-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0002 |  | PS5-60-26 - Instrument Air Compressor Skid | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4902 | PS5-60-BE-0004A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004A-CC01 | I | Cable FROM PS5-60-IN-0001A TO PS5-60-BE-0004A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4903 | PS5-60-BE-0004B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004B-CC01 | I | Cable FROM PS5-60-IN-0001B TO PS5-60-BE-0004B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4904 | PS5-60-BE-0004C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004C-CC01 | I | Cable FROM PS5-60-IN-0001C TO PS5-60-BE-0004C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4905 | PS5-60-BE-0004D-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004D-CC01 | I | Cable FROM PS5-60-IN-0001D TO PS5-60-BE-0004D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4906 | PS5-60-BE-0004E-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004E-CC01 | I | Cable FROM PS5-60-IN-0001E TO PS5-60-BE-0004E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4907 | PS5-60-BE-0004F-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004F-CC01 | I | Cable FROM PS5-60-IN-0001F TO PS5-60-BE-0004F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4908 | PS5-60-BE-0004G-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BE-0004G-CC01 | I | Cable FROM PS5-60-IN-0001G TO PS5-60-BE-0004G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4909 | PS5-60-BI-0001A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4910 | PS5-60-BI-0001A-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001A-CC03 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4911 | PS5-60-BI-0001B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4912 | PS5-60-BI-0001B-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001B-CC03 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4913 | PS5-60-BI-0001C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4914 | PS5-60-BI-0001C-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001C-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4915 | PS5-60-BI-0001D-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4916 | PS5-60-BI-0001D-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001D-CC03 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4917 | PS5-60-BI-0001E-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0001E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4918 | PS5-60-BI-0001E-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001E-CC03 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0001E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4919 | PS5-60-BI-0001F-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0001F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4920 | PS5-60-BI-0001F-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001F-CC03 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0001F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4921 | PS5-60-BI-0001G-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0001G |  | PS5-60-19 - Power Generation Package G | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4922 | PS5-60-BI-0001G-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0001G-CC03 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0001G |  | PS5-60-19 - Power Generation Package G | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4923 | PS5-60-BI-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0002-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0128 | 01-August-2026 | OPEN | Ferdinand | Testing
T-00254-4924 | PS5-60-BI-0002-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0002-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-4925 | PS5-60-BI-0002-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0002-CC03 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0128 | 01-August-2026 | OPEN | Ferdinand | Testing
T-00254-4926 | PS5-60-BI-0002-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0002-CC04 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0128 | 01-August-2026 | OPEN | Ferdinand | Testing
T-00254-4927 | PS5-60-BI-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0003-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 |  | PS5-60-22 - Power Gen Master UCP | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4928 | PS5-60-BI-0003-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0003-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 |  | PS5-60-22 - Power Gen Master UCP | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4929 | PS5-60-BI-0004A-CCO1 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004A-CCO1 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0004A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-4930 | PS5-60-BI-0004B-CCO1 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004B-CCO1 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0004B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-4931 | PS5-60-BI-0004C-CCO1 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004C-CCO1 | I | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0004C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-4932 | PS5-60-BI-0004D-CCO1 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004D-CCO1 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0004D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-4933 | PS5-60-BI-0004E-CCO1 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004E-CCO1 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-BI-0004E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-4934 | PS5-60-BI-0004F-CCO1 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004F-CCO1 | I | Cable FROM PS5-60-IE-0001F TO PS5-60-BI-0004F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-4935 | PS5-60-BI-0004G-CCO1 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0004G-CCO1 | I | Cable FROM PS5-60-IE-0001G TO PS5-60-BI-0004G |  | PS5-60-19 - Power Generation Package G | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-4936 | PS5-60-BI-0005A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-4937 | PS5-60-BI-0005A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005A-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-4938 | PS5-60-BI-0005B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-4939 | PS5-60-BI-0005B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005B-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-4940 | PS5-60-BI-0005C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-12-0124 | 2026-07-28 | open | Elizabeth | Testing
T-00254-4941 | PS5-60-BI-0005C-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005C-CC02 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-12-0124 | 2026-07-28 | open | Elizabeth | Testing
T-00254-4942 | PS5-60-BI-0005D-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0124 | 2026-07-28 | open | Elizabeth | Testing
T-00254-4943 | PS5-60-BI-0005D-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005D-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0124 | 2026-07-28 | open | Elizabeth | Testing
T-00254-4944 | PS5-60-BI-0005E-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0005E |  | PS5-60-13 - Power Generation Package E
T-00254-4945 | PS5-60-BI-0005E-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005E-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0005E |  | PS5-60-13 - Power Generation Package E
T-00254-4946 | PS5-60-BI-0005F-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0005F |  | PS5-60-16 - Power Generation Package F
T-00254-4947 | PS5-60-BI-0005F-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005F-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0005F |  | PS5-60-16 - Power Generation Package F
T-00254-4948 | PS5-60-BI-0005G-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0005G |  | PS5-60-19 - Power Generation Package G
T-00254-4949 | PS5-60-BI-0005G-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0005G-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0005G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-64-12-0123 | 29-July-2026 | Acceptable | Ferdinand | Testing
T-00254-4950 | PS5-60-BI-0006A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0006A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4951 | PS5-60-BI-0006A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC02 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-4952 | PS5-60-BI-0006A-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC03 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-4953 | PS5-60-BI-0006A-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC04 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-4954 | PS5-60-BI-0006A-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC05 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4955 | PS5-60-BI-0006A-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006A-CC06 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-4956 | PS5-60-BI-0006B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0006B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4957 | PS5-60-BI-0006B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC02 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-64-12-0102 |  | Accepted | Elizabeth | Testing
T-00254-4958 | PS5-60-BI-0006B-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC03 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-64-12-0102 |  | Accepted | Elizabeth | Testing
T-00254-4959 | PS5-60-BI-0006B-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC04 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | Testing
T-00254-4960 | PS5-60-BI-0006B-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC05 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4961 | PS5-60-BI-0006B-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006B-CC06 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-64-12-0102 |  | Accepted | Elizabeth | Testing
T-00254-4962 | PS5-60-BI-0006C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0006C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4963 | PS5-60-BI-0006C-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC02 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-RFI-68-64-12-0105 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4964 | PS5-60-BI-0006C-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC03 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-RFI-68-64-12-0105 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4965 | PS5-60-BI-0006C-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC04 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-RFI-68-64-12-0105 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4966 | PS5-60-BI-0006C-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC05 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4967 | PS5-60-BI-0006C-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006C-CC06 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-RFI-68-64-12-0105 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4968 | PS5-60-BI-0006D-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0006D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4969 | PS5-60-BI-0006D-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC02 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-64-12-0105 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4970 | PS5-60-BI-0006D-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC03 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-64-12-0105 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4971 | PS5-60-BI-0006D-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC04 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-64-12-0121 | 2026-07-29 | Accepted | G K RAO | TESTING
T-00254-4972 | PS5-60-BI-0006D-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC05 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4973 | PS5-60-BI-0006D-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006D-CC06 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-64-12-0105 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-4974 | PS5-60-BI-0006E-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0006E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4975 | PS5-60-BI-0006E-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC02 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00254-4976 | PS5-60-BI-0006E-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC03 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00254-4977 | PS5-60-BI-0006E-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC04 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00254-4978 | PS5-60-BI-0006E-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC05 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4979 | PS5-60-BI-0006E-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006E-CC06 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00254-4980 | PS5-60-BI-0006F-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0006F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4981 | PS5-60-BI-0006F-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC02 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00254-4982 | PS5-60-BI-0006F-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC03 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00254-4983 | PS5-60-BI-0006F-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC04 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00254-4984 | PS5-60-BI-0006F-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC05 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4985 | PS5-60-BI-0006F-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006F-CC06 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00254-4986 | PS5-60-BI-0006G-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0006G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4987 | PS5-60-BI-0006G-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC02 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00254-4988 | PS5-60-BI-0006G-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC03 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00254-4989 | PS5-60-BI-0006G-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC04 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00254-4990 | PS5-60-BI-0006G-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC05 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-4991 | PS5-60-BI-0006G-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0006G-CC06 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00254-4992 | PS5-60-BI-0008A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0008A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-4993 | PS5-60-BI-0008A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0008A-CC02 | I | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-4994 | PS5-60-BI-0008B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0008B-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008B |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-4995 | PS5-60-BI-0008B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0008B-CC02 | I | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008B |  | PS5-60-01 - Power Generation Package A | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-4996 | PS5-60-BI-0009A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0009A-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009A |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-4997 | PS5-60-BI-0009A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0009A-CC02 | I | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009A |  | PS5-60-04 - Power Generation Package B | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-4998 | PS5-60-BI-0009B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0009B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-4999 | PS5-60-BI-0009B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0009B-CC02 | I | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5000 | PS5-60-BI-0010A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0010A-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010A |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-12-0110 | 2026-07-23 | Accepted | G K RAO | TESTING
T-00254-5001 | PS5-60-BI-0010A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0010A-CC02 | I | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010A |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-12-0121 | 2026-07-29 | Accepted | G K RAO | TESTING
T-00254-5002 | PS5-60-BI-0010B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0010B-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010B |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-12-0110 | 2026-07-23 | Accepted | G K RAO | TESTING
T-00254-5003 | PS5-60-BI-0010B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0010B-CC02 | I | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010B |  | PS5-60-07 - Power Generation Package C | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5004 | PS5-60-BI-0011A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0011A-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011A |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0110 | 2026-07-23 | Accepted | G K RAO | TESTING
T-00254-5005 | PS5-60-BI-0011A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0011A-CC02 | I | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011A |  | PS5-60-10 - Power Generation Package D
T-00254-5006 | PS5-60-BI-0011B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0011B-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0110 | 2026-07-23 | Accepted | G K RAO | TESTING
T-00254-5007 | PS5-60-BI-0011B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0011B-CC02 | I | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011B |  | PS5-60-10 - Power Generation Package D | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5008 | PS5-60-BI-0012A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0012A-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0012A |  | PS5-60-13 - Power Generation Package E
T-00254-5009 | PS5-60-BI-0012A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0012A-CC02 | I | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0012A |  | PS5-60-13 - Power Generation Package E | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5010 | PS5-60-BI-0012B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0012B-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0012B |  | PS5-60-13 - Power Generation Package E
T-00254-5011 | PS5-60-BI-0012B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0012B-CC02 | I | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0012B |  | PS5-60-13 - Power Generation Package E | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5012 | PS5-60-BI-0013A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0013A-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0013A |  | PS5-60-16 - Power Generation Package F
T-00254-5013 | PS5-60-BI-0013A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0013A-CC02 | I | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0013A |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5014 | PS5-60-BI-0012B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0012B-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0013B |  | PS5-60-16 - Power Generation Package F
T-00254-5015 | PS5-60-BI-0013B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0013B-CC02 | I | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0013B |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5016 | PS5-60-BI-0014A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0014A-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0014A |  | PS5-60-19 - Power Generation Package G
T-00254-5017 | PS5-60-BI-0014A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0014A-CC02 | I | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0014A |  | PS5-60-19 - Power Generation Package G | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5018 | PS5-60-BI-0014B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0014B-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0014B |  | PS5-60-19 - Power Generation Package G
T-00254-5019 | PS5-60-BI-0014B-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0014B |  | PS5-60-19 - Power Generation Package G
T-00254-5020 | PS5-60-BI-0016A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5021 | PS5-60-BI-0016A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016A-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0102 |  | Accepted | Elizabeth | Testing
T-00254-5022 | PS5-60-BI-0016A-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016A-CC03 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5023 | PS5-60-BI-0016A-CCO4 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016A-CCO4 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0016A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-5024 | PS5-60-BI-0016B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5025 | PS5-60-BI-0016B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016B-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5026 | PS5-60-BI-0016B-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016B-CC03 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5027 | PS5-60-BI-0016B-CCO4 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016B-CCO4 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0016B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-5028 | PS5-60-BI-0016C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5029 | PS5-60-BI-0016C-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016C-CC02 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-12-0121 | 2026-07-29 | Accepted | G K RAO | TESTING
T-00254-5030 | PS5-60-BI-0016C-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016C-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5031 | PS5-60-BI-0016C-CCO4 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0016C |  | PS5-60-07 - Power Generation Package C
T-00254-5032 | PS5-60-BI-0016D-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5033 | PS5-60-BI-0016D-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016D-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0110 | 2026-07-23 | Accepted | G K RAO | TESTING
T-00254-5034 | PS5-60-BI-0016D-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016D-CC03 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5035 | PS5-60-BI-0016D-CCO4 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0016D |  | PS5-60-10 - Power Generation Package D
T-00254-5036 | PS5-60-BI-0016E-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5037 | PS5-60-BI-0016E-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016E-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E |  | PS5-60-13 - Power Generation Package E
T-00254-5038 | PS5-60-BI-0016E-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016E-CC03 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5039 | PS5-60-BI-0016E-CCO4 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016E-CCO4 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-BI-0016E |  | PS5-60-13 - Power Generation Package E
T-00254-5040 | PS5-60-BI-0016F-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5041 | PS5-60-BI-0016F-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016F-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F |  | PS5-60-16 - Power Generation Package F
T-00254-5042 | PS5-60-BI-0016F-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016F-CC03 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5043 | PS5-60-BI-0016F-CCO4 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0001F TO PS5-60-BI-0016F |  | PS5-60-16 - Power Generation Package F
T-00254-5044 | PS5-60-BI-0016G-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G |  | PS5-60-19 - Power Generation Package G | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5045 | PS5-60-BI-0016G-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016G-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G |  | PS5-60-19 - Power Generation Package G
T-00254-5046 | PS5-60-BI-0016G-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0016G-CC03 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5047 | PS5-60-BI-0016G-CCO4 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0001G TO PS5-60-BI-0016G |  | PS5-60-19 - Power Generation Package G
T-00254-5048 | PS5-60-BI-0017A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017A-CC02 | I | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A |  | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPP-RFI-68-64-12-0103 |  | Open | Elizabeth | TESTING
T-00254-5049 | PS5-60-BI-0017B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017B-CC02 | I | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B |  | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5050 | PS5-60-BI-0017C-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017C-CC02 | I | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C |  | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPP-RFI-68-64-12-0110 | 2026-07-23 | Accepted | G K RAO | TESTING
T-00254-5051 | PS5-60-BI-0017D-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017D-CC02 | I | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D |  | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPP-RFI-68-64-12-0105 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-5052 | PS5-60-BI-0017E-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017E-CC02 | I | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0017E |  | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E
T-00254-5053 | PS5-60-BI-0017F-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017F-CC02 | I | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0017F |  | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F
T-00254-5054 | PS5-60-BI-0017G-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0017G-CC02 | I | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0017G |  | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G
T-00254-5055 | PS5-60-BI-0019A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5056 | PS5-60-BI-0019A-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A |  | PS5-60-01 - Power Generation Package A | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5057 | PS5-60-BI-0019B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5058 | PS5-60-BI-0019B-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5059 | PS5-60-BI-0019C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5060 | PS5-60-BI-0019C-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5061 | PS5-60-BI-0019D-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5062 | PS5-60-BI-0019D-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019D-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5063 | PS5-60-BI-0019E-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0019E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5064 | PS5-60-BI-0019E-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019E-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0019E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5065 | PS5-60-BI-0019F-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0019F |  | PS5-60-16 - Power Generation Package F
T-00254-5066 | PS5-60-BI-0019F-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019F-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0019F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5067 | PS5-60-BI-0019G-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0019G |  | PS5-60-19 - Power Generation Package G
T-00254-5068 | PS5-60-BI-0019G-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-BI-0019G-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0019G |  | PS5-60-19 - Power Generation Package G | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5069 | PS5-60-IE-0002B-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002B-CC05 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0002B |  | PS5-60-04 - Power Generation Package B | CPP-68-64-12-0129 | 2026-07-31 | OPEN | Elizabeth | TESTING
T-00254-5070 | PS5-60-IE-0002C-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002C-CC05 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0002C |  | PS5-60-07 - Power Generation Package C | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5071 | PS5-60-IE-0002D-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002D-CC05 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0002D |  | PS5-60-10 - Power Generation Package D | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5072 | PS5-60-IE-0002E-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002E-CC05 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0002E |  | PS5-60-13 - Power Generation Package E | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5073 | PS5-60-IE-0002F-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002F-CC05 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0002F |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5074 | PS5-60-IE-0002G-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0002G-CC05 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0002G |  | PS5-60-19 - Power Generation Package G | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5075 | PS5-60-IE-0003A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC01 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5076 | PS5-60-IE-0003A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC02 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5077 | PS5-60-IE-0003A-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC03 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-5078 | PS5-60-IE-0003A-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC04 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-5079 | PS5-60-IE-0003A-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC05 | I | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5080 | PS5-60-IE-0003A-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC06 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5081 | PS5-60-IE-0003A-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC07 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-12-0102 |  | Accepted | Elizabeth | Testing
T-00254-5082 | PS5-60-IE-0003A-CC08 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC08 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5083 | PS5-60-IE-0003A-CC09 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC09 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5084 | PS5-60-IE-0003A-CC10 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5085 | PS5-60-IE-0003A-CC11 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5086 | PS5-60-IE-0003A-CC15 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC15 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5087 | PS5-60-IE-0003A-CC16 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC16 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5088 | PS5-60-IE-0003A-CC17 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC17 | I | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5093 | PS5-60-IE-0003A-CC25 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC25 | I | Cable FROM PS5-60-TX-41100A TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5094 | PS5-60-IE-0003A-CC26 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003A-CC26 | I | Cable FROM PS5-60-TX-41100B TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5095 | PS5-60-IE-0003B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC01 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-12-0126 | 2026-07-30 | Accepted | Bertus Wikael | Testing
T-00254-5096 | PS5-60-IE-0003B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC02 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5097 | PS5-60-IE-0003B-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC03 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5098 | PS5-60-IE-0003B-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC04 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-12-0102 |  | Accepted | Elizabeth | Testing
T-00254-5099 | PS5-60-IE-0003B-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC05 | I | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-12-0102 |  | Accepted | Elizabeth | Testing
T-00254-5100 | PS5-60-IE-0003B-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC06 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-5101 | PS5-60-IE-0003B-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC07 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-12-0102 |  | Accepted | Elizabeth | Testing
T-00254-5102 | PS5-60-IE-0003B-CC08 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC08 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5103 | PS5-60-IE-0003B-CC09 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC09 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5104 | PS5-60-IE-0003B-CC10 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5105 | PS5-60-IE-0003B-CC11 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5106 | PS5-60-IE-0003B-CC15 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC15 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5107 | PS5-60-IE-0003B-CC16 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC16 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5108 | PS5-60-IE-0003B-CC17 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC17 | I | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5113 | PS5-60-IE-0003B-CC25 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC25 | I | Cable FROM PS5-60-TX-41200A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5114 | PS5-60-IE-0003B-CC26 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003B-CC26 | I | Cable FROM PS5-60-TX-41200B TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5115 | PS5-60-IE-0003C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC01 | I | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0105 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-5116 | PS5-60-IE-0003C-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC02 | I | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5117 | PS5-60-IE-0003C-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC03 | I | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0110 | 2026-07-23 | Accepted | G K RAO | TESTING
T-00254-5118 | PS5-60-IE-0003C-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC04 | I | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0105 | 2026-07-22 | Accepted | G K RAO | TESTING
T-00254-5119 | PS5-60-IE-0003C-CC05 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00254-5120 | PS5-60-IE-0003C-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC06 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5121 | PS5-60-IE-0003C-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC07 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0121 | 2026-07-29 | Accepted | G K RAO | TESTING
T-00254-5122 | PS5-60-IE-0003C-CC08 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC08 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5123 | PS5-60-IE-0003C-CC09 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC09 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5124 | PS5-60-IE-0003C-CC10 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5125 | PS5-60-IE-0003C-CC11 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5126 | PS5-60-IE-0003C-CC15 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC15 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-12-0116 | 27-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5127 | PS5-60-IE-0003C-CC16 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC16 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5128 | PS5-60-IE-0003C-CC17 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC17 | I | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5133 | PS5-60-IE-0003C-CC25 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC25 | I | Cable FROM PS5-60-TX-41300A TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5134 | PS5-60-IE-0003C-CC26 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003C-CC26 | I | Cable FROM PS5-60-TX-41300B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5135 | PS5-60-IE-0003D-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC01 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5136 | PS5-60-IE-0003D-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC02 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5137 | PS5-60-IE-0003D-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC03 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0116 | 27-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5138 | PS5-60-IE-0003D-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC04 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5139 | PS5-60-IE-0003D-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC05 | I | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0116 | 27-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5140 | PS5-60-IE-0003D-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC06 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5141 | PS5-60-IE-0003D-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC07 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5142 | PS5-60-IE-0003D-CC08 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC08 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5143 | PS5-60-IE-0003D-CC09 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC09 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5144 | PS5-60-IE-0003D-CC10 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5145 | PS5-60-IE-0003D-CC11 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00254-5146 | PS5-60-IE-0003D-CC15 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC15 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-12-0116 | 27-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5147 | PS5-60-IE-0003D-CC16 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC16 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5148 | PS5-60-IE-0003D-CC17 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC17 | I | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5153 | PS5-60-IE-0003D-CC25 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC25 | I | Cable FROM PS5-60-TX-41400A TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5154 | PS5-60-IE-0003D-CC26 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003D-CC26 | I | Cable FROM PS5-60-TX-41400B TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5155 | PS5-60-IE-0003E-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC01 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00254-5156 | PS5-60-IE-0003E-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC02 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00254-5157 | PS5-60-IE-0003E-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC03 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00254-5158 | PS5-60-IE-0003E-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC04 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00254-5159 | PS5-60-IE-0003E-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC05 | I | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003F |  | PS5-60-14 - Power Gen Package E (UCP)
T-00254-5160 | PS5-60-IE-0003E-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC06 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5161 | PS5-60-IE-0003E-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC07 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00254-5162 | PS5-60-IE-0003E-CC08 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC08 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5163 | PS5-60-IE-0003E-CC09 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC09 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5164 | PS5-60-IE-0003E-CC10 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00254-5165 | PS5-60-IE-0003E-CC11 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00254-5166 | PS5-60-IE-0003E-CC15 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC15 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00254-5167 | PS5-60-IE-0003E-CC16 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC16 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5168 | PS5-60-IE-0003E-CC17 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC17 | I | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5173 | PS5-60-IE-0003E-CC25 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC25 | I | Cable FROM PS5-60-TX-41500A TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5174 | PS5-60-IE-0003E-CC26 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003E-CC26 | I | Cable FROM PS5-60-TX-41500B TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5175 | PS5-60-IE-0003F-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC01 | I | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5176 | PS5-60-IE-0003F-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC02 | I | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5177 | PS5-60-IE-0003F-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC03 | I | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5178 | PS5-60-IE-0003F-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC04 | I | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5179 | PS5-60-IE-0003F-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC05 | I | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0003G |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5180 | PS5-60-IE-0003F-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC06 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5181 | PS5-60-IE-0003F-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC07 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5182 | PS5-60-IE-0003F-CC08 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC08 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5183 | PS5-60-IE-0003F-CC09 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC09 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5184 | PS5-60-IE-0003F-CC10 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5185 | PS5-60-IE-0003F-CC11 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5186 | PS5-60-IE-0003F-CC15 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC15 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00254-5187 | PS5-60-IE-0003F-CC16 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC16 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5188 | PS5-60-IE-0003F-CC17 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC17 | I | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5193 | PS5-60-IE-0003F-CC25 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC25 | I | Cable FROM PS5-60-TX-41600A TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5194 | PS5-60-IE-0003F-CC26 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003F-CC26 | I | Cable FROM PS5-60-TX-41600B TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5195 | PS5-60-IE-0003G-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC01 | I | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00254-5196 | PS5-60-IE-0003G-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC02 | I | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00254-5197 | PS5-60-IE-0003G-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC03 | I | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5198 | PS5-60-IE-0003G-CC04 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00254-5199 | PS5-60-IE-0003G-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC05 | I | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0003H |  | PS5-60-20 - Power Gen Package G (UCP)
T-00254-5200 | PS5-60-IE-0003G-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC06 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00254-5201 | PS5-60-IE-0003G-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC07 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00254-5202 | PS5-60-IE-0003G-CC08 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC08 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00254-5203 | PS5-60-IE-0003G-CC09 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC09 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00254-5204 | PS5-60-IE-0003G-CC10 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00254-5205 | PS5-60-IE-0003G-CC11 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00254-5206 | PS5-60-IE-0003G-CC15 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC15 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00254-5207 | PS5-60-IE-0003G-CC16 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC16 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5208 | PS5-60-IE-0003G-CC17 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC17 | I | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5213 | PS5-60-IE-0003G-CC25 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC25 | I | Cable FROM PS5-60-TX-41700A TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5214 | PS5-60-IE-0003G-CC26 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0003G-CC26 | I | Cable FROM PS5-60-TX-41700B TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5215 | PS5-60-IE-0004-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-5216 | PS5-60-IE-0004-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-5217 | PS5-60-IE-0004-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-5218 | PS5-60-IE-0004-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC04 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-5219 | PS5-60-IE-0004-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC05 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-5220 | PS5-60-IE-0004-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC06 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-5221 | PS5-60-IE-0004-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IE-0004-CC07 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0103 |  | Accepted | Elizabeth | TESTING
T-00254-5225 | PS5-60-IN-0001A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5226 | PS5-60-IN-0001A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001A-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-5227 | PS5-60-IN-0001A-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001A-CC03 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5228 | PS5-60-IN-0001A-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001A-CC04 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5229 | PS5-60-IN-0001B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5230 | PS5-60-IN-0001B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001B-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-5231 | PS5-60-IN-0001B-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001B-CC03 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5232 | PS5-60-IN-0001B-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001B-CC04 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5233 | PS5-60-IN-0001C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5234 | PS5-60-IN-0001C-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001C-CC02 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5235 | PS5-60-IN-0001C-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001C-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5236 | PS5-60-IN-0001C-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001C-CC04 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5237 | PS5-60-IN-0001D-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5238 | PS5-60-IN-0001D-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001D-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5239 | PS5-60-IN-0001D-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001D-CC03 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5240 | PS5-60-IN-0001D-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001D-CC04 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5241 | PS5-60-IN-0001E-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5242 | PS5-60-IN-0001E-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001E-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5243 | PS5-60-IN-0001E-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001E-CC03 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5244 | PS5-60-IN-0001E-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001E-CC04 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5245 | PS5-60-IN-0001F-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5246 | PS5-60-IN-0001F-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001F-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5247 | PS5-60-IN-0001F-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001F-CC03 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5248 | PS5-60-IN-0001F-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001F-CC04 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5249 | PS5-60-IN-0001G-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5250 | PS5-60-IN-0001G-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001G-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5251 | PS5-60-IN-0001G-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001G-CC03 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5252 | PS5-60-IN-0001G-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0001G-CC04 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPP-RFI-68-64-12-0074 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5253 | PS5-60-IN-0002A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5254 | PS5-60-IN-0002A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5255 | PS5-60-IN-0002A-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC03 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-5256 | PS5-60-IN-0002A-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC04 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5257 | PS5-60-IN-0002A-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC05 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5258 | PS5-60-IN-0002A-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002A-CC06 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5259 | PS5-60-IN-0002B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5260 | PS5-60-IN-0002B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5261 | PS5-60-IN-0002B-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC03 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-64-12-0102 |  | Accepted | Elizabeth | Testing
T-00254-5262 | PS5-60-IN-0002B-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC04 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5263 | PS5-60-IN-0002B-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC05 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-RFI-68-64-12-0102 |  | Accepted | Elizabeth | Testing
T-00254-5264 | PS5-60-IN-0002B-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002B-CC06 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5265 | PS5-60-IN-0002C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5266 | PS5-60-IN-0002C-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC02 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-RFI-68-64-12-0116 | 27-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5267 | PS5-60-IN-0002C-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5268 | PS5-60-IN-0002C-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC04 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5269 | PS5-60-IN-0002C-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC05 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-RFI-68-64-12-0116 | 27-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5270 | PS5-60-IN-0002C-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002C-CC06 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5271 | PS5-60-IN-0002D-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5272 | PS5-60-IN-0002D-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5273 | PS5-60-IN-0002D-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC03 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-64-12-0116 | 27-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5274 | PS5-60-IN-0002D-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC04 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5275 | PS5-60-IN-0002D-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC05 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-RFI-68-64-12-0116 | 27-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5276 | PS5-60-IN-0002D-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002D-CC06 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5277 | PS5-60-IN-0002E-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5278 | PS5-60-IN-0002E-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00254-5279 | PS5-60-IN-0002E-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC03 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00254-5280 | PS5-60-IN-0002E-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC04 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5281 | PS5-60-IN-0002E-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC05 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00254-5282 | PS5-60-IN-0002E-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002E-CC06 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5283 | PS5-60-IN-0002F-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5284 | PS5-60-IN-0002F-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00254-5285 | PS5-60-IN-0002F-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC03 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00254-5286 | PS5-60-IN-0002F-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC04 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5287 | PS5-60-IN-0002F-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC05 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00254-5288 | PS5-60-IN-0002F-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002F-CC06 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5289 | PS5-60-IN-0002G-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5290 | PS5-60-IN-0002G-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00254-5291 | PS5-60-IN-0002G-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC03 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00254-5292 | PS5-60-IN-0002G-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC04 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5293 | PS5-60-IN-0002G-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC05 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00254-5294 | PS5-60-IN-0002G-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-IN-0002G-CC06 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5295 | PS5-60-IN-0004A-CC11 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00254-5296 | PS5-60-LA-0002A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5297 | PS5-60-LA-0002A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5298 | PS5-60-LA-0002A-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC03 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5299 | PS5-60-LA-0002A-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC04 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5300 | PS5-60-LA-0002A-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC05 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5301 | PS5-60-LA-0002A-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC06 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5302 | PS5-60-LA-0002A-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC07 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5303 | PS5-60-LA-0002A-CC08 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC08 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5304 | PS5-60-LA-0002A-CC09 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002A-CC09 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5305 | PS5-60-LA-0002B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002B-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5306 | PS5-60-LA-0002B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002B-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5307 | PS5-60-LA-0002B-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002B-CC03 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0101 | 2026-07-20 | ACCEPTED | G K RAO | TESTING
T-00254-5308 | PS5-60-LA-0002B-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002B-CC04 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0121 | 2026-07-29 | Accepted | G K RAO | TESTING
T-00254-5309 | PS5-60-LA-0002B-CC05 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00254-5310 | PS5-60-LA-0002B-CC06 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00254-5311 | PS5-60-LA-0002C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5312 | PS5-60-LA-0002C-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5313 | PS5-60-LA-0002C-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC03 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5314 | PS5-60-LA-0002C-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC04 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F |  |  | OPEN | Elizabeth | TESTING
T-00254-5315 | PS5-60-LA-0002C-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC05 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5316 | PS5-60-LA-0002C-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0002C-CC06 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5317 | PS5-60-LA-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LA-0003-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0123 | 29-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5318 | PS5-60-LIT-4301-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LIT-4301-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-60-LIT-4301 |  | PS5-60-24 - Cooling Water Tank & Pump | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5319 | PS5-60-LIT-4401-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-LIT-4401-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-60-LIT-4401 |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5320 | PS5-60-MOV-0005-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0005-CC01 | I | Cable FROM PS5-71-BI-2120 TO PS5-60-MOV-0005 |  | PS5-71-12 - CFO Service Tank
T-00254-5321 | PS5-60-MOV-0005-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0005-CC02 | I | Cable FROM PS5-71-BI-2124 TO PS5-60-MOV-0005 |  | PS5-71-12 - CFO Service Tank
T-00254-5322 | PS5-60-MOV-0006-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0006-CC01 | I | Cable FROM PS5-71-BI-2121 TO PS5-60-MOV-0006 |  | PS5-71-12 - CFO Service Tank
T-00254-5323 | PS5-60-MOV-0006-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0006-CC02 | I | Cable FROM PS5-71-BI-2125 TO PS5-60-MOV-0006 |  | PS5-71-12 - CFO Service Tank
T-00254-5324 | PS5-60-MOV-0011-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-2118 TO PS5-60-MOV-0011 |  | PS5-71-12 - CFO Service Tank
T-00254-5325 | PS5-60-MOV-0011-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0011-CC02 | I | Cable FROM PS5-71-BI-2122 TO PS5-60-MOV-0011 |  | PS5-71-12 - CFO Service Tank
T-00254-5326 | PS5-60-MOV-0012-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0012-CC01 | I | Cable FROM PS5-71-BI-2119 TO PS5-60-MOV-0012 |  | PS5-71-12 - CFO Service Tank
T-00254-5327 | PS5-60-MOV-0012-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-60-MOV-0012-CC02 | I | Cable FROM PS5-71-BI-2123 TO PS5-60-MOV-0012 |  | PS5-71-12 - CFO Service Tank
T-00254-5328 | PS5-60-SEA-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5329 | PS5-60-SEA-0001-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-5330 | PS5-60-SEA-0001-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC03 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5331 | PS5-60-SEA-0001-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC04 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5332 | PS5-60-SEA-0001-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC05 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5333 | PS5-60-SEA-0001-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC06 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5334 | PS5-60-SEA-0001-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC07 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5335 | PS5-60-SEA-0001-CC10 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC10 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5336 | PS5-60-SEA-0001-CC11 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC11 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5337 | PS5-60-SEA-0001-CC12 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC12 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5338 | PS5-60-SEA-0001-CC13 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00254-5339 | PS5-60-SEA-0001-CC14 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC14 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5340 | PS5-60-SEA-0001-CC15 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC15 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5341 | PS5-60-SEA-0001-CC16 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC16 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5342 | PS5-60-SEA-0001-CC17 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SEA-0001-CC17 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5344 | PS5-60-SY-0007-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0007-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0007 |  | PS5-60-28 - Air Receiver A & Air Regulator A
T-00254-5345 | PS5-60-SY-0008-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0008-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0008 |  | PS5-60-29 - Air Receiver B & Air Regulator B
T-00254-5346 | PS5-60-SY-0009-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0009-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0009 |  | PS5-60-30 - Air Receiver C & Air Regulator C
T-00254-5347 | PS5-60-SY-0010-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0010-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0010 |  | PS5-60-31 - Air Receiver D & Air Regulator D
T-00254-5348 | PS5-60-SY-0011-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0011-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0011 |  | PS5-60-32 - Air Receiver E & Air Regulator E
T-00254-5349 | PS5-60-SY-0012-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0012-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0012 |  | PS5-60-33 - Air Receiver F & Air Regulator F | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5350 | PS5-60-SY-0013-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-SY-0013-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-60-SY-0013 |  | PS5-60-34 - Air Receiver G & Air Regulator G | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5351 | PS5-60-VS-9101A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101A-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-60-VS-9101A |  | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5352 | PS5-60-VS-9101B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101B-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-60-VS-9101B |  | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5353 | PS5-60-VS-9101C-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101C-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-60-VS-9101C |  | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5354 | PS5-60-VS-9101D-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101D-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-60-VS-9101D |  | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5355 | PS5-60-VS-9101E-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101E-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-60-VS-9101E |  | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5356 | PS5-60-VS-9101F-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101F-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-60-VS-9101F |  | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5357 | PS5-60-VS-9101G-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-60-VS-9101G-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-60-VS-9101G |  | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5358 | PS5-61-BI-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0001-CC01 | I | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5359 | PS5-61-BI-0001-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0001-CC02 | I | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5360 | PS5-61-BI-0001-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0001-CC03 | I | Cable FROM PS5-61-TE-0003A TO PS5-61-BI-0001 |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-5361 | PS5-61-BI-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0002-CC01 | I | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-12-0056 | 2026-04-28 | Accepted | Elizabeth | TESTING
T-00254-5362 | PS5-61-BI-0002-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0002-CC02 | I | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5363 | PS5-61-BI-0002-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0002-CC03 | I | Cable FROM PS5-61-TE-0003B TO PS5-61-BI-0002 |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-64-12-0112 | 2026-07-23 | Accepted | Elizabeth | TESTING
T-00254-5364 | PS5-61-BI-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0003-CC01 | I | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5365 | PS5-61-BI-0003-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0003-CC02 | I | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5366 | PS5-61-BI-0003-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0003-CC03 | I | Cable FROM PS5-61-TE-0003C TO PS5-61-BI-0003 |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-64-12-0121 | 2026-07-29 | Accepted | G K RAO | TESTING
T-00254-5367 | PS5-61-BI-0004-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0004-CC01 | I | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5368 | PS5-61-BI-0004-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0004-CC02 | I | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5369 | PS5-61-BI-0004-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0004-CC03 | I | Cable FROM PS5-61-TE-0003D TO PS5-61-BI-0004 |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-64-12-0121 | 2026-07-29 | Accepted | G K RAO | TESTING
T-00254-5370 | PS5-61-BI-0005-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0005-CC01 | I | Cable FROM PS5-60-IE-0003E TO PS5-61-BI-0005 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5371 | PS5-61-BI-0005-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0005-CC02 | I | Cable FROM PS5-60-IE-0003E TO PS5-61-BI-0005 |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5372 | PS5-61-BI-0005-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0005-CC03 | I | Cable FROM PS5-61-TE-0003E TO PS5-61-BI-0005 |  | PS5-60-13 - Power Generation Package E
T-00254-5373 | PS5-61-BI-0006-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0006-CC01 | I | Cable FROM PS5-60-IE-0003F TO PS5-61-BI-0006 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5374 | PS5-61-BI-0006-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0006-CC02 | I | Cable FROM PS5-60-IE-0003F TO PS5-61-BI-0006 |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5375 | PS5-61-BI-0006-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0006-CC03 | I | Cable FROM PS5-61-TE-0003F TO PS5-61-BI-0006 |  | PS5-60-16 - Power Generation Package F
T-00254-5376 | PS5-61-BI-0007-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0007-CC01 | I | Cable FROM PS5-60-IE-0003G TO PS5-61-BI-0007 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5377 | PS5-61-BI-0007-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0007-CC02 | I | Cable FROM PS5-60-IE-0003G TO PS5-61-BI-0007 |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-64-12-0056 | 2026-05-28 | Accepted | Elizabeth | TESTING
T-00254-5378 | PS5-61-BI-0007-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-61-BI-0007-CC03 | I | Cable FROM PS5-61-TE-0003G TO PS5-61-BI-0007 |  | PS5-60-19 - Power Generation Package G
T-00254-5388 | PS5-71-BAV-0058-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BAV-0058-CC01 | I | Cable FROM PS5-71-BI-2113 TO PS5-71-BAV-0058 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5389 | PS5-71-BAV-0059-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BAV-0059-CC01 | I | Cable FROM PS5-71-BI-2113 TO PS5-71-BAV-0059 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5390 | PS5-71-BI-0001A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001A |  | PS5-71-06 - Crude Fuel Separation Module
T-00254-5391 | PS5-71-BI-0001B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001B |  | PS5-71-06 - Crude Fuel Separation Module
T-00254-5393 | PS5-71-BI-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0002 |  | PS5-71-18 - Diesel Separator Module
T-00254-5394 | PS5-71-BI-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0003-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5395 | PS5-71-BI-0003-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0003-CC02 | I | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
T-00254-5396 | PS5-71-BI-0003-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0003-CC03 | I | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
T-00254-5397 | PS5-71-BI-0003-CC04 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00254-5398 | PS5-71-BI-0004-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 |  | PS5-71-08 - CFO Pre-Pressure Modules
T-00254-5399 | PS5-71-BI-0005-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP)
T-00254-5400 | PS5-71-BI-0005-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0005-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0005 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5401 | PS5-71-BI-0006-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0006-CC01 | I | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-64-12-0123 | 29-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5402 | PS5-71-BI-0008A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0008A-CC01 | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A |  | PS5-71-06 - Crude Fuel Separation Module | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
T-00254-5403 | PS5-71-BI-0008A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0008A-CC02 | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A |  | PS5-71-06 - Crude Fuel Separation Module | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
T-00254-5404 | PS5-71-BI-0008B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B |  | PS5-71-06 - Crude Fuel Separation Module
T-00254-5405 | PS5-71-BI-0008B-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B |  | PS5-71-06 - Crude Fuel Separation Module
T-00254-5406 | PS5-71-BI-0009-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 |  | PS5-71-18 - Diesel Separator Module
T-00254-5407 | PS5-71-BI-0009-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0009-CC02 | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 |  | PS5-71-18 - Diesel Separator Module | CPP-68-64-12-0129 | 2026-07-31 | OPEN | Elizabeth | TESTING
T-00254-5408 | PS5-71-BI-0009-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0009-CC03 | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 |  | PS5-71-18 - Diesel Separator Module | CPP-68-64-12-0129 | 2026-07-31 | OPEN | Elizabeth | TESTING
T-00254-5409 | PS5-71-BI-0009-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0009-CC04 | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-12-0123 | 29-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5410 | PS5-71-BI-0010-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0010-CC01 | I | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0010 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-12-0123 | 29-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5411 | PS5-71-BI-0011A-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A |  | PS5-71-06 - Crude Fuel Separation Module
T-00254-5412 | PS5-71-BI-0011A-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A |  | PS5-71-06 - Crude Fuel Separation Module
T-00254-5413 | PS5-71-BI-0011A-CC03 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A |  | PS5-71-06 - Crude Fuel Separation Module
T-00254-5414 | PS5-71-BI-0011A-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0011A-CC04 | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A |  | PS5-71-06 - Crude Fuel Separation Module | CPP-68-64-12-0129 | 2026-07-31 | OPEN | Elizabeth | TESTING
T-00254-5415 | PS5-71-BI-0011A-CC05 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A |  | PS5-71-06 - Crude Fuel Separation Module
T-00254-5416 | PS5-71-BI-0011B-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B |  | PS5-71-06 - Crude Fuel Separation Module
T-00254-5417 | PS5-71-BI-0011B-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B |  | PS5-71-06 - Crude Fuel Separation Module
T-00254-5418 | PS5-71-BI-0011B-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0011B-CC03 | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B |  | PS5-71-06 - Crude Fuel Separation Module | CPP-68-64-12-0129 | 2026-07-31 | OPEN | Elizabeth | TESTING
T-00254-5419 | PS5-71-BI-0011B-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-71-BI-0011B-CC04 | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B |  | PS5-71-06 - Crude Fuel Separation Module | CPP-68-64-12-0129 | 2026-07-31 | OPEN | Elizabeth | TESTING
T-00254-5420 | PS5-71-BI-0011B-CC05 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B |  | PS5-71-06 - Crude Fuel Separation Module
T-00254-5453 | PS5-71-FCV-0018-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-FCV-0018-HPU TO PS5-71-FCV-0018 |  | PS5-71-13 - CFO Service Pump A/B
T-00254-5454 | PS5-71-FCV-0019-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FCV-0019-CC01 | I | Cable FROM PS5-71-FCV-0019-HPU TO PS5-71-FCV-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00254-5455 | PS5-71-FCV-0020-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-FCV-0020-HPU TO PS5-71-FCV-0020 |  | PS5-71-05 - CFO Transfer Pump A/B
T-00254-5456 | PS5-71-FIT-0005-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0005-CJ01 | I | Cable FROM PS5-71-BI-1111 TO PS5-71-FIT-0005 |  | PS5-71-17 - Diesel Fuel Distribution Header | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5457 | PS5-71-FIT-0011A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0011A-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-FIT-0011A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5458 | PS5-71-FIT-0011B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0011B-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-FIT-0011B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5459 | PS5-71-FIT-0012-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1112 TO PS5-71-FIT-0012 |  | PS5-71-17 - Diesel Fuel Distribution Header
T-00254-5460 | PS5-71-FIT-0018-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0018-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-FIT-0018 |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5461 | PS5-71-FIT-0019-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0019-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-FIT-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5462 | PS5-71-FIT-0020-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FIT-0020-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-FIT-0020 |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5463 | PS5-71-FXS-0018-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FXS-0018-CJ01 | I | Cable FROM PS5-71-BI-2107 TO PS5-71-FCV-0018 |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5464 | PS5-71-FXS-0019-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FXS-0019-CJ01 | I | Cable FROM PS5-71-BI-2114 TO PS5-71-FCV-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5465 | PS5-71-FXS-0020-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FXS-0020-CJ01 | I | Cable FROM PS5-71-BI-2107 TO PS5-71-FCV-0020 |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5466 | PS5-71-FY-0018-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FY-0018-CJ01 | I | Cable FROM PS5-71-BI-1116 TO PS5-71-FCV-0018 |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5467 | PS5-71-FY-0019-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FY-0019-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-71-FCV-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5468 | PS5-71-FY-0020-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-FY-0020-CJ01 | I | Cable FROM PS5-71-BI-1116 TO PS5-71-FCV-0020 |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5469 | PS5-71-IN-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5470 | PS5-71-IN-0001-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5471 | PS5-71-IN-0001-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC03 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5472 | PS5-71-IN-0001-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC04 | I | Cable FROM PS5-71-BI-0011A TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5473 | PS5-71-IN-0001-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC05 | I | Cable FROM PS5-71-BI-0011B TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5474 | PS5-71-IN-0001-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC06 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5475 | PS5-71-IN-0001-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0001-CC07 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5479 | PS5-71-IN-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0002-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5480 | PS5-71-IN-0002-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0002-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP)
T-00254-5481 | PS5-71-IN-0002-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0002-CC03 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5482 | PS5-71-IN-0002-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0002-CC04 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5486 | PS5-71-IN-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0003-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5487 | PS5-71-IN-0003-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0003-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-68-64-12-0084 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5488 | PS5-71-IN-0003-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0003-CC03 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5489 | PS5-71-IN-0003-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0003-CC04 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5493 | PS5-71-IN-0004A-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5494 | PS5-71-IN-0004A-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-12-0115 | 2026-07-24 | Accepted | G K RAO | Testing
T-00254-5495 | PS5-71-IN-0004A-CC03 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC03 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-12-0083 | 2026-07-13 | ACCEPTED | Elizabeth | TESTING
T-00254-5496 | PS5-71-IN-0004A-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC04 | I | Cable FROM PS5-71-BI-0011A TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5497 | PS5-71-IN-0004A-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC05 | I | Cable FROM PS5-71-BI-0011A TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5498 | PS5-71-IN-0004A-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC06 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5499 | PS5-71-IN-0004A-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC07 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5502 | PS5-71-IN-0004A-CC11 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC11 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) |  |  | OPEN | G K RAO | TESTING
T-00254-5504 | PS5-71-IN-0004A-CC13 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004A-CC13 | I | Cable FROM PS5-71-IN-0004B TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) |  |  | OPEN | G K RAO | TESTING
T-00254-5505 | PS5-71-IN-0004B-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC01 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-12-0116 | 27-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5506 | PS5-71-IN-0004B-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC02 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-12-0116 | 27-July-2026 | Acceptable | Ferdinand | Testing
T-00254-5507 | PS5-71-IN-0004B-CC03 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00254-5508 | PS5-71-IN-0004B-CC04 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC04 | I | Cable FROM PS5-71-BI-0011B TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5509 | PS5-71-IN-0004B-CC05 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC05 | I | Cable FROM PS5-71-BI-0011B TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-12-0082 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5510 | PS5-71-IN-0004B-CC06 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC06 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5511 | PS5-71-IN-0004B-CC07 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC07 | I | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-68-64-12-0085 | 2026-07-04 | Accepted | Elizabeth | TESTING
T-00254-5514 | PS5-71-IN-0004B-CC11 | TJX10 - Multi/Single-core instrument control cable | PS5-71-IN-0004B-CC11 | I | Cable FROM PS5-71-IN-0001 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) |  |  | OPEN | G K RAO | TESTING
T-00254-5516 | PS5-71-LCV-4101-CC01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-LCV-4101-HPU TO PS5-71-LCV-4101 |  | PS5-71-04 - CFO Storage Tank
T-00254-5517 | PS5-71-LI-4201B-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-LIT-4201 TO PS5-71-LI-4201B |  | PS5-71-12 - CFO Service Tank
T-00254-5518 | PS5-71-LIT-1201-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-LIT-1201-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-71-LIT-1201 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5519 | PS5-71-LIT-1202-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-LIT-1202-CJ01 | I | Cable FROM PS5-28-BI-1307 TO PS5-71-LIT-1202 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5520 | PS5-71-LIT-4101-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1109 TO PS5-71-LIT-4101 |  | PS5-71-04 - CFO Storage Tank
T-00254-5521 | PS5-71-LIT-4102-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1305 TO PS5-71-LIT-4102 |  | PS5-71-04 - CFO Storage Tank
T-00254-5522 | PS5-71-LIT-4201-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1109 TO PS5-71-LIT-4201 |  | PS5-71-12 - CFO Service Tank
T-00254-5523 | PS5-71-LIT-4202-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1306 TO PS5-71-LIT-4202 |  | PS5-71-12 - CFO Service Tank
T-00254-5524 | PS5-71-LIT-4401-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-LIT-4401-CJ01 | I | Cable FROM PS5-71-BI-1111 TO PS5-71-LIT-4401 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5525 | PS5-71-LIT-4402-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-LIT-4402-CJ01 | I | Cable FROM PS5-71-BI-1308 TO PS5-71-LIT-4402 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5526 | PS5-71-LXS-4101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-LXS-4101-CJ01 | I | Cable FROM PS5-71-BI-2107 TO PS5-71-LCV-4101 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5527 | PS5-71-LY-4101-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-LY-4101-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-LCV-4101 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5528 | PS5-71-MOV-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0001-CC01 | I | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0001 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5529 | PS5-71-MOV-0001-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0001-CC02 | I | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0001 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5530 | PS5-71-MOV-0002-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0002-CC01 | I | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0002 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5531 | PS5-71-MOV-0002-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0002-CC02 | I | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0002 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5532 | PS5-71-MOV-0003-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0003-CC01 | I | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5533 | PS5-71-MOV-0003-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0003-CC02 | I | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0003 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5534 | PS5-71-MOV-0004-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0004-CC01 | I | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0004 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5535 | PS5-71-MOV-0004-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0004-CC02 | I | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0004 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5536 | PS5-71-MOV-0007-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0007-CC01 | I | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0007 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5537 | PS5-71-MOV-0007-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0007-CC02 | I | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0007 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5538 | PS5-71-MOV-0008-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0008-CC01 | I | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0008 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5539 | PS5-71-MOV-0008-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0008-CC02 | I | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0008 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5540 | PS5-71-MOV-0009-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0009-CC01 | I | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0009 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5541 | PS5-71-MOV-0009-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0009-CC02 | I | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0009 |  | PS5-71-08 - CFO Pre-Pressure Modules | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5542 | PS5-71-MOV-0010-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0010-CC01 | I | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0010 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5543 | PS5-71-MOV-0010-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-MOV-0010-CC02 | I | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0010 |  | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPP-RFI-68-64-04-0100 | 2026-07-18 | Accepted | G K RAO | TESTING
T-00254-5544 | PS5-71-PDIT-0030-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PDIT-0030-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-PDIT-0030 |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5545 | PS5-71-PDIT-0056A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PDIT-0056A-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PDIT-0056A |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5546 | PS5-71-PDIT-0056B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PDIT-0056B-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PDIT-0056B |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5547 | PS5-71-PIT-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0001-CJ01 | I | Cable FROM PS5-28-BI-1307 TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5548 | PS5-71-PIT-0014-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0014-CJ01 | I | Cable FROM PS5-71-BI-1111 TO PS5-71-PIT-0014 |  | PS5-71-17 - Diesel Fuel Distribution Header | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5549 | PS5-71-PIT-0018A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0018A-CJ01 | I | Cable FROM PS5-71-BI-1116 TO PS5-71-FCV-0018 |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5550 | PS5-71-PIT-0019A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0019A-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-71-FCV-0019 |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5551 | PS5-71-PIT-0020A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0020A-CJ01 | I | Cable FROM PS5-71-BI-1116 TO PS5-71-FCV-0020 |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5552 | PS5-71-PIT-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0022-CJ01 | I | Cable FROM PS5-71-BI-1305 TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5553 | PS5-71-PIT-0029-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0029-CJ01 | I | Cable FROM PS5-71-BI-1308 TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5554 | PS5-71-PIT-0039-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0039-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5555 | PS5-71-PIT-0089-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0089-CJ01 | I | Cable FROM PS5-71-BI-1117 TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank
T-00254-5556 | PS5-71-PIT-0090-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0090-CJ01 | I | Cable FROM PS5-71-BI-1117 TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank
T-00254-5557 | PS5-71-PIT-0091-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0091-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5558 | PS5-71-PIT-0092-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-0092-CJ01 | I | Cable FROM PS5-71-BI-1113 TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5559 | PS5-71-PIT-2402A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-2402A-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-PIT-2402A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5560 | PS5-71-PIT-2402B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-2402B-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-PIT-2402B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5561 | PS5-71-PIT-3301A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3301A-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-PIT-3301A |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5562 | PS5-71-PIT-3301B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3301B-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-PIT-3301B |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5563 | PS5-71-PIT-3302A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3302A-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PIT-3302A |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5564 | PS5-71-PIT-3302B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3302B-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PIT-3302B |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5565 | PS5-71-PIT-3401A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3401A-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-PIT-3401A |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5566 | PS5-71-PIT-3401B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3401B-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-PIT-3401B |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5567 | PS5-71-PIT-3402A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3402A-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PIT-3402A |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5568 | PS5-71-PIT-3402B-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-3402B-CJ01 | I | Cable FROM PS5-71-BI-1110 TO PS5-71-PIT-3402B |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5569 | PS5-71-PIT-4101A-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-PIT-4101A-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-LCV-4101 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5570 | PS5-71-SDV-0001-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SDV-0001-CC01 | I | Cable FROM PS5-25-BI-2315 TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5571 | PS5-71-SDV-0001-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SDV-0001-CC02 | I | Cable FROM PS5-71-SDV-0001-HPU TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank
T-00254-5572 | PS5-71-SDV-0022-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SDV-0022-CC01 | I | Cable FROM PS5-71-BI-2306 TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank
T-00254-5573 | PS5-71-SDV-0022-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-SDV-0022-HPU TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank
T-00254-5574 | PS5-71-SDV-0029-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SDV-0029-CC01 | I | Cable FROM PS5-71-BI-2307 TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5575 | PS5-71-SDV-0029-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-SDV-0029-HPU TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00254-5576 | PS5-71-SDV-0039-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SDV-0039-CC01 | I | Cable FROM PS5-71-BI-2306 TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank
T-00254-5577 | PS5-71-SDV-0039-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-SDV-0039-HPU TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank
T-00254-5578 | PS5-71-SXS-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SXS-0001-CJ01 | I | Cable FROM PS5-25-BI-2312 TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5579 | PS5-71-SXS-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SXS-0022-CJ01 | I | Cable FROM PS5-71-BI-2314 TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5580 | PS5-71-SXS-0029-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SXS-0029-CJ01 | I | Cable FROM PS5-71-BI-2313 TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5581 | PS5-71-SXS-0039-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SXS-0039-CJ01 | I | Cable FROM PS5-71-BI-2314 TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5582 | PS5-71-SY-0001-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SY-0001-CJ01 | I | Cable FROM PS5-25-BI-2316 TO PS5-71-SDV-0001 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-12-0099 | 2026-07-16 | Accepted | G K RAO | TESTING
T-00254-5583 | PS5-71-SY-0022-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SY-0022-CJ01 | I | Cable FROM PS5-71-BI-2310 TO PS5-71-SDV-0022 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5584 | PS5-71-SY-0029-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SY-0029-CJ01 | I | Cable FROM PS5-71-BI-2317 TO PS5-71-SDV-0029 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5585 | PS5-71-SY-0039-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-SY-0039-CJ01 | I | Cable FROM PS5-71-BI-2310 TO PS5-71-SDV-0039 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5586 | PS5-71-TIT-0003-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-0003-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-TIT-0003 |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5587 | PS5-71-TIT-0004-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-0004-CJ01 | I | Cable FROM PS5-71-BI-1109 TO PS5-71-TIT-0004 |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-12-0104 | 2026-07-23 | Accepted | Bertus Wikael | TESTING
T-00254-5588 | PS5-71-TIT-0006-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-0006-CJ01 | I | Cable FROM PS5-71-BI-1305 TO PS5-71-TIT-0006 |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5589 | PS5-71-TIT-0007-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-0007-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-TIT-0007 |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5590 | PS5-71-TIT-2204-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1306 TO PS5-71-TIT-2204 |  | PS5-71-12 - CFO Service Tank
T-00254-5591 | PS5-71-TIT-2301-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1305 TO PS5-71-TIT-2301 |  | PS5-71-04 - CFO Storage Tank
T-00254-5592 | PS5-71-TIT-2402AA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-2402AA-CJ01 | I | Cable FROM PS5-71-BI-1305 TO PS5-71-TIT-2402AA |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5593 | PS5-71-TIT-2402BA-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-TIT-2402BA-CJ01 | I | Cable FROM PS5-71-BI-1306 TO PS5-71-TIT-2402BA |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5596 | PS5-71-TIT-4102-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1109 TO PS5-71-TIT-4102 |  | PS5-71-04 - CFO Storage Tank
T-00254-5597 | PS5-71-TIT-4103-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1305 TO PS5-71-TIT-4103 |  | PS5-71-04 - CFO Storage Tank
T-00254-5598 | PS5-71-TIT-4202-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1109 TO PS5-71-TIT-4202 |  | PS5-71-12 - CFO Service Tank
T-00254-5599 | PS5-71-TIT-4203-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-BI-1306 TO PS5-71-TIT-4203 |  | PS5-71-12 - CFO Service Tank
T-00254-5600 | PS5-71-XV-0089-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XV-0089-CC01 | I | Cable FROM PS5-71-BI-2116 TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank
T-00254-5601 | PS5-71-XV-0089-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-XV-0089-HPU TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank
T-00254-5602 | PS5-71-XV-0090-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XV-0090-CC01 | I | Cable FROM PS5-71-BI-2116 TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank
T-00254-5603 | PS5-71-XV-0090-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-XV-0090-HPU TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank
T-00254-5604 | PS5-71-XV-0091-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XV-0091-CC01 | I | Cable FROM PS5-71-BI-2113 TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5605 | PS5-71-XV-0091-CC02 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-71-XV-0091-HPU TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module
T-00254-5606 | PS5-71-XV-0092-CC01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XV-0092-CC01 | I | Cable FROM PS5-71-BI-2113 TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5607 | PS5-71-XV-0092-CC02 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XV-0092-CC02 | I | Cable FROM PS5-71-XV-0092-HPU TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank
T-00254-5608 | PS5-71-XXS-0089-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XXS-0089-CJ01 | I | Cable FROM PS5-71-BI-2107 TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5609 | PS5-71-XXS-0090-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XXS-0090-CJ01 | I | Cable FROM PS5-71-BI-2107 TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5610 | PS5-71-XXS-0091-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XXS-0091-CJ01 | I | Cable FROM PS5-71-BI-2114 TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5611 | PS5-71-XXS-0092-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XXS-0092-CJ01 | I | Cable FROM PS5-71-BI-2114 TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5612 | PS5-71-XY-0089-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XY-0089-CJ01 | I | Cable FROM PS5-71-BI-2101 TO PS5-71-XV-0089 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5613 | PS5-71-XY-0090-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XY-0090-CJ01 | I | Cable FROM PS5-71-BI-2101 TO PS5-71-XV-0090 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-64-12-0063 | 2026-06-10 | Accepted | Elizabeth | TESTING
T-00254-5614 | PS5-71-XY-0091-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XY-0091-CJ01 | I | Cable FROM PS5-71-BI-2115 TO PS5-71-XV-0091 |  | PS5-71-18 - Diesel Separator Module | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5615 | PS5-71-XY-0092-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-71-XY-0092-CJ01 | I | Cable FROM PS5-71-BI-2115 TO PS5-71-XV-0092 |  | PS5-71-20 - Diesel Fuel Day Tank | CPP-RFI-68-64-12-0075 | 2026-06-26 | Accepted | Elizabeth | TESTING
T-00254-5618 | PS5-74-PIT-0002-CJ01 | TJX10 - Multi/Single-core instrument control cable | PS5-74-PIT-0002-CJ01 | I | Cable FROM PS5-50-BI-1107 TO PS5-74-PIT-0002 |  | PS5-74-04 - Nitrogen Distribution Header | CPP-RFI-68-64-12-0061 | 2026-06-06 | Accepted | G K RAO | TESTING
T-00254-9420 | PS5-03-RMAC-1409-CJ01 | TJX10 - Multi/Single-core instrument control cable | #N/A | I | Cable FROM PS5-03-SEA-0003 TO PS5-03-RMAC-1409 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00255-0051 | PS5-71-FO-0013B | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00255-0052 | PS5-28-FO-0009A | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00255-0053 | PS5-28-FO-0009B | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00255-0054 | PS5-28-FO-0003 | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-05 - HP Relief Header
T-00255-0055 | PS5-50-FE-0001 | TJX11 - Orifice plate | #N/A | I | Orifice Flow Element |  | PS5-50-03 - Water Pre-Treatment Package
T-00255-0056 | PS5-60-FO-0002 | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-60-24 - Cooling Water Tank & Pump
T-00255-0057 | PS5-28-FO-0005 | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-06 - Relief Drum and Pump
T-00255-0058 | PS5-60-FO-0001 | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump
T-00255-0059 | PS5-25-FO-0008 | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-25-05 - Crude Oil Export Pumps Bypass
T-00255-0060 | PS5-71-FO-0013A | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-71-16 - Diesel Fuel Supply Pump A/B
T-00255-0061 | PS5-74-FO-0001 | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-74-04 - Nitrogen Distribution Header
T-00255-0062 | PS5-28-FO-0002A | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-08 - Open Drain Sump and Pumps
T-00255-0063 | PS5-28-FO-0002B | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-08 - Open Drain Sump and Pumps
T-00255-0064 | PS5-28-FO-0004 | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-16 - LP Relief Header
T-00255-0065 | PS5-28-FO-0006 | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-08 - Open Drain Sump and Pumps
T-00255-0066 | PS5-28-FO-0007 | TJX11 - Orifice plate | #N/A | I | Flow Restriction Orifice |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00256-0023 | PS5-09-LB-0006-CX01 | TJX12 - Optical fiber cable | #N/A | I | Cable FROM PS5-04-PNC-0001 TO PS5-09-LB-0006 |  | PS5-09-01 - HVAC for Office and Facilities building
T-00256-0024 | PS5-09-LB-0007-CX01 | TJX12 - Optical fiber cable | PS5-09-LB-0007-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-09-LB-0007 |  | PS5-09-04 - HVAC for Workshop & Warehouse
T-00256-0025 | PS5-09-LB-0008-CX01 | TJX12 - Optical fiber cable | PS5-09-LB-0008-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00256-0026 | PS5-53-LA-0001-CX01 | TJX12 - Optical fiber cable | PS5-53-LA-0001-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-53-LA-0001 |  | PS5-53-04 - Water Treatment Purification Package
T-00256-0027 | PS5-60-IE-0004-CX03 | TJX12 - Optical fiber cable | PS5-60-IE-0004-CX03 | I | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00256-0028 | PS5-60-IE-0004-CX04 | TJX12 - Optical fiber cable | PS5-60-IE-0004-CX04 | I | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00256-0029 | PS5-60-LA-0003-CX01 | TJX12 - Optical fiber cable | PS5-60-LA-0003-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 |  | PS5-60-22 - Power Gen Master UCP
T-00256-0030 | PS5-74-LB-5101-CX01 | TJX12 - Optical fiber cable | PS5-74-LB-5101-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-74-LB-5101 |  | PS5-74-02 - N2 Generation Skid (UCP)
T-00256-0031 | PS5-82-LA-0001-CX01 | TJX12 - Optical fiber cable | PS5-82-LA-0001-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-82-LA-0001 |  | PS5-82-03 - Sewage Treatment Plant Package (UCP)
T-00256-0085 | PS5-75-LA-6200-CX01 | TJX12 - Optical fiber cable | PS5-75-LA-6200-CX01 | I | Cable FROM PS5-04-PNC-0001 TO PS5-75-LA-6200 |  | PS5-75-01 - DRA Injection Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00257-0165 | PS5-60-TW-0006G | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-76 - Engine G Cooling system
T-00257-0166 | PS5-71-TW-4203 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-12 - CFO Service Tank
T-00257-0167 | PS5-71-TW-0007 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00257-0168 | PS5-71-TW-0003 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00257-0169 | PS5-60-TW-0007C | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-72 - Engine C Cooling system
T-00257-0170 | PS5-71-TW-0004 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00257-0171 | PS5-60-TW-0005F | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-75 - Engine F Cooling system
T-00257-0172 | PS5-28-TW-1201 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-28-06 - Relief Drum and Pump
T-00257-0173 | PS5-60-TW-0007B | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-71 - Engine B Cooling system
T-00257-0174 | PS5-60-TW-0006C | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-72 - Engine C Cooling system
T-00257-0175 | PS5-60-TW-0008A | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-70 - Engine A Cooling system
T-00257-0176 | PS5-60-TW-0007D | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-73 - Engine D Cooling system
T-00257-0177 | PS5-60-TW-0008C | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-72 - Engine C Cooling system
T-00257-0178 | PS5-28-TW-1402 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00257-0179 | PS5-60-TW-0005G | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-76 - Engine G Cooling system
T-00257-0180 | PS5-28-TW-1104 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00257-0181 | PS5-60-TW-0008E | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-74 - Engine E Cooling system
T-00257-0182 | PS5-60-TW-0007A | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-70 - Engine A Cooling system
T-00257-0183 | PS5-60-TW-0006D | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-73 - Engine D Cooling system
T-00257-0184 | PS5-60-TW-0008B | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-71 - Engine B Cooling system
T-00257-0185 | PS5-60-TW-0007E | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-74 - Engine E Cooling system
T-00257-0186 | PS5-60-TW-0008D | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-73 - Engine D Cooling system
T-00257-0187 | PS5-25-TW-0003B | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-03 - Crude Oil Export Pump B
T-00257-0188 | PS5-71-TW-4202 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-12 - CFO Service Tank
T-00257-0189 | PS5-60-TW-0008F | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-75 - Engine F Cooling system
T-00257-0190 | PS5-60-TW-0006E | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-74 - Engine E Cooling system
T-00257-0191 | PS5-25-TW-0002A | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-02 - Crude Oil Export Pump A
T-00257-0192 | PS5-25-TW-0003C | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-04 - Crude Oil Export Pump C
T-00257-0193 | PS5-71-TW-0006 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00257-0194 | PS5-60-TW-0006B | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-71 - Engine B Cooling system
T-00257-0195 | PS5-25-TW-0003A | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-02 - Crude Oil Export Pump A
T-00257-0196 | PS5-71-TW-4103 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-04 - CFO Storage Tank
T-00257-0197 | PS5-28-TW-1105 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-28-03 - Closed Drain Drum and Pump 01
T-00257-0198 | PS5-60-TW-0006A | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-70 - Engine A Cooling system
T-00257-0199 | PS5-60-TW-0007F | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-75 - Engine F Cooling system
T-00257-0200 | PS5-25-TW-0002B | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-03 - Crude Oil Export Pump B
T-00257-0201 | PS5-25-TW-0001 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-01 - Export Pipeline Pig Receiver
T-00257-0202 | PS5-25-TW-0004 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00257-0203 | PS5-25-TW-0002C | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-25-04 - Crude Oil Export Pump C
T-00257-0204 | PS5-71-TW-4102 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-71-04 - CFO Storage Tank
T-00257-0205 | PS5-74-TW-0001 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-74-04 - Nitrogen Distribution Header
T-00257-0206 | PS5-28-TW-1401 | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-28-04 - Closed Drain Drum and Pump 02
T-00257-0207 | PS5-60-TW-0005A | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-70 - Engine A Cooling system
T-00257-0208 | PS5-60-TW-0005B | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-71 - Engine B Cooling system
T-00257-0209 | PS5-60-TW-0005C | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-72 - Engine C Cooling system
T-00257-0210 | PS5-60-TW-0005D | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-73 - Engine D Cooling system
T-00257-0211 | PS5-60-TW-0005E | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-74 - Engine E Cooling system
T-00257-0212 | PS5-60-TW-0006F | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-75 - Engine F Cooling system
T-00257-0213 | PS5-60-TW-0007G | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-76 - Engine G Cooling system
T-00257-0214 | PS5-60-TW-0008G | TJX13 - Thermowell | #N/A | I | Thermowell |  | PS5-60-76 - Engine G Cooling system
T-00163-0369 | PS5-08-01LS-0604 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0370 | PS5-08-01LS-0605 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0371 | PS5-08-01LS-0606 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0372 | PS5-08-01LS-0607 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0373 | PS5-08-01LS-0608 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0374 | PS5-08-01LS-0609 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0375 | PS5-08-01LS-0610 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0376 | PS5-08-01LS-0611 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0377 | PS5-08-01LS-0612 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker (Haz. Area) |  | PS5-08-01 - PAGA
T-00163-0378 | PS5-08-01LS-0617 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0379 | PS5-08-01LS-0618 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker (Haz. Area) |  | PS5-08-01 - PAGA
T-00163-0380 | PS5-08-01LS-0619 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker (Haz. Area) |  | PS5-08-01 - PAGA
T-00163-0381 | PS5-08-01LS-0620 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker (Haz. Area) |  | PS5-08-01 - PAGA
T-00163-0382 | PS5-08-01LS-0621 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker (Haz. Area) |  | PS5-08-01 - PAGA
T-00163-0383 | PS5-08-01LS-0622 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0384 | PS5-08-01LS-0623 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0385 | PS5-08-01LS-0624 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0386 | PS5-08-01LS-0625 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0387 | PS5-08-01LS-0626 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0388 | PS5-08-01LS-0627 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0389 | PS5-08-01LS-0628 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0390 | PS5-08-01LS-0629 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 6 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0391 | PS5-08-01LS-0701 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Indoor wall-Mounted Loudspeaker |  | PS5-08-01 - PAGA
T-00163-0392 | PS5-08-01LS-0702 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0393 | PS5-08-01LS-0703 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0394 | PS5-08-01LS-0704 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0395 | PS5-08-01LS-0705 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable Safe area addressable ceiling-mounted speaker (including LTD) |  | PS5-08-01 - PAGA
T-00163-0396 | PS5-08-01LS-0706 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0397 | PS5-08-01LS-0707 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0398 | PS5-08-01LS-0708 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0399 | PS5-08-01LS-0709 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0400 | PS5-08-01LS-0710 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0401 | PS5-08-01LS-0711 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0402 | PS5-08-01LS-0712 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0403 | PS5-08-01LS-0713 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0404 | PS5-08-01LS-0714 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0405 | PS5-08-01LS-0715 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0406 | PS5-08-01LS-0716 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0407 | PS5-08-01LS-0717 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0408 | PS5-08-01LS-0718 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker (including LTD) |  | PS5-08-01 - PAGA
T-00163-0409 | PS5-08-01LS-0719 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable weatherproof Horn Speaker (including LTD) |  | PS5-08-01 - PAGA
T-00163-0410 | PS5-08-01LS-0720 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable weatherproof Horn Speaker |  | PS5-08-01 - PAGA
T-00163-0411 | PS5-08-01LS-0721 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0412 | PS5-08-01LS-0722 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0413 | PS5-08-01LS-0723 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0414 | PS5-08-01LS-0724 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0415 | PS5-08-01LS-0725 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0416 | PS5-08-01LS-0726 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0417 | PS5-08-01LS-0727 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0418 | PS5-08-01LS-0728 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0419 | PS5-08-01LS-0729 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0420 | PS5-08-01LS-0730 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0421 | PS5-08-01LS-0731 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0422 | PS5-08-01LS-0732 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0423 | PS5-08-01LS-0733 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 7 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0424 | PS5-08-01LS-0801 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0425 | PS5-08-01LS-0802 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0426 | PS5-08-01LS-0803 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0427 | PS5-08-01LS-0804 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable ceiling-mounted speaker (including LTD) |  | PS5-08-01 - PAGA
T-00163-0428 | PS5-08-01LS-0805 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0429 | PS5-08-01LS-0806 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0430 | PS5-08-01LS-0807 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0431 | PS5-08-01LS-0808 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0432 | PS5-08-01LS-0809 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0433 | PS5-08-01LS-0810 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0434 | PS5-08-01LS-0811 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0435 | PS5-08-01LS-0812 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0436 | PS5-08-01LS-0813 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0437 | PS5-08-01LS-0814 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0438 | PS5-08-01LS-0815 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0439 | PS5-08-01LS-0816 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00284-0085 | PS5-71-FIT-0019 | TJX06 - Tubing pressure test | #N/A | I | DP Flow Ind Transmitter |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00284-0086 | PS5-50-FIT-0001 | TJX06 - Tubing pressure test | #N/A | I | DP Flow Ind Transmitter |  | PS5-50-03 - Water Pre-Treatment Package
T-00284-0087 | PS5-71-FIT-0018 | TJX06 - Tubing pressure test | #N/A | I | DP Flow Ind Transmitter |  | PS5-71-13 - CFO Service Pump A/B
T-00284-0088 | PS5-71-FIT-0020 | TJX06 - Tubing pressure test | #N/A | I | DP Flow Ind Transmitter |  | PS5-71-05 - CFO Transfer Pump A/B
T-00284-0089 | PS5-71-FIT-0012 | TJX06 - Tubing pressure test | #N/A | I | DP Flow Ind Transmitter |  | PS5-71-17 - Diesel Fuel Distribution Header
T-00284-0090 | PS5-71-FIT-0005 | TJX06 - Tubing pressure test | #N/A | I | DP Flow Ind Transmitter |  | PS5-71-17 - Diesel Fuel Distribution Header
T-00284-0091 | PS5-71-LIT-1202 | TJX06 - Tubing pressure test | #N/A | I | DP Level Ind Transmitter |  | PS5-71-20 - Diesel Fuel Day Tank
T-00284-0092 | PS5-60-LIT-4401 | TJX06 - Tubing pressure test | #N/A | I | DP Level Ind Transmitter |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump
T-00284-0093 | PS5-71-LIT-4401 | TJX06 - Tubing pressure test | #N/A | I | DP Level Ind Transmitter |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00284-0094 | PS5-53-LIT-4101 | TJX06 - Tubing pressure test | #N/A | I | DP Level Ind Transmitter |  | PS5-53-01 - Utility Water / Storage Tank
T-00284-0095 | PS5-60-LIT-4301 | TJX06 - Tubing pressure test | #N/A | I | DP Level Ind Transmitter |  | PS5-60-24 - Cooling Water Tank & Pump
T-00284-0096 | PS5-71-LIT-1201 | TJX06 - Tubing pressure test | #N/A | I | DP Level Ind Transmitter |  | PS5-71-20 - Diesel Fuel Day Tank
T-00284-0097 | PS5-71-LIT-4402 | TJX06 - Tubing pressure test | #N/A | I | DP Level Ind Transmitter |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00284-0098 | PS5-53-LIT-4102 | TJX06 - Tubing pressure test | #N/A | I | DP Level Ind Transmitter |  | PS5-53-01 - Utility Water / Storage Tank
T-00284-0099 | PS5-25-PDIT-0034A | TJX06 - Tubing pressure test | #N/A | I | Diff Press Ind Transmitter |  | PS5-25-02 - Crude Oil Export Pump A
T-00284-0100 | PS5-01-PDIT-0012B | TJX06 - Tubing pressure test | #N/A | I | Diff Press Ind Transmitter |  | PS5-01-03 - Fire Water Pump B
T-00284-0101 | PS5-01-PDIT-0011A | TJX06 - Tubing pressure test | #N/A | I | Diff Press Ind Transmitter |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00284-0102 | PS5-25-PDIT-0050 | TJX06 - Tubing pressure test | #N/A | I | Diff Press Ind Transmitter |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00284-0103 | PS5-25-PDIT-0034C | TJX06 - Tubing pressure test | #N/A | I | Diff Press Ind Transmitter |  | PS5-25-04 - Crude Oil Export Pump C
T-00284-0104 | PS5-71-PDIT-0030 | TJX06 - Tubing pressure test | #N/A | I | Diff Press Ind Transmitter |  | PS5-71-01 - CFO Storage Tank Feed Heater
T-00284-0105 | PS5-01-PDIT-0011B | TJX06 - Tubing pressure test | #N/A | I | Diff Press Ind Transmitter |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00284-0106 | PS5-71-PDIT-0056B | TJX06 - Tubing pressure test | #N/A | I | Diff Press Ind Transmitter |  | PS5-71-05 - CFO Transfer Pump A/B
T-00284-0107 | PS5-71-PDIT-0056A | TJX06 - Tubing pressure test | #N/A | I | Diff Press Ind Transmitter |  | PS5-71-05 - CFO Transfer Pump A/B
T-00284-0108 | PS5-01-PDIT-0012A | TJX06 - Tubing pressure test | #N/A | I | Diff Press Ind Transmitter |  | PS5-01-02 - Fire Water Pump A
T-00284-0109 | PS5-25-PDIT-0034B | TJX06 - Tubing pressure test | #N/A | I | Diff Press Ind Transmitter |  | PS5-25-03 - Crude Oil Export Pump B
T-00284-0179 | PS5-01-FCV-0004B | TJX06 - Tubing pressure test | #N/A | I | Flow Control Valve |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00284-0180 | PS5-25-FCV-0004 | TJX06 - Tubing pressure test | #N/A | I | Flow Control Valve |  | PS5-25-06 - Crude Oil Export Pumps Discharge
T-00284-0181 | PS5-01-FCV-0003A | TJX06 - Tubing pressure test | #N/A | I | Flow Control Valve |  | PS5-01-02 - Fire Water Pump A
T-00284-0182 | PS5-01-FCV-0003B | TJX06 - Tubing pressure test | #N/A | I | Flow Control Valve |  | PS5-01-03 - Fire Water Pump B
T-00284-0183 | PS5-71-FCV-0018 | TJX06 - Tubing pressure test | #N/A | I | Flow Control Valve |  | PS5-71-13 - CFO Service Pump A/B
T-00284-0184 | PS5-25-FCV-0003B | TJX06 - Tubing pressure test | #N/A | I | Flow Control Valve |  | PS5-25-03 - Crude Oil Export Pump B
T-00284-0185 | PS5-71-LCV-4101 | TJX06 - Tubing pressure test | #N/A | I | Level Control Valve |  | PS5-71-04 - CFO Storage Tank
T-00284-0186 | PS5-71-FCV-0019 | TJX06 - Tubing pressure test | #N/A | I | Flow Control Valve |  | PS5-71-21 - Diesel Transfer Pump A/B
T-00284-0187 | PS5-71-FCV-0020 | TJX06 - Tubing pressure test | #N/A | I | Flow Control Valve |  | PS5-71-05 - CFO Transfer Pump A/B
T-00284-0188 | PS5-01-FCV-0004A | TJX06 - Tubing pressure test | #N/A | I | Flow Control Valve |  | PS5-01-01 - Fire Water Jockey Pump A/B
T-00284-0189 | PS5-25-FCV-0003A | TJX06 - Tubing pressure test | #N/A | I | Flow Control Valve |  | PS5-25-02 - Crude Oil Export Pump A
T-00284-0190 | PS5-25-FCV-0003C | TJX06 - Tubing pressure test | #N/A | I | Flow Control Valve |  | PS5-25-04 - Crude Oil Export Pump C
T-00284-0208 | PS5-09-PDIT-8207 | TJX06 - Tubing pressure test | #N/A | I | DIFFERENTIAL PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00284-0209 | PS5-09-PDIT-8407 | TJX06 - Tubing pressure test | #N/A | I | DIFFERENTIAL PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00284-0210 | PS5-09-PDIT-8408 | TJX06 - Tubing pressure test | #N/A | I | DIFFERENTIAL PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00284-0211 | PS5-09-PDIT-8409 | TJX06 - Tubing pressure test | #N/A | I | DIFFERENTIAL PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00284-0212 | PS5-09-PDIT-8411 | TJX06 - Tubing pressure test | #N/A | I | DIFFERENTIAL PRESSURE TRANSMITTER |  | PS5-09-03 - HVAC for Generator Building
T-00604-0248 | PS5-61-IJ-0001-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-63-NER-0010 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00604-0249 | PS5-61-IJ-0001-CL02 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-63-NER-0011 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00604-0250 | PS5-61-IJ-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-NER-0010 TO PS5-61-IJ-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00604-0251 | PS5-61-IJ-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-NER-0011 TO PS5-61-IJ-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00604-0252 | PS5-61-IK-0001-CG01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00604-0253 | PS5-61-IK-0001-CG02 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00604-0254 | PS5-61-IK-0001-CG03 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00604-0255 | PS5-61-IK-0001-CG04 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00604-0256 | PS5-61-IK-0001-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0257 | PS5-61-IK-0001-CL02 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0258 | PS5-61-IK-0001-CL03 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0259 | PS5-61-IK-0001-CL04 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0260 | PS5-61-IK-0001-CL05 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0261 | PS5-61-IK-0001-CL06 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0262 | PS5-61-IK-0001-CL07 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0263 | PS5-61-IK-0001-CL08 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0264 | PS5-61-IK-0001-CL09 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0265 | PS5-61-IK-0001-CL10 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0266 | PS5-61-IK-0001-CL11 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0267 | PS5-61-IK-0001-CL12 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0268 | PS5-61-IK-0001-CL13 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0269 | PS5-61-IK-0001-CL14 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0270 | PS5-61-IK-0001-CL15 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0271 | PS5-61-IK-0001-CL16 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0272 | PS5-61-IK-0001-CL17 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0273 | PS5-61-IK-0001-CL18 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00604-0274 | PS5-61-IK-0001-CL19 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0275 | PS5-61-IK-0001-CL20 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0276 | PS5-61-IK-0001-CL21 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0277 | PS5-61-IK-0001-CL22 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0278 | PS5-61-IK-0001-CL23 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0279 | PS5-61-IK-0001-CL24 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0280 | PS5-61-IK-0001-CL25 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0281 | PS5-61-IK-0001-CL26 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0282 | PS5-61-IK-0001-CL27 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0283 | PS5-61-IK-0001-CL28 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0284 | PS5-61-IK-0001-CL29 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0285 | PS5-61-IK-0001-CL30 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0250 | 2026-05-07 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0286 | PS5-61-IK-0001-CL31 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00604-0287 | PS5-61-IK-0001-CL32 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
| PS5-28-DM-3700A-CL01 | TPX | #N/A | E |  |  | PS5-28-04 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-60-DM-3400-CL01 | TPX | #N/A | E |  |  | PS5-60-25 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-60-IES-3400-CD01 | TPX | #N/A | E |  |  | PS5-60-25 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-61-IJ-0001-CD33 | TPX | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-61-IK-0001-CG01 | TPX | #N/A | E |  |  | #N/A | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-61-IK-0001-CL33 | TPX | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-61-IK-0001-CL34 | TPX | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-61-IK-0001-CL45 | TPX | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-61-NER-0010-CL01 | TPX | #N/A | E |  |  | PS5-61-02 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-61-NER-0011-CL01 | TPX | #N/A | E |  |  | PS5-61-03 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-63-IV-0010-CL01 | TPX | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-63-IV-0011-CL01 | TPX | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-63-NER-0010-CL01 | TPX | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-63-NER-0011-CL01 | TPX | #N/A | E |  |  | PS5-61-01 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
| PS5-79-IV-0012-CL01 | TPX | #N/A | E |  |  | PS5-79-12 | CPP-RFI-68-331-07-0255 | 2026-05-08 | Accepted | BERTUS WIKAEL | Testing
T-00604-0288 | PS5-61-IK-0001-CL33 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00604-0289 | PS5-61-IK-0001-CL34 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00604-0290 | PS5-61-IK-0001-CL35 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00604-0291 | PS5-61-IK-0001-CL36 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00604-0292 | PS5-61-IK-0001-CL44 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0266 | 2026-05-13 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0293 | PS5-61-IK-0001-CL45 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00604-0294 | PS5-61-ISR-0101-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-61-ISR-0101 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0239 | 30-April-20206 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0295 | PS5-61-ISR-0102-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-61-ISR-0102 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0239 | 30-April-20206 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0296 | PS5-61-IU-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-61-IU-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-05-0239 | 30-April-20206 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0297 | PS5-61-IU-0010-CL02 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-61-IU-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00604-0298 | PS5-61-IU-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-61-IU-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-05-0239 | 30-April-20206 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0299 | PS5-61-IU-0011-CL02 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-61-IU-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-05-0239 | 30-April-20206 | Accepted With Punch | Bertus Wikael | PULLING
T-00604-0300 | PS5-61-IV-0001A-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-61-IV-0001A |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00604-0301 | PS5-61-IV-0001B-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-61-IV-0001B |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00604-0302 | PS5-61-NER-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-61-NER-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00604-0303 | PS5-61-NER-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-61-NER-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00604-0304 | PS5-63-IV-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-63-IV-0010 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00604-0305 | PS5-63-IV-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-63-IV-0011 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00604-0306 | PS5-63-NER-0010-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-63-NER-0010 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00604-0307 | PS5-63-NER-0011-CL01 | CPX09a - LV Power Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IG-0008 TO PS5-63-NER-0011 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00606-0065 | PS5-61-IE-0002-CD01 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IE-0002 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00606-0066 | PS5-61-IE-0002-CD02 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IE-0002 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00606-0067 | PS5-61-IE-0002-CD03 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IE-0002 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00606-0068 | PS5-61-IE-0002-CD04 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IE-0002 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00606-0069 | PS5-61-IE-0002-CD05 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IE-0002 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00606-0070 | PS5-61-IE-0002-CD06 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IE-0002 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00606-0071 | PS5-61-IJ-0001-CD01 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-63-IV-0010 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00606-0072 | PS5-61-IJ-0001-CD03 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-63-IV-0011 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00606-0073 | PS5-61-IJ-0001-CD33 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001A TO PS5-61-IJ-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00606-0074 | PS5-61-IJ-0001-CD34 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0001B TO PS5-61-IJ-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00606-0075 | PS5-61-IJ-0001-CD35 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IJ-0001 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00606-0076 | PS5-61-IJ-0001-CD36 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IJ-0001 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00606-0077 | PS5-61-IJ-0001-CD37 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-ISR-0101 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING
| PS5-08-52BT-0137-CS01 |  | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0329 | 2026-06-10 | Acceptable | Ferdinand | PULLING
T-00606-0078 | PS5-61-IJ-0001-CD38 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-ISR-0102 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00606-0079 | PS5-61-IJ-0001-CD39 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0010 TO PS5-61-IJ-0001 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00606-0080 | PS5-61-IJ-0001-CD40 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IJ-0001 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00606-0081 | PS5-61-IJ-0001-CD41 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IJ-0001 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00606-0082 | PS5-61-IJ-0001-CD42 | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | #N/A | E | Cable FROM PS5-61-IU-0011 TO PS5-61-IJ-0001 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011)
T-00608-0350 | PS5-01-FIT-0003A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-01-FIT-0003A |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-33/1-05-0219 | 2026-04-16 | Accepted With Punch | Elizabeth | PULLING
T-00608-0351 | PS5-01-FIT-0003B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-01-FIT-0003B |  | PS5-01-03 - Fire Water Pump B | CPP-RFI-68-33/1-05-0219 | 2026-04-16 | Accepted With Punch | Elizabeth | PULLING
T-00608-0352 | PS5-01-FIT-0004A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-01-FIT-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-33/1-05-0219 | 2026-04-16 | Accepted With Punch | Elizabeth | PULLING
T-00608-0353 | PS5-01-FIT-0004B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-01-FIT-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-33/1-05-0219 | 2026-04-16 | Accepted With Punch | Elizabeth | PULLING
T-00608-0354 | PS5-01-IE-0001A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-01-IE-0001A |  | PS5-01-05 - Foam Skid | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0355 | PS5-01-IE-0001B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-01-IE-0001B |  | PS5-01-05 - Foam Skid | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0356 | PS5-01-IE-0002A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-01-IE-0002A |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-33/1-05-0219 | 2026-04-16 | Accepted With Punch | Elizabeth | PULLING
T-00608-0357 | PS5-01-IE-0002B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-01-IE-0002B |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-33/1-05-0219 | 2026-04-16 | Accepted With Punch | Elizabeth | PULLING
T-00608-0358 | PS5-01-IE-0009A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-01-IE-0009A |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-33/1-05-0219 | 2026-04-16 | Accepted With Punch | Elizabeth | PULLING
T-00608-0359 | PS5-01-IE-0009B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-01-IE-0009B |  | PS5-01-03 - Fire Water Pump B | CPP-RFI-68-33/1-05-0219 | 2026-04-16 | Accepted With Punch | Elizabeth | PULLING
T-00608-0360 | PS5-03-GDLHP-0137-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-03-GDLHP-0137 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0361 | PS5-03-GDLHP-0142-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-03-GDLHP-0142 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0362 | PS5-03-GDLHP-0143-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-03-GDLHP-0143 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0363 | PS5-03-GDLHP-0144-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-03-GDLHP-0144 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0364 | PS5-03-GDLHP-0146-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-03-GDLHP-0146 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0365 | PS5-03-GDLHP-0147-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-03-GDLHP-0147 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0366 | PS5-03-GDLHP-0149-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-03-GDLHP-0149 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0367 | PS5-03-GDLHP-0150-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-03-GDLHP-0150 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0368 | PS5-03-GDLHP-0401-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-03-GDLHP-0401 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0369 | PS5-05-IG-0004-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-05-IG-0004 |  | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0370 | PS5-05-IG-0006-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-05-IG-0006 |  | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0371 | PS5-25-DM-3200A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-3200A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0372 | PS5-25-DM-3200B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-3200B |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0373 | PS5-25-DM-3300A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-3300A |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0374 | PS5-25-DM-3300B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-3300B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0375 | PS5-25-DM-3400A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-3400A |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
| PS5-01-IE-0002A-CL01 | TPX | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-01-IE-0002A |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING
| PS5-01-IE-0002B-CL01 | TPX | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-01-IE-0002B |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING
| PS5-01-IE-0009A-CL01 | TPX | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-01-IE-0009A |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING
| PS5-01-IE-0009B-CL01 | TPX | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-01-IE-0009B |  | PS5-01-03 - Fire Water Pump B | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING
| PS5-01-FIT-0003A-CL01 | TPX | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-01-FIT-0003A |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING
| PS5-01-FIT-0003B-CL01 | TPX | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-01-FIT-0003B |  | PS5-01-03 - Fire Water Pump B | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING
| PS5-01-FIT-0004A-CL01 | TPX | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-01-FIT-0004A |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING
| PS5-01-FIT-0004B-CL01 | TPX | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-01-FIT-0004B |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING
| PS5-53-IES-3100A-CD01 | TPX | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-53-IES-3100A |  | PS5-53-02 - Water Distribution Pump A/B | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
| PS5-53-IES-3100B-CD01 | TPX | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-53-IES-3100B |  | PS5-53-02 - Water Distribution Pump A/B | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
| PS5-53-DM-3100A-CL01 | TPX | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-53-DM-3100A |  | PS5-53-02 - Water Distribution Pump A/B | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING
| PS5-53-DM-3100B-CL01 | TPX | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-53-DM-3100B |  | PS5-53-02 - Water Distribution Pump A/B | CPP-RFI-68-33/1-07-0220 | 2026-04-16 | Accepted | Elizabeth | PULLING
| PS5-25-DM-6400A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-DM-6400B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-DM-6500A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-DM-6500B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-DM-6600A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-DM-6600B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-FIT-0001-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-FIT-0003A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-FIT-0003B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-FIT-0003C-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-DM-3200A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-DM-3200B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-DM-3300A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-DM-3300B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-DM-3400A-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-DM-3400B-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-HE-2100-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-HE-2100-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-HE-2200-CD01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0279 | 2026-05-20 | Accepted | Bertus Wikael | Testing
| PS5-25-FIT-0004-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0308 | 2026-06-02 | Accepted | Bertus Wikael | Testing
T-00608-0376 | PS5-25-DM-3400B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-3400B |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0377 | PS5-25-DM-6400A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-6400A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0378 | PS5-25-DM-6400B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-6400B |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0379 | PS5-25-DM-6500A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-6500A |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0380 | PS5-25-DM-6500B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-6500B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0381 | PS5-25-DM-6600A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-6600A |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0382 | PS5-25-DM-6600B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-DM-6600B |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0383 | PS5-25-FIT-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-25-FIT-0001 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0384 | PS5-25-FIT-0003A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-25-FIT-0003A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0385 | PS5-25-FIT-0003B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-25-FIT-0003B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0386 | PS5-25-FIT-0003C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-25-FIT-0003C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0387 | PS5-25-FIT-0004-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-25-FIT-0004 |  | PS5-25-06 - Crude Oil Export Pumps Discharge | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0388 | PS5-25-HE-2100-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-HE-2100 |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0389 | PS5-25-HE-2200-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-HE-2200 |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0390 | PS5-25-HE-2300-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-HE-2300 |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0391 | PS5-25-UD-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-UD-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0392 | PS5-28-BE-0002A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-BE-0002A |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0393 | PS5-28-BE-0002B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-BE-0002B |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0394 | PS5-28-DM-3300-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3300 |  | PS5-28-06 - Relief Drum and Pump | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0395 | PS5-28-DM-3400-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3400 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-331-05-0238 | 2026-04-30 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0396 | PS5-28-DM-3500-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3500 |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0397 | PS5-28-DM-3600A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3600A |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0398 | PS5-28-DM-3600A-CL02 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3600A |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0399 | PS5-28-DM-3600B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3600B |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0400 | PS5-28-DM-3600B-CL02 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3600B |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0401 | PS5-28-DM-3700A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3700A |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00608-0402 | PS5-28-DM-3700B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3700B |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0403 | PS5-28-DM-3800A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3800A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0404 | PS5-28-DM-3800B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3800B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0405 | PS5-28-DM-3800C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3800C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0406 | PS5-28-DM-3900A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3900A |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00608-0407 | PS5-28-DM-3900B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-DM-3900B |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00608-0408 | PS5-28-HE-2100-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-HE-2100 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0409 | PS5-28-HE-2200-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-HE-2200 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0410 | PS5-28-ISO-2008-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-ISO-2008 |  | PS5-28-10 - Oil Skimmer Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0411 | PS5-50-IE-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-50-IE-0001 |  | PS5-50-01 - Water Well Submersible Pumps (3100) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0412 | PS5-50-IE-0002-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-50-IE-0002 |  | PS5-50-02 - Water Well Submersible Pumps (3200) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0413 | PS5-53-DM-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-53-DM-3100A |  | PS5-53-02 - Water Distribution Pump A/B | CPP-RFI-68-33/1-05-0219 | 2026-04-16 | Accepted With Punch | Elizabeth | PULLING
T-00608-0414 | PS5-53-DM-3100B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-53-DM-3100B |  | PS5-53-02 - Water Distribution Pump A/B | CPP-RFI-68-33/1-05-0219 | 2026-04-16 | Accepted With Punch | Elizabeth | PULLING
T-00608-0415 | PS5-53-IN-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-53-IN-0001 |  | PS5-53-04 - Water Treatment Purification Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0416 | PS5-60-DM-3300-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-60-DM-3300 |  | PS5-60-24 - Cooling Water Tank & Pump | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0417 | PS5-60-DM-3400-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-60-DM-3400 |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00608-0418 | PS5-61-IDH-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0001A TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00608-0419 | PS5-61-IDH-3100B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0001B TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00608-0420 | PS5-61-IDH-3100C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0001B TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00608-0421 | PS5-61-IG-0006-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-61-IG-0006 |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0422 | PS5-61-IG-0007-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-61-IG-0007 |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0423 | PS5-61-IG-0012A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-61-IG-0012A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0424 | PS5-61-IG-0012B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-61-IG-0012B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0425 | PS5-61-IG-0012C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-61-IG-0012C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0426 | PS5-61-IG-0014-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-61-IG-0014 |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0427 | PS5-61-IG-0042-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-61-IG-0042 |  | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0428 | PS5-61-IG-0043-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-61-IG-0043 |  | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | CPP-RFI-68-331-05-0239 | 30-April-20206 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0429 | PS5-61-IK-0001-CL37 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0430 | PS5-61-IK-0001-CL38 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0431 | PS5-61-IK-0001-CL39 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0432 | PS5-61-IK-0001-CL40 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0433 | PS5-61-IK-0001-CL41 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0434 | PS5-61-IK-0001-CL42 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0435 | PS5-61-IK-0001-CL43 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0436 | PS5-61-IK-0003-CG01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003)
T-00608-0437 | PS5-61-IK-0003-CG02 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003)
T-00608-0438 | PS5-61-IK-0003-CG03 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003)
T-00608-0439 | PS5-61-IK-0003-CG04 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003)
T-00608-0440 | PS5-61-IK-0003-CG05 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003)
T-00608-0441 | PS5-61-IK-0003-CG06 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IK-0003 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003)
T-00608-0442 | PS5-61-IK-0006-CG01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006)
T-00608-0443 | PS5-61-IK-0006-CG02 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006)
T-00608-0444 | PS5-61-IK-0006-CG03 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006)
T-00608-0445 | PS5-61-IK-0006-CG04 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IK-0006 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006)
T-00608-0446 | PS5-61-IV-0006A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-61-IV-0006A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0447 | PS5-61-IV-0006B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-61-IV-0006B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0228 | 2026-05-01 | Accepted With Punch | Ferdinand | PULLING
T-00608-0448 | PS5-61-IV-0006C-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-61-IV-0006C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00608-0449 | PS5-71-DM-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-DM-3100A |  | PS5-71-16 - Diesel Fuel Supply Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0450 | PS5-71-DM-3100B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-DM-3100B |  | PS5-71-16 - Diesel Fuel Supply Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0451 | PS5-71-DM-3200-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-DM-3200 |  | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0452 | PS5-71-DM-3300A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-DM-3300A |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0453 | PS5-71-DM-3300B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-DM-3300B |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0454 | PS5-71-DM-3400A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-DM-3400A |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0455 | PS5-71-DM-3400B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-DM-3400B |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0456 | PS5-71-DM-3500A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-DM-3500A |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00608-0457 | PS5-71-DM-3500B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-DM-3500B |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00608-0458 | PS5-71-FIT-0011A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-71-FIT-0011A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0459 | PS5-71-FIT-0011B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0002 TO PS5-71-FIT-0011B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0460 | PS5-71-HE-2200-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-HE-2200 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0461 | PS5-71-HE-2300-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-HE-2300 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0462 | PS5-74-IG-5101-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-74-IG-5101 |  | PS5-74-01 - N2 Generation Skid | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0463 | PS5-75-DM-3100A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-75-DM-3100A |  | PS5-75-03 - Corrosion Inhibitor Injection Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0464 | PS5-75-DM-3100B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-75-DM-3100B |  | PS5-75-03 - Corrosion Inhibitor Injection Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0465 | PS5-75-DM-3200A-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-75-DM-3200A |  | PS5-75-02 - Biocide Injection Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0466 | PS5-75-DM-3200B-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-75-DM-3200B |  | PS5-75-02 - Biocide Injection Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0467 | PS5-75-ISO-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-75-ISO-0001 |  | PS5-75-01 - DRA Injection Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0468 | PS5-75-ISO-0002-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-75-ISO-0002 |  | PS5-75-01 - DRA Injection Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0469 | PS5-79-IV-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0001 |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0470 | PS5-79-IV-0002-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0002 |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0471 | PS5-79-IV-0003-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0003 |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0472 | PS5-79-IV-0004-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0004 |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0473 | PS5-79-IV-0005-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0005 |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0474 | PS5-79-IV-0006-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0006 |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0475 | PS5-79-IV-0007-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0007 |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0476 | PS5-79-IV-0008-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0008 |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0477 | PS5-79-IV-0009-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0009 |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0478 | PS5-79-IV-0010-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0010 |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0479 | PS5-79-IV-0011-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0011 |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | CPP-RFI-68-331-05-0295 | 2026-05-24 | Accepted with punch | Bertus Wikael | PULLING
T-00608-0480 | PS5-79-IV-0012-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-79-IV-0012 |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00608-0481 | PS5-82-IN-0001-CL01 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-82-IN-0001 |  | PS5-82-02 - Sewage Treatment Plant Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00608-0943 | PS5-53-IN-0001-CL02 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0001A TO PS5-53-IN-0001 |  | PS5-53-04 - Water Treatment Purification Package | CPP-RFI-68-331-05-0295 | 2026-05-24 | Accepted with punch | Bertus Wikael | PULLING
| PS5-53-IN-0001-CL02 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0296 | 2026-05-24 | Accepted with punch | Bertus Wikael | TESTING
| PS5-53-IN-0001-CL03 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0296 | 2026-05-24 | Accepted with punch | Bertus Wikael | TESTING
| PS5-61-IE-0002-CD41 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0296 | 2026-05-24 | Accepted with punch | Bertus Wikael | TESTING
| PS5-61-IE-0002-CD42 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0296 | 2026-05-24 | Accepted with punch | Bertus Wikael | TESTING
| PS5-79-IV-0011-CL01 | TPX | #N/A | E |  |  |  | CPP-RFI-68-331-07-0296 | 2026-05-24 | Accepted with punch | Bertus Wikael | TESTING
T-00608-0944 | PS5-53-IN-0001-CL03 | CPX09b - LV Power Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-06-IG-0001B TO PS5-53-IN-0001 |  | PS5-53-04 - Water Treatment Purification Package | CPP-RFI-68-331-05-0295 | 2026-05-24 | Accepted with punch | Bertus Wikael | PULLING
T-00610-0177 | PS5-05-IE-8100-CD09 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0178 | PS5-05-IE-8100-CD22 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0179 | PS5-05-IE-8100-CD24 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0180 | PS5-05-IG-0004-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0003 TO PS5-05-IG-0004 |  | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0181 | PS5-05-IG-0006-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0003 TO PS5-05-IG-0006 |  | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0182 | PS5-05-IG-0025-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0003 TO PS5-05-IG-0025 |  | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00610-0183 | PS5-05-IG-0026-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0003 TO PS5-05-IG-0026 |  | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00610-0184 | PS5-06-GU-0003A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0003A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0185 | PS5-06-GU-0003B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0003B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0186 | PS5-06-IG-0004A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-06-IG-0004A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0187 | PS5-06-IG-0004B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-06-IG-0004B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00610-0188 | PS5-25-HE-2100-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-HE-2100 |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0189 | PS5-25-HE-2200-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-HE-2200 |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0190 | PS5-25-HE-2300-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-HE-2300 |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0191 | PS5-25-IES-3200A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-3200A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0192 | PS5-25-IES-3200B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-3200B |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0193 | PS5-25-IES-3300A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-3300A |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0194 | PS5-25-IES-3300B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-3300B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0195 | PS5-25-IES-3400A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-3400A |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0196 | PS5-25-IES-3400B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-3400B |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0197 | PS5-25-IES-6400A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-6400A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0198 | PS5-25-IES-6400B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-6400B |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0199 | PS5-25-IES-6500A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-6500A |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0200 | PS5-25-IES-6500B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-6500B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0201 | PS5-25-IES-6600A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-6600A |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0202 | PS5-25-IES-6600B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-25-IES-6600B |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING | CPP-RFI-68-33/1-06-0360 | ACCEPTED WITH PUNCH | 2026-06-20 | Bertus Wikael
T-00610-0203 | PS5-28-HE-2100-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-HE-2100 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0204 | PS5-28-HE-2200-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-HE-2200 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-331-05-0244 | 2026-05-05 | Accepted with Punch | Bertus Wikael | PULLING
T-00610-0205 | PS5-28-IES-2008-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-2008 |  | PS5-28-10 - Oil Skimmer Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0206 | PS5-28-IES-3300-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3300 |  | PS5-28-06 - Relief Drum and Pump | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0207 | PS5-28-IES-3400-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3400 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0208 | PS5-28-IES-3500-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3500 |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0209 | PS5-28-IES-3600A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3600A |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00610-0210 | PS5-28-IES-3600B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3600B |  | PS5-28-08 - Open Drain Sump and Pumps | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0211 | PS5-28-IES-3700A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3700A |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-331-05-0239 | 30-April-20206 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0212 | PS5-28-IES-3700B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3700B |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0213 | PS5-28-IES-3800A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3800A |  | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0214 | PS5-28-IES-3800B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3800B |  | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0215 | PS5-28-IES-3800C-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3800C |  | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0216 | PS5-28-IES-3900A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3900A |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00610-0217 | PS5-28-IES-3900B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-28-IES-3900B |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0218 | PS5-53-IES-3100A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-53-IES-3100A |  | PS5-53-02 - Water Distribution Pump A/B | CPP-RFI-68-33/1-05-0219 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00610-0219 | PS5-53-IES-3100B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-53-IES-3100B |  | PS5-53-02 - Water Distribution Pump A/B | CPP-RFI-68-33/1-05-0219 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00610-0220 | PS5-60-IE-0003A-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00610-0221 | PS5-60-IE-0003A-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00610-0222 | PS5-60-IE-0003A-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A |  | PS5-60-01 - Power Generation Package A | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0452 | OPEN | 2026-07-31 | Bertus Wikael
T-00610-0223 | PS5-60-IE-0003B-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0224 | PS5-60-IE-0003B-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0225 | PS5-60-IE-0003B-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B |  | PS5-60-04 - Power Generation Package B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0226 | PS5-60-IE-0003C-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0227 | PS5-60-IE-0003C-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0228 | PS5-60-IE-0003C-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003C |  | PS5-60-07 - Power Generation Package C | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0229 | PS5-60-IE-0003D-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0230 | PS5-60-IE-0003D-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0231 | PS5-60-IE-0003D-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003D |  | PS5-60-10 - Power Generation Package D | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0232 | PS5-60-IE-0003E-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00610-0233 | PS5-60-IE-0003E-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00610-0234 | PS5-60-IE-0003E-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003E |  | PS5-60-13 - Power Generation Package E | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0235 | PS5-60-IE-0003F-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0236 | PS5-60-IE-0003F-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0237 | PS5-60-IE-0003F-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003F |  | PS5-60-16 - Power Generation Package F
T-00610-0238 | PS5-60-IE-0003G-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0239 | PS5-60-IE-0003G-CD08 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0240 | PS5-60-IE-0003G-CD12 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003G |  | PS5-60-19 - Power Generation Package G | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0241 | PS5-60-IE-0004-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0242 | PS5-60-IE-0004-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0243 | PS5-60-IES-3300-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-60-IES-3300 |  | PS5-60-24 - Cooling Water Tank & Pump | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0244 | PS5-60-IES-3400-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-60-IES-3400 |  | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CPP-RFI-68-331-05-0240 | 2026-05-01 | Accepted with Punch | BERTUS WIKAEL | PULLING
T-00610-0245 | PS5-61-IDH-3100A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0246 | PS5-61-IDH-3100A-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0003 TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0247 | PS5-61-IDH-3100B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0248 | PS5-61-IDH-3100B-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0239 | 30-April-20206 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0249 | PS5-61-IDH-3100C-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0250 | PS5-61-IDH-3100C-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0251 | PS5-61-IE-0003-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-82-LA-0001 TO PS5-61-IE-0003 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0252 | PS5-61-IG-0006-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-61-IG-0006 |  | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0253 | PS5-61-IG-0007-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-61-IG-0007 |  | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0254 | PS5-61-IG-0014-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0003 TO PS5-61-IG-0014 |  | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0255 | PS5-61-IG-0015-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0003 TO PS5-61-IG-0015 |  | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0256 | PS5-61-IG-0016-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0003 TO PS5-61-IG-0016 |  | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | CPP-RFI-68-331-05-0264 | 2026-05-12 | Accepted with comment | Bertus Wikael | PULLING
T-00610-0257 | PS5-61-IG-0042-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-61-IG-0042 |  | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0258 | PS5-61-IG-0043-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IE-0002 TO PS5-61-IG-0043 |  | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
| PS5-61-IG-0043-CD01 |  | #N/A | E
T-00610-0259 | PS5-61-IJ-0001-CD04 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-61-IJ-0001 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0243 | 2026-05-03 | Accepted with Punch | Bertus Wikael | PULLING
T-00610-0260 | PS5-61-IJ-0001-CD05 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0003 TO PS5-61-IJ-0001 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-331-05-0260 | 2026-05-10 | Accepted with punch | Bertus Wikael | Pulling
T-00610-0261 | PS5-61-IJ-0001-CD06 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IJ-0001 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0226 | 2026-04-25 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0262 | PS5-61-IJ-0001-CD07 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0006 TO PS5-61-IJ-0001 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-331-05-0225 | 2026-04-24 | Accepted with punch | Bertus Wikael | PULLING
T-00610-0263 | PS5-61-IJ-0001-CD24 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IDH-3100A TO PS5-61-IJ-0001 |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0264 | PS5-61-IJ-0001-CD25 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IDH-3100B TO PS5-61-IJ-0001 |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0265 | PS5-61-IJ-0001-CD26 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IDH-3100C TO PS5-61-IJ-0001 |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-331-05-0215 | 2026-04-17 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0266 | PS5-61-IJ-0001-CD27 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0002A TO PS5-61-IJ-0001 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0267 | PS5-61-IJ-0001-CD28 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0002B TO PS5-61-IJ-0001 |  | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0268 | PS5-61-IJ-0001-CD29 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0007A TO PS5-61-IJ-0001 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0269 | PS5-61-IJ-0001-CD30 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0007B TO PS5-61-IJ-0001 |  | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0270 | PS5-61-IJ-0001-CD31 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0005A TO PS5-61-IJ-0001 |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00610-0271 | PS5-61-IJ-0001-CD32 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IV-0005B TO PS5-61-IJ-0001 |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00610-0272 | PS5-61-IK-0005-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IK-0005 |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00610-0273 | PS5-61-IK-0005-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-61-IK-0005 |  | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005)
T-00610-0274 | PS5-62-IE-0002-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-08-15CB-1001 TO PS5-62-IE-0002 |  | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0275 | PS5-71-HE-2200-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-HE-2200 |  | PS5-71-12 - CFO Service Tank | CPP-RFI-68-331-05-0239 | 30-April-20206 | Accepted With Punch | Bertus Wikael | PULLING
T-00610-0276 | PS5-71-HE-2300-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-HE-2300 |  | PS5-71-04 - CFO Storage Tank | CPP-RFI-68-33/1-05-0223 | 2026-04-25 | Accpeted With Punch | Ferdinand | PULLING
T-00610-0277 | PS5-71-IES-3100A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-IES-3100A |  | PS5-71-16 - Diesel Fuel Supply Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00610-0278 | PS5-71-IES-3100B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-IES-3100B |  | PS5-71-16 - Diesel Fuel Supply Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00610-0279 | PS5-71-IES-3200-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-IES-3200 |  | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00610-0280 | PS5-71-IES-3300A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-IES-3300A |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00610-0281 | PS5-71-IES-3300B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-IES-3300B |  | PS5-71-05 - CFO Transfer Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00610-0282 | PS5-71-IES-3400A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-IES-3400A |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00610-0283 | PS5-71-IES-3400B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-IES-3400B |  | PS5-71-13 - CFO Service Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0284 | PS5-71-IES-3500A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-IES-3500A |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00610-0285 | PS5-71-IES-3500B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-71-IES-3500B |  | PS5-71-21 - Diesel Transfer Pump A/B | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING | CPP-RFI-68-331-06-0379 | ACCEPTED WITH PUNCH | 2026-06-25 | Bertus Wikael
T-00610-0286 | PS5-75-IES-3100A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-75-IES-3100A |  | PS5-75-03 - Corrosion Inhibitor Injection Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0287 | PS5-75-IES-3100B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-75-IES-3100B |  | PS5-75-03 - Corrosion Inhibitor Injection Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0288 | PS5-75-IES-3200A-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-75-IES-3200A |  | PS5-75-02 - Biocide Injection Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0289 | PS5-75-IES-3200B-CD01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IK-0001 TO PS5-75-IES-3200B |  | PS5-75-02 - Biocide Injection Package | CPP-RFI-68-33/1-05-0211 | 2026-04-17 | Accepted With Punch | Ferdinand | PULLING
T-00610-0574 | PS5-60-IE-0004-CD14 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0438 | 28-July-2026 | Open | Ferdinand | Pulling
T-00610-0575 | PS5-60-IE-0004-CD15 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0438 | 28-July-2026 | Open | Ferdinand | Pulling
T-00610-0576 | PS5-60-IE-0004-CD16 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-33/1-05-0438 | 28-July-2026 | Open | Ferdinand | Pulling
T-00610-0577 | PS5-61-IE-0002-CD41 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003D TO PS5-61-IE-0002 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0295 | 2026-05-24 | Accepted with punch | Bertus Wikael | PULLING
T-00610-0578 | PS5-61-IE-0002-CD42 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003E TO PS5-61-IE-0002 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0295 | 2026-05-24 | Accepted with punch | Bertus Wikael | PULLING
T-00610-0579 | PS5-61-IE-0002-CD43 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003F TO PS5-61-IE-0002 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00610-0580 | PS5-61-IE-0002-CD44 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003G TO PS5-61-IE-0002 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-08-52BT-0131-CS01 |  | #N/A | E |  |  |  | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00610-0581 | PS5-61-IE-0003-CD02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003A TO PS5-61-IE-0003 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00610-0582 | PS5-61-IE-0003-CD03 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003B TO PS5-61-IE-0003 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00610-0583 | PS5-61-IE-0003-CD04 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003C TO PS5-61-IE-0003 |  | PS5-61-08 - Electrical Control System | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00610-0584 | PS5-61-IJ-0001-CD61 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003A TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00610-0585 | PS5-61-IJ-0001-CD62 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003B TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00610-0586 | PS5-61-IJ-0001-CD63 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003C TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00610-0587 | PS5-61-IJ-0001-CD64 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003D TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00610-0588 | PS5-61-IJ-0001-CD65 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003E TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00610-0589 | PS5-61-IJ-0001-CD66 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003F TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00610-0590 | PS5-61-IJ-0001-CD67 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | #N/A | E | Cable FROM PS5-60-IE-0003G TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPP-RFI-68-331-05-0275 | 2026-05-19 | Accepted With Punch | Bertus Wikael | Pulling
T-00614-0847 | PS5-01-BI-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0001-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-BI-0001 |  | PS5-01-05 - Foam Skid | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0848 | PS5-01-BI-0002-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0002-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-BI-0002 |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0849 | PS5-01-BI-0003-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0003-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-01-BI-0003 |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0850 | PS5-01-BI-0004-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0004-CC01 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-BI-0004 |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0851 | PS5-01-BI-0005-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0005-CC01 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-BI-0005 |  | PS5-01-05 - Foam Skid | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0852 | PS5-01-BI-0006-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-0006-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-01-BI-0006 |  | PS5-01-05 - Foam Skid | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0853 | PS5-01-BI-1117-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1117-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-01-BI-1117 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0854 | PS5-01-BI-1118-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1118-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-01-BI-1118 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0041 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-0855 | PS5-01-BI-1501-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1501-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-01-BI-1501 |  | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-04-0071 | 2026-06-23 | Accepted with punch | Elizabeth | PULLING
T-00614-0856 | PS5-01-BI-1515-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1515-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-01-BI-1515 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0857 | PS5-01-BI-1520-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1520-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-01-BI-1520 |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0858 | PS5-01-BI-1571-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-1571-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-01-BI-1571 |  | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0859 | PS5-01-BI-2110-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-2110-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-01-BI-2110 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0860 | PS5-01-BI-2520-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-2520-CC01 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-BI-2520 |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0861 | PS5-01-BI-2571A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-2571A-CC01 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-BI-2571A |  | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0862 | PS5-01-BI-2571B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-BI-2571B-CC01 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-BI-2571B |  | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0863 | PS5-01-IE-0002A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0002A-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-IE-0002A |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0864 | PS5-01-IE-0002A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0002A-CC02 | I | Cable FROM PS5-03-SFMC-0013 TO PS5-01-IE-0002A |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0865 | PS5-01-IE-0002B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0002B-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-IE-0002B |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0866 | PS5-01-IE-0002B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0002B-CC02 | I | Cable FROM PS5-03-SFMC-0013 TO PS5-01-IE-0002B |  | PS5-01-01 - Fire Water Jockey Pump A/B | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0867 | PS5-01-IE-0009A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0009A-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-IE-0009A |  | PS5-01-02 - Fire Water Pump A | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0868 | PS5-01-IE-0009A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-IE-0009A |  | PS5-01-02 - Fire Water Pump A
T-00614-0869 | PS5-01-IE-0009B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-IE-0009B-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-01-IE-0009B |  | PS5-01-03 - Fire Water Pump B | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0870 | PS5-01-IE-0009B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-IE-0009B |  | PS5-01-03 - Fire Water Pump B
T-00614-0871 | PS5-01-LB-0004-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-LB-0004-CC01 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-01-LB-0004 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0872 | PS5-01-LB-0004-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-LB-0004-CC02 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-01-LB-0004 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0873 | PS5-01-LB-0004-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-LB-0004-CC03 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-01-LB-0004 |  | PS5-01-11 - Inergen for Power Gen Building | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0874 | PS5-01-LIT-4201-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-LIT-4201-CJ01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-01-LIT-4201 |  | PS5-01-10 - Water Mist Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0875 | PS5-01-PIT-0014-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-PIT-0014-CJ01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-01-PIT-0014 |  | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0876 | PS5-01-PIT-0015-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-PIT-0015-CJ01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-01-PIT-0015 |  | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0877 | PS5-01-PIT-0016-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-PIT-0016-CJ01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-01-PIT-0016 |  | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0878 | PS5-01-PIT-0017-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-01-PIT-0017-CJ01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-01-PIT-0017 |  | PS5-01-07 - Fire Water Ring Main & Distribution | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0879 | PS5-03-BI-1502-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1502-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1502 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0880 | PS5-03-BI-1503-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1503-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1503 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0881 | PS5-03-BI-1506-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1506-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1506 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0882 | PS5-03-BI-1507-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1507-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1507 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0883 | PS5-03-BI-1508-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1508-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1508 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0884 | PS5-03-BI-1509-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1509-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1509 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0036/ CPP-RFI-68-64-11-0067 | 2026-04-16 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0885 | PS5-03-BI-1510-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1510-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1510 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0886 | PS5-03-BI-1511-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1511-CC01 | I | Cable FROM PS5-03-SFMC-0007 TO PS5-03-BI-1511 |  | PS5-03-07 - FZ-07 - Pretreatment Area | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0887 | PS5-03-BI-1512-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1512-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1512 |  | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0888 | PS5-03-BI-1513-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1513-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1513 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0889 | PS5-03-BI-1514-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1514-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1514 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0890 | PS5-03-BI-1516-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-1516-CC01 | I | Cable FROM PS5-03-SFMC-0008 TO PS5-03-BI-1516 |  | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0891 | PS5-03-BI-2501-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2501-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2501 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0892 | PS5-03-BI-2502-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2502-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2502 |  | PS5-03-06 - FZ-06 - Transformer Area | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0893 | PS5-03-BI-2503-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2503-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2503 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0894 | PS5-03-BI-2504-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2504-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2504 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0895 | PS5-03-BI-2505-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2505-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2505 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0896 | PS5-03-BI-2506-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2506-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2506 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0897 | PS5-03-BI-2507-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2507-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2507 |  | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0898 | PS5-03-BI-2508-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2508-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2508 |  | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0899 | PS5-03-BI-2509-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2509-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2509 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0900 | PS5-03-BI-2510-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2510 |  | PS5-03-03 - FZ-03 - Buildings Area
T-00614-0901 | PS5-03-BI-2511-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2511-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2511 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0035/ CPP-RFI-68-64-11-0067 | 2026-04-16 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0902 | PS5-03-BI-2512-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2512-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2512 |  | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0903 | PS5-03-BI-2514-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2514-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2514 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0904 | PS5-03-BI-2515-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-BI-2515-CC01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2515 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0905 | PS5-03-HS-7002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-HS-7002-CJ01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-03-HS-7002 |  | PS5-03-03 - FZ-03 - Buildings Area | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0906 | PS5-03-MTX-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0001 TO PS5-03-MTX-0001 |  | PS5-04-02 - Office Building SIS/FGS System
T-00614-0907 | PS5-03-MTX-0001-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0001 TO PS5-03-MTX-0001 |  | PS5-04-02 - Office Building SIS/FGS System
T-00614-0908 | PS5-03-MTX-0001-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0004 TO PS5-03-MTX-0001 |  | PS5-04-02 - Office Building SIS/FGS System
T-00614-0909 | PS5-03-MTX-0001-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0005 TO PS5-03-MTX-0001 |  | PS5-04-02 - Office Building SIS/FGS System
T-00614-0910 | PS5-03-MTX-0001-CC05 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-MTX-0001 |  | PS5-04-02 - Office Building SIS/FGS System
T-00614-0911 | PS5-03-MTX-0001-CC06 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0011 TO PS5-03-MTX-0001 |  | PS5-04-02 - Office Building SIS/FGS System
T-00614-0912 | PS5-03-MTX-0001-CC07 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0011 TO PS5-03-MTX-0001 |  | PS5-04-02 - Office Building SIS/FGS System
T-00614-0913 | PS5-03-MTX-0001-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0012 TO PS5-03-MTX-0001 |  | PS5-04-02 - Office Building SIS/FGS System
T-00614-0914 | PS5-03-NMR-0801-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-NMR-0801-CJ01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-NMR-0801 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0915 | PS5-03-NMR-0802-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-NMR-0802-CJ01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-NMR-0802 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0916 | PS5-03-NMR-0803-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-NMR-0803-CJ01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-NMR-0803 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0917 | PS5-03-NMR-0804-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-NMR-0804-CJ01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-NMR-0804 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0918 | PS5-03-RMAC-0120-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-RMAC-0120-CJ01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-RMAC-0120 |  | PS5-03-01 - FZ-01 - Process Area | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0919 | PS5-03-RMAC-0824-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-RMAC-0824-CJ01 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-03-RMAC-0824 |  | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0920 | PS5-03-SEA-0002-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0002-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-SEA-0002 |  | PS5-03-22 - FZ-G1 - Guard House | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-0921 | PS5-03-SEA-0002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0002-CJ01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-03-SEA-0002 |  | PS5-03-22 - FZ-G1 - Guard House | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0922 | PS5-03-SEA-0003-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0003-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-SEA-0003 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0923 | PS5-03-SEA-0003-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0003-CJ01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-03-SEA-0003 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0924 | PS5-03-SEA-0005-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-SEA-0005 |  | PS5-03-24 - FZ - Office and Facilities Building
T-00614-0925 | PS5-03-SEA-0005-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0004 TO PS5-03-SEA-0005 |  | PS5-03-24 - FZ - Office and Facilities Building
T-00614-0926 | PS5-03-SEA-0006-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0006-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-03-SEA-0006 |  | PS5-03-25 - FZ - Workshop & Warehouse | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-0927 | PS5-03-SEA-0006-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-03-SEA-0006-CJ01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-03-SEA-0006 |  | PS5-03-25 - FZ - Workshop & Warehouse | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0928 | PS5-05-BI-0002-CC11 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-05-BI-0002-CC11 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-05-BI-0002 |  | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Elizabeth
T-00614-0929 | PS5-05-BI-0002-CC12 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-05-BI-0002-CC12 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-05-BI-0002 |  | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0106 | Accepted | 2026-07-22 | Elizabeth
T-00614-0930 | PS5-05-IE-8100-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-05-IE-8100-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0931 | PS5-05-IE-8100-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-05-IE-8100-CC02 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-05-IE-8100 |  | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0932 | PS5-06-GU-0003A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-06-GU-0003A-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-06-GU-0003A |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0933 | PS5-06-GU-0003B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-06-GU-0003B-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-06-GU-0003B |  | PS5-06-02 - AC UPS - Power Generator Building | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0934 | PS5-09-BI-2501-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-BI-2501-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-09-BI-2501 |  | PS5-09-04 - HVAC for Workshop & Warehouse | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0935 | PS5-09-BI-2502-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-BI-2502 |  | PS5-09-01 - HVAC for Office and Facilities building
T-00614-0936 | PS5-09-BI-2503-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-BI-2503-CC01 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-BI-2503 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0937 | PS5-09-LB-0006-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0013 TO PS5-09-LB-0006 |  | PS5-09-01 - HVAC for Office and Facilities building
T-00614-0938 | PS5-09-LB-0006-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0006 |  | PS5-09-01 - HVAC for Office and Facilities building
T-00614-0939 | PS5-09-LB-0006-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0003 TO PS5-09-LB-0006 |  | PS5-09-01 - HVAC for Office and Facilities building
T-00614-0940 | PS5-09-LB-0006-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0006 |  | PS5-09-01 - HVAC for Office and Facilities building
T-00614-0941 | PS5-09-LB-0007-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0007-CC01 | I | Cable FROM PS5-03-SFMC-0013 TO PS5-09-LB-0007 |  | PS5-09-04 - HVAC for Workshop & Warehouse | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0942 | PS5-09-LB-0007-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0007-CC02 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0007 |  | PS5-09-04 - HVAC for Workshop & Warehouse | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-0943 | PS5-09-LB-0007-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0007-CC03 | I | Cable FROM PS5-04-PMC-0005 TO PS5-09-LB-0007 |  | PS5-09-04 - HVAC for Workshop & Warehouse | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0944 | PS5-09-LB-0007-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0007-CC04 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0007 |  | PS5-09-04 - HVAC for Workshop & Warehouse | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0945 | PS5-09-LB-0008-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC01 | I | Cable FROM PS5-03-SFMC-0013 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-0946 | PS5-09-LB-0008-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC02 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-0947 | PS5-09-LB-0008-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC03 | I | Cable FROM PS5-04-PMC-0005 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-0948 | PS5-09-LB-0008-CC04 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC04 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0949 | PS5-09-LB-0008-CC05 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC05 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0950 | PS5-09-LB-0008-CC06 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC06 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-0951 | PS5-09-LB-0008-CC07 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC07 | I | Cable FROM PS5-03-SFMC-0012 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0952 | PS5-09-LB-0008-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-09-LB-0008-CC08 | I | Cable FROM PS5-03-SFMC-0011 TO PS5-09-LB-0008 |  | PS5-09-03 - HVAC for Generator Building | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0953 | PS5-25-BI-1101-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1101-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1101 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0954 | PS5-25-BI-1102-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1102-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1102 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0041 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-0955 | PS5-25-BI-1103-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1103-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1103 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0956 | PS5-25-BI-1104-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1104-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1104 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0957 | PS5-25-BI-1115-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1115-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1115 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0958 | PS5-25-BI-1174A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1174A-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1174A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with punch | Elizabeth | PULLING
T-00614-0959 | PS5-25-BI-1174B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1174B-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1174B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with punch | Elizabeth | PULLING
T-00614-0960 | PS5-25-BI-1174C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1174C-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1174C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0961 | PS5-25-BI-1201-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1201-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-1201 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0962 | PS5-25-BI-1274A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1274A-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1274A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0963 | PS5-25-BI-1274B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1274B-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1274B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0964 | PS5-25-BI-1274C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1274C-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-1274C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0965 | PS5-25-BI-1301-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1301-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1301 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0966 | PS5-25-BI-1302-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1302-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1302 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0967 | PS5-25-BI-1310-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1310-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1310 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with Punch | Elizabeth | PULLING | CPP-RFI-68-64-11-0067
T-00614-0968 | PS5-25-BI-1801A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1801A-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1801A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-0969 | PS5-25-BI-1801B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1801B-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1801B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0970 | PS5-25-BI-1801C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1801C-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1801C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0971 | PS5-25-BI-1802A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1802A-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1802A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0972 | PS5-25-BI-1802B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1802B-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1802B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0973 | PS5-25-BI-1802C-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1802C-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1802C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0974 | PS5-25-BI-1803A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803A-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0975 | PS5-25-BI-1803A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803A-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0976 | PS5-25-BI-1803B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803B-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0977 | PS5-25-BI-1803B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803B-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0978 | PS5-25-BI-1803C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803C-CC01 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0979 | PS5-25-BI-1803C-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-1803C-CC02 | I | Cable FROM PS5-25-IE-0001 TO PS5-25-BI-1803C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0980 | PS5-25-BI-2101-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2101-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-25-BI-2101 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0981 | PS5-25-BI-2102-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2102-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-25-BI-2102 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0982 | PS5-25-BI-2103-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2103-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2103 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0041 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-0983 | PS5-25-BI-2104-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2104-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-25-BI-2104 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0984 | PS5-25-BI-2105-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2105-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2105 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0985 | PS5-25-BI-2106-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2106-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2106 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0986 | PS5-25-BI-2108-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2108-CC01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-25-BI-2108 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0987 | PS5-25-BI-2109-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2109-CC01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-25-BI-2109 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0041 | 2026-05-06 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0988 | PS5-25-BI-2201-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2201-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-2201 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0989 | PS5-25-BI-2203-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2203-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-2203 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0041 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-0990 | PS5-25-BI-2205-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2205-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-2205 |  | PS5-25-01 - Export Pipeline Pig Receiver | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0991 | PS5-25-BI-2301-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2301-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2301 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
| PS5-25-BI-1801A-CC01 | TPX | PS5-25-BI-1801A-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1801B-CC01 | TPX | PS5-25-BI-1801B-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1801C-CC01 | TPX | PS5-25-BI-1801C-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1802A-CC02 | TPX | PS5-25-BI-1802A-CC02 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1802B-CC02 | TPX | PS5-25-BI-1802B-CC02 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1802C-CC02 | TPX | PS5-25-BI-1802C-CC02 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803A-CC01 | TPX | PS5-25-BI-1803A-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803A-CC02 | TPX | PS5-25-BI-1803A-CC02 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803B-CC01 | TPX | PS5-25-BI-1803B-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803B-CC02 | TPX | PS5-25-BI-1803B-CC02 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2103-CC01 | TPX | PS5-25-BI-2103-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2104-CC01 | TPX | PS5-25-BI-2104-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2105-CC01 | TPX | PS5-25-BI-2105-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2106-CC01 | TPX | PS5-25-BI-2106-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2108-CC01 | TPX | PS5-25-BI-2108-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2109-CC01 | TPX | PS5-25-BI-2109-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2201-CC01 | TPX | PS5-25-BI-2201-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2203-CC01 | TPX | PS5-25-BI-2203-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2301-CC01 | TPX | PS5-25-BI-2301-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2302-CC01 | TPX | PS5-25-BI-2302-CC01 | I |  |  |  | CPP-RFI-68-64-12-0046 | 2026-05-11 | Accepted | Elizabeth | TESTING
T-00614-0992 | PS5-25-BI-2302-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2302-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-25-BI-2302 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0993 | PS5-25-BI-2305-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2305-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2305 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-0994 | PS5-25-BI-2308-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2308-CC01 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-25-BI-2308 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0041 | 2026-05-06 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0995 | PS5-25-BI-2309-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2309-CC01 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-25-BI-2309 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-0996 | PS5-25-BI-2312-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2312-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2312 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0041 | 2026-05-06 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0997 | PS5-25-BI-2315-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2315-CC01 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2315 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0041 | 2026-05-06 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0998 | PS5-25-BI-2316-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-BI-2316-CC01 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-25-BI-2316 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-0999 | PS5-25-MXS-3101AA-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101AA-CJ01 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1000 | PS5-25-MXS-3101AB-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101AB-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1001 | PS5-25-MXS-3101BA-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101BA-CJ01 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1002 | PS5-25-MXS-3101BB-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101BB-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1003 | PS5-25-MXS-3101CA-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101CA-CJ01 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1004 | PS5-25-MXS-3101CB-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-MXS-3101CB-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1005 | PS5-25-PIT-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-PIT-0052-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-SDV-0052 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1006 | PS5-25-PIT-0071A-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-PIT-0071A-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-PIT-0071A |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1007 | PS5-25-PIT-0071B-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-PIT-0071B-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-PIT-0071B |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1008 | PS5-25-PIT-0071C-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-PIT-0071C-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-PIT-0071C |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1009 | PS5-25-SDV-0052-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-SDV-0052-CC01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-SDV-0052 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1010 | PS5-25-SDV-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-SDV-0052-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-SDV-0052 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted With Punch | Elizabeth | PULLING
T-00614-1011 | PS5-25-SHSR-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-SHSR-0052-CJ01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-25-SDV-0052 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1012 | PS5-25-SXS-0052-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-SXS-0052-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-SDV-0052 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1013 | PS5-25-SY-0052A-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-25-SY-0052A-CJ01 | I | Cable FROM PS5-01-LA-0001 TO PS5-25-SDV-0052 |  | PS5-25-07 - Export Pipeline Pig Launcher | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1014 | PS5-28-BI-1105-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-1105-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-28-BI-1105 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0041 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1015 | PS5-28-BI-1106-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-1106-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-28-BI-1106 |  | PS5-28-06 - Relief Drum and Pump | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1016 | PS5-28-BI-1114-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-1114-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-28-BI-1114 |  | PS5-28-04 - Closed Drain Drum and Pump 02 | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-1017 | PS5-28-BI-1303-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-1303-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-28-BI-1303 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1018 | PS5-28-BI-1307-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-1307-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-28-BI-1307 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1019 | PS5-28-BI-2304-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-BI-2304-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-28-BI-2304 |  | PS5-28-17 - Reinjection Pump | CPP-RFI-68-64-04-0038 | 2026-04-15 | Accepted with Punch | Elizabeth | PULLING
T-00614-1020 | PS5-28-HXA-1101-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-HXA-1101-CJ01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-28-HXA-1101 |  | PS5-28-03 - Closed Drain Drum and Pump 01 | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1021 | PS5-28-LB-8200-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-LB-8200-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-28-LB-8200 |  | PS5-28-11 - Open Drain Interceptor | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1022 | PS5-28-LB-8200-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-28-LB-8200-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-28-LB-8200 |  | PS5-28-11 - Open Drain Interceptor | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1023 | PS5-50-BI-1107-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-50-BI-1107-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-50-BI-1107 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1024 | PS5-50-IE-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-50-IE-0001-CC01 | I | Cable FROM PS5-04-PMC-0008 TO PS5-50-IE-0001 |  | PS5-50-01 - Water Well Submersible Pumps (3100) | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1025 | PS5-50-IE-0001-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-50-IE-0001-CC02 | I | Cable FROM PS5-04-PMC-0007 TO PS5-50-IE-0001 |  | PS5-50-01 - Water Well Submersible Pumps (3100) | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1026 | PS5-50-IE-0002-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-50-IE-0002-CC01 | I | Cable FROM PS5-04-PMC-0008 TO PS5-50-IE-0002 |  | PS5-50-02 - Water Well Submersible Pumps (3200) | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1027 | PS5-50-IE-0002-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-50-IE-0002-CC02 | I | Cable FROM PS5-04-PMC-0007 TO PS5-50-IE-0002 |  | PS5-50-02 - Water Well Submersible Pumps (3200) | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1028 | PS5-50-LIT-0001-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0001 TO PS5-50-LIT-0001 |  | PS5-50-01 - Water Well Submersible Pumps (3100) | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1029 | PS5-50-LIT-0002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0001 TO PS5-50-LIT-0002 |  | PS5-50-02 - Water Well Submersible Pumps (3200)
T-00614-1030 | PS5-53-BI-1108-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-53-BI-1108-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-53-BI-1108 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1031 | PS5-53-BI-1304-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-53-BI-1304-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-53-BI-1304 |  | PS5-53-01 - Utility Water / Storage Tank |  |  | Accepted with Punch /Accepted | Elizabeth | PULLING | CPP-RFI-68-64-11-0068 | Accepted With Comment
T-00614-1032 | PS5-53-LA-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-53-LA-0001-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-53-LA-0001 |  | PS5-53-04 - Water Treatment Purification Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1033 | PS5-53-LA-0001-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-53-LA-0001-CC02 | I | Cable FROM PS5-04-PMC-0002 TO PS5-53-LA-0001 |  | PS5-53-04 - Water Treatment Purification Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1034 | PS5-60-IE-0003A-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003A-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1035 | PS5-60-IE-0003A-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003A-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1036 | PS5-60-IE-0003A-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003A-CC23 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1037 | PS5-60-IE-0003A-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003A-CC24 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003A |  | PS5-60-02 - Power Gen Package A (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1038 | PS5-60-IE-0003B-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003B-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1039 | PS5-60-IE-0003B-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003B-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1040 | PS5-60-IE-0003B-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003B-CC23 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1041 | PS5-60-IE-0003B-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003B-CC24 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1042 | PS5-60-IE-0003C-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003C-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1043 | PS5-60-IE-0003C-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003C-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1044 | PS5-60-IE-0003C-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003C-CC23 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1045 | PS5-60-IE-0003C-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003C-CC24 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1046 | PS5-60-IE-0003D-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003D-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1047 | PS5-60-IE-0003D-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003D-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1048 | PS5-60-IE-0003D-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003D-CC23 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1049 | PS5-60-IE-0003D-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003D-CC24 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1050 | PS5-60-IE-0003E-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003E-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1051 | PS5-60-IE-0003E-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003E-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-1052 | PS5-60-IE-0003E-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003E-CC23 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1053 | PS5-60-IE-0003E-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003E-CC24 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1054 | PS5-60-IE-0003F-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003F-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1055 | PS5-60-IE-0003F-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003F-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1056 | PS5-60-IE-0003F-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003F-CC23 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1057 | PS5-60-IE-0003F-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003F-CC24 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1058 | PS5-60-IE-0003G-CC21 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003G-CC21 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1059 | PS5-60-IE-0003G-CC22 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003G-CC22 | I | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1060 | PS5-60-IE-0003G-CC23 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003G-CC23 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1061 | PS5-60-IE-0003G-CC24 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0003G-CC24 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1062 | PS5-60-IE-0004-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0004-CC08 | I | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-1063 | PS5-60-IE-0004-CC11 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0004-CC11 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1064 | PS5-60-IE-0004-CC12 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-IE-0004-CC12 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1065 | PS5-60-SEA-0001-CC18 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-60-SEA-0001-CC18 | I | Cable FROM PS5-03-SFMC-0009 TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1066 | PS5-61-IDH-3100A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100A-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1067 | PS5-61-IDH-3100A-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100A-CC02 | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1068 | PS5-61-IDH-3100A-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100A-CC03 | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1069 | PS5-61-IDH-3100B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100B-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1070 | PS5-61-IDH-3100B-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100B-CC02 | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-1071 | PS5-61-IDH-3100B-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100B-CC03 | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-1072 | PS5-61-IDH-3100C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100C-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-1073 | PS5-61-IDH-3100C-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-61-IDH-3100C-CC02 | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-1074 | PS5-61-IDH-3100C-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0006 TO PS5-61-IDH-3100C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1075 | PS5-71-BI-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-0001-CC01 | I | Cable FROM PS5-26-LA-0001 TO PS5-71-BI-0001 |  | PS5-71-02 - CFO Allocation Metering Package | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1076 | PS5-71-BI-0021-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-26-LA-0001 TO PS5-71-BI-0021 |  | PS5-71-02 - CFO Allocation Metering Package | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1077 | PS5-71-BI-0021-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-0021-CC02 | I | Cable FROM PS5-26-LA-0001 TO PS5-71-BI-0021 |  | PS5-71-02 - CFO Allocation Metering Package | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1078 | PS5-71-BI-1109-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1109-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1109 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0041 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1079 | PS5-71-BI-1110-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1110-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-71-BI-1110 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-1080 | PS5-71-BI-1111-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1111-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1111 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1081 | PS5-71-BI-1112-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1112-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1112 |  | PS5-71-17 - Diesel Fuel Distribution Header | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1082 | PS5-71-BI-1113-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1113-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1113 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1083 | PS5-71-BI-1116-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1116-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1116 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-1084 | PS5-71-BI-1117-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1117-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-71-BI-1117 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1085 | PS5-71-BI-1201-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | #N/A | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2101 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1086 | PS5-71-BI-1305-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1305-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-71-BI-1305 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0041 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1087 | PS5-71-BI-1306-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1306-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-71-BI-1306 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-1088 | PS5-71-BI-1308-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-1308-CC01 | I | Cable FROM PS5-03-SFMC-0001 TO PS5-71-BI-1308 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
| PS5-25-BI-2305-CC01 | TPX | PS5-25-BI-2305-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2308-CC01 | TPX | PS5-25-BI-2308-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2309-CC01 | TPX | PS5-25-BI-2309-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2312-CC01 | TPX | PS5-25-BI-2312-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2315-CC01 | TPX | PS5-25-BI-2315-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2316-CC01 | TPX | PS5-25-BI-2316-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-28-BI-1105-CC01 | TPX | PS5-28-BI-1105-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-28-BI-1303-CC01 | TPX | PS5-28-BI-1303-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-28-BI-1307-CC01 | TPX | PS5-28-BI-1307-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-50-BI-1107-CC01 | TPX | PS5-50-BI-1107-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-53-BI-1108-CC01 | TPX | PS5-53-BI-1108-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1109-CC01 | TPX | PS5-71-BI-1109-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1110-CC01 | TPX | PS5-71-BI-1110-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1116-CC01 | TPX | PS5-71-BI-1116-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1305-CC01 | TPX | PS5-71-BI-1305-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1306-CC01 | TPX | PS5-71-BI-1306-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2107-CC01 | TPX | PS5-71-BI-2107-CC01 | I |  |  |  | CPP-RFI-68-64-12-0048 | 2026-05-11 | Accepted | Elizabeth | TESTING
T-00614-1089 | PS5-71-BI-2107-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2107-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2107 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1090 | PS5-71-BI-2113-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2113-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-71-BI-2113 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1091 | PS5-71-BI-2114-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2114-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2114 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1092 | PS5-71-BI-2115-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2115-CC01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2115 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1093 | PS5-71-BI-2116-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2116-CC01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-71-BI-2116 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1094 | PS5-71-BI-2118-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2118-CC01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2118 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1095 | PS5-71-BI-2119-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2119-CC01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2119 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1096 | PS5-71-BI-2120-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2120-CC01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2120 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1097 | PS5-71-BI-2121-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2121-CC01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2121 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0043 | 2026-05-06 | Accepted with Punch | Elizabeth | PULLING
T-00614-1098 | PS5-71-BI-2122-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2122-CC01 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2122 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1099 | PS5-71-BI-2123-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2123-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2123 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1100 | PS5-71-BI-2124-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2124-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2124 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1101 | PS5-71-BI-2125-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2125-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2125 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
| PS5-60-BI-0001A-CC02 | TJX | PS5-60-BI-0001A-CC02 | I
| PS5-60-BI-0001B-CC02 | TJX | PS5-60-BI-0001B-CC02 | I
| PS5-60-BI-0003-CC03 | TJX | PS5-60-BI-0003-CC03 | I |  |  |  | CPP-RFI-68-64-12-0123 | 29-July-2026 | Acceptable | Ferdinand | Testing
| PS5-60-IE-0002A-CC01 | TJX | PS5-60-IE-0002A-CC01 | I |  |  |  | CPP-RFI-68-64-12-0124 | 2026-07-28 | open | Elizabeth | Testing
| PS5-60-IE-0002A-CC02 | TJX | PS5-60-IE-0002A-CC02 | I |  |  |  | CPP-RFI-68-64-12-0124 | 2026-07-28 | open | Elizabeth | Testing
| PS5-60-IE-0002A-CC03 | TJX | PS5-60-IE-0002A-CC03 | I |  |  |  | CPP-RFI-68-64-12-0124 | 2026-07-28 | open | Elizabeth | Testing
| PS5-60-IE-0002B-CC01 | TJX | PS5-60-IE-0002B-CC01 | I |  |  |  | CPP-RFI-68-64-12-0124 | 2026-07-28 | open | Elizabeth | Testing
| PS5-60-IE-0002B-CC02 | TJX | PS5-60-IE-0002B-CC02 | I |  |  |  | CPP-RFI-68-64-12-0124 | 2026-07-28 | open | Elizabeth | Testing
| PS5-60-IE-0002B-CC03 | TJX | PS5-60-IE-0002B-CC03 | I |  |  |  | CPP-RFI-68-64-12-0124 | 2026-07-28 | open | Elizabeth | Testing
| PS5-60-IH-0001A-CC01 | TJX | PS5-60-IH-0001A-CC01 | I |  |  |  | CPP-RFI-68-65-20-0039 | 2026-07-30 | Accepted | G K RAO | TESTING
| PS5-60-IH-0001A-CC02 | TJX | PS5-60-IH-0001A-CC02 | I |  |  |  | CPP-RFI-68-65-20-0039 | 2026-07-30 | Accepted | G K RAO | TESTING
| PS5-60-IH-0001B-CC01 | TJX | PS5-60-IH-0001B-CC01 | I |  |  |  | CPP-RFI-68-65-20-0039 | 2026-07-30 | Accepted | G K RAO | TESTING
| PS5-60-IH-0001B-CC02 | TJX | PS5-60-IH-0001B-CC02 | I |  |  |  | CPP-RFI-68-65-20-0039 | 2026-07-30 | Accepted | G K RAO | TESTING
| PS5-60-IH-0002-CC01 | TJX | PS5-60-IH-0002-CC01 | I |  |  |  | Double Tag |  |  |  | Testing
| PS5-60-IH-0002-CC02 | TJX | PS5-60-IH-0002-CC02 | I |  |  |  | Double Tag |  |  |  | Testing
| PS5-60-LA-0003-CC02 | TJX | PS5-60-LA-0003-CC02 | I |  |  |  | Double Tag |  |  |  | Testing
| PS5-60-LA-0003-CC03 | TJX | PS5-60-LA-0003-CC03 | I |  |  |  | Double Tag |  |  |  | Testing
| PS5-60-PIT-8113A-CC01 | TJX INSTRUMENT CABLE | PS5-60-PIT-8113A-CC01 | I |  |  |  | CPP-RFI-68-64-12-0130 | 2026-08-01 | OPEN | Bertus Wikael | Testing
| PS5-60-PIT-8113B-CC01 | TJX INSTRUMENT CABLE | PS5-60-PIT-8113B-CC01 | I |  |  |  | CPP-RFI-68-64-12-0130 | 2026-08-01 | OPEN | Bertus Wikael | Testing
| PS5-60-PIT-8114A-CC01 | TJX INSTRUMENT CABLE | #N/A | I |  |  |  | CPP-RFI-68-64-12-0130 | 2026-08-01 | OPEN | Bertus Wikael | Testing
| PS5-60-PIT-8114B-CC01 | TJX INSTRUMENT CABLE | #N/A | I |  |  |  | CPP-RFI-68-64-12-0130 | 2026-08-01 | OPEN | Bertus Wikael | Testing
| PS5-60-LA-0003-CX02 | TJX | PS5-60-LA-0003-CX02 | I
| PS5-60-BI-0001A-CC02 | CJX | PS5-60-BI-0001A-CC02 | I
| PS5-60-BI-0001B-CC02 | CJX | PS5-60-BI-0001B-CC02 | I
| PS5-60-BI-0003-CC03 | CJX | PS5-60-BI-0003-CC03 | I
| PS5-60-IE-0002A-CC01 | CJX | PS5-60-IE-0002A-CC01 | I
| PS5-60-IE-0002A-CC02 | CJX | PS5-60-IE-0002A-CC02 | I
| PS5-60-IE-0002A-CC03 | CJX | PS5-60-IE-0002A-CC03 | I
| PS5-60-IE-0002B-CC01 | CJX | PS5-60-IE-0002B-CC01 | I
| PS5-60-IE-0002B-CC02 | CJX | PS5-60-IE-0002B-CC02 | I
| PS5-60-IE-0002B-CC03 | CJX | PS5-60-IE-0002B-CC03 | I
| PS5-60-IH-0001A-CC01 | CJX | PS5-60-IH-0001A-CC01 | I
| PS5-60-IH-0001A-CC02 | CJX | PS5-60-IH-0001A-CC02 | I
| PS5-60-IH-0001B-CC01 | CJX | PS5-60-IH-0001B-CC01 | I
| PS5-60-IH-0001B-CC02 | CJX | PS5-60-IH-0001B-CC02 | I
| PS5-60-IH-0002-CC01 | CJX | PS5-60-IH-0002-CC01 | I
| PS5-60-IH-0002-CC02 | CJX | PS5-60-IH-0002-CC02 | I
| PS5-60-LA-0003-CC02 | CJX | PS5-60-LA-0003-CC02 | I
| PS5-60-LA-0003-CC03 | CJX | PS5-60-LA-0003-CC03 | I
| PS5-60-PIT-8113A-CC01 | CJX | PS5-60-PIT-8113A-CC01 | I
| PS5-60-PIT-8113B-CC01 | CJX | PS5-60-PIT-8113B-CC01 | I
| PS5-60-PIT-8114A-CC01 | CJX | #N/A | I
| PS5-60-PIT-8114B-CC01 | CJX | #N/A | I
| PS5-60-LA-0003-CX02 | CJX | PS5-60-LA-0003-CX02 | I
T-00614-1102 | PS5-71-BI-2306-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2306-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2306 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1103 | PS5-71-BI-2307-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2307-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2307 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-1104 | PS5-71-BI-2310-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2310-CC01 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-71-BI-2310 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1105 | PS5-71-BI-2313-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2313-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2313 |  | PS5-71-15 - Diesel Fuel Storage Tank
T-00614-1106 | PS5-71-BI-2314-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2314-CC01 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2314 |  | PS5-91-01 - Multicore cables & JB | CPP-RFI-68-64-04-0035 | 2026-05-09 | Accepted with Punch /Accepted | Elizabeth | PULLING
T-00614-1107 | PS5-71-BI-2317-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-BI-2317-CC01 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-71-BI-2317 |  | PS5-71-15 - Diesel Fuel Storage Tank | CPP-RFI-68-64-04-0054 | 2026-04-24 | Accepted with punch | Elizabeth | PULLING
T-00614-1108 | PS5-71-IN-0001-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0001-CC08 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1109 | PS5-71-IN-0001-CC09 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0001-CC09 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1110 | PS5-71-IN-0001-CC10 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0001-CC10 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1111 | PS5-71-IN-0002-CC05 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0002-CC05 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-RFI-68-64-04-0038 | 2026-04-17 | Accepted with Punch | Elizabeth | PULLING
T-00614-1112 | PS5-71-IN-0002-CC06 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0002-CC06 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-RFI-68-64-04-0038 | 2026-04-17 | Accepted with Punch | Elizabeth | PULLING
T-00614-1113 | PS5-71-IN-0002-CC07 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0002-CC07 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPP-RFI-68-64-04-0038 | 2026-04-17 | Accepted with Punch | Elizabeth | PULLING
T-00614-1114 | PS5-71-IN-0003-CC05 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0003-CC05 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1115 | PS5-71-IN-0003-CC06 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0003-CC06 | I | Cable FROM PS5-03-SFMC-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1116 | PS5-71-IN-0003-CC07 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0003-CC07 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1117 | PS5-71-IN-0004A-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004A-CC08 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1118 | PS5-71-IN-0004A-CC09 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004A-CC09 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1119 | PS5-71-IN-0004A-CC12 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004A-CC12 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1120 | PS5-71-IN-0004B-CC08 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004B-CC08 | I | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1121 | PS5-71-IN-0004B-CC09 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004B-CC09 | I | Cable FROM PS5-03-SFMC-0003 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1122 | PS5-71-IN-0004B-CC12 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-IN-0004B-CC12 | I | Cable FROM PS5-03-SFMC-0005 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1123 | PS5-71-TIT-2403A-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-TIT-2403A-CJ01 | I | Cable FROM PS5-71-IE-0001 TO PS5-71-TIT-2403A |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1124 | PS5-71-TIT-2403B-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-71-TIT-2403B-CJ01 | I | Cable FROM PS5-71-IE-0002 TO PS5-71-TIT-2403B |  | PS5-71-01 - CFO Storage Tank Feed Heater | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1125 | PS5-74-LB-5101-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-74-LB-5101-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-74-LB-5101 |  | PS5-74-02 - N2 Generation Skid (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
| PS5-03-BI-1502-CC01 | TPX | PS5-03-BI-1502-CC01 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1510-CC01 | TPX | PS5-03-BI-1510-CC01 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2501-CC01 | TPX | PS5-03-BI-2501-CC01 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2505-CC01 | TPX | PS5-03-BI-2505-CC01 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-53-LA-0001-CC01 | TPX | PS5-53-LA-0001-CC01 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-53-LA-0001-CC02 | TPX | PS5-53-LA-0001-CC02 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003C-CC23 | TPX | PS5-60-IE-0003C-CC23 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003E-CC23 | TPX | PS5-60-IE-0003E-CC23 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003F-CC23 | TPX | PS5-60-IE-0003F-CC23 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-71-BI-1308-CC01 | TPX | PS5-71-BI-1308-CC01 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2307-CC01 | TPX | PS5-71-BI-2307-CC01 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2317-CC01 | TPX | PS5-71-BI-2317-CC01 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-74-LB-5101-CC01 | TPX | PS5-74-LB-5101-CC01 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
| PS5-74-LB-5101-CJ01 | TPX | PS5-74-LB-5101-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0063 | 2026-06-16 | Accepted | Elizabeth | TESTING
T-00614-1126 | PS5-74-LB-5101-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-74-LB-5101-CJ01 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-74-LB-5101 |  | PS5-74-02 - N2 Generation Skid (UCP) | CPP-RFI-68-64-04-0036 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1127 | PS5-75-BI-1177-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-1177-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-75-BI-1177 |  | PS5-75-02 - Biocide Injection Package | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1128 | PS5-75-BI-1178-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-1178-CC01 | I | Cable FROM PS5-04-PMC-0002 TO PS5-75-BI-1178 |  | PS5-75-03 - Corrosion Inhibitor Injection Package | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1129 | PS5-75-BI-1371-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-1371-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-75-BI-1371 |  | PS5-75-02 - Biocide Injection Package | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1130 | PS5-75-BI-1372-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-1372-CC01 | I | Cable FROM PS5-03-SFMC-0002 TO PS5-75-BI-1372 |  | PS5-75-03 - Corrosion Inhibitor Injection Package | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1131 | PS5-75-BI-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-0001-CC01 | I | Cable FROM PS5-04-PMC-0001 TO PS5-75-BI-0001 |  | PS5-75-01 - DRA Injection Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-1132 | PS5-75-BI-0002-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-0002-CC01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-75-BI-0002 |  | PS5-75-01 - DRA Injection Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-1133 | PS5-75-BI-0002-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-0002-CC02 | I | Cable FROM PS5-04-PMC-0006 TO PS5-75-BI-0002 |  | PS5-75-01 - DRA Injection Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
| PS5-01-BI-0002-CC01 | TPX | PS5-01-BI-0002-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-01-BI-0003-CC01 | TPX | PS5-01-BI-0003-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-01-BI-2520-CC01 | TPX | PS5-01-BI-2520-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-01-LIT-4201-CJ01 | TPX | PS5-01-LIT-4201-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-01-PIT-0015-CJ01 | TPX | PS5-01-PIT-0015-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1511-CC01 | TPX | PS5-03-BI-1511-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-03-BI-1512-CC01 | TPX | PS5-03-BI-1512-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2508-CC01 | TPX | PS5-03-BI-2508-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-03-NMR-0801-CJ01 | TPX | PS5-03-NMR-0801-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-03-NMR-0802-CJ01 | TPX | PS5-03-NMR-0802-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-03-NMR-0803-CJ01 | TPX | PS5-03-NMR-0803-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-03-NMR-0804-CJ01 | TPX | PS5-03-NMR-0804-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-03-RMAC-0824-CJ01 | TPX | PS5-03-RMAC-0824-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-03-SEA-0003-CC01 | TPX | PS5-03-SEA-0003-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-09-BI-2503-CC01 | TPX | PS5-09-BI-2503-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-09-LB-0008-CC03 | TPX | PS5-09-LB-0008-CC03 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-09-LB-0008-CC07 | TPX | PS5-09-LB-0008-CC07 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-09-LB-0008-CC08 | TPX | PS5-09-LB-0008-CC08 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-28-BI-1114-CC01 | TPX | PS5-28-BI-1114-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003D-CC24 | TPX | PS5-60-IE-0003D-CC24 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003E-CC24 | TPX | PS5-60-IE-0003E-CC24 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003F-CC22 | TPX | PS5-60-IE-0003F-CC22 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003F-CC24 | TPX | PS5-60-IE-0003F-CC24 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003G-CC21 | TPX | PS5-60-IE-0003G-CC21 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0003G-CC22 | TPX | PS5-60-IE-0003G-CC22 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100B-CC02 | TPX | PS5-61-IDH-3100B-CC02 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100B-CC03 | TPX | PS5-61-IDH-3100B-CC03 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100C-CC01 | TPX | PS5-61-IDH-3100C-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-61-IDH-3100C-CC02 | TPX | PS5-61-IDH-3100C-CC02 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-75-BI-0001-CC01 | TPX | PS5-75-BI-0001-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-75-BI-0002-CC01 | TPX | PS5-75-BI-0002-CC01 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
| PS5-75-BI-0002-CC03 | TPX | PS5-75-BI-0002-CC03 | I |  |  |  | CPP-RFI-68-64-12-0056 | 2026-05-31 | Accepted | Elizabeth | TESTING
T-00614-1134 | PS5-75-BI-0002-CC03 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-BI-0002-CC03 | I | Cable FROM PS5-03-SFMC-0006 TO PS5-75-BI-0002 |  | PS5-75-01 - DRA Injection Package | CPP-RFI-68-64-04-0049 | 2026-05-20 | Accepted with Punch | Elizabeth | PULLING
T-00614-1135 | PS5-75-MOV-0001-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-MOV-0001-CC01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-75-MOV-0001 |  | PS5-28-07 - Open Drains (OD2) | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1136 | PS5-75-MOV-0001-CC02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-75-MOV-0001-CC02 | I | Cable FROM PS5-04-PMC-0003 TO PS5-75-MOV-0001 |  | PS5-28-07 - Open Drains (OD2) | CPP-RFI-68-64-04-0037 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1137 | PS5-79-IG-0001-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0001-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0001 |  | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1138 | PS5-79-IG-0002-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0002-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0002 |  | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1139 | PS5-79-IG-0003-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0003-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0003 |  | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1140 | PS5-79-IG-0004-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0004-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0004 |  | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1141 | PS5-79-IG-0005-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0005-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0005 |  | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1142 | PS5-79-IG-0006-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0006-CJ01 | I | Cable FROM PS5-04-PMC-0003 TO PS5-79-XA-0006 |  | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1143 | PS5-79-IG-0007-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0007-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0007 |  | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1144 | PS5-79-IG-0008-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0008-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0008 |  | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
| PS5-01-BI-0001-CC01 | TPX | PS5-01-BI-0001-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-60-BI-0001A-CC02 | TPX | PS5-60-BI-0001A-CC02 | I |  |  |  | CPP-RFI-68-64-12-0123 | 29-July-2026 | Acceptable | Ferdinand | Testing
| PS5-60-BI-0001B-CC02 | TPX | PS5-60-BI-0001B-CC02 | I |  |  |  | CPP-RFI-68-64-12-0123 | 29-July-2026 | Acceptable | Ferdinand | Testing
| PS5-60-IH-0002-CC01 | TJX | PS5-60-IH-0002-CC01 | I |  |  |  | CPP-RFI-68-64-12-0128 | 01-August-2026 | Open | Ferdinand | Testing
| PS5-60-IH-0002-CC02 | TJX | PS5-60-IH-0002-CC02 | I |  |  |  | CPP-RFI-68-64-12-0128 | 01-August-2026 | Open | Ferdinand | Testing
| PS5-60-LA-0003-CC02 | TJX | PS5-60-LA-0003-CC02 | I |  |  |  | CPP-RFI-68-64-12-0128 | 01-August-2026 | Open | Ferdinand | Testing
| PS5-60-LA-0003-CC03 | TJX | PS5-60-LA-0003-CC03 | I |  |  |  | CPP-RFI-68-64-12-0128 | 01-August-2026 | Open | Ferdinand | Testing
| PS5-01-BI-0004-CC01 | TPX | PS5-01-BI-0004-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-BI-0005-CC01 | TPX | PS5-01-BI-0005-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-BI-0006-CC01 | TPX | PS5-01-BI-0006-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-BI-1571-CC01 | TPX | PS5-01-BI-1571-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-BI-2571A-CC01 | TPX | PS5-01-BI-2571A-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-BI-2571B-CC01 | TPX | PS5-01-BI-2571B-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0002A-CC01 | TPX | PS5-01-IE-0002A-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0002A-CC02 | TPX | PS5-01-IE-0002A-CC02 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0002B-CC01 | TPX | PS5-01-IE-0002B-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0002B-CC02 | TPX | PS5-01-IE-0002B-CC02 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0009A-CC01 | TPX | PS5-01-IE-0009A-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-IE-0009B-CC01 | TPX | PS5-01-IE-0009B-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-PIT-0014-CJ01 | TPX | PS5-01-PIT-0014-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-PIT-0016-CJ01 | TPX | PS5-01-PIT-0016-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-01-PIT-0017-CJ01 | TPX | PS5-01-PIT-0017-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-03-BI-2502-CC01 | TPX | PS5-03-BI-2502-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-03-SEA-0002-CC01 | TPX | PS5-03-SEA-0002-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-05-BI-0002-CC11 | TPX | PS5-05-BI-0002-CC11 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-05-BI-0002-CC12 | TPX | PS5-05-BI-0002-CC12 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803C-CC01 | TPX | PS5-25-BI-1803C-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-25-BI-1803C-CC02 | TPX | PS5-25-BI-1803C-CC02 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2101-CC01 | TPX | PS5-25-BI-2101-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2102-CC01 | TPX | PS5-25-BI-2102-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-25-BI-2205-CC01 | TPX | PS5-25-BI-2205-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-25-PIT-0052-CJ01 | TPX | PS5-25-PIT-0052-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-25-PIT-0071A-CJ01 | TPX | PS5-25-PIT-0071A-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-25-PIT-0071B-CJ01 | TPX | PS5-25-PIT-0071B-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-25-PIT-0071C-CJ01 | TPX | PS5-25-PIT-0071C-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-25-SDV-0052-CC01 | TPX | PS5-25-SDV-0052-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-50-IE-0002-CC01 | TPX | PS5-50-IE-0002-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-50-IE-0002-CC02 | TPX | PS5-50-IE-0002-CC02 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0004-CC11 | TPX | PS5-60-IE-0004-CC11 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-60-IE-0004-CC12 | TPX | PS5-60-IE-0004-CC12 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-60-SEA-0001-CC18 | TPX | PS5-60-SEA-0001-CC18 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2118-CC01 | TPX | PS5-71-BI-2118-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2119-CC01 | TPX | PS5-71-BI-2119-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2120-CC01 | TPX | PS5-71-BI-2120-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-71-BI-2121-CC01 | TPX | PS5-71-BI-2121-CC01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0001-CC08 | TPX | PS5-71-IN-0001-CC08 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0001-CC09 | TPX | PS5-71-IN-0001-CC09 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0001-CC10 | TPX | PS5-71-IN-0001-CC10 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0003-CC05 | TPX | PS5-71-IN-0003-CC05 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0003-CC06 | TPX | PS5-71-IN-0003-CC06 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-71-IN-0003-CC07 | TPX | PS5-71-IN-0003-CC07 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0006-CJ01 | TPX | PS5-79-IG-0006-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0007-CJ01 | TPX | PS5-79-IG-0007-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0008-CJ01 | TPX | PS5-79-IG-0008-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
| PS5-79-IG-0009-CJ01 | TPX | PS5-79-IG-0009-CJ01 | I |  |  |  | CPP-RFI-68-64-12-0055 | 2026-05-29 | Accepted | Elizabeth | TESTING
T-00614-1145 | PS5-79-IG-0009-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0009-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0009 |  | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1146 | PS5-79-IG-0010-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0010-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0010 |  | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1147 | PS5-79-IG-0011-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0011-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0011 |  | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1148 | PS5-79-IG-0012-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-79-IG-0012-CJ01 | I | Cable FROM PS5-04-PMC-0005 TO PS5-79-XA-0012 |  | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1149 | PS5-83-EHO-0001A-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001A-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-83-EHO-0001A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1150 | PS5-83-EHO-0001A-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001A-CJ01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-83-EHO-0001A |  | PS5-25-02 - Crude Oil Export Pump A | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1151 | PS5-83-EHO-0001B-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001B-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-83-EHO-0001B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1152 | PS5-83-EHO-0001B-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001B-CJ01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-83-EHO-0001B |  | PS5-25-03 - Crude Oil Export Pump B | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1153 | PS5-83-EHO-0001C-CC01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001C-CC01 | I | Cable FROM PS5-03-SFMC-0010 TO PS5-83-EHO-0001C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00614-1154 | PS5-83-EHO-0001C-CJ01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PS5-83-EHO-0001C-CJ01 | I | Cable FROM PS5-04-PMC-0006 TO PS5-83-EHO-0001C |  | PS5-25-04 - Crude Oil Export Pump C | CPP-RFI-68-64-04-0038 | 2026-04-16 | Accepted with Punch | Elizabeth | PULLING
T-00163-0440 | PS5-08-01LS-0817 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0441 | PS5-08-01LS-0818 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker (including LTD) |  | PS5-08-01 - PAGA
T-00163-0442 | PS5-08-01LS-0819 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable weatherproof Horn Speaker (including LTD) |  | PS5-08-01 - PAGA
T-00163-0443 | PS5-08-01LS-0820 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0444 | PS5-08-01LS-0821 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0445 | PS5-08-01LS-0822 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0446 | PS5-08-01LS-0823 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0447 | PS5-08-01LS-0824 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable safe area addressable ceiling speaker |  | PS5-08-01 - PAGA
T-00163-0448 | PS5-08-01LS-0825 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0449 | PS5-08-01LS-0826 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0450 | PS5-08-01LS-0827 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0451 | PS5-08-01LS-0828 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0452 | PS5-08-01LS-0829 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0453 | PS5-08-01LS-0830 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0454 | PS5-08-01LS-0831 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0455 | PS5-08-01LS-0832 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0456 | PS5-08-01LS-0833 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00163-0457 | PS5-08-01LS-0834 | CIX01 - PA/GA loudspeakers (40,25,8,6W) + JB | #N/A | T | Loop 8 - Adressable Safe area addressable wall-mounted speaker |  | PS5-08-01 - PAGA
T-00164-0020 | PS5-08-01FB-0901 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0021 | PS5-08-01FB-0902 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0022 | PS5-08-01FB-0903 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0023 | PS5-08-01FB-0904 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0024 | PS5-08-01FB-0905 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0025 | PS5-08-01FB-0906 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0026 | PS5-08-01FB-0907 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0027 | PS5-08-01FB-0908 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0028 | PS5-08-01FB-0909 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0029 | PS5-08-01FB-0910 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0030 | PS5-08-01FB-0911 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0031 | PS5-08-01FB-0912 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0032 | PS5-08-01FB-0913 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 9 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0033 | PS5-08-01FB-1001 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0034 | PS5-08-01FB-1002 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0035 | PS5-08-01FB-1003 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0036 | PS5-08-01FB-1004 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0037 | PS5-08-01FB-1005 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0038 | PS5-08-01FB-1006 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0039 | PS5-08-01FB-1007 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0040 | PS5-08-01FB-1008 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0041 | PS5-08-01FB-1009 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0042 | PS5-08-01FB-1010 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0043 | PS5-08-01FB-1011 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0044 | PS5-08-01FB-1012 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0045 | PS5-08-01FB-1013 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 10 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0046 | PS5-08-01FB-1101 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 11 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0047 | PS5-08-01FB-1102 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 11 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0048 | PS5-08-01FB-1103 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 11 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0049 | PS5-08-01FB-1201 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 12 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0050 | PS5-08-01FB-1202 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 12 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00164-0051 | PS5-08-01FB-1203 | CIX02 - PA/GA flashing beacon + JB | #N/A | T | Loop 12 - SAFE AREA FLASHING BEACON |  | PS5-08-01 - PAGA
T-00165-0014 | PS5-08-01OC-0001 | CIX03 - P.A. Access and Override control unit | #N/A | T | OVERRIDE CONTROL UNIT (OCU) - Primary muster point |  | PS5-08-01 - PAGA
T-00165-0015 | PS5-08-01OC-0002 | CIX03 - P.A. Access and Override control unit | #N/A | T | OVERRIDE CONTROL UNIT (OCU) - Secondary muster point |  | PS5-08-01 - PAGA
T-00165-0016 | PS5-08-01PA-1201 | CIX03 - P.A. Access and Override control unit | #N/A | T | VIRTUAL PC PAGA ACCESS UNIT |  | PS5-08-01 - PAGA
T-00165-0017 | PS5-08-01PA-1501 | CIX03 - P.A. Access and Override control unit | #N/A | T | VIRTUAL PC PAGA ACCESS UNIT |  | PS5-08-01 - PAGA
T-00166-0004 | PS5-08-01MP-0001 | CIX04 - PA/GA Central System and Marshalling Cabinet | #N/A | T | Outdoor Marshalling enclosure (IDF) |  | PS5-08-01 - PAGA
T-00170-0494 | PS5-08-03FB-0101 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Safe Area FB+Sounder Outdoor 230Vca |  | PS5-08-03 - Telephone
T-00170-0495 | PS5-08-03FB-0001 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Safe Area FB+Sounder Outdoor 230Vca |  | PS5-08-03 - Telephone
T-00170-0496 | PS5-08-03FB-0002 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Safe Area FB+Sounder Outdoor 230Vca |  | PS5-08-03 - Telephone
T-00170-0497 | PS5-08-03FB-0003 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Safe Area FB+Sounder Outdoor 230Vca |  | PS5-08-03 - Telephone
T-00170-0498 | PS5-08-03FB-0004 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Safe Area FB+Sounder Outdoor 230Vca |  | PS5-08-03 - Telephone
T-00170-0499 | PS5-08-03FB-0103 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Safe Area FB+Sounder Outdoor 230Vca |  | PS5-08-03 - Telephone
T-00170-0500 | PS5-08-03FB-0102 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Safe Area FB+Sounder Outdoor 230Vca |  | PS5-08-03 - Telephone
T-00170-0501 | PS5-08-03HO-0001 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Accoustic Hood |  | PS5-08-03 - Telephone
T-00170-0502 | PS5-08-03HO-0002 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Accoustic Hood |  | PS5-08-03 - Telephone
T-00170-0503 | PS5-08-03HO-0003 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Accoustic Hood |  | PS5-08-03 - Telephone
T-00170-0504 | PS5-08-03HO-0004 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Accoustic Hood |  | PS5-08-03 - Telephone
T-00170-0505 | PS5-08-03HO-0103 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Accoustic Hood |  | PS5-08-03 - Telephone
T-00170-0506 | PS5-08-03HO-0101 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Accoustic Hood |  | PS5-08-03 - Telephone
T-00170-0507 | PS5-08-03HO-0102 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Accoustic Hood |  | PS5-08-03 - Telephone
T-00170-0508 | PS5-08-03TP-0001 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00170-0509 | PS5-08-03TP-0002 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00170-0510 | PS5-08-03TP-0003 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00170-0511 | PS5-08-03TP-0004 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00170-0512 | PS5-08-03TP-0103 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00170-0513 | PS5-08-03TP-0101 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00170-0514 | PS5-08-03TP-0102 | CIX08 - Telephone Hood Eex w / Telephone Beacon & Sounder | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00171-10676 | PS5-04-PNC-0001-CA94 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-04-PSC-0001 TO PS5-04-PNC-0001 |  | PS5-04-03 - 33kV ICSS System
T-00171-10677 | PS5-04-PNC-0001-CA95 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-04-PSC-0001 TO PS5-04-PNC-0001 |  | PS5-04-03 - 33kV ICSS System
T-00171-10678 | PS5-08-13CB-1001-CA24 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-13CB-1001 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00171-4342 | PS5-60-IE-0003B-CA02 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0003B-CA02 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00171-4343 | PS5-60-IE-0003B-CA03 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0003B-CA03 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00171-4344 | PS5-60-IE-0003B-CA04 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0003B-CA04 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00171-4345 | PS5-60-IE-0003B-CA05 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0003B-CA05 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP)
T-00171-4346 | PS5-60-IE-0003C-CA02 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0003C-CA02 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00171-4347 | PS5-60-IE-0003C-CA03 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0003C-CA03 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00171-4348 | PS5-60-IE-0003C-CA04 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0003C-CA04 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00171-4349 | PS5-60-IE-0003C-CA05 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0003C-CA05 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP)
T-00171-4350 | PS5-60-IE-0003D-CA02 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0003D-CA02 | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00171-4351 | PS5-60-IE-0003D-CA03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00171-4352 | PS5-60-IE-0003D-CA04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00171-4353 | PS5-60-IE-0003D-CA05 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP)
T-00171-4354 | PS5-60-IE-0003E-CA02 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0003E-CA02 | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00171-4355 | PS5-60-IE-0003E-CA03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00171-4356 | PS5-60-IE-0003E-CA04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00171-4357 | PS5-60-IE-0003E-CA05 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00171-4358 | PS5-60-IE-0003F-CA02 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0003F-CA02 | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00171-4359 | PS5-60-IE-0003F-CA03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00171-4360 | PS5-60-IE-0003F-CA04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00171-4361 | PS5-60-IE-0003F-CA05 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00171-4362 | PS5-60-IE-0003G-CA03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00171-4363 | PS5-60-IE-0003G-CA04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00171-4364 | PS5-60-IE-0003G-CA05 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00171-4365 | PS5-60-IE-0004-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0004-CA01 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00171-4366 | PS5-60-IE-0004-CA07 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0004-CA07 | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00171-4367 | PS5-60-IE-0004-CA08 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0004-CA08 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00171-4368 | PS5-60-IE-0004-CA14 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0004-CA14 | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00171-4369 | PS5-60-IE-0004-CA15 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0004-CA15 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00171-4370 | PS5-60-IE-0004-CA21 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IE-0004-CA21 | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP
T-00171-4371 | PS5-60-IH-0001A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IH-0001A-CA01 | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs
T-00171-4372 | PS5-60-IH-0001B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IH-0001B-CA01 | T | Cable FROM PS5-60-IE-0001B TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs
T-00171-4373 | PS5-60-IH-0001C-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IH-0001C-CA01 | T | Cable FROM PS5-60-IE-0001C TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs
T-00171-4374 | PS5-60-IH-0001D-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IH-0001D-CA01 | T | Cable FROM PS5-60-IE-0001D TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs
T-00171-4375 | PS5-60-IH-0001E-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IH-0001E-CA01 | T | Cable FROM PS5-60-IE-0001E TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00171-4376 | PS5-60-IH-0001F-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IH-0001F-CA01 | T | Cable FROM PS5-60-IE-0001F TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00171-4377 | PS5-60-IH-0001G-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IH-0001G-CA01 | T | Cable FROM PS5-60-IE-0001G TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00171-4378 | PS5-60-IN-0001A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IN-0001A-CA01 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A
T-00171-4379 | PS5-60-IN-0001B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IN-0001B-CA01 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B
T-00171-4380 | PS5-60-IN-0001C-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IN-0001C-CA01 | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C
T-00171-4381 | PS5-60-IN-0001D-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IN-0001D-CA01 | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D
T-00171-4382 | PS5-60-IN-0001E-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IN-0001E-CA01 | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E
T-00171-4383 | PS5-60-IN-0001F-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IN-0001F-CA01 | T | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F
T-00171-4384 | PS5-60-IN-0001G-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IN-0001G-CA01 | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G
T-00171-4385 | PS5-60-IN-0002A-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IN-0002A-CA01 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00171-4386 | PS5-60-IN-0002B-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-60-IN-0002B-CA01 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00171-4387 | PS5-60-IN-0002C-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00171-4388 | PS5-60-IN-0002D-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00171-4389 | PS5-60-IN-0002E-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00171-4390 | PS5-60-IN-0002F-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00171-4391 | PS5-60-IN-0002G-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00171-4392 | PS5-60-LA-0002B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00171-4393 | PS5-60-LA-0002B-CA02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00171-4394 | PS5-60-LA-0002B-CA03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00171-4395 | PS5-60-LA-0002B-CA04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00171-4396 | PS5-60-LA-0002B-CA05 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00171-4397 | PS5-60-LA-0002B-CA06 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D
T-00171-4398 | PS5-60-LA-0002C-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00171-4399 | PS5-60-LA-0002C-CA02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00171-4400 | PS5-60-LA-0002C-CA03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00171-4401 | PS5-60-LA-0002C-CA04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00171-4402 | PS5-60-LA-0002C-CA05 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00171-4403 | PS5-60-LA-0002C-CA06 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00171-4404 | PS5-60-SEA-0001-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00171-4405 | PS5-71-IN-0001-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP)
T-00171-4406 | PS5-71-IN-0001-CA11 | CIX09 - Telecom cable power / Control / Multicore | PS5-71-IN-0001-CA11 | T | Cable FROM PS5-60-IE-0003A TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP)
T-00171-4407 | PS5-71-IN-0002-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP)
T-00171-4408 | PS5-71-IN-0003-CA01 | CIX09 - Telecom cable power / Control / Multicore | PS5-71-IN-0003-CA01 | T | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP)
T-00171-4409 | PS5-71-IN-0004A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00171-4410 | PS5-71-IN-0004B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00171-7728 | PS5-08-01BT-0001-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01BT-0001 |  | PS5-08-01 - PAGA
T-00171-7729 | PS5-08-01BT-0001-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01OC-0001 TO PS5-08-01BT-0001 |  | PS5-08-01 - PAGA
T-00171-7730 | PS5-08-01BT-0002-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1202 TO PS5-08-01BT-0002 |  | PS5-08-01 - PAGA
T-00171-7731 | PS5-08-01BT-0002-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01OC-0001 TO PS5-08-01BT-0002 |  | PS5-08-01 - PAGA
T-00171-7732 | PS5-08-01BT-0003-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0102 TO PS5-08-01BT-0003 |  | PS5-08-01 - PAGA
T-00171-7733 | PS5-08-01BT-0003-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01OC-0002 TO PS5-08-01BT-0003 |  | PS5-08-01 - PAGA
T-00171-7734 | PS5-08-01BT-0004-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0201 TO PS5-08-01BT-0004 |  | PS5-08-01 - PAGA
T-00171-7735 | PS5-08-01BT-0004-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01OC-0002 TO PS5-08-01BT-0004 |  | PS5-08-01 - PAGA
T-00171-7736 | PS5-08-01BT-1201-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-01BT-1201 |  | PS5-08-01 - PAGA
T-00171-7737 | PS5-08-01BT-1201-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1201 |  | PS5-08-01 - PAGA
T-00171-7738 | PS5-08-01BT-1201-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01BT-1201 |  | PS5-08-01 - PAGA
T-00171-7739 | PS5-08-01BT-1201-CR03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1203 TO PS5-08-01BT-1201 |  | PS5-08-01 - PAGA
T-00171-7740 | PS5-08-01BT-1202-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-01BT-1202 |  | PS5-08-01 - PAGA
T-00171-7741 | PS5-08-01BT-1202-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1202 |  | PS5-08-01 - PAGA
T-00171-7742 | PS5-08-01BT-1202-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1202 |  | PS5-08-01 - PAGA
T-00171-7743 | PS5-08-01BT-1202-CR03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1203 TO PS5-08-01BT-1202 |  | PS5-08-01 - PAGA
T-00171-7744 | PS5-08-01BT-1203-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1203 |  | PS5-08-01 - PAGA
T-00171-7745 | PS5-08-01BT-1203-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1203 |  | PS5-08-01 - PAGA
T-00171-7746 | PS5-08-01BT-1203-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-01BT-1203 |  | PS5-08-01 - PAGA
T-00171-7747 | PS5-08-01BT-1203-CN02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-01BT-1203 |  | PS5-08-01 - PAGA
T-00171-7748 | PS5-08-01BT-1501-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0307 TO PS5-08-01BT-1501 |  | PS5-08-01 - PAGA
T-00171-7749 | PS5-08-01BT-1501-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1503 TO PS5-08-01BT-1501 |  | PS5-08-01 - PAGA
T-00171-7750 | PS5-08-01BT-1502-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0405 TO PS5-08-01BT-1502 |  | PS5-08-01 - PAGA
T-00171-7751 | PS5-08-01BT-1502-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1503 TO PS5-08-01BT-1502 |  | PS5-08-01 - PAGA
T-00171-7752 | PS5-08-01BT-1503-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1503 |  | PS5-08-01 - PAGA
T-00171-7753 | PS5-08-01BT-1503-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1503 |  | PS5-08-01 - PAGA
T-00171-7754 | PS5-08-01BT-1503-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-01BT-1503 |  | PS5-08-01 - PAGA
T-00171-7755 | PS5-08-01BT-1503-CN02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-01BT-1503 |  | PS5-08-01 - PAGA
T-00171-7756 | PS5-08-01BT-1601-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0720 TO PS5-08-01BT-1601 |  | PS5-08-01 - PAGA
T-00171-7757 | PS5-08-01BT-1601-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1601 |  | PS5-08-01 - PAGA
T-00171-7758 | PS5-08-01BT-1602-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-0002 TO PS5-08-01BT-1602 |  | PS5-08-01 - PAGA
T-00171-7759 | PS5-08-01BT-1602-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1602 |  | PS5-08-01 - PAGA
T-00171-7760 | PS5-08-01BT-1901-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1903 TO PS5-08-01BT-1901 |  | PS5-08-01 - PAGA
T-00171-7761 | PS5-08-01BT-1901-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1901 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0034 | 2026-07-01 | Open | Ferdinand | Pulling
T-00171-7762 | PS5-08-01BT-1902-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1904 TO PS5-08-01BT-1902 |  | PS5-08-01 - PAGA
T-00171-7763 | PS5-08-01BT-1902-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1902 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00171-7764 | PS5-08-01BT-1903-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1903 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00171-7765 | PS5-08-01BT-1904-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1904 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00171-7766 | PS5-08-01LS-0101-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0101 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00171-7767 | PS5-08-01LS-0102-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0101 TO PS5-08-01LS-0102 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7768 | PS5-08-01LS-0103-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01OC-0002 TO PS5-08-01LS-0103 |  | PS5-08-01 - PAGA
T-00171-7769 | PS5-08-01LS-0104-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-0003 TO PS5-08-01LS-0104 |  | PS5-08-01 - PAGA
T-00171-7770 | PS5-08-01LS-0105-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0104 TO PS5-08-01LS-0105 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7771 | PS5-08-01LS-0106-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0105 TO PS5-08-01LS-0106 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7772 | PS5-08-01LS-0107-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0106 TO PS5-08-01LS-0107 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7773 | PS5-08-01LS-0108-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0107 TO PS5-08-01LS-0108 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7774 | PS5-08-01LS-0109-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0108 TO PS5-08-01LS-0109 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7775 | PS5-08-01LS-0110-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0109 TO PS5-08-01LS-0110 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7776 | PS5-08-01LS-0110-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0110 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7777 | PS5-08-01LS-0201-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0201 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00171-7778 | PS5-08-01LS-0202-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01OC-0002 TO PS5-08-01LS-0202 |  | PS5-08-01 - PAGA
T-00171-7779 | PS5-08-01LS-0203-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-0004 TO PS5-08-01LS-0203 |  | PS5-08-01 - PAGA
T-00171-7780 | PS5-08-01LS-0204-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0203 TO PS5-08-01LS-0204 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7781 | PS5-08-01LS-0205-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0204 TO PS5-08-01LS-0205 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7782 | PS5-08-01LS-0206-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0205 TO PS5-08-01LS-0206 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7783 | PS5-08-01LS-0207-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0206 TO PS5-08-01LS-0207 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7784 | PS5-08-01LS-0208-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0207 TO PS5-08-01LS-0208 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7785 | PS5-08-01LS-0209-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0208 TO PS5-08-01LS-0209 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7786 | PS5-08-01LS-0210-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0209 TO PS5-08-01LS-0210 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7787 | PS5-08-01LS-0211-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0210 TO PS5-08-01LS-0211 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7788 | PS5-08-01LS-0211-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0211 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7789 | PS5-08-01LS-0301-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0301 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7790 | PS5-08-01LS-0302-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0301 TO PS5-08-01LS-0302 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7791 | PS5-08-01LS-0303-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0302 TO PS5-08-01LS-0303 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7792 | PS5-08-01LS-0304-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0303 TO PS5-08-01LS-0304 |  | PS5-08-01 - PAGA
T-00171-7793 | PS5-08-01LS-0305-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0304 TO PS5-08-01LS-0305 |  | PS5-08-01 - PAGA
T-00171-7794 | PS5-08-01LS-0306-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0305 TO PS5-08-01LS-0306 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7795 | PS5-08-01LS-0307-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0306 TO PS5-08-01LS-0307 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0034 | 2026-07-01 | Open | Ferdinand | Pulling
T-00171-7796 | PS5-08-01LS-0308-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1501 TO PS5-08-01LS-0308 |  | PS5-08-01 - PAGA
T-00171-7797 | PS5-08-01LS-0309-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0308 TO PS5-08-01LS-0309 |  | PS5-08-01 - PAGA
T-00171-7798 | PS5-08-01LS-0310-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1501 TO PS5-08-01LS-0310 |  | PS5-08-01 - PAGA
T-00171-7799 | PS5-08-01LS-0310-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0310 |  | PS5-08-01 - PAGA
T-00171-7800 | PS5-08-01LS-0318-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0318 |  | PS5-08-01 - PAGA
T-00171-7801 | PS5-08-01LS-0401-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0401 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7802 | PS5-08-01LS-0402-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0401 TO PS5-08-01LS-0402 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7803 | PS5-08-01LS-0403-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0402 TO PS5-08-01LS-0403 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7804 | PS5-08-01LS-0404-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0403 TO PS5-08-01LS-0404 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0034 | 2026-07-01 | Open | Ferdinand | Pulling
T-00171-7805 | PS5-08-01LS-0405-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0404 TO PS5-08-01LS-0405 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7806 | PS5-08-01LS-0406-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1502 TO PS5-08-01LS-0406 |  | PS5-08-01 - PAGA
T-00171-7807 | PS5-08-01LS-0407-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0406 TO PS5-08-01LS-0407 |  | PS5-08-01 - PAGA
T-00171-7808 | PS5-08-01LS-0408-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0407 TO PS5-08-01LS-0408 |  | PS5-08-01 - PAGA
T-00171-7809 | PS5-08-01LS-0409-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1502 TO PS5-08-01LS-0409 |  | PS5-08-01 - PAGA
T-00171-7810 | PS5-08-01LS-0410-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0409 TO PS5-08-01LS-0410 |  | PS5-08-01 - PAGA
T-00171-7811 | PS5-08-01LS-0411-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0410 TO PS5-08-01LS-0411 |  | PS5-08-01 - PAGA
T-00171-7812 | PS5-08-01LS-0411-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0411 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0024 | 2026-04-12 | Accepted with punch | Bertus Wikael | PULLING
T-00171-7813 | PS5-08-01LS-0418-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0418 |  | PS5-08-01 - PAGA
T-00171-7814 | PS5-08-01LS-0501-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1903 TO PS5-08-01LS-0501 |  | PS5-08-01 - PAGA
T-00171-7815 | PS5-08-01LS-0502-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0501 TO PS5-08-01LS-0502 |  | PS5-08-01 - PAGA
T-00171-7816 | PS5-08-01LS-0503-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0502 TO PS5-08-01LS-0503 |  | PS5-08-01 - PAGA
T-00171-7817 | PS5-08-01LS-0504-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0503 TO PS5-08-01LS-0504 |  | PS5-08-01 - PAGA
T-00171-7818 | PS5-08-01LS-0505-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0504 TO PS5-08-01LS-0505 |  | PS5-08-01 - PAGA
T-00171-7819 | PS5-08-01LS-0506-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0505 TO PS5-08-01LS-0506 |  | PS5-08-01 - PAGA
T-00171-7820 | PS5-08-01LS-0507-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0506 TO PS5-08-01LS-0507 |  | PS5-08-01 - PAGA
T-00171-7821 | PS5-08-01LS-0508-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0507 TO PS5-08-01LS-0508 |  | PS5-08-01 - PAGA
T-00171-7822 | PS5-08-01LS-0509-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0508 TO PS5-08-01LS-0509 |  | PS5-08-01 - PAGA
T-00171-7823 | PS5-08-01LS-0510-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0509 TO PS5-08-01LS-0510 |  | PS5-08-01 - PAGA
T-00171-7824 | PS5-08-01LS-0511-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0510 TO PS5-08-01LS-0511 |  | PS5-08-01 - PAGA
T-00171-7825 | PS5-08-01LS-0512-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0511 TO PS5-08-01LS-0512 |  | PS5-08-01 - PAGA
T-00171-7826 | PS5-08-01LS-0517-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0512 TO PS5-08-01LS-0517 |  | PS5-08-01 - PAGA
T-00171-7827 | PS5-08-01LS-0518-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0517 TO PS5-08-01LS-0518 |  | PS5-08-01 - PAGA
T-00171-7828 | PS5-08-01LS-0519-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0518 TO PS5-08-01LS-0519 |  | PS5-08-01 - PAGA
T-00171-7829 | PS5-08-01LS-0520-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0519 TO PS5-08-01LS-0520 |  | PS5-08-01 - PAGA
T-00171-7830 | PS5-08-01LS-0521-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0520 TO PS5-08-01LS-0521 |  | PS5-08-01 - PAGA
T-00171-7831 | PS5-08-01LS-0522-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0521 TO PS5-08-01LS-0522 |  | PS5-08-01 - PAGA
T-00171-7832 | PS5-08-01LS-0522-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1903 TO PS5-08-01LS-0522 |  | PS5-08-01 - PAGA
T-00171-7833 | PS5-08-01LS-0523-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1901 TO PS5-08-01LS-0523 |  | PS5-08-01 - PAGA
T-00171-7834 | PS5-08-01LS-0524-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0523 TO PS5-08-01LS-0524 |  | PS5-08-01 - PAGA
T-00171-7835 | PS5-08-01LS-0525-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0524 TO PS5-08-01LS-0525 |  | PS5-08-01 - PAGA
T-00171-7836 | PS5-08-01LS-0526-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0525 TO PS5-08-01LS-0526 |  | PS5-08-01 - PAGA
T-00171-7837 | PS5-08-01LS-0527-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0526 TO PS5-08-01LS-0527 |  | PS5-08-01 - PAGA
T-00171-7838 | PS5-08-01LS-0528-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0527 TO PS5-08-01LS-0528 |  | PS5-08-01 - PAGA
T-00171-7839 | PS5-08-01LS-0529-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0528 TO PS5-08-01LS-0529 |  | PS5-08-01 - PAGA
T-00171-7840 | PS5-08-01LS-0530-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0529 TO PS5-08-01LS-0530 |  | PS5-08-01 - PAGA
T-00171-7841 | PS5-08-01LS-0530-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1901 TO PS5-08-01LS-0530 |  | PS5-08-01 - PAGA
T-00171-7842 | PS5-08-01LS-0601-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1904 TO PS5-08-01LS-0601 |  | PS5-08-01 - PAGA
T-00171-7843 | PS5-08-01LS-0602-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0601 TO PS5-08-01LS-0602 |  | PS5-08-01 - PAGA
T-00171-7844 | PS5-08-01LS-0603-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0602 TO PS5-08-01LS-0603 |  | PS5-08-01 - PAGA
T-00171-7845 | PS5-08-01LS-0604-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0603 TO PS5-08-01LS-0604 |  | PS5-08-01 - PAGA
T-00171-7846 | PS5-08-01LS-0605-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0604 TO PS5-08-01LS-0605 |  | PS5-08-01 - PAGA
T-00171-7847 | PS5-08-01LS-0606-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0605 TO PS5-08-01LS-0606 |  | PS5-08-01 - PAGA
T-00171-7848 | PS5-08-01LS-0607-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0606 TO PS5-08-01LS-0607 |  | PS5-08-01 - PAGA
T-00171-7849 | PS5-08-01LS-0608-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0607 TO PS5-08-01LS-0608 |  | PS5-08-01 - PAGA
T-00171-7850 | PS5-08-01LS-0609-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0608 TO PS5-08-01LS-0609 |  | PS5-08-01 - PAGA
T-00171-7851 | PS5-08-01LS-0610-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0609 TO PS5-08-01LS-0610 |  | PS5-08-01 - PAGA
T-00171-7852 | PS5-08-01LS-0611-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0610 TO PS5-08-01LS-0611 |  | PS5-08-01 - PAGA
T-00171-7853 | PS5-08-01LS-0612-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0611 TO PS5-08-01LS-0612 |  | PS5-08-01 - PAGA
T-00171-7854 | PS5-08-01LS-0617-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0612 TO PS5-08-01LS-0617 |  | PS5-08-01 - PAGA
T-00171-7855 | PS5-08-01LS-0618-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0617 TO PS5-08-01LS-0618 |  | PS5-08-01 - PAGA
T-00171-7856 | PS5-08-01LS-0619-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0618 TO PS5-08-01LS-0619 |  | PS5-08-01 - PAGA
T-00171-7857 | PS5-08-01LS-0620-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0619 TO PS5-08-01LS-0620 |  | PS5-08-01 - PAGA
T-00171-7858 | PS5-08-01LS-0621-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0620 TO PS5-08-01LS-0621 |  | PS5-08-01 - PAGA
T-00171-7859 | PS5-08-01LS-0621-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1904 TO PS5-08-01LS-0621 |  | PS5-08-01 - PAGA
T-00171-7860 | PS5-08-01LS-0622-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1902 TO PS5-08-01LS-0622 |  | PS5-08-01 - PAGA
T-00171-7861 | PS5-08-01LS-0623-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0622 TO PS5-08-01LS-0623 |  | PS5-08-01 - PAGA
T-00171-7862 | PS5-08-01LS-0624-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0623 TO PS5-08-01LS-0624 |  | PS5-08-01 - PAGA
T-00171-7863 | PS5-08-01LS-0625-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0624 TO PS5-08-01LS-0625 |  | PS5-08-01 - PAGA
T-00171-7864 | PS5-08-01LS-0626-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0625 TO PS5-08-01LS-0626 |  | PS5-08-01 - PAGA
T-00171-7865 | PS5-08-01LS-0627-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0626 TO PS5-08-01LS-0627 |  | PS5-08-01 - PAGA
T-00171-7866 | PS5-08-01LS-0628-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0627 TO PS5-08-01LS-0628 |  | PS5-08-01 - PAGA
T-00171-7867 | PS5-08-01LS-0629-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0628 TO PS5-08-01LS-0629 |  | PS5-08-01 - PAGA
T-00171-7868 | PS5-08-01LS-0629-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1902 TO PS5-08-01LS-0629 |  | PS5-08-01 - PAGA
T-00171-7869 | PS5-08-01LS-0701-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01LS-0701 |  | PS5-08-01 - PAGA
T-00171-7870 | PS5-08-01LS-0702-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0701 TO PS5-08-01LS-0702 |  | PS5-08-01 - PAGA
T-00171-7871 | PS5-08-01LS-0703-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0704 TO PS5-08-01LS-0703 |  | PS5-08-01 - PAGA
T-00171-7872 | PS5-08-01LS-0704-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0702 TO PS5-08-01LS-0704 |  | PS5-08-01 - PAGA
T-00171-7873 | PS5-08-01LS-0705-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01LS-0705 |  | PS5-08-01 - PAGA
T-00171-7874 | PS5-08-01LS-0706-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0703 TO PS5-08-01LS-0706 |  | PS5-08-01 - PAGA
T-00171-7875 | PS5-08-01LS-0707-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0706 TO PS5-08-01LS-0707 |  | PS5-08-01 - PAGA
T-00171-7876 | PS5-08-01LS-0708-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0707 TO PS5-08-01LS-0708 |  | PS5-08-01 - PAGA
T-00171-7877 | PS5-08-01LS-0709-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0708 TO PS5-08-01LS-0709 |  | PS5-08-01 - PAGA
T-00171-7878 | PS5-08-01LS-0710-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0709 TO PS5-08-01LS-0710 |  | PS5-08-01 - PAGA
T-00171-7879 | PS5-08-01LS-0711-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0710 TO PS5-08-01LS-0711 |  | PS5-08-01 - PAGA
T-00171-7880 | PS5-08-01LS-0712-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01LS-0712 |  | PS5-08-01 - PAGA
T-00171-7881 | PS5-08-01LS-0713-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0712 TO PS5-08-01LS-0713 |  | PS5-08-01 - PAGA
T-00171-7882 | PS5-08-01LS-0714-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0711 TO PS5-08-01LS-0714 |  | PS5-08-01 - PAGA
T-00171-7883 | PS5-08-01LS-0715-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0714 TO PS5-08-01LS-0715 |  | PS5-08-01 - PAGA
T-00171-7884 | PS5-08-01LS-0716-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0715 TO PS5-08-01LS-0716 |  | PS5-08-01 - PAGA
T-00171-7885 | PS5-08-01LS-0716-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01LS-0716 |  | PS5-08-01 - PAGA
T-00171-7886 | PS5-08-01LS-0717-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0713 TO PS5-08-01LS-0717 |  | PS5-08-01 - PAGA
T-00171-7887 | PS5-08-01LS-0718-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0717 TO PS5-08-01LS-0718 |  | PS5-08-01 - PAGA
T-00171-7888 | PS5-08-01LS-0719-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01OC-0001 TO PS5-08-01LS-0719 |  | PS5-08-01 - PAGA
T-00171-7889 | PS5-08-01LS-0720-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-0001 TO PS5-08-01LS-0720 |  | PS5-08-01 - PAGA
T-00171-7890 | PS5-08-01LS-0721-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1601 TO PS5-08-01LS-0721 |  | PS5-08-01 - PAGA
T-00171-7891 | PS5-08-01LS-0722-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0721 TO PS5-08-01LS-0722 |  | PS5-08-01 - PAGA
T-00171-7892 | PS5-08-01LS-0723-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0722 TO PS5-08-01LS-0723 |  | PS5-08-01 - PAGA
T-00171-7893 | PS5-08-01LS-0724-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0723 TO PS5-08-01LS-0724 |  | PS5-08-01 - PAGA
T-00171-7894 | PS5-08-01LS-0725-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0724 TO PS5-08-01LS-0725 |  | PS5-08-01 - PAGA
T-00171-7895 | PS5-08-01LS-0726-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0725 TO PS5-08-01LS-0726 |  | PS5-08-01 - PAGA
T-00171-7896 | PS5-08-01LS-0727-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0726 TO PS5-08-01LS-0727 |  | PS5-08-01 - PAGA
T-00171-7897 | PS5-08-01LS-0728-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0727 TO PS5-08-01LS-0728 |  | PS5-08-01 - PAGA
T-00171-7898 | PS5-08-01LS-0729-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0728 TO PS5-08-01LS-0729 |  | PS5-08-01 - PAGA
T-00171-7899 | PS5-08-01LS-0730-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0729 TO PS5-08-01LS-0730 |  | PS5-08-01 - PAGA
T-00171-7900 | PS5-08-01LS-0731-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0730 TO PS5-08-01LS-0731 |  | PS5-08-01 - PAGA
T-00171-7901 | PS5-08-01LS-0732-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0731 TO PS5-08-01LS-0732 |  | PS5-08-01 - PAGA
T-00171-7902 | PS5-08-01LS-0733-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0732 TO PS5-08-01LS-0733 |  | PS5-08-01 - PAGA
T-00171-7903 | PS5-08-01LS-0733-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1601 TO PS5-08-01LS-0733 |  | PS5-08-01 - PAGA
T-00171-7904 | PS5-08-01LS-0801-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1202 TO PS5-08-01LS-0801 |  | PS5-08-01 - PAGA
T-00171-7905 | PS5-08-01LS-0802-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0801 TO PS5-08-01LS-0802 |  | PS5-08-01 - PAGA
T-00171-7906 | PS5-08-01LS-0803-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0802 TO PS5-08-01LS-0803 |  | PS5-08-01 - PAGA
T-00171-7907 | PS5-08-01LS-0804-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1202 TO PS5-08-01LS-0804 |  | PS5-08-01 - PAGA
T-00171-7908 | PS5-08-01LS-0805-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0803 TO PS5-08-01LS-0805 |  | PS5-08-01 - PAGA
T-00171-7909 | PS5-08-01LS-0806-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0805 TO PS5-08-01LS-0806 |  | PS5-08-01 - PAGA
T-00171-7910 | PS5-08-01LS-0807-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0806 TO PS5-08-01LS-0807 |  | PS5-08-01 - PAGA
T-00171-7911 | PS5-08-01LS-0808-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0807 TO PS5-08-01LS-0808 |  | PS5-08-01 - PAGA
T-00171-7912 | PS5-08-01LS-0809-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0808 TO PS5-08-01LS-0809 |  | PS5-08-01 - PAGA
T-00171-7913 | PS5-08-01LS-0810-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0809 TO PS5-08-01LS-0810 |  | PS5-08-01 - PAGA
T-00171-7914 | PS5-08-01LS-0811-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1202 TO PS5-08-01LS-0811 |  | PS5-08-01 - PAGA
T-00171-7915 | PS5-08-01LS-0812-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0811 TO PS5-08-01LS-0812 |  | PS5-08-01 - PAGA
T-00171-7916 | PS5-08-01LS-0813-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0810 TO PS5-08-01LS-0813 |  | PS5-08-01 - PAGA
T-00171-7917 | PS5-08-01LS-0814-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0813 TO PS5-08-01LS-0814 |  | PS5-08-01 - PAGA
T-00171-7918 | PS5-08-01LS-0815-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0814 TO PS5-08-01LS-0815 |  | PS5-08-01 - PAGA
T-00171-7919 | PS5-08-01LS-0816-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0815 TO PS5-08-01LS-0816 |  | PS5-08-01 - PAGA
T-00171-7920 | PS5-08-01LS-0816-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1202 TO PS5-08-01LS-0816 |  | PS5-08-01 - PAGA
T-00171-7921 | PS5-08-01LS-0817-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0812 TO PS5-08-01LS-0817 |  | PS5-08-01 - PAGA
T-00171-7922 | PS5-08-01LS-0818-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0817 TO PS5-08-01LS-0818 |  | PS5-08-01 - PAGA
T-00171-7923 | PS5-08-01LS-0819-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01OC-0001 TO PS5-08-01LS-0819 |  | PS5-08-01 - PAGA
T-00171-7924 | PS5-08-01LS-0820-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1602 TO PS5-08-01LS-0820 |  | PS5-08-01 - PAGA
T-00171-7925 | PS5-08-01LS-0821-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0820 TO PS5-08-01LS-0821 |  | PS5-08-01 - PAGA
T-00171-7926 | PS5-08-01LS-0822-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0821 TO PS5-08-01LS-0822 |  | PS5-08-01 - PAGA
T-00171-7927 | PS5-08-01LS-0823-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0822 TO PS5-08-01LS-0823 |  | PS5-08-01 - PAGA
T-00171-7928 | PS5-08-01LS-0824-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0823 TO PS5-08-01LS-0824 |  | PS5-08-01 - PAGA
T-00171-7929 | PS5-08-01LS-0825-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0824 TO PS5-08-01LS-0825 |  | PS5-08-01 - PAGA
T-00171-7930 | PS5-08-01LS-0826-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0825 TO PS5-08-01LS-0826 |  | PS5-08-01 - PAGA
T-00171-7931 | PS5-08-01LS-0827-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0826 TO PS5-08-01LS-0827 |  | PS5-08-01 - PAGA
T-00171-7932 | PS5-08-01LS-0828-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0827 TO PS5-08-01LS-0828 |  | PS5-08-01 - PAGA
T-00171-7933 | PS5-08-01LS-0829-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0828 TO PS5-08-01LS-0829 |  | PS5-08-01 - PAGA
T-00171-7934 | PS5-08-01LS-0830-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0829 TO PS5-08-01LS-0830 |  | PS5-08-01 - PAGA
T-00171-7935 | PS5-08-01LS-0831-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0830 TO PS5-08-01LS-0831 |  | PS5-08-01 - PAGA
T-00171-7936 | PS5-08-01LS-0832-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0831 TO PS5-08-01LS-0832 |  | PS5-08-01 - PAGA
T-00171-7937 | PS5-08-01LS-0833-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0832 TO PS5-08-01LS-0833 |  | PS5-08-01 - PAGA
T-00171-7938 | PS5-08-01LS-0834-CR01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01LS-0833 TO PS5-08-01LS-0834 |  | PS5-08-01 - PAGA
T-00171-7939 | PS5-08-01LS-0834-CR02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1602 TO PS5-08-01LS-0834 |  | PS5-08-01 - PAGA
T-00171-7940 | PS5-08-01MP-0001-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-13CB-1001 TO PS5-08-01MP-0001 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00171-7941 | PS5-08-01MP-0001-CC02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-13CB-1001 TO PS5-08-01MP-0001 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
| PS5-61-IG-0012A-CX01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | PS5-61-IG-0012A TO PS5-61-IE-0002 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0034 | 2026-07-01 | Open | Ferdinand | Pulling
| PS5-61-IG-0012B-CX01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | PS5-61-IG-0012B TO PS5-61-IE-0002 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0034 | 2026-07-01 | Open | Ferdinand | Pulling
| PS5-61-IG-0012C-CX01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | PS5-61-IG-0012C TO PS5-61-IE-0002 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0034 | 2026-07-01 | Open | Ferdinand | Pulling
T-00171-7942 | PS5-08-01MP-0001-CC03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-13CB-1001 TO PS5-08-01MP-0001 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00171-7943 | PS5-08-01MP-0001-CC04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-13CB-1001 TO PS5-08-01MP-0001 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00171-7944 | PS5-08-01OC-0001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0001 |  | PS5-08-01 - PAGA
T-00171-7945 | PS5-08-01OC-0001-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0001 |  | PS5-08-01 - PAGA
T-00171-7946 | PS5-08-01OC-0001-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0001 |  | PS5-08-01 - PAGA
T-00171-7947 | PS5-08-01OC-0001-CN02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0001 |  | PS5-08-01 - PAGA
T-00171-7948 | PS5-08-01OC-0002-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0002 |  | PS5-08-01 - PAGA
T-00171-7949 | PS5-08-01OC-0002-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0002 |  | PS5-08-01 - PAGA
T-00171-7950 | PS5-08-01OC-0002-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0002 |  | PS5-08-01 - PAGA
T-00171-7951 | PS5-08-01OC-0002-CN02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0002 |  | PS5-08-01 - PAGA
T-00171-7952 | PS5-08-01PA-1201-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-01PA-1201 |  | PS5-08-01 - PAGA
T-00171-7953 | PS5-08-01PA-1201-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1203 TO PS5-08-01PA-1201 |  | PS5-08-01 - PAGA
T-00171-7954 | PS5-08-01PA-1501-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-01PA-1501 |  | PS5-08-01 - PAGA
T-00171-7955 | PS5-08-01PA-1501-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-01BT-1503 TO PS5-08-01PA-1501 |  | PS5-08-01 - PAGA
T-00171-7956 | PS5-08-03TP-0001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-03TP-0001 |  | PS5-08-03 - Telephone | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00171-7957 | PS5-08-03TP-0001-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-03FB-0001 TO PS5-08-03TP-0001 |  | PS5-08-03 - Telephone
T-00171-7958 | PS5-08-03TP-0002-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-03TP-0002 |  | PS5-08-03 - Telephone
T-00171-7959 | PS5-08-03TP-0002-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-03FB-0002 TO PS5-08-03TP-0002 |  | PS5-08-03 - Telephone
T-00171-7960 | PS5-08-03TP-0003-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-03TP-0003 |  | PS5-08-03 - Telephone
T-00171-7961 | PS5-08-03TP-0003-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-03FB-0003 TO PS5-08-03TP-0003 |  | PS5-08-03 - Telephone
T-00171-7962 | PS5-08-03TP-0004-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-03TP-0004 |  | PS5-08-03 - Telephone
T-00171-7963 | PS5-08-03TP-0004-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-03FB-0004 TO PS5-08-03TP-0004 |  | PS5-08-03 - Telephone
T-00171-7964 | PS5-08-03TP-0101-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-03TP-0101 |  | PS5-08-03 - Telephone
T-00171-7965 | PS5-08-03TP-0101-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-03FB-0101 TO PS5-08-03TP-0101 |  | PS5-08-03 - Telephone
T-00171-7966 | PS5-08-03TP-0102-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-03TP-0102 |  | PS5-08-03 - Telephone
T-00171-7967 | PS5-08-03TP-0102-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-03FB-0102 TO PS5-08-03TP-0102 |  | PS5-08-03 - Telephone
T-00171-7968 | PS5-08-03TP-0103-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-03TP-0103 |  | PS5-08-03 - Telephone | CPP-RFI-68-65-05-0029 | 11-May-2026 | Accepted | Ferdinand | Pulling
T-00171-7969 | PS5-08-03TP-0103-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-03FB-0103 TO PS5-08-03TP-0103 |  | PS5-08-03 - Telephone
T-00171-7970 | PS5-08-03TP-1903-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-03TP-1903 |  | PS5-08-03 - Telephone
T-00171-7971 | PS5-08-03TP-1903-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-03FB-1903 TO PS5-08-03TP-1903 |  | PS5-08-03 - Telephone
T-00171-7972 | PS5-08-03TP-1904-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-03TP-1904 |  | PS5-08-03 - Telephone
T-00171-7973 | PS5-08-03TP-1904-CJ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-03FB-1904 TO PS5-08-03TP-1904 |  | PS5-08-03 - Telephone
T-00171-7974 | PS5-08-05IN-0001-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-05IN-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | Pulling
T-00171-7975 | PS5-08-05IN-0002-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-05IN-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | Pulling
T-00171-7976 | PS5-08-05IN-0003-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-05IN-0003 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | Pulling
T-00171-7977 | PS5-08-05IN-0004-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-05IN-0004 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | Pulling
T-00171-7978 | PS5-08-05IN-0005-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-05IN-0005 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | Pulling
T-00171-7979 | PS5-08-12AP-0001-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-0001 TO PS5-08-12AP-0001 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7980 | PS5-08-12AP-0002-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-0002 TO PS5-08-12AP-0002 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7981 | PS5-08-12AP-0003-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-0003 TO PS5-08-12AP-0003 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7982 | PS5-08-12AP-0101-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-0101 TO PS5-08-12AP-0101 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7983 | PS5-08-12AP-0103-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-0103 TO PS5-08-12AP-0103 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7984 | PS5-08-12AP-0104-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-0104 TO PS5-08-12AP-0104 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7985 | PS5-08-12AP-0105-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-0105 TO PS5-08-12AP-0105 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7986 | PS5-08-12AP-0106-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-0106 TO PS5-08-12AP-0106 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7987 | PS5-08-12AP-0107-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-0107 TO PS5-08-12AP-0107 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7988 | PS5-08-12AP-0108-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-0108 TO PS5-08-12AP-0108 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7989 | PS5-08-12AP-0109-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-0109 TO PS5-08-12AP-0109 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7990 | PS5-08-12AP-1903-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-1903 TO PS5-08-12AP-1903 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7991 | PS5-08-12AP-1904-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-12BT-1904 TO PS5-08-12AP-1904 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7992 | PS5-08-12BT-0002-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-12BT-0002 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7993 | PS5-08-12BT-0003-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-12BT-0003 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7994 | PS5-08-12BT-0101-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-0101 |  | PS5-08-12 - Corporate Wireless LAN (SIE) | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00171-7995 | PS5-08-12BT-0103-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-0103 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00171-7996 | PS5-08-13CB-1201-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00171-7997 | PS5-08-13CB-1201-CA02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00171-7998 | PS5-08-13CB-1201-CA03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00171-7999 | PS5-08-13CB-1201-CA04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00171-8000 | PS5-08-13CB-1201-CA05 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00171-8001 | PS5-08-13CB-1201-CA06 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00171-8002 | PS5-08-13CB-1201-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-14CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-93 - Telecom Monitoring System
T-00171-8003 | PS5-08-13CB-1201-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-04-PMC-0006 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00171-8004 | PS5-08-14CB-1201-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00171-8005 | PS5-08-14CB-1201-CA02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00171-8006 | PS5-08-14CB-1201-CA03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00171-8007 | PS5-08-14CB-1201-CA04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00171-8008 | PS5-08-14CB-1201-CA05 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00171-8009 | PS5-08-14CB-1201-CA06 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00171-8010 | PS5-08-23AN-0001-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-23LA-1201 TO PS5-08-23AN-0001 |  | PS5-08-23 - VHF Trunk Radio System
T-00171-8011 | PS5-08-23AN-0002-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-23LA-1501 TO PS5-08-23AN-0002 |  | PS5-08-23 - VHF Trunk Radio System
T-00171-8012 | PS5-08-23AN-0003-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-23LA-1601 TO PS5-08-23AN-0003 |  | PS5-08-23 - VHF Trunk Radio System
T-00171-8013 | PS5-08-23AN-0005-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-23LA-1901 TO PS5-08-23AN-0005 |  | PS5-08-23 - VHF Trunk Radio System
T-00171-8014 | PS5-08-23AN-0901-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-23LA-1202 TO PS5-08-23AN-0901 |  | PS5-08-23 - VHF Trunk Radio System
T-00171-8015 | PS5-08-23AN-1201-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-13CB-1201 TO PS5-08-23AN-1201 |  | PS5-08-23 - VHF Trunk Radio System
T-00171-8016 | PS5-08-23AN-1601-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-23LA-1601 TO PS5-08-23AN-1601 |  | PS5-08-23 - VHF Trunk Radio System
T-00171-8017 | PS5-08-23AN-1901-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-23LA-1901 TO PS5-08-23AN-1901 |  | PS5-08-23 - VHF Trunk Radio System
T-00171-8018 | PS5-08-23LA-1201-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-23BS-1201 TO PS5-08-23LA-1201 |  | PS5-08-23 - VHF Trunk Radio System
T-00171-8019 | PS5-08-23LA-1202-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-13CB-1201 TO PS5-08-23LA-1202 |  | PS5-08-23 - VHF Trunk Radio System
T-00171-8020 | PS5-08-23LA-1501-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-23BS-1501 TO PS5-08-23LA-1501 |  | PS5-08-23 - VHF Trunk Radio System
T-00171-8021 | PS5-08-34AN-0001-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-34LA-1201 TO PS5-08-34AN-0001 |  | PS5-08-34 - Satphone
T-00171-8022 | PS5-08-34AN-0002-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-34LA-1501 TO PS5-08-34AN-0002 |  | PS5-08-34 - Satphone
T-00171-8023 | PS5-08-34LA-1201-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-34DS-1211 TO PS5-08-34LA-1201 |  | PS5-08-34 - Satphone
T-00171-8024 | PS5-08-34LA-1501-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-34DS-1511 TO PS5-08-34LA-1501 |  | PS5-08-34 - Satphone
T-00171-8025 | PS5-08-51AN-0001-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-51LA-1201 TO PS5-08-51AN-0001 |  | PS5-08-51 - Entertainment
T-00171-8026 | PS5-08-51AN-0001-CV02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-51LA-1202 TO PS5-08-51AN-0001 |  | PS5-08-51 - Entertainment
T-00171-8027 | PS5-08-51AN-0001-CV03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-51LA-1203 TO PS5-08-51AN-0001 |  | PS5-08-51 - Entertainment
T-00171-8028 | PS5-08-51AN-0001-CV04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-51LA-1204 TO PS5-08-51AN-0001 |  | PS5-08-51 - Entertainment
T-00171-8029 | PS5-08-51LA-1201-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51LA-1201 |  | PS5-08-51 - Entertainment
T-00171-8030 | PS5-08-51LA-1202-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51LA-1202 |  | PS5-08-51 - Entertainment
T-00171-8031 | PS5-08-51LA-1203-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51LA-1203 |  | PS5-08-51 - Entertainment
T-00171-8032 | PS5-08-51LA-1204-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51LA-1204 |  | PS5-08-51 - Entertainment
T-00171-8033 | PS5-08-51SK-1201-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1201 |  | PS5-08-51 - Entertainment
T-00171-8034 | PS5-08-51SK-1202-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1202 |  | PS5-08-51 - Entertainment
T-00171-8035 | PS5-08-51SK-1203-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1203 |  | PS5-08-51 - Entertainment
T-00171-8036 | PS5-08-51SK-1204-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1204 |  | PS5-08-51 - Entertainment
T-00171-8037 | PS5-08-51SK-1205-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1205 |  | PS5-08-51 - Entertainment
T-00171-8038 | PS5-08-51SK-1206-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1206 |  | PS5-08-51 - Entertainment
T-00171-8039 | PS5-08-51SK-1207-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1207 |  | PS5-08-51 - Entertainment
T-00171-8040 | PS5-08-51SK-1208-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1208 |  | PS5-08-51 - Entertainment
T-00171-8041 | PS5-08-51SK-1209-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1209 |  | PS5-08-51 - Entertainment
T-00171-8042 | PS5-08-51SK-1210-CV01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1210 |  | PS5-08-51 - Entertainment
T-00171-8043 | PS5-08-52CM-0001-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0001 |  | PS5-08-52 - Process & Security CCTV
T-00171-8044 | PS5-08-52CM-0002-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0002 |  | PS5-08-52 - Process & Security CCTV
T-00171-8045 | PS5-08-52CM-0003-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0003 |  | PS5-08-52 - Process & Security CCTV
T-00171-8046 | PS5-08-52CM-0004-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0004 |  | PS5-08-52 - Process & Security CCTV
T-00171-8047 | PS5-08-52CM-0005-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0005 |  | PS5-08-52 - Process & Security CCTV
T-00171-8048 | PS5-08-52CM-0031-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-52CM-0031 |  | PS5-08-52 - Process & Security CCTV
T-00171-8049 | PS5-08-52CM-0032-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0006 TO PS5-08-52CM-0032 |  | PS5-08-52 - Process & Security CCTV
T-00171-8050 | PS5-08-52CM-0033-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0008 TO PS5-08-52CM-0033 |  | PS5-08-52 - Process & Security CCTV
T-00171-8051 | PS5-08-52CM-0034-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0034 |  | PS5-08-52 - Process & Security CCTV
T-00171-8052 | PS5-08-52CM-0071-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0001 TO PS5-08-52CM-0071 |  | PS5-08-52 - Process & Security CCTV
T-00171-8053 | PS5-08-52CM-0072-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-52CM-0072 |  | PS5-08-52 - Process & Security CCTV
T-00171-8054 | PS5-08-52CM-0073-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0003 TO PS5-08-52CM-0073 |  | PS5-08-52 - Process & Security CCTV
T-00171-8055 | PS5-08-52CM-0074-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-52CM-0074 |  | PS5-08-52 - Process & Security CCTV
T-00171-8056 | PS5-08-52CM-0075-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0005 TO PS5-08-52CM-0075 |  | PS5-08-52 - Process & Security CCTV
T-00171-8057 | PS5-08-52CM-0076-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0006 TO PS5-08-52CM-0076 |  | PS5-08-52 - Process & Security CCTV
T-00171-8058 | PS5-08-52CM-0077-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-52CM-0077 |  | PS5-08-52 - Process & Security CCTV
T-00171-8059 | PS5-08-52CM-0078-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0008 TO PS5-08-52CM-0078 |  | PS5-08-52 - Process & Security CCTV
T-00171-8060 | PS5-08-52CM-0134-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-0134 |  | PS5-08-52 - Process & Security CCTV
T-00171-8061 | PS5-08-52CM-0137-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-0137 |  | PS5-08-52 - Process & Security CCTV
T-00171-8062 | PS5-08-52CM-0140-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-0140 |  | PS5-08-52 - Process & Security CCTV
T-00171-8063 | PS5-08-52CM-0931-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-52CM-0931 |  | PS5-08-52 - Process & Security CCTV
T-00171-8064 | PS5-08-52CM-1201-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-52CM-1201 |  | PS5-08-52 - Process & Security CCTV
T-00171-8065 | PS5-08-52CM-1202-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-52CM-1202 |  | PS5-08-52 - Process & Security CCTV
T-00171-8066 | PS5-08-52CM-1901-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-1901 |  | PS5-08-52 - Process & Security CCTV
T-00171-8067 | PS5-08-52CM-1902-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-1902 |  | PS5-08-52 - Process & Security CCTV
T-00171-8068 | PS5-08-52CM-1903-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-1903 |  | PS5-08-52 - Process & Security CCTV
T-00171-8069 | PS5-08-52TK-0031-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0031 TO PS5-08-52TK-0031 |  | PS5-08-52 - Process & Security CCTV
T-00171-8070 | PS5-08-52TK-0032-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0032 TO PS5-08-52TK-0032 |  | PS5-08-52 - Process & Security CCTV
T-00171-8071 | PS5-08-52TK-0033-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0033 TO PS5-08-52TK-0033 |  | PS5-08-52 - Process & Security CCTV
T-00171-8072 | PS5-08-52TK-0131-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0131 TO PS5-08-52TK-0131 |  | PS5-08-52 - Process & Security CCTV
T-00171-8073 | PS5-08-52TK-0132-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0132 TO PS5-08-52TK-0132 |  | PS5-08-52 - Process & Security CCTV
T-00171-8074 | PS5-08-52TK-0133-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0133 TO PS5-08-52TK-0133 |  | PS5-08-52 - Process & Security CCTV
T-00171-8075 | PS5-08-52TK-0134-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0134 TO PS5-08-52TK-0134 |  | PS5-08-52 - Process & Security CCTV
T-00171-8076 | PS5-08-52TK-0135-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0135 TO PS5-08-52TK-0135 |  | PS5-08-52 - Process & Security CCTV
T-00171-8077 | PS5-08-52TK-0136-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0136 TO PS5-08-52TK-0136 |  | PS5-08-52 - Process & Security CCTV
T-00171-8078 | PS5-08-52TK-0137-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0137 TO PS5-08-52TK-0137 |  | PS5-08-52 - Process & Security CCTV
T-00171-8079 | PS5-08-52TK-0138-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0138 TO PS5-08-52TK-0138 |  | PS5-08-52 - Process & Security CCTV
T-00171-8080 | PS5-08-52TK-0139-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0139 TO PS5-08-52TK-0139 |  | PS5-08-52 - Process & Security CCTV
T-00171-8081 | PS5-08-52TK-0140-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0140 TO PS5-08-52TK-0140 |  | PS5-08-52 - Process & Security CCTV
T-00171-8082 | PS5-08-52TK-0931-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-52CM-0931 TO PS5-08-52TK-0931 |  | PS5-08-52 - Process & Security CCTV
T-00171-8083 | PS5-08-61BT-0001-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-14CB-1201 TO PS5-08-61BT-0001 |  | PS5-08-61 - Meteocean
T-00171-8084 | PS5-08-61BT-0001-CC02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-14CB-1201 TO PS5-08-61BT-0001 |  | PS5-08-61 - Meteocean
T-00171-8085 | PS5-08-61BT-0001-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-14CB-1201 TO PS5-08-61BT-0001 |  | PS5-08-61 - Meteocean
T-00171-8086 | PS5-08-61BT-0002-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-14CB-1201 TO PS5-08-61BT-0002 |  | PS5-08-61 - Meteocean
T-00171-8087 | PS5-08-61BT-0901-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-61BT-0001 TO PS5-08-61BT-0901 |  | PS5-08-61 - Meteocean
T-00171-8088 | PS5-08-61SN-0003-CZ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-61BT-0001 TO PS5-08-61SN-0003 |  | PS5-08-61 - Meteocean
T-00171-8089 | PS5-08-61SN-0004-CZ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-61BT-0001 TO PS5-08-61SN-0004 |  | PS5-08-61 - Meteocean
T-00171-8090 | PS5-08-61SN-0005-CZ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-61BT-0002 TO PS5-08-61SN-0005 |  | PS5-08-61 - Meteocean
T-00171-8091 | PS5-08-61SN-0005-CZ02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-61BT-0002 TO PS5-08-61SN-0005 |  | PS5-08-61 - Meteocean
T-00171-8092 | PS5-08-61SN-0901-CZ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-61BT-0901 TO PS5-08-61SN-0901 |  | PS5-08-61 - Meteocean
T-00171-8093 | PS5-08-71SK-1201-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1201 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8094 | PS5-08-71SK-1202-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1202 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8095 | PS5-08-71SK-1203-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1203 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8096 | PS5-08-71SK-1204-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1204 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8097 | PS5-08-71SK-1205-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1205 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8098 | PS5-08-71SK-1206A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1206A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8099 | PS5-08-71SK-1206B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1206B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8100 | PS5-08-71SK-1207-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1207 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8101 | PS5-08-71SK-1208-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1208 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8102 | PS5-08-71SK-1209-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1209 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8103 | PS5-08-71SK-1210-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1210 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8104 | PS5-08-71SK-1211-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1211 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8105 | PS5-08-71SK-1212A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1212A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8106 | PS5-08-71SK-1212B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1212B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8107 | PS5-08-71SK-1213-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1213 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8108 | PS5-08-71SK-1214A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1214A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8109 | PS5-08-71SK-1214B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1214B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8110 | PS5-08-71SK-1214C-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1214C |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8111 | PS5-08-71SK-1214D-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1214D |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8112 | PS5-08-71SK-1215A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1215A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8113 | PS5-08-71SK-1215B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1215B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8114 | PS5-08-71SK-1216A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1216A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8115 | PS5-08-71SK-1216B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1216B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8116 | PS5-08-71SK-1217A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1217A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8117 | PS5-08-71SK-1217B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1217B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8118 | PS5-08-71SK-1218A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1218A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8119 | PS5-08-71SK-1218B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1218B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8120 | PS5-08-71SK-1219A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1219A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8121 | PS5-08-71SK-1219B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1219B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8122 | PS5-08-71SK-1220A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1220A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8123 | PS5-08-71SK-1220B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1220B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8124 | PS5-08-71SK-1221A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1221A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8125 | PS5-08-71SK-1221B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1221B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8126 | PS5-08-71SK-1222A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1222A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8127 | PS5-08-71SK-1222B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1222B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8128 | PS5-08-71SK-1223A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1223A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8129 | PS5-08-71SK-1223B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1223B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8130 | PS5-08-71SK-1224A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1224A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8131 | PS5-08-71SK-1224B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1224B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8132 | PS5-08-71SK-1225A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1225A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8133 | PS5-08-71SK-1225B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1225B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8134 | PS5-08-71SK-1226A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1226A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8135 | PS5-08-71SK-1226B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1226B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8136 | PS5-08-71SK-1227A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1227A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8137 | PS5-08-71SK-1227B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1227B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8138 | PS5-08-71SK-1228A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1228A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8139 | PS5-08-71SK-1228B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1228B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8140 | PS5-08-71SK-1229-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1229 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8141 | PS5-08-71SK-1230A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1230A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8142 | PS5-08-71SK-1230B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1230B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8143 | PS5-08-71SK-1231-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1231 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8144 | PS5-08-71SK-1232A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1232A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8145 | PS5-08-71SK-1232B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1232B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8146 | PS5-08-71SK-1233A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1233A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8147 | PS5-08-71SK-1233B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1233B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8148 | PS5-08-71SK-1234-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1234 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8149 | PS5-08-71SK-1235-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1235 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8150 | PS5-08-71SK-1236A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1236A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8151 | PS5-08-71SK-1236B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1236B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8152 | PS5-08-71SK-1237-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1237 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8153 | PS5-08-71SK-1238-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1238 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8154 | PS5-08-71SK-1239-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1239 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8155 | PS5-08-71SK-1240-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1240 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8156 | PS5-08-71SK-1241A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1241A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8157 | PS5-08-71SK-1241B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1241B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8158 | PS5-08-71SK-1242A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1242A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8159 | PS5-08-71SK-1242B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1242B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8160 | PS5-08-71SK-1243A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1243A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8161 | PS5-08-71SK-1243B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1243B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8162 | PS5-08-71SK-1244A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1244A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8163 | PS5-08-71SK-1244B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1244B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8164 | PS5-08-71SK-1245A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1245A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8165 | PS5-08-71SK-1245B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1245B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8166 | PS5-08-71SK-1246A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1246A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8167 | PS5-08-71SK-1246B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1246B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8168 | PS5-08-71SK-1247-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1247 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8169 | PS5-08-71SK-1248-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1248 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8170 | PS5-08-71SK-1249A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1249A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8171 | PS5-08-71SK-1249B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1249B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8172 | PS5-08-71SK-1249C-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1249C |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8173 | PS5-08-71SK-1249D-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1249D |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8174 | PS5-08-71SK-1250A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1250A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8175 | PS5-08-71SK-1250B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1250B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8176 | PS5-08-71SK-1501A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1501A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8177 | PS5-08-71SK-1501B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1501B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8178 | PS5-08-71SK-1502A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1502A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8179 | PS5-08-71SK-1502B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1502B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8180 | PS5-08-71SK-1503A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1503A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8181 | PS5-08-71SK-1503B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1503B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8182 | PS5-08-71SK-1504A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1504A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8183 | PS5-08-71SK-1504B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1504B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8184 | PS5-08-71SK-1505-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1505 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8185 | PS5-08-71SK-1506-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1506 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8186 | PS5-08-71SK-1507-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1507 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8187 | PS5-08-71SK-1508-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1508 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8188 | PS5-08-71SK-1509-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1509 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8189 | PS5-08-71SK-1510A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1510A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8190 | PS5-08-71SK-1510B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1510B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8191 | PS5-08-71SK-1511A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1511A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8192 | PS5-08-71SK-1511B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1511B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8193 | PS5-08-71SK-1512-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1512 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8194 | PS5-08-71SK-1513-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1513 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8195 | PS5-08-71SK-1601A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1601A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8196 | PS5-08-71SK-1601B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1601B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8197 | PS5-08-71SK-1602A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1602A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8198 | PS5-08-71SK-1602B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1602B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8199 | PS5-08-71SK-1603A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1603A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8200 | PS5-08-71SK-1603B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1603B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8201 | PS5-08-71SK-1604A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1604A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8202 | PS5-08-71SK-1604B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1604B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8203 | PS5-08-71SK-1605A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1605A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8204 | PS5-08-71SK-1605B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1605B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8205 | PS5-08-71SK-1606-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1606 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8206 | PS5-08-71SK-1607-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1607 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8207 | PS5-08-71SK-1608-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1608 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8208 | PS5-08-71SK-1609-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1609 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8209 | PS5-08-71SK-1610-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1610 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8210 | PS5-08-71SK-1611-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1611 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8211 | PS5-08-71SK-1901-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1901 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8212 | PS5-08-71SK-1903A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1903A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8213 | PS5-08-71SK-1903B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1903B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8214 | PS5-08-71SK-1904A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1904A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8215 | PS5-08-71SK-1904B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1904B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8216 | PS5-08-71SK-1905A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1905A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8217 | PS5-08-71SK-1905B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1905B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00171-8218 | PS5-08-85BG-1201-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1201 TO PS5-08-85BG-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8219 | PS5-08-85BG-1202-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1202 TO PS5-08-85BG-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8220 | PS5-08-85BG-1203-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1203 TO PS5-08-85BG-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8221 | PS5-08-85BG-1204-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1205 TO PS5-08-85BG-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8222 | PS5-08-85BG-1501-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1503 TO PS5-08-85BG-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8223 | PS5-08-85BG-1601-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1603 TO PS5-08-85BG-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8224 | PS5-08-85BG-1602-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1605 TO PS5-08-85BG-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8225 | PS5-08-85BG-1603-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1606 TO PS5-08-85BG-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8226 | PS5-08-85BG-1604-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1607 TO PS5-08-85BG-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8227 | PS5-08-85BG-1605-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1608 TO PS5-08-85BG-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8228 | PS5-08-85BG-1901-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1901 TO PS5-08-85BG-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8229 | PS5-08-85BG-1902-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1902 TO PS5-08-85BG-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8230 | PS5-08-85BR-0001-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8231 | PS5-08-85BR-0002-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8232 | PS5-08-85BR-0003-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0003 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8233 | PS5-08-85BR-0004-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0004 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8234 | PS5-08-85BR-0005-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0005 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8235 | PS5-08-85BR-0006-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0006 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8236 | PS5-08-85BR-0007-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0007 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8237 | PS5-08-85BR-0008-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0008 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8238 | PS5-08-85BR-0009-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1201 TO PS5-08-85BR-0009 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8239 | PS5-08-85BR-0010-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-0010 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8240 | PS5-08-85BR-0011-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-0024 TO PS5-08-85BR-0011 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8241 | PS5-08-85BR-0012-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-0025 TO PS5-08-85BR-0012 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8242 | PS5-08-85BR-1201-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8243 | PS5-08-85BR-1202-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8244 | PS5-08-85BR-1203-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8245 | PS5-08-85BR-1204-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8246 | PS5-08-85BR-1205-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1201 TO PS5-08-85BR-1205 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8247 | PS5-08-85BR-1206-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-1206 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8248 | PS5-08-85BR-1501-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8249 | PS5-08-85BR-1502-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-1502 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8250 | PS5-08-85BR-1601-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BR-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8251 | PS5-08-85BR-1602-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BR-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8252 | PS5-08-85BR-1603-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BR-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8253 | PS5-08-85BR-1604-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BR-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8254 | PS5-08-85BR-1605-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BR-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8255 | PS5-08-85BR-1901-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BR-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8256 | PS5-08-85BR-1902-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BR-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8257 | PS5-08-85BT-0001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8258 | PS5-08-85BT-0002-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8259 | PS5-08-85BT-0003-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0003 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8260 | PS5-08-85BT-0004-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0005 TO PS5-08-85BT-0004 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8261 | PS5-08-85BT-0005-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0005 TO PS5-08-85BT-0005 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0011 | 2025-12-06 | Accepted | Elizabeth | PULLING
T-00171-8262 | PS5-08-85BT-0006-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0005 TO PS5-08-85BT-0006 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8263 | PS5-08-85BT-0007-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0005 TO PS5-08-85BT-0007 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0011 | 2025-12-06 | Accepted | Elizabeth | PULLING
T-00171-8264 | PS5-08-85BT-0008-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-85BT-0008 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8265 | PS5-08-85BT-0009-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-85BT-0009 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8266 | PS5-08-85BT-0010-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-85BT-0010 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0013 | 2025-12-11 | Accepted | Ferdinand | PULLING
T-00171-8267 | PS5-08-85BT-0011-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-85BT-0011 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8268 | PS5-08-85BT-0012-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-85BT-0012 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8269 | PS5-08-85BT-0013-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-85BT-0013 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0015 | 2025-12-15 | Accepted | Ferdinand | PULLING
T-00171-8270 | PS5-08-85BT-0014-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-85BT-0014 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0023 | 2026-04-10 | Accepted | Bertus Wikael | PULLING
T-00171-8271 | PS5-08-85BT-0015-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-85BT-0015 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0015 | 2025-12-15 | Accepted | Ferdinand | PULLING
T-00171-8272 | PS5-08-85BT-0016-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-85BT-0016 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0034 | 2026-07-01 | Open | Ferdinand | Pulling
| PS5-60-IE-0004-CX02 | CIX09 | #N/A | T |  |  |  | CPP-RFI-68-65-05-0034 | 2026-07-01 | Open | Ferdinand | Pulling
| PS5-60-IE-0004-CX01 | CIX09 | #N/A | T |  |  |  | CPP-RFI-68-65-05-0034 | 2026-07-01 | Open | Ferdinand | Pulling
| PS5-61-IK-0003-CX01 | CIX09 | #N/A | T |  |  |  | CPP-RFI-68-65-05-0034 | 2026-07-01 | Open | Ferdinand | Pulling
| PS5-61-IK-0006-CX01 | CIX09 | #N/A | T |  |  |  | CPP-RFI-68-65-05-0034 | 2026-07-01 | Open | Ferdinand | Pulling
#N/A
#N/A
#N/A
#N/A
T-00171-8273 | PS5-08-85BT-0017-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0017 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8274 | PS5-08-85BT-0017-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-85BT-0017 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8275 | PS5-08-85BT-0018-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0018 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8276 | PS5-08-85BT-0019-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0019 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8277 | PS5-08-85BT-0020-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0020 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8278 | PS5-08-85BT-0021-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0021 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8279 | PS5-08-85BT-0022-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0022 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8280 | PS5-08-85BT-0023-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0023 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8281 | PS5-08-85BT-0024-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0024 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8282 | PS5-08-85BT-0025-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0025 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8283 | PS5-08-85BT-0026-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0026 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-05-0032 | 19-June-2026 | Open | Ferdinand | PULLING
T-00171-8284 | PS5-08-85BT-0027-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-0027 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8285 | PS5-08-85BT-0028-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-0028 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8286 | PS5-08-85BT-1201-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BT-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8287 | PS5-08-85BT-1201-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8288 | PS5-08-85BT-1202-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BT-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8289 | PS5-08-85BT-1202-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8290 | PS5-08-85BT-1203-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BT-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8291 | PS5-08-85BT-1203-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8292 | PS5-08-85BT-1204-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1201 TO PS5-08-85BT-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8293 | PS5-08-85BT-1205-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BT-1205 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8294 | PS5-08-85BT-1205-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-1205 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8295 | PS5-08-85BT-1501-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8296 | PS5-08-85BT-1502-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-1502 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8297 | PS5-08-85BT-1503-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-1503 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8298 | PS5-08-85BT-1503-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-85BT-1503 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8299 | PS5-08-85BT-1601-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8300 | PS5-08-85BT-1602-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8301 | PS5-08-85BT-1603-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8302 | PS5-08-85BT-1603-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85BT-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8303 | PS5-08-85BT-1604-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8304 | PS5-08-85BT-1605-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8305 | PS5-08-85BT-1605-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85BT-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8306 | PS5-08-85BT-1606-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1606 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8307 | PS5-08-85BT-1606-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85BT-1606 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8308 | PS5-08-85BT-1607-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1607 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8309 | PS5-08-85BT-1607-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85BT-1607 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8310 | PS5-08-85BT-1608-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1608 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8311 | PS5-08-85BT-1608-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85BT-1608 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8312 | PS5-08-85BT-1609-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1609 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8313 | PS5-08-85BT-1610-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1610 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8314 | PS5-08-85BT-1611-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1611 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8315 | PS5-08-85BT-1612-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1612 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8316 | PS5-08-85BT-1613-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1613 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8317 | PS5-08-85BT-1614-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1614 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8318 | PS5-08-85BT-1901-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8319 | PS5-08-85BT-1901-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-85BT-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8320 | PS5-08-85BT-1902-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8321 | PS5-08-85BT-1902-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-85BT-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8322 | PS5-08-85BT-1903-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1903 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8323 | PS5-08-85BT-1904-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1904 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8324 | PS5-08-85BT-1905-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1905 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8325 | PS5-08-85BT-1906-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1906 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8326 | PS5-08-85BT-1907-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1907 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8327 | PS5-08-85BT-1908-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1908 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8328 | PS5-08-85BT-1909-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1909 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8329 | PS5-08-85CP-1201-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85CP-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8330 | PS5-08-85CP-1202-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85CP-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8331 | PS5-08-85CP-1501-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-85CP-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8332 | PS5-08-85CP-1601-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85CP-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8333 | PS5-08-85CP-1901-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-85CP-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8334 | PS5-08-85DC-0001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0017 TO PS5-08-85DC-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8335 | PS5-08-85DC-0002-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0001 TO PS5-08-85DC-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8336 | PS5-08-85DC-0003-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0019 TO PS5-08-85DC-0003 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8337 | PS5-08-85DC-0004-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0002 TO PS5-08-85DC-0004 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8338 | PS5-08-85DC-0005-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0003 TO PS5-08-85DC-0005 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8339 | PS5-08-85DC-0006-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0004 TO PS5-08-85DC-0006 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8340 | PS5-08-85DC-0007-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0005 TO PS5-08-85DC-0007 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8341 | PS5-08-85DC-0008-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0006 TO PS5-08-85DC-0008 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8342 | PS5-08-85DC-0009-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0007 TO PS5-08-85DC-0009 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8343 | PS5-08-85DC-0010-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0008 TO PS5-08-85DC-0010 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8344 | PS5-08-85DC-0011-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0010 TO PS5-08-85DC-0011 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8345 | PS5-08-85DC-0012-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0009 TO PS5-08-85DC-0012 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8346 | PS5-08-85DC-0013-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0012 TO PS5-08-85DC-0013 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8347 | PS5-08-85DC-0014-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0011 TO PS5-08-85DC-0014 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8348 | PS5-08-85DC-0015-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0013 TO PS5-08-85DC-0015 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8349 | PS5-08-85DC-0016-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0014 TO PS5-08-85DC-0016 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8350 | PS5-08-85DC-0017-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0015 TO PS5-08-85DC-0017 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8351 | PS5-08-85DC-0018-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0016 TO PS5-08-85DC-0018 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8352 | PS5-08-85DC-0019-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0024 TO PS5-08-85DC-0019 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8353 | PS5-08-85DC-0021-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0025 TO PS5-08-85DC-0021 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8354 | PS5-08-85DC-0022-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0026 TO PS5-08-85DC-0022 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8355 | PS5-08-85DC-0023-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0018 TO PS5-08-85DC-0023 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8356 | PS5-08-85DC-0024-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0001 TO PS5-08-85DC-0024 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8357 | PS5-08-85DC-0025-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0009 TO PS5-08-85DC-0025 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8358 | PS5-08-85DC-0026-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0024 TO PS5-08-85DC-0026 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8359 | PS5-08-85DC-0027-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0025 TO PS5-08-85DC-0027 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8360 | PS5-08-85DC-0028-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0026 TO PS5-08-85DC-0028 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8361 | PS5-08-85DC-1201-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1201 TO PS5-08-85DC-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8362 | PS5-08-85DC-1202-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1202 TO PS5-08-85DC-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8363 | PS5-08-85DC-1203-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1202 TO PS5-08-85DC-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8364 | PS5-08-85DC-1204-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1203 TO PS5-08-85DC-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8365 | PS5-08-85DC-1205-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1204 TO PS5-08-85DC-1205 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8366 | PS5-08-85DC-1206-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1204 TO PS5-08-85DC-1206 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8367 | PS5-08-85DC-1207-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1205 TO PS5-08-85DC-1207 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8368 | PS5-08-85DC-1501-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1501 TO PS5-08-85DC-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8369 | PS5-08-85DC-1502-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1502 TO PS5-08-85DC-1502 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8370 | PS5-08-85DC-1503-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1503 TO PS5-08-85DC-1503 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8371 | PS5-08-85DC-1601-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1601 TO PS5-08-85DC-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8372 | PS5-08-85DC-1602-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1602 TO PS5-08-85DC-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8373 | PS5-08-85DC-1603-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1603 TO PS5-08-85DC-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8374 | PS5-08-85DC-1604-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1603 TO PS5-08-85DC-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8375 | PS5-08-85DC-1605-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1604 TO PS5-08-85DC-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8376 | PS5-08-85DC-1606-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1604 TO PS5-08-85DC-1606 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8377 | PS5-08-85DC-1607-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1607 TO PS5-08-85DC-1607 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8378 | PS5-08-85DC-1608-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1606 TO PS5-08-85DC-1608 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8379 | PS5-08-85DC-1609-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1606 TO PS5-08-85DC-1609 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8380 | PS5-08-85DC-1610-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1614 TO PS5-08-85DC-1610 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8381 | PS5-08-85DC-1611-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1613 TO PS5-08-85DC-1611 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8382 | PS5-08-85DC-1612-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1613 TO PS5-08-85DC-1612 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8383 | PS5-08-85DC-1613-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1612 TO PS5-08-85DC-1613 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8384 | PS5-08-85DC-1614-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1611 TO PS5-08-85DC-1614 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8385 | PS5-08-85DC-1615-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1610 TO PS5-08-85DC-1615 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8386 | PS5-08-85DC-1616-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1609 TO PS5-08-85DC-1616 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8387 | PS5-08-85DC-1617-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1605 TO PS5-08-85DC-1617 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8388 | PS5-08-85DC-1618-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1608 TO PS5-08-85DC-1618 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8389 | PS5-08-85DC-1901-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1903 TO PS5-08-85DC-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8390 | PS5-08-85DC-1902-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1903 TO PS5-08-85DC-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8391 | PS5-08-85DC-1903-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1904 TO PS5-08-85DC-1903 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8392 | PS5-08-85DC-1904-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1904 TO PS5-08-85DC-1904 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8393 | PS5-08-85DC-1905-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1905 TO PS5-08-85DC-1905 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8394 | PS5-08-85DC-1906-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1905 TO PS5-08-85DC-1906 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8395 | PS5-08-85DC-1907-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1906 TO PS5-08-85DC-1907 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8396 | PS5-08-85DC-1908-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1906 TO PS5-08-85DC-1908 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8397 | PS5-08-85DC-1909-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1907 TO PS5-08-85DC-1909 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8398 | PS5-08-85DC-1910-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1907 TO PS5-08-85DC-1910 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8399 | PS5-08-85DC-1911-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1901 TO PS5-08-85DC-1911 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8400 | PS5-08-85DC-1912-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1902 TO PS5-08-85DC-1912 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8401 | PS5-08-85DC-1913-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1908 TO PS5-08-85DC-1913 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8402 | PS5-08-85DC-1914-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1908 TO PS5-08-85DC-1914 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8403 | PS5-08-85DC-1915-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1908 TO PS5-08-85DC-1915 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8404 | PS5-08-85DC-1916-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1909 TO PS5-08-85DC-1916 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8405 | PS5-08-85ML-0001-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0017 TO PS5-08-85ML-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8406 | PS5-08-85ML-1201-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1201 TO PS5-08-85ML-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8407 | PS5-08-85ML-1202-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1202 TO PS5-08-85ML-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8408 | PS5-08-85ML-1203-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1203 TO PS5-08-85ML-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8409 | PS5-08-85ML-1204-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1205 TO PS5-08-85ML-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8410 | PS5-08-85ML-1501-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1503 TO PS5-08-85ML-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8411 | PS5-08-85ML-1601-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1603 TO PS5-08-85ML-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8412 | PS5-08-85ML-1602-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1605 TO PS5-08-85ML-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8413 | PS5-08-85ML-1603-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1606 TO PS5-08-85ML-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8414 | PS5-08-85ML-1604-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1608 TO PS5-08-85ML-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8415 | PS5-08-85ML-1605-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1607 TO PS5-08-85ML-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8416 | PS5-08-85ML-1901-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1901 TO PS5-08-85ML-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8417 | PS5-08-85ML-1902-CN01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1902 TO PS5-08-85ML-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8418 | PS5-08-85PB-0001-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0017 TO PS5-08-85PB-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8419 | PS5-08-85PB-1201-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1201 TO PS5-08-85PB-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8420 | PS5-08-85PB-1202-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1202 TO PS5-08-85PB-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8421 | PS5-08-85PB-1203-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1203 TO PS5-08-85PB-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8422 | PS5-08-85PB-1204-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1205 TO PS5-08-85PB-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8423 | PS5-08-85PB-1501-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85PB-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8424 | PS5-08-85PB-1601-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1603 TO PS5-08-85PB-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8425 | PS5-08-85PB-1602-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1605 TO PS5-08-85PB-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8426 | PS5-08-85PB-1603-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1606 TO PS5-08-85PB-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8427 | PS5-08-85PB-1604-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1607 TO PS5-08-85PB-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8428 | PS5-08-85PB-1605-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1608 TO PS5-08-85PB-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8429 | PS5-08-85PB-1901-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1901 TO PS5-08-85PB-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8430 | PS5-08-85PB-1902-CJ01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-1902 TO PS5-08-85PB-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8431 | PS5-82-MBA-0001-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0021 TO PS5-82-MBA-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8432 | PS5-82-MBA-0002-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0023 TO PS5-82-MBA-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8433 | PS5-82-MBA-0003-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0020 TO PS5-82-MBA-0003 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8434 | PS5-82-MGV-0002-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0019 TO PS5-82-MGV-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-8435 | PS5-82-MTL-0001-CC01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-85BT-0022 TO PS5-82-MTL-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00171-9279 | PS5-06-GU-0001A-CA04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001A |  | PS5-06-01 - AC UPS - EITS Building
T-00171-9281 | PS5-06-GU-0001B-CA05 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001B |  | PS5-06-01 - AC UPS - EITS Building
T-00171-9282 | PS5-06-GU-0001-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-06-GU-0001 |  | PS5-06-01 - AC UPS - EITS Building
T-00171-9437 | PS5-61-IJ-0011-CA03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-61-IJ-0010 TO PS5-61-IJ-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011)
T-00171-9468 | PS5-09-LB-8451A-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451A |  | PS5-09-03 - HVAC for Generator Building
T-00171-9469 | PS5-09-LB-8451B-CA01 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451B |  | PS5-09-03 - HVAC for Generator Building
T-00171-9474 | PS5-06-GU-0001A-CA03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001A |  | PS5-06-01 - AC UPS - EITS Building
T-00171-9475 | PS5-06-GU-0001B-CA02 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001B |  | PS5-06-01 - AC UPS - EITS Building
T-00171-9477 | PS5-61-IJ-0001-CA08 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00171-9478 | PS5-61-IJ-0001-CA09 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00171-9479 | PS5-61-IJ-0001-CA10 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00171-9480 | PS5-04-PNC-0001-CA03 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-35CB-1001 TO PS5-04-PNC-0001 |  | PS5-04-03 - 33kV ICSS System
T-00171-9481 | PS5-04-PNC-0001-CA04 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-35CB-1001 TO PS5-04-PNC-0001 |  | PS5-04-03 - 33kV ICSS System
T-00171-9482 | PS5-04-PNC-0001-CA15 | CIX09 - Telecom cable power / Control / Multicore | #N/A | T | Cable FROM PS5-08-35CB-1001 TO PS5-04-PNC-0001 |  | PS5-04-03 - 33kV ICSS System
T-00173-0003 | PS5-08-83SP-1001 | CIX11 - Fiber Optic Patch Panel | #N/A | T | Rack Fiber Connection Module |  | PS5-08-83 - Perimeter & Pipeline intrusion detection system
T-00173-0354 | PS5-08-83SP-0001 | CIX11 - Fiber Optic Patch Panel | #N/A | T | OUTDOOR SPLICE ENCLOSURE |  | PS5-08-83 - Perimeter & Pipeline intrusion detection system
T-00173-0360 | PS5-08-83SP-0002 | CIX11 - Fiber Optic Patch Panel & Splicing box | #N/A | T | OUTDOOR SPLICE ENCLOSURE |  | PS5-08-83 - Perimeter & Pipeline intrusion detection system
T-00174-0116 | PS5-08-11CB-1501 | CIX12 - System Cabinet | #N/A | T | Cabinet |  | PS5-08-11 - Corporate LAN (SIE)
T-00174-0117 | PS5-08-14CB-1201 | CIX12 - System Cabinet | #N/A | T | Cabinet |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00174-0121 | PS5-08-82CB-1201 | CIX12 - System Cabinet | #N/A | T | Safe Haven Key Cabinet |  | PS5-08-82 - Key Management
T-00174-0122 | PS5-08-82CB-1501 | CIX12 - System Cabinet | #N/A | T | Security Room Key Cabinet |  | PS5-08-82 - Key Management
T-00174-0242 | PS5-08-13CB-1201 | CIX12 - System Cabinet | #N/A | T | Cabinet |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00174-0321 | PS5-08-11CB-1201 | CIX12 - System Cabinet | #N/A | T | Telecom cabinet |  | PS5-08-11 - Corporate LAN (SIE)
T-00174-0322 | PS5-08-11CB-1601 | CIX12 - System Cabinet | #N/A | T | Telecom cabinet |  | PS5-08-11 - Corporate LAN (SIE)
T-00174-0323 | PS5-08-11CB-1901 | CIX12 - System Cabinet | #N/A | T | Telecom cabinet |  | PS5-08-11 - Corporate LAN (SIE)
T-00176-0008 | PS5-08-61SN-0001 | CIX14 - Meteorological Sensor / Cable Equipment / Display | #N/A | T | PRESSURE SENSOR |  | PS5-08-61 - Meteocean
T-00176-0009 | PS5-08-61SN-0002 | CIX14 - Meteorological Sensor / Cable Equipment / Display | #N/A | T | BAROMETER SENSOR |  | PS5-08-61 - Meteocean
T-00176-0010 | PS5-08-61SN-0003 | CIX14 - Meteorological Sensor / Cable Equipment / Display | #N/A | T | TEMPERATURE / HUMIDITY SENSOR |  | PS5-08-61 - Meteocean
T-00176-0011 | PS5-08-61SN-0004 | CIX14 - Meteorological Sensor / Cable Equipment / Display | #N/A | T | PRECIPITATION SENSOR |  | PS5-08-61 - Meteocean
T-00176-0012 | PS5-08-61SN-0005 | CIX14 - Meteorological Sensor / Cable Equipment / Display | #N/A | T | CLOUD SENSOR |  | PS5-08-61 - Meteocean
T-00176-0013 | PS5-08-61SN-0901 | CIX14 - Meteorological Sensor / Cable Equipment / Display | #N/A | T | WIND SENSOR |  | PS5-08-61 - Meteocean
T-00176-0041 | PS5-08-61BT-0003 | CIX14 - Meteorological Sensor / Cable Equipment / Display | #N/A | T | SOLAR RADIATION SHIELD |  | PS5-08-61 - Meteocean
T-00180-0018 | PS5-08-55TV-1201 | CIX18 - Monitor/Screen/Projector | #N/A | T | TV set |  | PS5-08-55 - Videoconference
T-00180-0019 | PS5-08-55TV-1202 | CIX18 - Monitor/Screen/Projector | #N/A | T | TV set |  | PS5-08-55 - Videoconference
T-00180-0032 | PS5-08-51TV-1201 | CIX18 - Monitor/Screen/Projector | #N/A | T | 32 TV set + Wall mounting kit model for 32” TV |  | PS5-08-51 - Entertainment
T-00180-0033 | PS5-08-51TV-1202 | CIX18 - Monitor/Screen/Projector | #N/A | T | 32 TV set + Wall mounting kit model for 32” TV |  | PS5-08-51 - Entertainment
T-00180-0034 | PS5-08-51TV-1203 | CIX18 - Monitor/Screen/Projector | #N/A | T | 32 TV set + Wall mounting kit model for 32” TV |  | PS5-08-51 - Entertainment
T-00180-0035 | PS5-08-51TV-1204 | CIX18 - Monitor/Screen/Projector | #N/A | T | 32 TV set + Wall mounting kit model for 32” TV |  | PS5-08-51 - Entertainment
T-00180-0036 | PS5-08-51TV-1205 | CIX18 - Monitor/Screen/Projector | #N/A | T | 75 TV set + Wall mounting kit model for 75” TV |  | PS5-08-51 - Entertainment
T-00180-0037 | PS5-08-51TV-1206 | CIX18 - Monitor/Screen/Projector | #N/A | T | 32 TV set + Wall mounting kit model for 32” TV |  | PS5-08-51 - Entertainment
T-00180-0048 | PS5-08-51TV-1207 | CIX18 - Monitor/Screen/Projector | #N/A | T | 32 TV set + Wall mounting kit model for 32” TV |  | PS5-08-51 - Entertainment
T-00180-0049 | PS5-08-51TV-1208 | CIX18 - Monitor/Screen/Projector | #N/A | T | 32 TV set + Wall mounting kit model for 32” TV |  | PS5-08-51 - Entertainment
T-00180-0050 | PS5-08-51TV-1209 | CIX18 - Monitor/Screen/Projector | #N/A | T | 32 TV set + Wall mounting kit model for 32” TV |  | PS5-08-51 - Entertainment
T-00180-0051 | PS5-08-51TV-1210 | CIX18 - Monitor/Screen/Projector | #N/A | T | 32 TV set + Wall mounting kit model for 32” TV |  | PS5-08-51 - Entertainment
T-00180-0165 | PS5-08-86DY-1201A | CIX18 - Monitor/Screen/Projector | #N/A | T | DISPLAY 24" |  | PS5-08-86 - Integrated Security Management System
T-00180-0166 | PS5-08-86DY-1201B | CIX18 - Monitor/Screen/Projector | #N/A | T | DISPLAY 24" |  | PS5-08-86 - Integrated Security Management System
T-00180-0167 | PS5-08-86DY-1501A | CIX18 - Monitor/Screen/Projector | #N/A | T | DISPLAY 24" |  | PS5-08-86 - Integrated Security Management System
T-00180-0168 | PS5-08-86DY-1501B | CIX18 - Monitor/Screen/Projector | #N/A | T | DISPLAY 24" |  | PS5-08-86 - Integrated Security Management System
T-00180-0169 | PS5-08-86DY-1501C | CIX18 - Monitor/Screen/Projector | #N/A | T | DISPLAY 24" |  | PS5-08-86 - Integrated Security Management System
T-00180-0170 | PS5-08-86DY-1502A | CIX18 - Monitor/Screen/Projector | #N/A | T | DISPLAY 24" |  | PS5-08-86 - Integrated Security Management System
T-00180-0171 | PS5-08-86DY-1502B | CIX18 - Monitor/Screen/Projector | #N/A | T | DISPLAY 24" |  | PS5-08-86 - Integrated Security Management System
T-00180-0172 | PS5-08-86DY-1502C | CIX18 - Monitor/Screen/Projector | #N/A | T | DISPLAY 24" |  | PS5-08-86 - Integrated Security Management System
T-00182-0598 | PS5-08-52BT-0931 | CIX20 - CCTV Camera and housing | #N/A | T | JUNCTION BOX PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0599 | PS5-08-52CM-0001 | CIX20 - CCTV Camera and housing | #N/A | T | FIXED OPTICAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0600 | PS5-08-52CM-0002 | CIX20 - CCTV Camera and housing | #N/A | T | FIXED OPTICAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0601 | PS5-08-52CM-0003 | CIX20 - CCTV Camera and housing | #N/A | T | FIXED OPTICAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0602 | PS5-08-52CM-0004 | CIX20 - CCTV Camera and housing | #N/A | T | FIXED OPTICAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0603 | PS5-08-52CM-0005 | CIX20 - CCTV Camera and housing | #N/A | T | FIXED OPTICAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0604 | PS5-08-52CM-0031 | CIX20 - CCTV Camera and housing | #N/A | T | SAFE AREA PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0605 | PS5-08-52CM-0032 | CIX20 - CCTV Camera and housing | #N/A | T | SAFE AREA PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0606 | PS5-08-52CM-0033 | CIX20 - CCTV Camera and housing | #N/A | T | SAFE AREA PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0607 | PS5-08-52CM-0034 | CIX20 - CCTV Camera and housing | #N/A | T | PANORAMIC AMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0608 | PS5-08-52CM-0071 | CIX20 - CCTV Camera and housing | #N/A | T | THERMAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0609 | PS5-08-52CM-0072 | CIX20 - CCTV Camera and housing | #N/A | T | THERMAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0610 | PS5-08-52CM-0073 | CIX20 - CCTV Camera and housing | #N/A | T | THERMAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0611 | PS5-08-52CM-0074 | CIX20 - CCTV Camera and housing | #N/A | T | THERMAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0612 | PS5-08-52CM-0075 | CIX20 - CCTV Camera and housing | #N/A | T | THERMAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0613 | PS5-08-52CM-0076 | CIX20 - CCTV Camera and housing | #N/A | T | THERMAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0614 | PS5-08-52CM-0077 | CIX20 - CCTV Camera and housing | #N/A | T | THERMAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0615 | PS5-08-52CM-0078 | CIX20 - CCTV Camera and housing | #N/A | T | THERMAL CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0616 | PS5-08-52CM-0131 | CIX20 - CCTV Camera and housing | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0617 | PS5-08-52CM-0132 | CIX20 - CCTV Camera and housing | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0618 | PS5-08-52CM-0133 | CIX20 - CCTV Camera and housing | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0619 | PS5-08-52CM-0134 | CIX20 - CCTV Camera and housing | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0620 | PS5-08-52CM-0135 | CIX20 - CCTV Camera and housing | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0621 | PS5-08-52CM-0136 | CIX20 - CCTV Camera and housing | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0622 | PS5-08-52CM-0137 | CIX20 - CCTV Camera and housing | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0623 | PS5-08-52CM-0138 | CIX20 - CCTV Camera and housing | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0624 | PS5-08-52CM-0139 | CIX20 - CCTV Camera and housing | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0625 | PS5-08-52CM-0140 | CIX20 - CCTV Camera and housing | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0626 | PS5-08-52CM-0931 | CIX20 - CCTV Camera and housing | #N/A | T | SAFE AREA PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0636 | PS5-08-52CM-1201 | CIX20 - CCTV Camera and housing | #N/A | T | OUTDOOR DOME CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0637 | PS5-08-52CM-1202 | CIX20 - CCTV Camera and housing | #N/A | T | OUTDOOR DOME CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0638 | PS5-08-52CM-1203 | CIX20 - CCTV Camera and housing | #N/A | T | INDOOR DOME CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0639 | PS5-08-52CM-1204 | CIX20 - CCTV Camera and housing | #N/A | T | INDOOR DOME CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0640 | PS5-08-52CM-1531 | CIX20 - CCTV Camera and housing | #N/A | T | INDOOR PANORAMIC CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0641 | PS5-08-52CM-1602 | CIX20 - CCTV Camera and housing | #N/A | T | INDOOR DUAL DOME CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0642 | PS5-08-52CM-1603 | CIX20 - CCTV Camera and housing | #N/A | T | INDOOR DUAL DOME CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0643 | PS5-08-52CM-1631 | CIX20 - CCTV Camera and housing | #N/A | T | INDOOR PANORAMIC CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00182-0644 | PS5-08-52TK-0031 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0645 | PS5-08-52TK-0032 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0646 | PS5-08-52TK-0033 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0647 | PS5-08-52TK-0131 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0648 | PS5-08-52TK-0132 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0649 | PS5-08-52TK-0133 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0650 | PS5-08-52TK-0134 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0651 | PS5-08-52TK-0135 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0652 | PS5-08-52TK-0136 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0653 | PS5-08-52TK-0137 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0654 | PS5-08-52TK-0138 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0655 | PS5-08-52TK-0139 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0656 | PS5-08-52TK-0140 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00182-0657 | PS5-08-52TK-0931 | CIX20 - CCTV Camera and housing | #N/A | T | WATER TANK 23L |  | PS5-08-52 - Process & Security CCTV
T-00183-0005 | PS5-08-34AN-0001 | CIX21 - Radio Antenna | #N/A | T | Marine IRIDIUM Antenna |  | PS5-08-34 - Satphone
T-00183-0006 | PS5-08-34AN-0002 | CIX21 - Radio Antenna | #N/A | T | Marine IRIDIUM Antenna |  | PS5-08-34 - Satphone
T-00183-0086 | PS5-08-23AN-0001 | CIX21 - Radio Antenna | #N/A | T | Antenna |  | PS5-08-23 - VHF Trunk Radio System
T-00183-0087 | PS5-08-23AN-0002 | CIX21 - Radio Antenna | #N/A | T | Antenna |  | PS5-08-23 - VHF Trunk Radio System
T-00183-0088 | PS5-08-23AN-0003 | CIX21 - Radio Antenna | #N/A | T | Yagi Donor Antenna |  | PS5-08-23 - VHF Trunk Radio System
T-00183-0089 | PS5-08-23AN-0004 | CIX21 - Radio Antenna | #N/A | T | Yagi Donor Antenna |  | PS5-08-23 - VHF Trunk Radio System
T-00183-0090 | PS5-08-23AN-0901 | CIX21 - Radio Antenna | #N/A | T | Antenna |  | PS5-08-23 - VHF Trunk Radio System
T-00183-0093 | PS5-08-23AN-1201 | CIX21 - Radio Antenna | #N/A | T | Flat Panel Antenna |  | PS5-08-23 - VHF Trunk Radio System
T-00183-0094 | PS5-08-23AN-1601 | CIX21 - Radio Antenna | #N/A | T | Flat Panel Antenna |  | PS5-08-23 - VHF Trunk Radio System
T-00183-0229 | PS5-08-51AN-0001 | CIX21 - Radio Antenna | #N/A | T | Satellite antenna |  | PS5-08-51 - Entertainment
T-00183-0230 | PS5-08-51LN-0001 | CIX21 - Radio Antenna | #N/A | T | Quattro LNB |  | PS5-08-51 - Entertainment
T-00187-0009 | PS5-08-34DS-1201 | CIX25 - Radio Remote Control Unit / Station / Console | #N/A | T | Docking station |  | PS5-08-34 - Satphone
T-00187-0010 | PS5-08-34DS-1211 | CIX25 - Radio Remote Control Unit / Station / Console | #N/A | T | BIAS Box |  | PS5-08-34 - Satphone
T-00187-0011 | PS5-08-34DS-1501 | CIX25 - Radio Remote Control Unit / Station / Console | #N/A | T | Docking station |  | PS5-08-34 - Satphone
T-00187-0012 | PS5-08-34DS-1511 | CIX25 - Radio Remote Control Unit / Station / Console | #N/A | T | BIAS Box |  | PS5-08-34 - Satphone
T-00188-0023 | PS5-08-23BS-1201 | CIX26 - Radio Base Station | #N/A | T | Fixed Base station |  | PS5-08-23 - VHF Trunk Radio System
T-00188-0024 | PS5-08-23BS-1501 | CIX26 - Radio Base Station | #N/A | T | Fixed Base station |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0005 | PS5-08-34MB-3001 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | SATPHONE |  | PS5-08-34 - Satphone
T-00189-0006 | PS5-08-34MB-3002 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | SATPHONE |  | PS5-08-34 - Satphone
T-00189-0116 | PS5-08-23CH-1201 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | Multiway Charger |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0117 | PS5-08-23CH-1202 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | Multiway Charger |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0118 | PS5-08-23HP-3001 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0119 | PS5-08-23HP-3002 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0120 | PS5-08-23HP-3003 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0121 | PS5-08-23HP-3004 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0122 | PS5-08-23HP-3005 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0123 | PS5-08-23HP-3006 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0124 | PS5-08-23HP-3007 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0125 | PS5-08-23HP-3008 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0126 | PS5-08-23HP-3009 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0127 | PS5-08-23HP-3010 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0128 | PS5-08-23HP-3011 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0129 | PS5-08-23HP-3012 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0130 | PS5-08-23HP-3013 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0131 | PS5-08-23HP-3014 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0132 | PS5-08-23HP-3015 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0133 | PS5-08-23HP-3016 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0134 | PS5-08-23HP-3017 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0135 | PS5-08-23HP-3018 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0136 | PS5-08-23HP-3019 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0137 | PS5-08-23HP-3020 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0138 | PS5-08-23HP-3021 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0139 | PS5-08-23HP-3022 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0140 | PS5-08-23HP-3023 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0141 | PS5-08-23HP-3024 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0142 | PS5-08-23HP-3025 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00189-0310 | PS5-08-85DS-1201 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | Muster Tablet Docking Station |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00189-0311 | PS5-08-85MT-1201 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | Muster Tablet - 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00189-0312 | PS5-08-85MT-1202 | CIX27 - Radio Handheld, Pager and Battery Charger | #N/A | T | Muster Tablet - 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00190-0006 | PS5-08-92MT-0001 | CIX28 - Radio Mast / Tower | #N/A | T | Telecom Mast lattice structure, 4legs / Square base, - 10.5m high (AGL) |  | PS5-08-92 - Telecom Mast
T-00200-1040 | PS5-08-71SK-1201 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1041 | PS5-08-71SK-1202 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1042 | PS5-08-71SK-1203 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1043 | PS5-08-71SK-1204 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1044 | PS5-08-71SK-1205 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1045 | PS5-08-71SK-1206A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1046 | PS5-08-71SK-1206B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1047 | PS5-08-71SK-1207 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1048 | PS5-08-71SK-1208 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1049 | PS5-08-71SK-1209 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1050 | PS5-08-71SK-1210 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1051 | PS5-08-71SK-1211 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1052 | PS5-08-71SK-1212A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1053 | PS5-08-71SK-1212B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1054 | PS5-08-71SK-1213 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1055 | PS5-08-71SK-1214A | CIX38 - RJ45 Socket | #N/A | T | quad RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1056 | PS5-08-71SK-1214B | CIX38 - RJ45 Socket | #N/A | T | quad RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1057 | PS5-08-71SK-1214C | CIX38 - RJ45 Socket | #N/A | T | quad RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1058 | PS5-08-71SK-1214D | CIX38 - RJ45 Socket | #N/A | T | quad RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1059 | PS5-08-71SK-1215A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1060 | PS5-08-71SK-1215B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1061 | PS5-08-71SK-1216A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1062 | PS5-08-71SK-1216B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1063 | PS5-08-71SK-1217A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1064 | PS5-08-71SK-1217B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1065 | PS5-08-71SK-1218A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1066 | PS5-08-71SK-1218B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1067 | PS5-08-71SK-1219A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1068 | PS5-08-71SK-1219B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1069 | PS5-08-71SK-1220A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1070 | PS5-08-71SK-1220B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1071 | PS5-08-71SK-1221A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1072 | PS5-08-71SK-1221B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1073 | PS5-08-71SK-1222A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1074 | PS5-08-71SK-1222B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1075 | PS5-08-71SK-1223A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1076 | PS5-08-71SK-1223B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1077 | PS5-08-71SK-1224A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1078 | PS5-08-71SK-1224B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1079 | PS5-08-71SK-1225A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1080 | PS5-08-71SK-1225B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1081 | PS5-08-71SK-1226A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1082 | PS5-08-71SK-1226B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1083 | PS5-08-71SK-1227A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1084 | PS5-08-71SK-1227B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1085 | PS5-08-71SK-1228A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1086 | PS5-08-71SK-1228B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1087 | PS5-08-71SK-1229 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1088 | PS5-08-71SK-1230A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1089 | PS5-08-71SK-1230B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1090 | PS5-08-71SK-1231 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1091 | PS5-08-71SK-1232A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1092 | PS5-08-71SK-1232B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1093 | PS5-08-71SK-1233A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1094 | PS5-08-71SK-1233B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1095 | PS5-08-71SK-1234 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1096 | PS5-08-71SK-1235 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1097 | PS5-08-71SK-1236A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1098 | PS5-08-71SK-1236B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1099 | PS5-08-71SK-1237 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1100 | PS5-08-71SK-1238 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1101 | PS5-08-71SK-1239 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1102 | PS5-08-71SK-1240 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1103 | PS5-08-71SK-1241A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1104 | PS5-08-71SK-1241B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1105 | PS5-08-71SK-1242A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1106 | PS5-08-71SK-1242B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1107 | PS5-08-71SK-1243A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1108 | PS5-08-71SK-1243B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1109 | PS5-08-71SK-1244A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1110 | PS5-08-71SK-1244B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1111 | PS5-08-71SK-1245A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1112 | PS5-08-71SK-1245B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1113 | PS5-08-71SK-1246A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1114 | PS5-08-71SK-1246B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1115 | PS5-08-71SK-1247 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1116 | PS5-08-71SK-1248 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1117 | PS5-08-71SK-1249A | CIX38 - RJ45 Socket | #N/A | T | quad RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1118 | PS5-08-71SK-1249B | CIX38 - RJ45 Socket | #N/A | T | quad RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1119 | PS5-08-71SK-1249C | CIX38 - RJ45 Socket | #N/A | T | quad RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1120 | PS5-08-71SK-1249D | CIX38 - RJ45 Socket | #N/A | T | quad RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1121 | PS5-08-71SK-1250A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1122 | PS5-08-71SK-1250B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1123 | PS5-08-71SK-1501A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1124 | PS5-08-71SK-1501B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1125 | PS5-08-71SK-1502A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1126 | PS5-08-71SK-1502B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1127 | PS5-08-71SK-1503A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1128 | PS5-08-71SK-1503B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1129 | PS5-08-71SK-1504A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1130 | PS5-08-71SK-1504B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1131 | PS5-08-71SK-1505 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1132 | PS5-08-71SK-1506 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1133 | PS5-08-71SK-1507 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1134 | PS5-08-71SK-1508 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1135 | PS5-08-71SK-1509 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1136 | PS5-08-71SK-1510A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1137 | PS5-08-71SK-1510B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1138 | PS5-08-71SK-1511A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1139 | PS5-08-71SK-1511B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1140 | PS5-08-71SK-1512 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1141 | PS5-08-71SK-1513 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1142 | PS5-08-71SK-1601A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1143 | PS5-08-71SK-1601B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1144 | PS5-08-71SK-1602A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1145 | PS5-08-71SK-1602B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1146 | PS5-08-71SK-1603A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1147 | PS5-08-71SK-1604A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1148 | PS5-08-71SK-1604B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1149 | PS5-08-71SK-1605A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1150 | PS5-08-71SK-1605B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1151 | PS5-08-71SK-1606 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1152 | PS5-08-71SK-1607 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1153 | PS5-08-71SK-1608 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1154 | PS5-08-71SK-1609 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1155 | PS5-08-71SK-1610 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1156 | PS5-08-71SK-1611 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1157 | PS5-08-71SK-1901 | CIX38 - RJ45 Socket | #N/A | T | Single RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1158 | PS5-08-71SK-1903A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1159 | PS5-08-71SK-1903B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1160 | PS5-08-71SK-1904A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1161 | PS5-08-71SK-1904B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1162 | PS5-08-71SK-1905A | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1163 | PS5-08-71SK-1905B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00200-1164 | PS5-08-71SK-1603B | CIX38 - RJ45 Socket | #N/A | T | Dual RJ45 socket |  | PS5-08-71 - Structured Cabling (CAT6)
T-00202-0012 | PS5-08-61WK-1201 | CIX40 - PC workstation | #N/A | T | METEOCEAN WORKSTATION (Inclus. Monitor, keyboard & mouse) |  | PS5-08-61 - Meteocean
T-00202-0090 | PS5-08-86CM-1501 | CIX40 - PC workstation | #N/A | T | WEBCAM |  | PS5-08-86 - Integrated Security Management System
T-00202-0091 | PS5-08-86PR-1201 | CIX40 - PC workstation | #N/A | T | PAPER PRINTER |  | PS5-08-86 - Integrated Security Management System
T-00202-0092 | PS5-08-86WK-1201 | CIX40 - PC workstation | #N/A | T | WORKSTATION |  | PS5-08-86 - Integrated Security Management System
T-00202-0093 | PS5-08-86WK-1501 | CIX40 - PC workstation | #N/A | T | WORKSTATION |  | PS5-08-86 - Integrated Security Management System
T-00202-0094 | PS5-08-86WK-1502 | CIX40 - PC workstation | #N/A | T | WORKSTATION |  | PS5-08-86 - Integrated Security Management System
T-00202-0104 | PS5-04-OWS-0001 | CIX40 - PC workstation | #N/A | T | PCS Operator Workstation (68OWS1) |  | PS5-04-01 - Office Building PCS System
T-00203-0013 | PS5-08-81DS-1501 | CIX41 - Server | #N/A | T | Data Collector Station |  | PS5-08-81 - Guard tour
T-00203-0014 | PS5-08-81DS-1502 | CIX41 - Server | #N/A | T | Data Collector Station |  | PS5-08-81 - Guard tour
T-00204-0010 | PS5-04-PR-0001 | CIX42 - Data Network Equipment | #N/A | T | Alarm Report Printer |  | PS5-04-01 - Office Building PCS System
T-00206-0005 | PS5-08-61BT-0001 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX |  | PS5-08-61 - Meteocean
T-00206-0006 | PS5-08-61BT-0002 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX |  | PS5-08-61 - Meteocean
T-00206-0008 | PS5-08-61BT-0901 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX |  | PS5-08-61 - Meteocean
T-00206-0435 | PS5-08-01BT-0001 | CIX44 - Telecom Junction Box | #N/A | T | OCU junction box #1 at Primary muster point |  | PS5-08-01 - PAGA
T-00206-0436 | PS5-08-01BT-0002 | CIX44 - Telecom Junction Box | #N/A | T | OCU junction box #2 at Primary muster point |  | PS5-08-01 - PAGA
T-00206-0437 | PS5-08-01BT-0003 | CIX44 - Telecom Junction Box | #N/A | T | OCU junction box #1 at Secondary muster point |  | PS5-08-01 - PAGA
T-00206-0438 | PS5-08-01BT-0004 | CIX44 - Telecom Junction Box | #N/A | T | OCU junction box #2 at Secondary muster point |  | PS5-08-01 - PAGA
T-00206-0439 | PS5-08-01BT-1201 | CIX44 - Telecom Junction Box | #N/A | T | Building LS junction box with muting arrangement and bedroom zone relay |  | PS5-08-01 - PAGA
T-00206-0440 | PS5-08-01BT-1202 | CIX44 - Telecom Junction Box | #N/A | T | Building LS junction box with muting arrangement and bedroom zone relay |  | PS5-08-01 - PAGA
T-00206-0441 | PS5-08-01BT-1203 | CIX44 - Telecom Junction Box | #N/A | T | ACCESS UNIT junction box |  | PS5-08-01 - PAGA
T-00206-0442 | PS5-08-01BT-1501 | CIX44 - Telecom Junction Box | #N/A | T | Building LS junction box without muting arrangement |  | PS5-08-01 - PAGA
T-00206-0443 | PS5-08-01BT-1502 | CIX44 - Telecom Junction Box | #N/A | T | Building LS junction box without muting arrangement |  | PS5-08-01 - PAGA
T-00206-0444 | PS5-08-01BT-1503 | CIX44 - Telecom Junction Box | #N/A | T | ACCESS UNIT junction box |  | PS5-08-01 - PAGA
T-00206-0445 | PS5-08-01BT-1601 | CIX44 - Telecom Junction Box | #N/A | T | Building LS junction box without muting arrangement |  | PS5-08-01 - PAGA
T-00206-0446 | PS5-08-01BT-1602 | CIX44 - Telecom Junction Box | #N/A | T | Building LS junction box without muting arrangement |  | PS5-08-01 - PAGA
T-00206-0447 | PS5-08-01BT-1901 | CIX44 - Telecom Junction Box | #N/A | T | Building LS junction box without muting arrangement |  | PS5-08-01 - PAGA
T-00206-0448 | PS5-08-01BT-1902 | CIX44 - Telecom Junction Box | #N/A | T | Building LS junction box without muting arrangement |  | PS5-08-01 - PAGA
T-00206-0449 | PS5-08-01BT-1903 | CIX44 - Telecom Junction Box | #N/A | T | Building LS junction box without muting arrangement |  | PS5-08-01 - PAGA
T-00206-0450 | PS5-08-01BT-1904 | CIX44 - Telecom Junction Box | #N/A | T | Building LS junction box without muting arrangement |  | PS5-08-01 - PAGA
T-00206-0682 | PS5-08-52BT-0131 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00206-0683 | PS5-08-52BT-0132 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00206-0684 | PS5-08-52BT-0133 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00206-0685 | PS5-08-52BT-0134 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00206-0686 | PS5-08-52BT-0135 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00206-0687 | PS5-08-52BT-0136 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00206-0688 | PS5-08-52BT-0137 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00206-0689 | PS5-08-52BT-0138 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00206-0690 | PS5-08-52BT-0139 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00206-0691 | PS5-08-52BT-0140 | CIX44 - Telecom Junction Box | #N/A | T | JUNCTION BOX PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00206-0768 | PS5-08-12BT-0001 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0769 | PS5-08-12BT-0002 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0770 | PS5-08-12BT-0003 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0771 | PS5-08-12BT-0101 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0772 | PS5-08-12BT-0103 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0773 | PS5-08-12BT-0104 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0774 | PS5-08-12BT-0105 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0775 | PS5-08-12BT-0106 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0776 | PS5-08-12BT-0107 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0777 | PS5-08-12BT-0108 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0778 | PS5-08-12BT-0109 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0779 | PS5-08-12BT-1903 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0780 | PS5-08-12BT-1904 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00206-0813 | PS5-08-85BT-0027 | CIX44 - Telecom Junction Box | #N/A | T | WiFi Access Point A - Junction Box |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0820 | PS5-08-85BT-1006 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - ED Room Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0821 | PS5-08-85BT-1201 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Main Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0822 | PS5-08-85BT-1202 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Clinic Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0823 | PS5-08-85BT-1203 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Dining Area to Office Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0824 | PS5-08-85BT-1204 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Tel. Room - Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0825 | PS5-08-85BT-1205 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Telecom Room Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0826 | PS5-08-85BT-1501 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box 1 - Search Area |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0827 | PS5-08-85BT-1502 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box 2 - Search Area |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0828 | PS5-08-85BT-1503 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Safe Haven Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0829 | PS5-08-85BT-1601 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Warehouse Ramp |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0830 | PS5-08-85BT-1602 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Warehouse Emergency Escape - 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0831 | PS5-08-85BT-1603 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Warehouse Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0832 | PS5-08-85BT-1604 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Main Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0833 | PS5-08-85BT-1605 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Warehouse Office Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0834 | PS5-08-85BT-1606 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Elec. Ins. Store Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0835 | PS5-08-85BT-1607 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - AC Controlled Store |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0836 | PS5-08-85BT-1608 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Elec. Ins. Workshop Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0837 | PS5-08-85BT-1609 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Workshop Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0838 | PS5-08-85BT-1610 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Workshop Ramp |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0839 | PS5-08-85BT-1611 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Workshop Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0840 | PS5-08-85BT-1612 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - AC Controlled Store Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0841 | PS5-08-85BT-1613 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Oil Spill response store |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0842 | PS5-08-85BT-1614 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Warehouse Emergency Escape - 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0843 | PS5-08-85BT-1901 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Entrance 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0844 | PS5-08-85BT-1902 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Entrance 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0845 | PS5-08-85BT-1903 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Double Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0846 | PS5-08-85BT-1904 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Double Door & Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0847 | PS5-08-85BT-1905 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Double Door & Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0848 | PS5-08-85BT-1906 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Double Door & Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0849 | PS5-08-85BT-1907 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Double Door & Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0850 | PS5-08-85BT-1908 | CIX44 - Telecom Junction Box | #N/A | T | Junction Box - Double Door & Single Door 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0851 | PS5-08-85CP-0024 | CIX44 - Telecom Junction Box | #N/A | T | Outdoor Muster Enclosure A |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0852 | PS5-08-85CP-0025 | CIX44 - Telecom Junction Box | #N/A | T | Outdoor Muster Enclosure B |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0854 | PS5-08-85CP-1201 | CIX44 - Telecom Junction Box | #N/A | T | Controller Enclosure - 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0855 | PS5-08-85CP-1202 | CIX44 - Telecom Junction Box | #N/A | T | Controller Enclosure - 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0856 | PS5-08-85CP-1501 | CIX44 - Telecom Junction Box | #N/A | T | Controller Enclosure |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0857 | PS5-08-85CP-1502 | CIX44 - Telecom Junction Box | #N/A | T | Controller Enclosure |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0858 | PS5-08-85CP-1601 | CIX44 - Telecom Junction Box | #N/A | T | Controller Enclosure |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0859 | PS5-08-85CP-1901 | CIX44 - Telecom Junction Box | #N/A | T | Controller Enclosure |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0860 | PS5-08-85BT-0028 | CIX44 - Telecom Junction Box | #N/A | T | WiFi Access Point A - Junction Box |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00206-0921 | PS5-08-15CP-0001 | CIX44 - Telecom Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00206-0922 | PS5-08-15CP-0002 | CIX44 - Telecom Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00206-0923 | PS5-08-15CP-0003 | CIX44 - Telecom Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00206-0924 | PS5-08-15CP-0004 | CIX44 - Telecom Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00206-0925 | PS5-08-15CP-0005 | CIX44 - Telecom Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00206-0926 | PS5-08-15CP-0006 | CIX44 - Telecom Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00206-0927 | PS5-08-15CP-0007 | CIX44 - Telecom Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00206-0928 | PS5-08-15CP-0008 | CIX44 - Telecom Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00207-0003 | PS5-08-82BR-1201 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader |  | PS5-08-82 - Key Management
T-00207-0004 | PS5-08-82BR-1501 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader |  | PS5-08-82 - Key Management
T-00207-1249 | PS5-08-86DB-1501 | CIX45 - Access Control Device & Field enclosure | #N/A | T | ENROLLER |  | PS5-08-86 - Integrated Security Management System
T-00207-1250 | PS5-08-86PR-1501 | CIX45 - Access Control Device & Field enclosure | #N/A | T | BADGE PRINTER |  | PS5-08-86 - Integrated Security Management System
T-00207-1295 | PS5-08-81RF-0001 | CIX45 - Access Control Device & Field enclosure | #N/A | T | DALLAS Check point |  | PS5-08-81 - Guard tour
T-00207-1296 | PS5-08-81RF-0002 | CIX45 - Access Control Device & Field enclosure | #N/A | T | DALLAS Check point |  | PS5-08-81 - Guard tour
T-00207-1297 | PS5-08-81RF-0003 | CIX45 - Access Control Device & Field enclosure | #N/A | T | DALLAS Check point |  | PS5-08-81 - Guard tour
T-00207-1298 | PS5-08-81RF-0004 | CIX45 - Access Control Device & Field enclosure | #N/A | T | DALLAS Check point |  | PS5-08-81 - Guard tour
T-00207-1299 | PS5-08-81RF-0005 | CIX45 - Access Control Device & Field enclosure | #N/A | T | DALLAS Check point |  | PS5-08-81 - Guard tour
T-00207-1300 | PS5-08-81RF-0006 | CIX45 - Access Control Device & Field enclosure | #N/A | T | DALLAS Check point |  | PS5-08-81 - Guard tour
T-00207-1301 | PS5-08-81RF-0007 | CIX45 - Access Control Device & Field enclosure | #N/A | T | DALLAS Check point |  | PS5-08-81 - Guard tour
T-00207-1302 | PS5-08-81RF-0008 | CIX45 - Access Control Device & Field enclosure | #N/A | T | DALLAS Check point |  | PS5-08-81 - Guard tour
T-00207-1327 | PS5-08-85BG-1201 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - Main Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1328 | PS5-08-85BG-1202 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - Clinic Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1329 | PS5-08-85BG-1203 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - Dining Area to Office Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1330 | PS5-08-85BG-1204 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - Telecom Room Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1331 | PS5-08-85BG-1501 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - Safe Haven Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1332 | PS5-08-85BG-1601 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - Warehouse Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1333 | PS5-08-85BG-1602 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - Warehouse Office Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1334 | PS5-08-85BG-1603 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - Elec. Ins. Store Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1335 | PS5-08-85BG-1604 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - AC Controlled Store |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1336 | PS5-08-85BG-1605 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - Elec. Ins. Workshop Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1337 | PS5-08-85BG-1901 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - Entrance 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1338 | PS5-08-85BG-1902 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Emergency Breack Glass - Entrance 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1339 | PS5-08-85BR-0009 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader A - Primary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1340 | PS5-08-85BR-0010 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader B - Primary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1341 | PS5-08-85BR-0011 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader A - Secondary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1342 | PS5-08-85BR-0012 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader B - Secondary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1345 | PS5-08-85BR-1201 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader - Main Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1346 | PS5-08-85BR-1202 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader - Clinic Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1347 | PS5-08-85BR-1203 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader - Dining Area to Office Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1348 | PS5-08-85BR-1204 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Biometric Badge Reader - Telecom Room Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1349 | PS5-08-85BR-1205 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader A - Safe Haven |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1350 | PS5-08-85BR-1206 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader B - Safe Haven |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1351 | PS5-08-85BR-1501 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Biometric Badge Reader - Safe Haven Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1352 | PS5-08-85BR-1502 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader - Safe Haven Exit |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1353 | PS5-08-85BR-1601 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader - Warehouse Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1354 | PS5-08-85BR-1602 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader - Warehouse Office Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1355 | PS5-08-85BR-1603 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader - Elec. Ins. Store Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1356 | PS5-08-85BR-1604 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader - AC Controlled Store |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1357 | PS5-08-85BR-1605 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader - Elec. Ins. Workshop Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1358 | PS5-08-85BR-1901 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader - Entrance 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1359 | PS5-08-85BR-1902 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Standard Badge Reader - Entrance 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1368 | PS5-08-85DC-1008 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 2 - ED Room Emergency Escape 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1369 | PS5-08-85DC-1201 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Main Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1370 | PS5-08-85DC-1202 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Clinic Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1371 | PS5-08-85DC-1203 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Clinic Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1372 | PS5-08-85DC-1204 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Dining Area to Office Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1373 | PS5-08-85DC-1205 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 1 - Tel. Room - Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1374 | PS5-08-85DC-1206 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 2 - Tel. Room - Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1375 | PS5-08-85DC-1207 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Telecom Room Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1376 | PS5-08-85DC-1501 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 1 - Search Area |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1377 | PS5-08-85DC-1502 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 2 - Search Area |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1378 | PS5-08-85DC-1503 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Safe Haven Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1379 | PS5-08-85DC-1601 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Warehouse Ramp |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1380 | PS5-08-85DC-1602 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Warehouse Emergency Escape - 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1381 | PS5-08-85DC-1603 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Warehouse Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1382 | PS5-08-85DC-1604 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Warehouse Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1383 | PS5-08-85DC-1605 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 1 - Main Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1384 | PS5-08-85DC-1606 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 2 - Main Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1385 | PS5-08-85DC-1607 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - AC Controlled Store |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1386 | PS5-08-85DC-1608 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 1 - Elec. Ins. Store Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1387 | PS5-08-85DC-1609 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 2 - Elec. Ins. Store Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1388 | PS5-08-85DC-1610 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Warehouse Emergency Escape - 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1389 | PS5-08-85DC-1611 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 1 - Oil Spill response store |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1390 | PS5-08-85DC-1612 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 2 - Oil Spill response store |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1391 | PS5-08-85DC-1613 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 2 - AC Controlled Store Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1392 | PS5-08-85DC-1614 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 2 - Workshop Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1393 | PS5-08-85DC-1615 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 2 - Workshop Ramp |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1394 | PS5-08-85DC-1616 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact 2 - Workshop Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1395 | PS5-08-85DC-1617 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Warehouse Office Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1396 | PS5-08-85DC-1618 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Elec. Ins. Workshop Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1397 | PS5-08-85DC-1901 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Double Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1398 | PS5-08-85DC-1902 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Double Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1399 | PS5-08-85DC-1903 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Double Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1400 | PS5-08-85DC-1904 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1401 | PS5-08-85DC-1905 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Double Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1402 | PS5-08-85DC-1906 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1403 | PS5-08-85DC-1907 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Double Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1404 | PS5-08-85DC-1908 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1405 | PS5-08-85DC-1909 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Double Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1406 | PS5-08-85DC-1910 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1407 | PS5-08-85DC-1911 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Entrance 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1408 | PS5-08-85DC-1912 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Entrance 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1409 | PS5-08-85DC-1913 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Single Door 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1410 | PS5-08-85DC-1914 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Double Door 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1411 | PS5-08-85DC-1915 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Door Contact - Double Door 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1415 | PS5-08-85ML-1201 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - Main Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1416 | PS5-08-85ML-1202 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - Clinic Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1417 | PS5-08-85ML-1203 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - Dining Area to Office Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1418 | PS5-08-85ML-1204 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - Telecom Room Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1419 | PS5-08-85ML-1501 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - Safe Haven Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1420 | PS5-08-85ML-1601 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - Warehouse Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1421 | PS5-08-85ML-1602 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - Warehouse Office Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1422 | PS5-08-85ML-1603 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - Elec. Ins. Store Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1423 | PS5-08-85ML-1604 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - Elec. Ins. Workshop Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1424 | PS5-08-85ML-1605 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - AC Controlled Store |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1425 | PS5-08-85ML-1901 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - Entrance 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1426 | PS5-08-85ML-1902 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Magnetic Lock Fail Safe - Entrance 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1429 | PS5-08-85PB-1201 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Exit Push Button - Main Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1430 | PS5-08-85PB-1202 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Exit Push Button -Clinic Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1431 | PS5-08-85PB-1203 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Exit Push Button - Dining Area to Office Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1432 | PS5-08-85PB-1204 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Exit Push Button -Telecom Room Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1433 | PS5-08-85PB-1501 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Panic Button |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1434 | PS5-08-85PB-1601 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Exit Push Button - Warehouse Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1435 | PS5-08-85PB-1602 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Exit Push Button - Warehouse Office Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1436 | PS5-08-85PB-1603 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Exit Push Button - Elec. Ins. Store Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1437 | PS5-08-85PB-1604 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Exit Push Button - AC Controlled Store |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1438 | PS5-08-85PB-1605 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Exit Push Button - Elec. Ins. Workshop Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1439 | PS5-08-85PB-1901 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Exit Push Button - Entrance 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1440 | PS5-08-85PB-1902 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Exit Push Button - Entrance 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1441 | PS5-82-MBA-0001 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Barrier - 1 - Site Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1442 | PS5-82-MBA-0002 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Barrier - 2 - Site Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1443 | PS5-82-MBA-0003 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Barrier - 3 - Site Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00207-1444 | PS5-82-MTL-0001 | CIX45 - Access Control Device & Field enclosure | #N/A | T | Turnstile - Site Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00208-0025 | PS5-08-04TP-1201 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | Red hotline handset with patch cord without keyboard |  | PS5-08-04 - Hotline
T-00208-0026 | PS5-08-04TP-1202 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | Red hotline handset with patch cord without keyboard |  | PS5-08-04 - Hotline
T-00208-0027 | PS5-08-04TP-1501 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | Red hotline handset with patch cord without keyboard |  | PS5-08-04 - Hotline
T-00208-0028 | PS5-08-04TP-1502 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | Red hotline handset with patch cord without keyboard |  | PS5-08-04 - Hotline
T-00208-0666 | PS5-08-03AF-1201 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | Audio Conference Phone |  | PS5-08-03 - Telephone
T-00208-0669 | PS5-08-03TP-1201 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0670 | PS5-08-03TP-1202 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0671 | PS5-08-03TP-1203 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0672 | PS5-08-03TP-1204 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0673 | PS5-08-03TP-1205 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0674 | PS5-08-03TP-1206 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0675 | PS5-08-03TP-1207 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0676 | PS5-08-03TP-1208 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0677 | PS5-08-03TP-1209 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0678 | PS5-08-03TP-1210 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0679 | PS5-08-03TP-1211 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0680 | PS5-08-03TP-1212 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0681 | PS5-08-03TP-1213 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0682 | PS5-08-03TP-1214 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0683 | PS5-08-03TP-1215 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0684 | PS5-08-03TP-1216 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0685 | PS5-08-03TP-1217 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0686 | PS5-08-03TP-1218 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0687 | PS5-08-03TP-1219 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0688 | PS5-08-03TP-1220 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0689 | PS5-08-03TP-1221 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0690 | PS5-08-03TP-1222 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0691 | PS5-08-03TP-1501 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0692 | PS5-08-03TP-1502 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0693 | PS5-08-03TP-1601 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0694 | PS5-08-03TP-1602 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0695 | PS5-08-03TP-1603 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0696 | PS5-08-03TP-1604 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0697 | PS5-08-03TP-1605 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0698 | PS5-08-55VF-1201 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | Video Conference Unit |  | PS5-08-55 - Videoconference
T-00208-0752 | PS5-08-03TP-1223 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0753 | PS5-08-03TP-1224 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0754 | PS5-08-03TP-1225 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00208-0755 | PS5-08-03TP-1226 | CIX46 - IP/Digital/ Analogue Phone | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00275-1945 | PS5-60-IE-0003B-CA02 | TIX01 - RJ45 Cable | PS5-60-IE-0003B-CA02 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-65-20-0040 | 2026-07-30 | OPEN | G K RAO | TESTING
T-00275-1946 | PS5-60-IE-0003B-CA03 | TIX01 - RJ45 Cable | PS5-60-IE-0003B-CA03 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-65-20-0040 | 2026-07-30 | OPEN | G K RAO | TESTING
T-00275-1947 | PS5-60-IE-0003B-CA04 | TIX01 - RJ45 Cable | PS5-60-IE-0003B-CA04 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-65-20-0040 | 2026-07-30 | OPEN | G K RAO | TESTING
T-00275-1948 | PS5-60-IE-0003B-CA05 | TIX01 - RJ45 Cable | PS5-60-IE-0003B-CA05 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B |  | PS5-60-05 - Power Gen Package B (UCP) | CPP-RFI-68-65-20-0040 | 2026-07-30 | OPEN | G K RAO | TESTING
T-00275-1949 | PS5-60-IE-0003C-CA02 | TIX01 - RJ45 Cable | PS5-60-IE-0003C-CA02 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-1950 | PS5-60-IE-0003C-CA03 | TIX01 - RJ45 Cable | PS5-60-IE-0003C-CA03 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-1951 | PS5-60-IE-0003C-CA04 | TIX01 - RJ45 Cable | PS5-60-IE-0003C-CA04 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-1952 | PS5-60-IE-0003C-CA05 | TIX01 - RJ45 Cable | PS5-60-IE-0003C-CA05 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C |  | PS5-60-08 - Power Gen Package C (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-1953 | PS5-60-IE-0003D-CA02 | TIX01 - RJ45 Cable | PS5-60-IE-0003D-CA02 | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-1954 | PS5-60-IE-0003D-CA03 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-1955 | PS5-60-IE-0003D-CA04 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-1956 | PS5-60-IE-0003D-CA05 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D |  | PS5-60-11 - Power Gen Package D (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-1957 | PS5-60-IE-0003E-CA02 | TIX01 - RJ45 Cable | PS5-60-IE-0003E-CA02 | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00275-1958 | PS5-60-IE-0003E-CA03 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00275-1959 | PS5-60-IE-0003E-CA04 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00275-1960 | PS5-60-IE-0003E-CA05 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E |  | PS5-60-14 - Power Gen Package E (UCP)
T-00275-1961 | PS5-60-IE-0003F-CA02 | TIX01 - RJ45 Cable | PS5-60-IE-0003F-CA02 | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00275-1962 | PS5-60-IE-0003F-CA03 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00275-1963 | PS5-60-IE-0003F-CA04 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00275-1964 | PS5-60-IE-0003F-CA05 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F |  | PS5-60-17 - Power Gen Package F (UCP)
T-00275-1965 | PS5-60-IE-0003G-CA03 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00275-1966 | PS5-60-IE-0003G-CA04 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00275-1967 | PS5-60-IE-0003G-CA05 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G |  | PS5-60-20 - Power Gen Package G (UCP)
T-00275-1968 | PS5-60-IE-0004-CA01 | TIX01 - RJ45 Cable | PS5-60-IE-0004-CA01 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-65-20-0040 | 2026-07-30 | OPEN | G K RAO | TESTING
T-00275-1969 | PS5-60-IE-0004-CA07 | TIX01 - RJ45 Cable | PS5-60-IE-0004-CA07 | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-65-20-0040 | 2026-07-30 | OPEN | G K RAO | TESTING
T-00275-1970 | PS5-60-IE-0004-CA08 | TIX01 - RJ45 Cable | PS5-60-IE-0004-CA08 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-65-20-0040 | 2026-07-30 | OPEN | G K RAO | TESTING
T-00275-1971 | PS5-60-IE-0004-CA14 | TIX01 - RJ45 Cable | PS5-60-IE-0004-CA14 | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-65-20-0040 | 2026-07-30 | OPEN | G K RAO | TESTING
T-00275-1972 | PS5-60-IE-0004-CA15 | TIX01 - RJ45 Cable | PS5-60-IE-0004-CA15 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-65-20-0040 | 2026-07-30 | OPEN | G K RAO | TESTING
T-00275-1973 | PS5-60-IE-0004-CA21 | TIX01 - RJ45 Cable | PS5-60-IE-0004-CA21 | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 |  | PS5-60-22 - Power Gen Master UCP | CPP-RFI-68-64-12-0128 | 01-August-2026 | OPEN | Ferdinand | Testing
T-00275-1974 | PS5-60-IH-0001A-CA01 | TIX01 - RJ45 Cable | PS5-60-IH-0001A-CA01 | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001A |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | CPP-RFI-68-64-12-0123 | 29-July-2026 | Acceptable | Ferdinand | Testing
T-00275-1975 | PS5-60-IH-0001B-CA01 | TIX01 - RJ45 Cable | PS5-60-IH-0001B-CA01 | T | Cable FROM PS5-60-IE-0001B TO PS5-60-IH-0001B |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | CPP-RFI-68-64-12-0125 | 2026-07-30 | Accepted | G K RAO | TESTING
T-00275-1976 | PS5-60-IH-0001C-CA01 | TIX01 - RJ45 Cable | PS5-60-IH-0001C-CA01 | T | Cable FROM PS5-60-IE-0001C TO PS5-60-IH-0001C |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | CPP-RFI-68-64-12-0125 | 2026-07-30 | Accepted | G K RAO | TESTING
T-00275-1977 | PS5-60-IH-0001D-CA01 | TIX01 - RJ45 Cable | PS5-60-IH-0001D-CA01 | T | Cable FROM PS5-60-IE-0001D TO PS5-60-IH-0001D |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | CPP-RFI-68-64-12-0125 | 2026-07-30 | Accepted | G K RAO | TESTING
T-00275-1978 | PS5-60-IH-0001E-CA01 | TIX01 - RJ45 Cable | PS5-60-IH-0001E-CA01 | T | Cable FROM PS5-60-IE-0001E TO PS5-60-IH-0001E |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | CPP-RFI-68-64-12-0125 | 2026-07-30 | Accepted | G K RAO | TESTING
T-00275-1979 | PS5-60-IH-0001F-CA01 | TIX01 - RJ45 Cable | PS5-60-IH-0001F-CA01 | T | Cable FROM PS5-60-IE-0001F TO PS5-60-IH-0001F |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | CPP-RFI-68-64-12-0125 | 2026-07-30 | Accepted | G K RAO | TESTING
T-00275-1980 | PS5-60-IH-0001G-CA01 | TIX01 - RJ45 Cable | PS5-60-IH-0001G-CA01 | T | Cable FROM PS5-60-IE-0001G TO PS5-60-IH-0001G |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | CPP-RFI-68-64-12-0125 | 2026-07-30 | Accepted | G K RAO | TESTING
T-00275-1981 | PS5-60-IN-0001A-CA01 | TIX01 - RJ45 Cable | PS5-60-IN-0001A-CA01 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPP-RFI-68-65-20-0040 | 2026-07-30 | OPEN | G K RAO | TESTING
T-00275-1982 | PS5-60-IN-0001B-CA01 | TIX01 - RJ45 Cable | PS5-60-IN-0001B-CA01 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPP-RFI-68-65-20-0040 | 2026-07-30 | OPEN | G K RAO | TESTING
T-00275-1983 | PS5-60-IN-0001C-CA01 | TIX01 - RJ45 Cable | PS5-60-IN-0001C-CA01 | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  |  | OPEN | G K RAO | TESTING
T-00275-1984 | PS5-60-IN-0001D-CA01 | TIX01 - RJ45 Cable | PS5-60-IN-0001D-CA01 | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  |  | OPEN | G K RAO | TESTING
T-00275-1985 | PS5-60-IN-0001E-CA01 | TIX01 - RJ45 Cable | PS5-60-IN-0001E-CA01 | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E
T-00275-1986 | PS5-60-IN-0001F-CA01 | TIX01 - RJ45 Cable | PS5-60-IN-0001F-CA01 | T | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F
T-00275-1987 | PS5-60-IN-0001G-CA01 | TIX01 - RJ45 Cable | PS5-60-IN-0001G-CA01 | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G
T-00275-1988 | PS5-60-IN-0002A-CA01 | TIX01 - RJ45 Cable | PS5-60-IN-0002A-CA01 | T | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00275-1989 | PS5-60-IN-0002B-CA01 | TIX01 - RJ45 Cable | PS5-60-IN-0002B-CA01 | T | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00275-1990 | PS5-60-IN-0002C-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-1991 | PS5-60-IN-0002D-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-1992 | PS5-60-IN-0002E-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00275-1993 | PS5-60-IN-0002F-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00275-1994 | PS5-60-IN-0002G-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00275-1995 | PS5-60-LA-0002B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D |  |  | OPEN | G K RAO | TESTING
T-00275-1996 | PS5-60-LA-0002B-CA02 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D |  |  | OPEN | G K RAO | TESTING
T-00275-1997 | PS5-60-LA-0002B-CA03 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D |  |  | OPEN | G K RAO | TESTING
T-00275-1998 | PS5-60-LA-0002B-CA04 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D |  |  | OPEN | G K RAO | TESTING
T-00275-1999 | PS5-60-LA-0002B-CA05 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D |  |  | OPEN | G K RAO | TESTING
T-00275-2000 | PS5-60-LA-0002B-CA06 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B |  | PS5-60-10 - Power Generation Package D |  |  | OPEN | G K RAO | TESTING
T-00275-2001 | PS5-60-LA-0002C-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00275-2002 | PS5-60-LA-0002C-CA02 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00275-2003 | PS5-60-LA-0002C-CA03 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00275-2004 | PS5-60-LA-0002C-CA04 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00275-2005 | PS5-60-LA-0002C-CA05 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00275-2006 | PS5-60-LA-0002C-CA06 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C |  | PS5-60-16 - Power Generation Package F
T-00275-2007 | PS5-60-SEA-0001-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  |  | OPEN | G K RAO | TESTING
T-00275-2008 | PS5-71-IN-0001-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP)
T-00275-2009 | PS5-71-IN-0001-CA11 | TIX01 - RJ45 Cable | PS5-71-IN-0001-CA11 | T | Cable FROM PS5-60-IE-0003A TO PS5-71-IN-0001 |  | PS5-71-19 - Diesel Separator Module (UCP)
T-00275-2010 | PS5-71-IN-0002-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP)
T-00275-2011 | PS5-71-IN-0003-CA01 | TIX01 - RJ45 Cable | PS5-71-IN-0003-CA01 | T | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPP-RFI-68-64-12-0128 | 01-August-2026 | OPEN | Ferdinand | Testing
T-00275-2012 | PS5-71-IN-0004A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A |  | PS5-71-07 - Crude Fuel Separation Module (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-2013 | PS5-71-IN-0004B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B |  | PS5-71-07 - Crude Fuel Separation Module (UCP) |  |  | OPEN | G K RAO | TESTING
T-00275-3196 | PS5-08-01PA-1201-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-01PA-1201 |  | PS5-08-01 - PAGA
T-00275-3197 | PS5-08-01PA-1501-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-01PA-1501 |  | PS5-08-01 - PAGA
T-00275-3198 | PS5-08-05IN-0001-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-05IN-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00275-3199 | PS5-08-05IN-0002-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-05IN-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00275-3200 | PS5-08-05IN-0003-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-05IN-0003 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00275-3201 | PS5-08-05IN-0004-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-05IN-0004 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00275-3202 | PS5-08-05IN-0005-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-05IN-0005 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00275-3203 | PS5-08-12AP-0002-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-12BT-0002 TO PS5-08-12AP-0002 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00275-3204 | PS5-08-12AP-0003-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-12BT-0003 TO PS5-08-12AP-0003 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00275-3205 | PS5-08-12AP-0101-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-12BT-0101 TO PS5-08-12AP-0101 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00275-3206 | PS5-08-12AP-0103-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-12BT-0103 TO PS5-08-12AP-0103 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00275-3207 | PS5-08-12BT-0002-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-12BT-0002 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00275-3208 | PS5-08-12BT-0003-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-12BT-0003 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00275-3209 | PS5-08-12BT-0101-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-0101 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00275-3210 | PS5-08-12BT-0103-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-0103 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00275-3211 | PS5-08-13CB-1201-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00275-3212 | PS5-08-13CB-1201-CA02 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00275-3213 | PS5-08-13CB-1201-CA03 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00275-3214 | PS5-08-13CB-1201-CA04 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00275-3215 | PS5-08-13CB-1201-CA05 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00275-3216 | PS5-08-13CB-1201-CA06 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00275-3217 | PS5-08-14CB-1201-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00275-3218 | PS5-08-14CB-1201-CA02 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00275-3219 | PS5-08-14CB-1201-CA03 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00275-3220 | PS5-08-14CB-1201-CA04 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00275-3221 | PS5-08-14CB-1201-CA05 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00275-3222 | PS5-08-14CB-1201-CA06 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-14CB-1201 |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00275-3223 | PS5-08-52CM-0001-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0001 |  | PS5-08-52 - Process & Security CCTV
T-00275-3224 | PS5-08-52CM-0002-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0002 |  | PS5-08-52 - Process & Security CCTV
T-00275-3225 | PS5-08-52CM-0003-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0003 |  | PS5-08-52 - Process & Security CCTV
T-00275-3226 | PS5-08-52CM-0004-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0004 |  | PS5-08-52 - Process & Security CCTV
T-00275-3227 | PS5-08-52CM-0005-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0005 |  | PS5-08-52 - Process & Security CCTV
T-00275-3228 | PS5-08-52CM-0031-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-52CM-0031 |  | PS5-08-52 - Process & Security CCTV
T-00275-3229 | PS5-08-52CM-0032-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0006 TO PS5-08-52CM-0032 |  | PS5-08-52 - Process & Security CCTV
T-00275-3230 | PS5-08-52CM-0033-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0008 TO PS5-08-52CM-0033 |  | PS5-08-52 - Process & Security CCTV
T-00275-3231 | PS5-08-52CM-0034-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-52CM-0034 |  | PS5-08-52 - Process & Security CCTV
T-00275-3232 | PS5-08-52CM-0071-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0001 TO PS5-08-52CM-0071 |  | PS5-08-52 - Process & Security CCTV
T-00275-3233 | PS5-08-52CM-0072-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-52CM-0072 |  | PS5-08-52 - Process & Security CCTV
T-00275-3234 | PS5-08-52CM-0073-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0003 TO PS5-08-52CM-0073 |  | PS5-08-52 - Process & Security CCTV
T-00275-3235 | PS5-08-52CM-0074-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-52CM-0074 |  | PS5-08-52 - Process & Security CCTV
T-00275-3236 | PS5-08-52CM-0075-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0005 TO PS5-08-52CM-0075 |  | PS5-08-52 - Process & Security CCTV
T-00275-3237 | PS5-08-52CM-0076-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0006 TO PS5-08-52CM-0076 |  | PS5-08-52 - Process & Security CCTV
T-00275-3238 | PS5-08-52CM-0077-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-52CM-0077 |  | PS5-08-52 - Process & Security CCTV
T-00275-3239 | PS5-08-52CM-0078-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CP-0008 TO PS5-08-52CM-0078 |  | PS5-08-52 - Process & Security CCTV
T-00275-3240 | PS5-08-52CM-0134-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-0134 |  | PS5-08-52 - Process & Security CCTV
T-00275-3241 | PS5-08-52CM-0137-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-0137 |  | PS5-08-52 - Process & Security CCTV
T-00275-3242 | PS5-08-52CM-0140-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-0140 |  | PS5-08-52 - Process & Security CCTV
T-00275-3243 | PS5-08-52CM-0931-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-52CM-0931 |  | PS5-08-52 - Process & Security CCTV
T-00275-3244 | PS5-08-52CM-1201-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-52CM-1201 |  | PS5-08-52 - Process & Security CCTV
T-00275-3245 | PS5-08-52CM-1202-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-52CM-1202 |  | PS5-08-52 - Process & Security CCTV
T-00275-3246 | PS5-08-52CM-1901-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-1901 |  | PS5-08-52 - Process & Security CCTV
T-00275-3247 | PS5-08-52CM-1902-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-1902 |  | PS5-08-52 - Process & Security CCTV
T-00275-3248 | PS5-08-52CM-1903-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-1903 |  | PS5-08-52 - Process & Security CCTV
T-00275-3249 | PS5-08-71SK-1201-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1201 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3250 | PS5-08-71SK-1202-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1202 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3251 | PS5-08-71SK-1203-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1203 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3252 | PS5-08-71SK-1204-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1204 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3253 | PS5-08-71SK-1205-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1205 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3254 | PS5-08-71SK-1206A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1206A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3255 | PS5-08-71SK-1206B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1206B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3256 | PS5-08-71SK-1207-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1207 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3257 | PS5-08-71SK-1208-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1208 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3258 | PS5-08-71SK-1209-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1209 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3259 | PS5-08-71SK-1210-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1210 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3260 | PS5-08-71SK-1211-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1211 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3261 | PS5-08-71SK-1212A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1212A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3262 | PS5-08-71SK-1212B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1212B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3263 | PS5-08-71SK-1213-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1213 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3264 | PS5-08-71SK-1214A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1214A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3265 | PS5-08-71SK-1214B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1214B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3266 | PS5-08-71SK-1214C-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1214C |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3267 | PS5-08-71SK-1214D-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1214D |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3268 | PS5-08-71SK-1215A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1215A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3269 | PS5-08-71SK-1215B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1215B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3270 | PS5-08-71SK-1216A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1216A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3271 | PS5-08-71SK-1216B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1216B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3272 | PS5-08-71SK-1217A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1217A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3273 | PS5-08-71SK-1217B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1217B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3274 | PS5-08-71SK-1218A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1218A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3275 | PS5-08-71SK-1218B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1218B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3276 | PS5-08-71SK-1219A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1219A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3277 | PS5-08-71SK-1219B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1219B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3278 | PS5-08-71SK-1220A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1220A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3279 | PS5-08-71SK-1220B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1220B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3280 | PS5-08-71SK-1221A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1221A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3281 | PS5-08-71SK-1221B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1221B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3282 | PS5-08-71SK-1222A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1222A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3283 | PS5-08-71SK-1222B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1222B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3284 | PS5-08-71SK-1223A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1223A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3285 | PS5-08-71SK-1223B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1223B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3286 | PS5-08-71SK-1224A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1224A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3287 | PS5-08-71SK-1224B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1224B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3288 | PS5-08-71SK-1225A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1225A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3289 | PS5-08-71SK-1225B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1225B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3290 | PS5-08-71SK-1226A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1226A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3291 | PS5-08-71SK-1226B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1226B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3292 | PS5-08-71SK-1227A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1227A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3293 | PS5-08-71SK-1227B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1227B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3294 | PS5-08-71SK-1228A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1228A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3295 | PS5-08-71SK-1228B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1228B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3296 | PS5-08-71SK-1229-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1229 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3297 | PS5-08-71SK-1230A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1230A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3298 | PS5-08-71SK-1230B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1230B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3299 | PS5-08-71SK-1231-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1231 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3300 | PS5-08-71SK-1232A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1232A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3301 | PS5-08-71SK-1232B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1232B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3302 | PS5-08-71SK-1233A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1233A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3303 | PS5-08-71SK-1233B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1233B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3304 | PS5-08-71SK-1234-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1234 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3305 | PS5-08-71SK-1235-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1235 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3306 | PS5-08-71SK-1236A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1236A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3307 | PS5-08-71SK-1236B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1236B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3308 | PS5-08-71SK-1237-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1237 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3309 | PS5-08-71SK-1238-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1238 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3310 | PS5-08-71SK-1239-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1239 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3311 | PS5-08-71SK-1240-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1240 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3312 | PS5-08-71SK-1241A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1241A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3313 | PS5-08-71SK-1241B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1241B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3314 | PS5-08-71SK-1242A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1242A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3315 | PS5-08-71SK-1242B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1242B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3316 | PS5-08-71SK-1243A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1243A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3317 | PS5-08-71SK-1243B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1243B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3318 | PS5-08-71SK-1244A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1244A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3319 | PS5-08-71SK-1244B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1244B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3320 | PS5-08-71SK-1245A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1245A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3321 | PS5-08-71SK-1245B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1245B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3322 | PS5-08-71SK-1246A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1246A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3323 | PS5-08-71SK-1246B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1246B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3324 | PS5-08-71SK-1247-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1247 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3325 | PS5-08-71SK-1248-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1248 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3326 | PS5-08-71SK-1249A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1249A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3327 | PS5-08-71SK-1249B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1249B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3328 | PS5-08-71SK-1249C-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1249C |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3329 | PS5-08-71SK-1249D-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1249D |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3330 | PS5-08-71SK-1250A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1250A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3331 | PS5-08-71SK-1250B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-71SK-1250B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3332 | PS5-08-71SK-1501A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1501A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3333 | PS5-08-71SK-1501B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1501B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3334 | PS5-08-71SK-1502A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1502A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3335 | PS5-08-71SK-1502B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1502B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3336 | PS5-08-71SK-1503A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1503A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3337 | PS5-08-71SK-1503B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1503B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3338 | PS5-08-71SK-1504A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1504A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3339 | PS5-08-71SK-1504B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1504B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3340 | PS5-08-71SK-1505-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1505 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3341 | PS5-08-71SK-1506-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1506 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3342 | PS5-08-71SK-1507-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1507 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3343 | PS5-08-71SK-1508-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1508 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3344 | PS5-08-71SK-1509-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1509 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3345 | PS5-08-71SK-1510A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1510A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3346 | PS5-08-71SK-1510B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1510B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3347 | PS5-08-71SK-1511A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1511A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3348 | PS5-08-71SK-1511B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1511B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3349 | PS5-08-71SK-1512-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1512 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3350 | PS5-08-71SK-1513-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-71SK-1513 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3351 | PS5-08-71SK-1601A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1601A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3352 | PS5-08-71SK-1601B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1601B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3353 | PS5-08-71SK-1602A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1602A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3354 | PS5-08-71SK-1602B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1602B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3355 | PS5-08-71SK-1603A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1603A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3356 | PS5-08-71SK-1603B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1603B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3357 | PS5-08-71SK-1604A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1604A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3358 | PS5-08-71SK-1604B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1604B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3359 | PS5-08-71SK-1605A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1605A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3360 | PS5-08-71SK-1605B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1605B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3361 | PS5-08-71SK-1606-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1606 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3362 | PS5-08-71SK-1607-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1607 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3363 | PS5-08-71SK-1608-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1608 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3364 | PS5-08-71SK-1609-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1609 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3365 | PS5-08-71SK-1610-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1610 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3366 | PS5-08-71SK-1611-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-71SK-1611 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3367 | PS5-08-71SK-1901-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1901 |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3368 | PS5-08-71SK-1903A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1903A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3369 | PS5-08-71SK-1903B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1903B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3370 | PS5-08-71SK-1904A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1904A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3371 | PS5-08-71SK-1904B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1904B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3372 | PS5-08-71SK-1905A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1905A |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3373 | PS5-08-71SK-1905B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-71SK-1905B |  | PS5-08-71 - Structured Cabling (CAT6)
T-00275-3374 | PS5-08-85BT-0027-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-0027 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00275-3375 | PS5-08-85BT-0028-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-0028 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00275-3376 | PS5-08-85CP-1201-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85CP-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00275-3377 | PS5-08-85CP-1202-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85CP-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00275-3378 | PS5-08-85CP-1501-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-85CP-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00275-3379 | PS5-08-85CP-1601-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85CP-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00275-3380 | PS5-08-85CP-1901-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-85CP-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00275-4059 | PS5-06-GU-0001A-CA04 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001A |  | PS5-06-01 - AC UPS - EITS Building
T-00275-4061 | PS5-06-GU-0001B-CA05 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001B |  | PS5-06-01 - AC UPS - EITS Building
T-00275-4062 | PS5-06-GU-0001-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-06-GU-0001 |  | PS5-06-01 - AC UPS - EITS Building
T-00275-4194 | PS5-61-IJ-0011-CA03 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-61-IJ-0010 TO PS5-61-IJ-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011)
T-00275-4202 | PS5-09-LB-8451A-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451A |  | PS5-09-03 - HVAC for Generator Building
T-00275-4203 | PS5-09-LB-8451B-CA01 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-09-LB-0008 TO PS5-09-LB-8451B |  | PS5-09-03 - HVAC for Generator Building
T-00275-4208 | PS5-06-GU-0001A-CA03 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001A |  | PS5-06-01 - AC UPS - EITS Building
T-00275-4209 | PS5-06-GU-0001B-CA02 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001B |  | PS5-06-01 - AC UPS - EITS Building
T-00275-4211 | PS5-61-IJ-0001-CA08 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00275-4212 | PS5-61-IJ-0001-CA09 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00275-4213 | PS5-61-IJ-0001-CA10 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00275-4214 | PS5-04-PNC-0001-CA03 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-35CB-1001 TO PS5-04-PNC-0001 |  | PS5-04-03 - 33kV ICSS System
T-00275-4215 | PS5-04-PNC-0001-CA04 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-35CB-1001 TO PS5-04-PNC-0001 |  | PS5-04-03 - 33kV ICSS System
T-00275-4216 | PS5-04-PNC-0001-CA15 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-35CB-1001 TO PS5-04-PNC-0001 |  | PS5-04-03 - 33kV ICSS System
T-00275-4963 | PS5-04-PNC-0001-CA94 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-04-PSC-0001 TO PS5-04-PNC-0001 |  | PS5-04-03 - 33kV ICSS System
T-00275-4964 | PS5-04-PNC-0001-CA95 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-04-PSC-0001 TO PS5-04-PNC-0001 |  | PS5-04-03 - 33kV ICSS System
T-00275-4965 | PS5-08-13CB-1001-CA24 | TIX01 - RJ45 Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-13CB-1001 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00276-1489 | PS5-08-11CB-1201-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-11CB-1201 |  | PS5-08-11 - Corporate LAN (SIE)
T-00276-1490 | PS5-08-11CB-1501-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-11CB-1501 |  | PS5-08-11 - Corporate LAN (SIE)
T-00276-1491 | PS5-08-11CB-1601-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-11CB-1601 |  | PS5-08-11 - Corporate LAN (SIE)
T-00276-1492 | PS5-08-11CB-1901-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-11CB-1901 |  | PS5-08-11 - Corporate LAN (SIE)
T-00276-1493 | PS5-08-12BT-0001-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-12BT-0001 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00276-1494 | PS5-08-12BT-0104-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-12BT-0104 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00276-1495 | PS5-08-12BT-0105-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-12BT-0105 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00276-1496 | PS5-08-12BT-0106-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-12BT-0106 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00276-1497 | PS5-08-12BT-0107-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-0107 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00276-1498 | PS5-08-12BT-0108-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-0108 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00276-1499 | PS5-08-12BT-0109-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-12BT-0109 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00276-1500 | PS5-08-12BT-1903-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-1903 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00276-1501 | PS5-08-12BT-1904-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-1904 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00276-1502 | PS5-08-15CP-0001-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CP-0008 TO PS5-08-15CP-0001 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00276-1503 | PS5-08-15CP-0002-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CP-0001 TO PS5-08-15CP-0002 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00276-1504 | PS5-08-15CP-0003-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-15CP-0003 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00276-1505 | PS5-08-15CP-0004-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CP-0003 TO PS5-08-15CP-0004 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00276-1506 | PS5-08-15CP-0005-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-15CP-0005 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00276-1507 | PS5-08-15CP-0005-CX02 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-15CP-0005 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00276-1508 | PS5-08-15CP-0006-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-15CP-0006 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00276-1509 | PS5-08-15CP-0007-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CP-0006 TO PS5-08-15CP-0007 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00276-1510 | PS5-08-15CP-0008-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-15CP-0008 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00276-1511 | PS5-08-36SP-0101-CX02 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-35CB-1001 TO PS5-08-36SP-0101 |  | PS5-08-36 - Pipeline FO Cable & EPRS
T-00276-1512 | PS5-08-36SP-0102-CX02 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-35CB-1001 TO PS5-08-36SP-0102 |  | PS5-08-36 - Pipeline FO Cable & EPRS
T-00276-1513 | PS5-08-52CM-0131-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-52CM-0131 |  | PS5-08-52 - Process & Security CCTV
T-00276-1514 | PS5-08-52CM-0132-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-52CM-0132 |  | PS5-08-52 - Process & Security CCTV
T-00276-1515 | PS5-08-52CM-0133-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-52CM-0133 |  | PS5-08-52 - Process & Security CCTV
T-00276-1516 | PS5-08-52CM-0135-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-0135 |  | PS5-08-52 - Process & Security CCTV
T-00276-1517 | PS5-08-52CM-0136-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-0136 |  | PS5-08-52 - Process & Security CCTV
T-00276-1518 | PS5-08-52CM-0138-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-52CM-0138 |  | PS5-08-52 - Process & Security CCTV
T-00276-1519 | PS5-08-52CM-0139-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-52CM-0139 |  | PS5-08-52 - Process & Security CCTV
T-00276-1520 | PS5-08-83SP-0001-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-83SP-0001 |  | PS5-08-83 - Perimeter & Pipeline intrusion detection system
T-00276-1521 | PS5-08-83SP-0001-CX02 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-83SP-0001 |  | PS5-08-83 - Perimeter & Pipeline intrusion detection system
T-00276-1522 | PS5-08-85CP-0024-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-85CP-0024 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00276-1523 | PS5-08-85CP-0024-CX02 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-85CP-0024 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00276-1524 | PS5-08-85CP-0025-CX01 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-85CP-0025 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00276-1525 | PS5-08-85CP-0025-CX02 | TIX02 - Fiber Optic cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-85CP-0025 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00278-0189 | PS5-08-23AN-0001-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-23LA-1201 TO PS5-08-23AN-0001 |  | PS5-08-23 - VHF Trunk Radio System
T-00278-0190 | PS5-08-23AN-0002-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-23LA-1501 TO PS5-08-23AN-0002 |  | PS5-08-23 - VHF Trunk Radio System
T-00278-0191 | PS5-08-23AN-0003-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-23LA-1601 TO PS5-08-23AN-0003 |  | PS5-08-23 - VHF Trunk Radio System
T-00278-0192 | PS5-08-23AN-0005-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-23LA-1901 TO PS5-08-23AN-0005 |  | PS5-08-23 - VHF Trunk Radio System
T-00278-0193 | PS5-08-23AN-0901-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-23LA-1202 TO PS5-08-23AN-0901 |  | PS5-08-23 - VHF Trunk Radio System
T-00278-0194 | PS5-08-23AN-1201-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-13CB-1201 TO PS5-08-23AN-1201 |  | PS5-08-23 - VHF Trunk Radio System
T-00278-0195 | PS5-08-23AN-1601-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-23LA-1601 TO PS5-08-23AN-1601 |  | PS5-08-23 - VHF Trunk Radio System
T-00278-0196 | PS5-08-23AN-1901-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-23LA-1901 TO PS5-08-23AN-1901 |  | PS5-08-23 - VHF Trunk Radio System
T-00278-0197 | PS5-08-23LA-1201-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-23BS-1201 TO PS5-08-23LA-1201 |  | PS5-08-23 - VHF Trunk Radio System
T-00278-0198 | PS5-08-23LA-1202-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-13CB-1201 TO PS5-08-23LA-1202 |  | PS5-08-23 - VHF Trunk Radio System
T-00278-0199 | PS5-08-23LA-1501-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-23BS-1501 TO PS5-08-23LA-1501 |  | PS5-08-23 - VHF Trunk Radio System
T-00278-0200 | PS5-08-34AN-0001-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-34LA-1201 TO PS5-08-34AN-0001 |  | PS5-08-34 - Satphone
T-00278-0201 | PS5-08-34AN-0002-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-34LA-1501 TO PS5-08-34AN-0002 |  | PS5-08-34 - Satphone
T-00278-0202 | PS5-08-34LA-1201-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-34DS-1211 TO PS5-08-34LA-1201 |  | PS5-08-34 - Satphone
T-00278-0203 | PS5-08-34LA-1501-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-34DS-1511 TO PS5-08-34LA-1501 |  | PS5-08-34 - Satphone
T-00278-0204 | PS5-08-51AN-0001-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-51LA-1201 TO PS5-08-51AN-0001 |  | PS5-08-51 - Entertainment
T-00278-0205 | PS5-08-51AN-0001-CV02 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-51LA-1202 TO PS5-08-51AN-0001 |  | PS5-08-51 - Entertainment
T-00278-0206 | PS5-08-51AN-0001-CV03 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-51LA-1203 TO PS5-08-51AN-0001 |  | PS5-08-51 - Entertainment
T-00278-0207 | PS5-08-51AN-0001-CV04 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-51LA-1204 TO PS5-08-51AN-0001 |  | PS5-08-51 - Entertainment
T-00278-0208 | PS5-08-51LA-1201-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51LA-1201 |  | PS5-08-51 - Entertainment
T-00278-0209 | PS5-08-51LA-1202-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51LA-1202 |  | PS5-08-51 - Entertainment
T-00278-0210 | PS5-08-51LA-1203-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51LA-1203 |  | PS5-08-51 - Entertainment
T-00278-0211 | PS5-08-51LA-1204-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51LA-1204 |  | PS5-08-51 - Entertainment
T-00278-0212 | PS5-08-51SK-1201-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1201 |  | PS5-08-51 - Entertainment
T-00278-0213 | PS5-08-51SK-1202-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1202 |  | PS5-08-51 - Entertainment
T-00278-0214 | PS5-08-51SK-1203-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1203 |  | PS5-08-51 - Entertainment
T-00278-0215 | PS5-08-51SK-1204-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1204 |  | PS5-08-51 - Entertainment
T-00278-0216 | PS5-08-51SK-1205-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1205 |  | PS5-08-51 - Entertainment
T-00278-0217 | PS5-08-51SK-1206-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1206 |  | PS5-08-51 - Entertainment
T-00278-0218 | PS5-08-51SK-1207-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1207 |  | PS5-08-51 - Entertainment
T-00278-0219 | PS5-08-51SK-1208-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1208 |  | PS5-08-51 - Entertainment
T-00278-0220 | PS5-08-51SK-1209-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1209 |  | PS5-08-51 - Entertainment
T-00278-0221 | PS5-08-51SK-1210-CV01 | TIX04 - Coaxial Cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-51SK-1210 |  | PS5-08-51 - Entertainment
T-00279-3531 | PS5-08-01BT-0001-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01BT-0001 |  | PS5-08-01 - PAGA
T-00279-3532 | PS5-08-01BT-0001-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01OC-0001 TO PS5-08-01BT-0001 |  | PS5-08-01 - PAGA
T-00279-3533 | PS5-08-01BT-0002-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1202 TO PS5-08-01BT-0002 |  | PS5-08-01 - PAGA
T-00279-3534 | PS5-08-01BT-0002-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01OC-0001 TO PS5-08-01BT-0002 |  | PS5-08-01 - PAGA
T-00279-3535 | PS5-08-01BT-0003-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0102 TO PS5-08-01BT-0003 |  | PS5-08-01 - PAGA
T-00279-3536 | PS5-08-01BT-0003-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01OC-0002 TO PS5-08-01BT-0003 |  | PS5-08-01 - PAGA
T-00279-3537 | PS5-08-01BT-0004-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0201 TO PS5-08-01BT-0004 |  | PS5-08-01 - PAGA
T-00279-3538 | PS5-08-01BT-0004-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01OC-0002 TO PS5-08-01BT-0004 |  | PS5-08-01 - PAGA
T-00279-3539 | PS5-08-01BT-1201-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-01BT-1201 |  | PS5-08-01 - PAGA
T-00279-3540 | PS5-08-01BT-1201-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1201 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3541 | PS5-08-01BT-1201-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01BT-1201 |  | PS5-08-01 - PAGA
T-00279-3542 | PS5-08-01BT-1201-CR03 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1203 TO PS5-08-01BT-1201 |  | PS5-08-01 - PAGA
T-00279-3543 | PS5-08-01BT-1202-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-01BT-1202 |  | PS5-08-01 - PAGA
T-00279-3544 | PS5-08-01BT-1202-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1202 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3545 | PS5-08-01BT-1202-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1202 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3546 | PS5-08-01BT-1202-CR03 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1203 TO PS5-08-01BT-1202 |  | PS5-08-01 - PAGA
T-00279-3547 | PS5-08-01BT-1203-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-01BT-1203 |  | PS5-08-01 - PAGA
T-00279-3548 | PS5-08-01BT-1203-CN02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-01BT-1203 |  | PS5-08-01 - PAGA
T-00279-3549 | PS5-08-01BT-1501-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0307 TO PS5-08-01BT-1501 |  | PS5-08-01 - PAGA
T-00279-3550 | PS5-08-01BT-1501-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1503 TO PS5-08-01BT-1501 |  | PS5-08-01 - PAGA
T-00279-3551 | PS5-08-01BT-1502-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0405 TO PS5-08-01BT-1502 |  | PS5-08-01 - PAGA
T-00279-3552 | PS5-08-01BT-1502-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1503 TO PS5-08-01BT-1502 |  | PS5-08-01 - PAGA
T-00279-3553 | PS5-08-01BT-1503-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-01BT-1503 |  | PS5-08-01 - PAGA
T-00279-3554 | PS5-08-01BT-1503-CN02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-01BT-1503 |  | PS5-08-01 - PAGA
T-00279-3555 | PS5-08-01BT-1601-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0720 TO PS5-08-01BT-1601 |  | PS5-08-01 - PAGA
T-00279-3556 | PS5-08-01BT-1601-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1601 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3557 | PS5-08-01BT-1602-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-0002 TO PS5-08-01BT-1602 |  | PS5-08-01 - PAGA
T-00279-3558 | PS5-08-01BT-1602-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1602 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3559 | PS5-08-01BT-1901-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1903 TO PS5-08-01BT-1901 |  | PS5-08-01 - PAGA
T-00279-3560 | PS5-08-01BT-1901-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1901 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3561 | PS5-08-01BT-1902-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1904 TO PS5-08-01BT-1902 |  | PS5-08-01 - PAGA
T-00279-3562 | PS5-08-01BT-1902-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1902 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3563 | PS5-08-01BT-1903-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1903 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3564 | PS5-08-01BT-1904-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1904 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3565 | PS5-08-01LS-0101-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0101 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3566 | PS5-08-01LS-0102-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0101 TO PS5-08-01LS-0102 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3567 | PS5-08-01LS-0103-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01OC-0002 TO PS5-08-01LS-0103 |  | PS5-08-01 - PAGA
T-00279-3568 | PS5-08-01LS-0104-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-0003 TO PS5-08-01LS-0104 |  | PS5-08-01 - PAGA
T-00279-3569 | PS5-08-01LS-0105-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0104 TO PS5-08-01LS-0105 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3570 | PS5-08-01LS-0106-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0105 TO PS5-08-01LS-0106 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3571 | PS5-08-01LS-0107-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0106 TO PS5-08-01LS-0107 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3572 | PS5-08-01LS-0108-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0107 TO PS5-08-01LS-0108 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3573 | PS5-08-01LS-0109-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0108 TO PS5-08-01LS-0109 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3574 | PS5-08-01LS-0110-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0109 TO PS5-08-01LS-0110 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3575 | PS5-08-01LS-0110-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0110 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3576 | PS5-08-01LS-0201-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0201 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3577 | PS5-08-01LS-0202-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01OC-0002 TO PS5-08-01LS-0202 |  | PS5-08-01 - PAGA
T-00279-3578 | PS5-08-01LS-0203-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-0004 TO PS5-08-01LS-0203 |  | PS5-08-01 - PAGA
T-00279-3579 | PS5-08-01LS-0204-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0203 TO PS5-08-01LS-0204 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3580 | PS5-08-01LS-0205-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0204 TO PS5-08-01LS-0205 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3581 | PS5-08-01LS-0206-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0205 TO PS5-08-01LS-0206 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3582 | PS5-08-01LS-0207-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0206 TO PS5-08-01LS-0207 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3583 | PS5-08-01LS-0208-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0207 TO PS5-08-01LS-0208 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3584 | PS5-08-01LS-0209-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0208 TO PS5-08-01LS-0209 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3585 | PS5-08-01LS-0210-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0209 TO PS5-08-01LS-0210 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3586 | PS5-08-01LS-0211-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0210 TO PS5-08-01LS-0211 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3587 | PS5-08-01LS-0211-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0211 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3588 | PS5-08-01LS-0301-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0301 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3589 | PS5-08-01LS-0302-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0301 TO PS5-08-01LS-0302 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3590 | PS5-08-01LS-0303-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0302 TO PS5-08-01LS-0303 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3591 | PS5-08-01LS-0304-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0303 TO PS5-08-01LS-0304 |  | PS5-08-01 - PAGA
T-00279-3592 | PS5-08-01LS-0305-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0304 TO PS5-08-01LS-0305 |  | PS5-08-01 - PAGA
T-00279-3593 | PS5-08-01LS-0306-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0305 TO PS5-08-01LS-0306 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3594 | PS5-08-01LS-0307-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0306 TO PS5-08-01LS-0307 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3595 | PS5-08-01LS-0308-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1501 TO PS5-08-01LS-0308 |  | PS5-08-01 - PAGA
T-00279-3596 | PS5-08-01LS-0309-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0308 TO PS5-08-01LS-0309 |  | PS5-08-01 - PAGA
T-00279-3597 | PS5-08-01LS-0310-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1501 TO PS5-08-01LS-0310 |  | PS5-08-01 - PAGA
T-00279-3598 | PS5-08-01LS-0310-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0310 |  | PS5-08-01 - PAGA
T-00279-3599 | PS5-08-01LS-0318-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0318 |  | PS5-08-01 - PAGA
T-00279-3600 | PS5-08-01LS-0401-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0401 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3601 | PS5-08-01LS-0402-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0401 TO PS5-08-01LS-0402 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3602 | PS5-08-01LS-0403-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0402 TO PS5-08-01LS-0403 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3603 | PS5-08-01LS-0404-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0403 TO PS5-08-01LS-0404 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3604 | PS5-08-01LS-0405-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0404 TO PS5-08-01LS-0405 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3605 | PS5-08-01LS-0406-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1502 TO PS5-08-01LS-0406 |  | PS5-08-01 - PAGA
T-00279-3606 | PS5-08-01LS-0407-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0406 TO PS5-08-01LS-0407 |  | PS5-08-01 - PAGA
T-00279-3607 | PS5-08-01LS-0408-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0407 TO PS5-08-01LS-0408 |  | PS5-08-01 - PAGA
T-00279-3608 | PS5-08-01LS-0409-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1502 TO PS5-08-01LS-0409 |  | PS5-08-01 - PAGA
T-00279-3609 | PS5-08-01LS-0410-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0409 TO PS5-08-01LS-0410 |  | PS5-08-01 - PAGA
T-00279-3610 | PS5-08-01LS-0411-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0410 TO PS5-08-01LS-0411 |  | PS5-08-01 - PAGA
T-00279-3611 | PS5-08-01LS-0411-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0411 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0031 | 2026-06-03 | Accepted | Ferdinand | Testing
T-00279-3612 | PS5-08-01LS-0418-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01LS-0418 |  | PS5-08-01 - PAGA
T-00279-3613 | PS5-08-01LS-0501-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1903 TO PS5-08-01LS-0501 |  | PS5-08-01 - PAGA
T-00279-3614 | PS5-08-01LS-0502-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0501 TO PS5-08-01LS-0502 |  | PS5-08-01 - PAGA
T-00279-3615 | PS5-08-01LS-0503-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0502 TO PS5-08-01LS-0503 |  | PS5-08-01 - PAGA
T-00279-3616 | PS5-08-01LS-0504-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0503 TO PS5-08-01LS-0504 |  | PS5-08-01 - PAGA
T-00279-3617 | PS5-08-01LS-0505-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0504 TO PS5-08-01LS-0505 |  | PS5-08-01 - PAGA
T-00279-3618 | PS5-08-01LS-0506-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0505 TO PS5-08-01LS-0506 |  | PS5-08-01 - PAGA
T-00279-3619 | PS5-08-01LS-0507-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0506 TO PS5-08-01LS-0507 |  | PS5-08-01 - PAGA
T-00279-3620 | PS5-08-01LS-0508-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0507 TO PS5-08-01LS-0508 |  | PS5-08-01 - PAGA
T-00279-3621 | PS5-08-01LS-0509-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0508 TO PS5-08-01LS-0509 |  | PS5-08-01 - PAGA
T-00279-3622 | PS5-08-01LS-0510-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0509 TO PS5-08-01LS-0510 |  | PS5-08-01 - PAGA
T-00279-3623 | PS5-08-01LS-0511-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0510 TO PS5-08-01LS-0511 |  | PS5-08-01 - PAGA
T-00279-3624 | PS5-08-01LS-0512-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0511 TO PS5-08-01LS-0512 |  | PS5-08-01 - PAGA
T-00279-3625 | PS5-08-01LS-0517-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0512 TO PS5-08-01LS-0517 |  | PS5-08-01 - PAGA
T-00279-3626 | PS5-08-01LS-0518-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0517 TO PS5-08-01LS-0518 |  | PS5-08-01 - PAGA
T-00279-3627 | PS5-08-01LS-0519-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0518 TO PS5-08-01LS-0519 |  | PS5-08-01 - PAGA
T-00279-3628 | PS5-08-01LS-0520-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0519 TO PS5-08-01LS-0520 |  | PS5-08-01 - PAGA
T-00279-3629 | PS5-08-01LS-0521-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0520 TO PS5-08-01LS-0521 |  | PS5-08-01 - PAGA
T-00279-3630 | PS5-08-01LS-0522-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0521 TO PS5-08-01LS-0522 |  | PS5-08-01 - PAGA
T-00279-3631 | PS5-08-01LS-0522-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1903 TO PS5-08-01LS-0522 |  | PS5-08-01 - PAGA
T-00279-3632 | PS5-08-01LS-0523-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1901 TO PS5-08-01LS-0523 |  | PS5-08-01 - PAGA
T-00279-3633 | PS5-08-01LS-0524-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0523 TO PS5-08-01LS-0524 |  | PS5-08-01 - PAGA
T-00279-3634 | PS5-08-01LS-0525-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0524 TO PS5-08-01LS-0525 |  | PS5-08-01 - PAGA
T-00279-3635 | PS5-08-01LS-0526-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0525 TO PS5-08-01LS-0526 |  | PS5-08-01 - PAGA
T-00279-3636 | PS5-08-01LS-0527-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0526 TO PS5-08-01LS-0527 |  | PS5-08-01 - PAGA
T-00279-3637 | PS5-08-01LS-0528-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0527 TO PS5-08-01LS-0528 |  | PS5-08-01 - PAGA
T-00279-3638 | PS5-08-01LS-0529-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0528 TO PS5-08-01LS-0529 |  | PS5-08-01 - PAGA
T-00279-3639 | PS5-08-01LS-0530-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0529 TO PS5-08-01LS-0530 |  | PS5-08-01 - PAGA
T-00279-3640 | PS5-08-01LS-0530-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1901 TO PS5-08-01LS-0530 |  | PS5-08-01 - PAGA
T-00279-3641 | PS5-08-01LS-0601-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1904 TO PS5-08-01LS-0601 |  | PS5-08-01 - PAGA
T-00279-3642 | PS5-08-01LS-0602-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0601 TO PS5-08-01LS-0602 |  | PS5-08-01 - PAGA
T-00279-3643 | PS5-08-01LS-0603-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0602 TO PS5-08-01LS-0603 |  | PS5-08-01 - PAGA
T-00279-3644 | PS5-08-01LS-0604-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0603 TO PS5-08-01LS-0604 |  | PS5-08-01 - PAGA
T-00279-3645 | PS5-08-01LS-0605-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0604 TO PS5-08-01LS-0605 |  | PS5-08-01 - PAGA
T-00279-3646 | PS5-08-01LS-0606-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0605 TO PS5-08-01LS-0606 |  | PS5-08-01 - PAGA
T-00279-3647 | PS5-08-01LS-0607-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0606 TO PS5-08-01LS-0607 |  | PS5-08-01 - PAGA
T-00279-3648 | PS5-08-01LS-0608-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0607 TO PS5-08-01LS-0608 |  | PS5-08-01 - PAGA
T-00279-3649 | PS5-08-01LS-0609-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0608 TO PS5-08-01LS-0609 |  | PS5-08-01 - PAGA
T-00279-3650 | PS5-08-01LS-0610-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0609 TO PS5-08-01LS-0610 |  | PS5-08-01 - PAGA
T-00279-3651 | PS5-08-01LS-0611-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0610 TO PS5-08-01LS-0611 |  | PS5-08-01 - PAGA
T-00279-3652 | PS5-08-01LS-0612-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0611 TO PS5-08-01LS-0612 |  | PS5-08-01 - PAGA
T-00279-3653 | PS5-08-01LS-0617-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0612 TO PS5-08-01LS-0617 |  | PS5-08-01 - PAGA
T-00279-3654 | PS5-08-01LS-0618-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0617 TO PS5-08-01LS-0618 |  | PS5-08-01 - PAGA
T-00279-3655 | PS5-08-01LS-0619-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0618 TO PS5-08-01LS-0619 |  | PS5-08-01 - PAGA
T-00279-3656 | PS5-08-01LS-0620-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0619 TO PS5-08-01LS-0620 |  | PS5-08-01 - PAGA
T-00279-3657 | PS5-08-01LS-0621-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0620 TO PS5-08-01LS-0621 |  | PS5-08-01 - PAGA
T-00279-3658 | PS5-08-01LS-0621-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1904 TO PS5-08-01LS-0621 |  | PS5-08-01 - PAGA
T-00279-3659 | PS5-08-01LS-0622-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1902 TO PS5-08-01LS-0622 |  | PS5-08-01 - PAGA
T-00279-3660 | PS5-08-01LS-0623-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0622 TO PS5-08-01LS-0623 |  | PS5-08-01 - PAGA
T-00279-3661 | PS5-08-01LS-0624-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0623 TO PS5-08-01LS-0624 |  | PS5-08-01 - PAGA
T-00279-3662 | PS5-08-01LS-0625-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0624 TO PS5-08-01LS-0625 |  | PS5-08-01 - PAGA
T-00279-3663 | PS5-08-01LS-0626-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0625 TO PS5-08-01LS-0626 |  | PS5-08-01 - PAGA
T-00279-3664 | PS5-08-01LS-0627-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0626 TO PS5-08-01LS-0627 |  | PS5-08-01 - PAGA
T-00279-3665 | PS5-08-01LS-0628-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0627 TO PS5-08-01LS-0628 |  | PS5-08-01 - PAGA
T-00279-3666 | PS5-08-01LS-0629-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0628 TO PS5-08-01LS-0629 |  | PS5-08-01 - PAGA
T-00279-3667 | PS5-08-01LS-0629-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1902 TO PS5-08-01LS-0629 |  | PS5-08-01 - PAGA
T-00279-3668 | PS5-08-01LS-0701-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01LS-0701 |  | PS5-08-01 - PAGA
T-00279-3669 | PS5-08-01LS-0702-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0701 TO PS5-08-01LS-0702 |  | PS5-08-01 - PAGA
T-00279-3670 | PS5-08-01LS-0703-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0704 TO PS5-08-01LS-0703 |  | PS5-08-01 - PAGA
T-00279-3671 | PS5-08-01LS-0704-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0702 TO PS5-08-01LS-0704 |  | PS5-08-01 - PAGA
T-00279-3672 | PS5-08-01LS-0705-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01LS-0705 |  | PS5-08-01 - PAGA
T-00279-3673 | PS5-08-01LS-0706-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0703 TO PS5-08-01LS-0706 |  | PS5-08-01 - PAGA
T-00279-3674 | PS5-08-01LS-0707-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0706 TO PS5-08-01LS-0707 |  | PS5-08-01 - PAGA
T-00279-3675 | PS5-08-01LS-0708-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0707 TO PS5-08-01LS-0708 |  | PS5-08-01 - PAGA
T-00279-3676 | PS5-08-01LS-0709-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0708 TO PS5-08-01LS-0709 |  | PS5-08-01 - PAGA
T-00279-3677 | PS5-08-01LS-0710-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0709 TO PS5-08-01LS-0710 |  | PS5-08-01 - PAGA
T-00279-3678 | PS5-08-01LS-0711-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0710 TO PS5-08-01LS-0711 |  | PS5-08-01 - PAGA
T-00279-3679 | PS5-08-01LS-0712-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01LS-0712 |  | PS5-08-01 - PAGA
T-00279-3680 | PS5-08-01LS-0713-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0712 TO PS5-08-01LS-0713 |  | PS5-08-01 - PAGA
T-00279-3681 | PS5-08-01LS-0714-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0711 TO PS5-08-01LS-0714 |  | PS5-08-01 - PAGA
T-00279-3682 | PS5-08-01LS-0715-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0714 TO PS5-08-01LS-0715 |  | PS5-08-01 - PAGA
T-00279-3683 | PS5-08-01LS-0716-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0715 TO PS5-08-01LS-0716 |  | PS5-08-01 - PAGA
T-00279-3684 | PS5-08-01LS-0716-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1201 TO PS5-08-01LS-0716 |  | PS5-08-01 - PAGA
T-00279-3685 | PS5-08-01LS-0717-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0713 TO PS5-08-01LS-0717 |  | PS5-08-01 - PAGA
T-00279-3686 | PS5-08-01LS-0718-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0717 TO PS5-08-01LS-0718 |  | PS5-08-01 - PAGA
T-00279-3687 | PS5-08-01LS-0719-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01OC-0001 TO PS5-08-01LS-0719 |  | PS5-08-01 - PAGA
T-00279-3688 | PS5-08-01LS-0720-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-0001 TO PS5-08-01LS-0720 |  | PS5-08-01 - PAGA
T-00279-3689 | PS5-08-01LS-0721-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1601 TO PS5-08-01LS-0721 |  | PS5-08-01 - PAGA
T-00279-3690 | PS5-08-01LS-0722-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0721 TO PS5-08-01LS-0722 |  | PS5-08-01 - PAGA
T-00279-3691 | PS5-08-01LS-0723-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0722 TO PS5-08-01LS-0723 |  | PS5-08-01 - PAGA
T-00279-3692 | PS5-08-01LS-0724-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0723 TO PS5-08-01LS-0724 |  | PS5-08-01 - PAGA
T-00279-3693 | PS5-08-01LS-0725-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0724 TO PS5-08-01LS-0725 |  | PS5-08-01 - PAGA
T-00279-3694 | PS5-08-01LS-0726-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0725 TO PS5-08-01LS-0726 |  | PS5-08-01 - PAGA
T-00279-3695 | PS5-08-01LS-0727-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0726 TO PS5-08-01LS-0727 |  | PS5-08-01 - PAGA
T-00279-3696 | PS5-08-01LS-0728-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0727 TO PS5-08-01LS-0728 |  | PS5-08-01 - PAGA
T-00279-3697 | PS5-08-01LS-0729-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0728 TO PS5-08-01LS-0729 |  | PS5-08-01 - PAGA
T-00279-3698 | PS5-08-01LS-0730-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0729 TO PS5-08-01LS-0730 |  | PS5-08-01 - PAGA
T-00279-3699 | PS5-08-01LS-0731-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0730 TO PS5-08-01LS-0731 |  | PS5-08-01 - PAGA
T-00279-3700 | PS5-08-01LS-0732-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0731 TO PS5-08-01LS-0732 |  | PS5-08-01 - PAGA
T-00279-3701 | PS5-08-01LS-0733-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0732 TO PS5-08-01LS-0733 |  | PS5-08-01 - PAGA
T-00279-3702 | PS5-08-01LS-0733-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1601 TO PS5-08-01LS-0733 |  | PS5-08-01 - PAGA
T-00279-3703 | PS5-08-01LS-0801-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1202 TO PS5-08-01LS-0801 |  | PS5-08-01 - PAGA
T-00279-3704 | PS5-08-01LS-0802-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0801 TO PS5-08-01LS-0802 |  | PS5-08-01 - PAGA
T-00279-3705 | PS5-08-01LS-0803-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0802 TO PS5-08-01LS-0803 |  | PS5-08-01 - PAGA
T-00279-3706 | PS5-08-01LS-0804-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1202 TO PS5-08-01LS-0804 |  | PS5-08-01 - PAGA
T-00279-3707 | PS5-08-01LS-0805-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0803 TO PS5-08-01LS-0805 |  | PS5-08-01 - PAGA
T-00279-3708 | PS5-08-01LS-0806-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0805 TO PS5-08-01LS-0806 |  | PS5-08-01 - PAGA
T-00279-3709 | PS5-08-01LS-0807-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0806 TO PS5-08-01LS-0807 |  | PS5-08-01 - PAGA
T-00279-3710 | PS5-08-01LS-0808-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0807 TO PS5-08-01LS-0808 |  | PS5-08-01 - PAGA
T-00279-3711 | PS5-08-01LS-0809-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0808 TO PS5-08-01LS-0809 |  | PS5-08-01 - PAGA
T-00279-3712 | PS5-08-01LS-0810-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0809 TO PS5-08-01LS-0810 |  | PS5-08-01 - PAGA
T-00279-3713 | PS5-08-01LS-0811-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1202 TO PS5-08-01LS-0811 |  | PS5-08-01 - PAGA
T-00279-3714 | PS5-08-01LS-0812-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0811 TO PS5-08-01LS-0812 |  | PS5-08-01 - PAGA
T-00279-3715 | PS5-08-01LS-0813-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0810 TO PS5-08-01LS-0813 |  | PS5-08-01 - PAGA
T-00279-3716 | PS5-08-01LS-0814-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0813 TO PS5-08-01LS-0814 |  | PS5-08-01 - PAGA
T-00279-3717 | PS5-08-01LS-0815-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0814 TO PS5-08-01LS-0815 |  | PS5-08-01 - PAGA
T-00279-3718 | PS5-08-01LS-0816-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0815 TO PS5-08-01LS-0816 |  | PS5-08-01 - PAGA
T-00279-3719 | PS5-08-01LS-0816-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1202 TO PS5-08-01LS-0816 |  | PS5-08-01 - PAGA
T-00279-3720 | PS5-08-01LS-0817-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0812 TO PS5-08-01LS-0817 |  | PS5-08-01 - PAGA
T-00279-3721 | PS5-08-01LS-0818-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0817 TO PS5-08-01LS-0818 |  | PS5-08-01 - PAGA
T-00279-3722 | PS5-08-01LS-0819-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01OC-0001 TO PS5-08-01LS-0819 |  | PS5-08-01 - PAGA
T-00279-3723 | PS5-08-01LS-0820-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1602 TO PS5-08-01LS-0820 |  | PS5-08-01 - PAGA
T-00279-3724 | PS5-08-01LS-0821-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0820 TO PS5-08-01LS-0821 |  | PS5-08-01 - PAGA
T-00279-3725 | PS5-08-01LS-0822-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0821 TO PS5-08-01LS-0822 |  | PS5-08-01 - PAGA
T-00279-3726 | PS5-08-01LS-0823-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0822 TO PS5-08-01LS-0823 |  | PS5-08-01 - PAGA
T-00279-3727 | PS5-08-01LS-0824-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0823 TO PS5-08-01LS-0824 |  | PS5-08-01 - PAGA
T-00279-3728 | PS5-08-01LS-0825-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0824 TO PS5-08-01LS-0825 |  | PS5-08-01 - PAGA
T-00279-3729 | PS5-08-01LS-0826-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0825 TO PS5-08-01LS-0826 |  | PS5-08-01 - PAGA
T-00279-3730 | PS5-08-01LS-0827-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0826 TO PS5-08-01LS-0827 |  | PS5-08-01 - PAGA
T-00279-3731 | PS5-08-01LS-0828-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0827 TO PS5-08-01LS-0828 |  | PS5-08-01 - PAGA
T-00279-3732 | PS5-08-01LS-0829-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0828 TO PS5-08-01LS-0829 |  | PS5-08-01 - PAGA
T-00279-3733 | PS5-08-01LS-0830-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0829 TO PS5-08-01LS-0830 |  | PS5-08-01 - PAGA
T-00279-3734 | PS5-08-01LS-0831-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0830 TO PS5-08-01LS-0831 |  | PS5-08-01 - PAGA
T-00279-3735 | PS5-08-01LS-0832-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0831 TO PS5-08-01LS-0832 |  | PS5-08-01 - PAGA
T-00279-3736 | PS5-08-01LS-0833-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0832 TO PS5-08-01LS-0833 |  | PS5-08-01 - PAGA
T-00279-3737 | PS5-08-01LS-0834-CR01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01LS-0833 TO PS5-08-01LS-0834 |  | PS5-08-01 - PAGA
T-00279-3738 | PS5-08-01LS-0834-CR02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01BT-1602 TO PS5-08-01LS-0834 |  | PS5-08-01 - PAGA
T-00279-3739 | PS5-08-01OC-0001-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0001 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3740 | PS5-08-01OC-0001-CN02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0001 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00279-3741 | PS5-08-01OC-0002-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0002 |  | PS5-08-01 - PAGA
T-00279-3742 | PS5-08-01OC-0002-CN02 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0002 |  | PS5-08-01 - PAGA
T-00279-3743 | PS5-08-12AP-0001-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-12BT-0001 TO PS5-08-12AP-0001 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00279-3744 | PS5-08-12AP-0104-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-12BT-0104 TO PS5-08-12AP-0104 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00279-3745 | PS5-08-12AP-0105-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-12BT-0105 TO PS5-08-12AP-0105 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00279-3746 | PS5-08-12AP-0106-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-12BT-0106 TO PS5-08-12AP-0106 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00279-3747 | PS5-08-12AP-0107-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-12BT-0107 TO PS5-08-12AP-0107 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00279-3748 | PS5-08-12AP-0108-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-12BT-0108 TO PS5-08-12AP-0108 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00279-3749 | PS5-08-12AP-0109-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-12BT-0109 TO PS5-08-12AP-0109 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00279-3750 | PS5-08-12AP-1903-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-12BT-1903 TO PS5-08-12AP-1903 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00279-3751 | PS5-08-12AP-1904-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-12BT-1904 TO PS5-08-12AP-1904 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00279-3752 | PS5-08-61BT-0001-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-14CB-1201 TO PS5-08-61BT-0001 |  | PS5-08-61 - Meteocean
T-00279-3753 | PS5-08-85BT-0017-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-85BT-0017 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00279-3754 | PS5-08-85BT-1201-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3755 | PS5-08-85BT-1202-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3756 | PS5-08-85BT-1203-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3757 | PS5-08-85BT-1205-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1201 TO PS5-08-85BT-1205 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3758 | PS5-08-85BT-1503-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1501 TO PS5-08-85BT-1503 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3759 | PS5-08-85BT-1603-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85BT-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3760 | PS5-08-85BT-1605-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85BT-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3761 | PS5-08-85BT-1606-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85BT-1606 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3762 | PS5-08-85BT-1607-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85BT-1607 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3763 | PS5-08-85BT-1608-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-85BT-1608 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3764 | PS5-08-85BT-1901-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-85BT-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3765 | PS5-08-85BT-1902-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-85BT-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3766 | PS5-08-85ML-0001-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-0017 TO PS5-08-85ML-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3767 | PS5-08-85ML-1201-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1201 TO PS5-08-85ML-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3768 | PS5-08-85ML-1202-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1202 TO PS5-08-85ML-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3769 | PS5-08-85ML-1203-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1203 TO PS5-08-85ML-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3770 | PS5-08-85ML-1204-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1205 TO PS5-08-85ML-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3771 | PS5-08-85ML-1501-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1503 TO PS5-08-85ML-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3772 | PS5-08-85ML-1601-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1603 TO PS5-08-85ML-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3773 | PS5-08-85ML-1602-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1605 TO PS5-08-85ML-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3774 | PS5-08-85ML-1603-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1606 TO PS5-08-85ML-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3775 | PS5-08-85ML-1604-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1608 TO PS5-08-85ML-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3776 | PS5-08-85ML-1605-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1607 TO PS5-08-85ML-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3777 | PS5-08-85ML-1901-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1901 TO PS5-08-85ML-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00279-3778 | PS5-08-85ML-1902-CN01 | TIX09 - Telecom power and control cable | #N/A | T | Cable FROM PS5-08-85BT-1902 TO PS5-08-85ML-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0815 | PS5-08-01BT-1203-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1203 |  | PS5-08-01 - PAGA
T-00280-0816 | PS5-08-01BT-1203-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1203 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00280-0817 | PS5-08-01BT-1503-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1503 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00280-0818 | PS5-08-01BT-1503-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01BT-1503 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00280-0819 | PS5-08-01MP-0001-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-13CB-1001 TO PS5-08-01MP-0001 |  | PS5-08-01 - PAGA
T-00280-0820 | PS5-08-01MP-0001-CC02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-13CB-1001 TO PS5-08-01MP-0001 |  | PS5-08-01 - PAGA
T-00280-0821 | PS5-08-01MP-0001-CC03 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-13CB-1001 TO PS5-08-01MP-0001 |  | PS5-08-01 - PAGA
T-00280-0822 | PS5-08-01MP-0001-CC04 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-13CB-1001 TO PS5-08-01MP-0001 |  | PS5-08-01 - PAGA
T-00280-0823 | PS5-08-01OC-0001-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0001 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00280-0824 | PS5-08-01OC-0001-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0001 |  | PS5-08-01 - PAGA | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
T-00280-0825 | PS5-08-01OC-0002-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0002 |  | PS5-08-01 - PAGA
T-00280-0826 | PS5-08-01OC-0002-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-01MP-0001 TO PS5-08-01OC-0002 |  | PS5-08-01 - PAGA
T-00280-0827 | PS5-08-01PA-1201-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-01BT-1203 TO PS5-08-01PA-1201 |  | PS5-08-01 - PAGA
T-00280-0828 | PS5-08-01PA-1501-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-01BT-1503 TO PS5-08-01PA-1501 |  | PS5-08-01 - PAGA
T-00280-0829 | PS5-08-03TP-0001-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-03TP-0001 |  | PS5-08-03 - Telephone
T-00280-0830 | PS5-08-03TP-0001-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-03FB-0001 TO PS5-08-03TP-0001 |  | PS5-08-03 - Telephone
T-00280-0831 | PS5-08-03TP-0002-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-03TP-0002 |  | PS5-08-03 - Telephone
T-00280-0832 | PS5-08-03TP-0002-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-03FB-0002 TO PS5-08-03TP-0002 |  | PS5-08-03 - Telephone
T-00280-0833 | PS5-08-03TP-0003-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-03TP-0003 |  | PS5-08-03 - Telephone
T-00280-0834 | PS5-08-03TP-0003-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-03FB-0003 TO PS5-08-03TP-0003 |  | PS5-08-03 - Telephone
T-00280-0835 | PS5-08-03TP-0004-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-03TP-0004 |  | PS5-08-03 - Telephone
T-00280-0836 | PS5-08-03TP-0004-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-03FB-0004 TO PS5-08-03TP-0004 |  | PS5-08-03 - Telephone
T-00280-0837 | PS5-08-03TP-0101-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-03TP-0101 |  | PS5-08-03 - Telephone
T-00280-0838 | PS5-08-03TP-0101-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-03FB-0101 TO PS5-08-03TP-0101 |  | PS5-08-03 - Telephone
T-00280-0839 | PS5-08-03TP-0102-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-03TP-0102 |  | PS5-08-03 - Telephone
T-00280-0840 | PS5-08-03TP-0102-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-03FB-0102 TO PS5-08-03TP-0102 |  | PS5-08-03 - Telephone
T-00280-0841 | PS5-08-03TP-0103-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-03TP-0103 |  | PS5-08-03 - Telephone
| PS5-08-85IN-0005-CA01 | TIX | #N/A | T
T-00280-0842 | PS5-08-03TP-0103-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-03FB-0103 TO PS5-08-03TP-0103 |  | PS5-08-03 - Telephone
T-00280-0843 | PS5-08-03TP-1903-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-03TP-1903 |  | PS5-08-03 - Telephone
T-00280-0844 | PS5-08-03TP-1903-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-03FB-1903 TO PS5-08-03TP-1903 |  | PS5-08-03 - Telephone
T-00280-0845 | PS5-08-03TP-1904-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-03TP-1904 |  | PS5-08-03 - Telephone
T-00280-0846 | PS5-08-03TP-1904-CJ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-03FB-1904 TO PS5-08-03TP-1904 |  | PS5-08-03 - Telephone
T-00280-0847 | PS5-08-13CB-1201-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-14CB-1201 TO PS5-08-13CB-1201 |  | PS5-08-93 - Telecom Monitoring System
T-00280-0848 | PS5-08-13CB-1201-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-04-PMC-0006 TO PS5-08-13CB-1201 |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00280-0849 | PS5-08-52TK-0031-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0031 TO PS5-08-52TK-0031 |  | PS5-08-52 - Process & Security CCTV
T-00280-0850 | PS5-08-52TK-0032-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0032 TO PS5-08-52TK-0032 |  | PS5-08-52 - Process & Security CCTV
T-00280-0851 | PS5-08-52TK-0033-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0033 TO PS5-08-52TK-0033 |  | PS5-08-52 - Process & Security CCTV
T-00280-0852 | PS5-08-52TK-0131-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0131 TO PS5-08-52TK-0131 |  | PS5-08-52 - Process & Security CCTV
T-00280-0853 | PS5-08-52TK-0132-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0132 TO PS5-08-52TK-0132 |  | PS5-08-52 - Process & Security CCTV
T-00280-0854 | PS5-08-52TK-0133-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0133 TO PS5-08-52TK-0133 |  | PS5-08-52 - Process & Security CCTV
T-00280-0855 | PS5-08-52TK-0134-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0134 TO PS5-08-52TK-0134 |  | PS5-08-52 - Process & Security CCTV
T-00280-0856 | PS5-08-52TK-0135-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0135 TO PS5-08-52TK-0135 |  | PS5-08-52 - Process & Security CCTV
T-00280-0857 | PS5-08-52TK-0136-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0136 TO PS5-08-52TK-0136 |  | PS5-08-52 - Process & Security CCTV
T-00280-0858 | PS5-08-52TK-0137-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0137 TO PS5-08-52TK-0137 |  | PS5-08-52 - Process & Security CCTV
T-00280-0859 | PS5-08-52TK-0138-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0138 TO PS5-08-52TK-0138 |  | PS5-08-52 - Process & Security CCTV
T-00280-0860 | PS5-08-52TK-0139-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0139 TO PS5-08-52TK-0139 |  | PS5-08-52 - Process & Security CCTV
T-00280-0861 | PS5-08-52TK-0140-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0140 TO PS5-08-52TK-0140 |  | PS5-08-52 - Process & Security CCTV
T-00280-0862 | PS5-08-52TK-0931-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-52CM-0931 TO PS5-08-52TK-0931 |  | PS5-08-52 - Process & Security CCTV
T-00280-0863 | PS5-08-61BT-0001-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-14CB-1201 TO PS5-08-61BT-0001 |  | PS5-08-61 - Meteocean
T-00280-0864 | PS5-08-61BT-0001-CC02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-14CB-1201 TO PS5-08-61BT-0001 |  | PS5-08-61 - Meteocean
T-00280-0865 | PS5-08-61BT-0002-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-14CB-1201 TO PS5-08-61BT-0002 |  | PS5-08-61 - Meteocean
T-00280-0866 | PS5-08-61BT-0901-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-61BT-0001 TO PS5-08-61BT-0901 |  | PS5-08-61 - Meteocean
T-00280-0867 | PS5-08-61SN-0003-CZ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-61BT-0001 TO PS5-08-61SN-0003 |  | PS5-08-61 - Meteocean
T-00280-0868 | PS5-08-61SN-0004-CZ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-61BT-0001 TO PS5-08-61SN-0004 |  | PS5-08-61 - Meteocean
T-00280-0869 | PS5-08-61SN-0005-CZ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-61BT-0002 TO PS5-08-61SN-0005 |  | PS5-08-61 - Meteocean
T-00280-0870 | PS5-08-61SN-0005-CZ02 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-61BT-0002 TO PS5-08-61SN-0005 |  | PS5-08-61 - Meteocean
T-00280-0871 | PS5-08-61SN-0901-CZ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-61BT-0901 TO PS5-08-61SN-0901 |  | PS5-08-61 - Meteocean
T-00280-0872 | PS5-08-85BG-1201-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1201 TO PS5-08-85BG-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0873 | PS5-08-85BG-1202-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1202 TO PS5-08-85BG-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0874 | PS5-08-85BG-1203-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1203 TO PS5-08-85BG-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0875 | PS5-08-85BG-1204-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1205 TO PS5-08-85BG-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0876 | PS5-08-85BG-1501-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1503 TO PS5-08-85BG-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0877 | PS5-08-85BG-1601-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1603 TO PS5-08-85BG-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0878 | PS5-08-85BG-1602-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1605 TO PS5-08-85BG-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0879 | PS5-08-85BG-1603-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1606 TO PS5-08-85BG-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0880 | PS5-08-85BG-1604-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1607 TO PS5-08-85BG-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0881 | PS5-08-85BG-1605-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1608 TO PS5-08-85BG-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0882 | PS5-08-85BG-1901-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1901 TO PS5-08-85BG-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0883 | PS5-08-85BG-1902-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1902 TO PS5-08-85BG-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0884 | PS5-08-85BR-0001-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0885 | PS5-08-85BR-0002-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0886 | PS5-08-85BR-0003-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0003 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0887 | PS5-08-85BR-0004-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0004 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0888 | PS5-08-85BR-0005-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0005 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0889 | PS5-08-85BR-0006-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0006 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0890 | PS5-08-85BR-0007-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0007 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0891 | PS5-08-85BR-0008-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-0008 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0892 | PS5-08-85BR-0009-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1201 TO PS5-08-85BR-0009 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0893 | PS5-08-85BR-0010-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-0010 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0894 | PS5-08-85BR-0011-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-0024 TO PS5-08-85BR-0011 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0895 | PS5-08-85BR-0012-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-0025 TO PS5-08-85BR-0012 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0896 | PS5-08-85BR-1201-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0897 | PS5-08-85BR-1202-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0898 | PS5-08-85BR-1203-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0899 | PS5-08-85BR-1204-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0900 | PS5-08-85BR-1205-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1201 TO PS5-08-85BR-1205 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0901 | PS5-08-85BR-1206-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BR-1206 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0902 | PS5-08-85BR-1501-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0903 | PS5-08-85BR-1502-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BR-1502 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0904 | PS5-08-85BR-1601-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BR-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0905 | PS5-08-85BR-1602-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BR-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0906 | PS5-08-85BR-1603-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BR-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0907 | PS5-08-85BR-1604-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BR-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0908 | PS5-08-85BR-1605-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BR-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0909 | PS5-08-85BR-1901-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BR-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0910 | PS5-08-85BR-1902-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BR-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0911 | PS5-08-85BT-0001-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0912 | PS5-08-85BT-0002-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0913 | PS5-08-85BT-0003-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0003 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0914 | PS5-08-85BT-0004-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0005 TO PS5-08-85BT-0004 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0915 | PS5-08-85BT-0005-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0005 TO PS5-08-85BT-0005 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0916 | PS5-08-85BT-0006-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0005 TO PS5-08-85BT-0006 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0917 | PS5-08-85BT-0007-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0005 TO PS5-08-85BT-0007 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0918 | PS5-08-85BT-0008-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-85BT-0008 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0919 | PS5-08-85BT-0009-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-85BT-0009 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0920 | PS5-08-85BT-0010-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-85BT-0010 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0921 | PS5-08-85BT-0011-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-85BT-0011 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0922 | PS5-08-85BT-0012-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-85BT-0012 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0923 | PS5-08-85BT-0013-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-85BT-0013 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0924 | PS5-08-85BT-0014-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-85BT-0014 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0925 | PS5-08-85BT-0015-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-85BT-0015 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0926 | PS5-08-85BT-0016-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-85BT-0016 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0035 | 03-July-2026 | Open | Ferdinand | Testing
| PS5-61-IG-0012A-CX01 | TIX | #N/A | T | [7 empty] | Testing
| PS5-61-IG-0012B-CX01 | TIX | #N/A | T | [7 empty] | Testing
| PS5-61-IG-0012C-CX01 | TIX | #N/A | T | [7 empty] | Testing
| PS5-60-IE-0004-CX02 | TIX | #N/A | T | [7 empty] | Testing
| PS5-60-IE-0004-CX01 | TIX | #N/A | T | [7 empty] | Testing
| PS5-61-IK-0003-CX01 | TIX | #N/A | T | [7 empty] | Testing
| PS5-61-IK-0006-CX01 | TIX | #N/A | T | [7 empty] | Testing
T-00280-0927 | PS5-08-85BT-0017-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0017 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0928 | PS5-08-85BT-0018-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0018 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0929 | PS5-08-85BT-0019-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0019 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0930 | PS5-08-85BT-0020-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0020 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0931 | PS5-08-85BT-0021-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0021 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0932 | PS5-08-85BT-0022-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0022 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0933 | PS5-08-85BT-0023-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-0023 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0934 | PS5-08-85BT-0024-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0024 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0935 | PS5-08-85BT-0025-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0025 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0936 | PS5-08-85BT-0026-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-85BT-0026 |  | PS5-08-85 - Access Control, POB & e-Mustering | CPP-RFI-68-65-20-0033 | 20-June-2026 | Open | Ferdinand | Testing
T-00280-0937 | PS5-08-85BT-1201-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BT-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0938 | PS5-08-85BT-1202-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BT-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0939 | PS5-08-85BT-1203-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BT-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0940 | PS5-08-85BT-1204-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1201 TO PS5-08-85BT-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0941 | PS5-08-85BT-1205-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1202 TO PS5-08-85BT-1205 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0942 | PS5-08-85BT-1501-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0943 | PS5-08-85BT-1502-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-1502 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0944 | PS5-08-85BT-1503-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85BT-1503 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0945 | PS5-08-85BT-1601-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0946 | PS5-08-85BT-1602-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0947 | PS5-08-85BT-1603-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0948 | PS5-08-85BT-1604-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0949 | PS5-08-85BT-1605-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0950 | PS5-08-85BT-1606-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1606 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0951 | PS5-08-85BT-1607-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1607 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0952 | PS5-08-85BT-1608-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1608 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0953 | PS5-08-85BT-1609-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1609 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0954 | PS5-08-85BT-1610-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1610 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0955 | PS5-08-85BT-1611-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1611 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0956 | PS5-08-85BT-1612-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1612 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0957 | PS5-08-85BT-1613-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1613 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0958 | PS5-08-85BT-1614-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1601 TO PS5-08-85BT-1614 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0959 | PS5-08-85BT-1901-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0960 | PS5-08-85BT-1902-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0961 | PS5-08-85BT-1903-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1903 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0962 | PS5-08-85BT-1904-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1904 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0963 | PS5-08-85BT-1905-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1905 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0964 | PS5-08-85BT-1906-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1906 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0965 | PS5-08-85BT-1907-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1907 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0966 | PS5-08-85BT-1908-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1908 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0967 | PS5-08-85BT-1909-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1901 TO PS5-08-85BT-1909 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0968 | PS5-08-85DC-0001-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0017 TO PS5-08-85DC-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0969 | PS5-08-85DC-0002-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0001 TO PS5-08-85DC-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0970 | PS5-08-85DC-0003-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0019 TO PS5-08-85DC-0003 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0971 | PS5-08-85DC-0004-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0002 TO PS5-08-85DC-0004 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0972 | PS5-08-85DC-0005-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0003 TO PS5-08-85DC-0005 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0973 | PS5-08-85DC-0006-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0004 TO PS5-08-85DC-0006 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0974 | PS5-08-85DC-0007-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0005 TO PS5-08-85DC-0007 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0975 | PS5-08-85DC-0008-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0006 TO PS5-08-85DC-0008 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0976 | PS5-08-85DC-0009-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0007 TO PS5-08-85DC-0009 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0977 | PS5-08-85DC-0010-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0008 TO PS5-08-85DC-0010 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0978 | PS5-08-85DC-0011-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0010 TO PS5-08-85DC-0011 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0979 | PS5-08-85DC-0012-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0009 TO PS5-08-85DC-0012 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0980 | PS5-08-85DC-0013-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0012 TO PS5-08-85DC-0013 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0981 | PS5-08-85DC-0014-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0011 TO PS5-08-85DC-0014 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0982 | PS5-08-85DC-0015-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0013 TO PS5-08-85DC-0015 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0983 | PS5-08-85DC-0016-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0014 TO PS5-08-85DC-0016 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0984 | PS5-08-85DC-0017-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0015 TO PS5-08-85DC-0017 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0985 | PS5-08-85DC-0018-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0016 TO PS5-08-85DC-0018 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0986 | PS5-08-85DC-0019-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0024 TO PS5-08-85DC-0019 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0987 | PS5-08-85DC-0021-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0025 TO PS5-08-85DC-0021 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0988 | PS5-08-85DC-0022-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0026 TO PS5-08-85DC-0022 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0989 | PS5-08-85DC-0023-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0018 TO PS5-08-85DC-0023 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0990 | PS5-08-85DC-0024-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0001 TO PS5-08-85DC-0024 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0991 | PS5-08-85DC-0025-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0009 TO PS5-08-85DC-0025 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0992 | PS5-08-85DC-0026-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0024 TO PS5-08-85DC-0026 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0993 | PS5-08-85DC-0027-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0025 TO PS5-08-85DC-0027 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0994 | PS5-08-85DC-0028-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0026 TO PS5-08-85DC-0028 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0995 | PS5-08-85DC-1201-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1201 TO PS5-08-85DC-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0996 | PS5-08-85DC-1202-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1202 TO PS5-08-85DC-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0997 | PS5-08-85DC-1203-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1202 TO PS5-08-85DC-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0998 | PS5-08-85DC-1204-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1203 TO PS5-08-85DC-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-0999 | PS5-08-85DC-1205-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1204 TO PS5-08-85DC-1205 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1000 | PS5-08-85DC-1206-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1204 TO PS5-08-85DC-1206 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1001 | PS5-08-85DC-1207-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1205 TO PS5-08-85DC-1207 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1002 | PS5-08-85DC-1501-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1501 TO PS5-08-85DC-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1003 | PS5-08-85DC-1502-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1502 TO PS5-08-85DC-1502 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1004 | PS5-08-85DC-1503-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1503 TO PS5-08-85DC-1503 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1005 | PS5-08-85DC-1601-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1601 TO PS5-08-85DC-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1006 | PS5-08-85DC-1602-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1602 TO PS5-08-85DC-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1007 | PS5-08-85DC-1603-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1603 TO PS5-08-85DC-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1008 | PS5-08-85DC-1604-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1603 TO PS5-08-85DC-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1009 | PS5-08-85DC-1605-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1604 TO PS5-08-85DC-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1010 | PS5-08-85DC-1606-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1604 TO PS5-08-85DC-1606 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1011 | PS5-08-85DC-1607-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1607 TO PS5-08-85DC-1607 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1012 | PS5-08-85DC-1608-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1606 TO PS5-08-85DC-1608 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1013 | PS5-08-85DC-1609-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1606 TO PS5-08-85DC-1609 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1014 | PS5-08-85DC-1610-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1614 TO PS5-08-85DC-1610 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1015 | PS5-08-85DC-1611-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1613 TO PS5-08-85DC-1611 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1016 | PS5-08-85DC-1612-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1613 TO PS5-08-85DC-1612 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1017 | PS5-08-85DC-1613-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1612 TO PS5-08-85DC-1613 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1018 | PS5-08-85DC-1614-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1611 TO PS5-08-85DC-1614 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1019 | PS5-08-85DC-1615-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1610 TO PS5-08-85DC-1615 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1020 | PS5-08-85DC-1616-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1609 TO PS5-08-85DC-1616 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1021 | PS5-08-85DC-1617-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1605 TO PS5-08-85DC-1617 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1022 | PS5-08-85DC-1618-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1608 TO PS5-08-85DC-1618 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1023 | PS5-08-85DC-1901-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1903 TO PS5-08-85DC-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1024 | PS5-08-85DC-1902-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1903 TO PS5-08-85DC-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1025 | PS5-08-85DC-1903-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1904 TO PS5-08-85DC-1903 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1026 | PS5-08-85DC-1904-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1904 TO PS5-08-85DC-1904 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1027 | PS5-08-85DC-1905-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1905 TO PS5-08-85DC-1905 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1028 | PS5-08-85DC-1906-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1905 TO PS5-08-85DC-1906 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1029 | PS5-08-85DC-1907-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1906 TO PS5-08-85DC-1907 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1030 | PS5-08-85DC-1908-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1906 TO PS5-08-85DC-1908 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1031 | PS5-08-85DC-1909-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1907 TO PS5-08-85DC-1909 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1032 | PS5-08-85DC-1910-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1907 TO PS5-08-85DC-1910 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1033 | PS5-08-85DC-1911-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1901 TO PS5-08-85DC-1911 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1034 | PS5-08-85DC-1912-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1902 TO PS5-08-85DC-1912 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1035 | PS5-08-85DC-1913-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1908 TO PS5-08-85DC-1913 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1036 | PS5-08-85DC-1914-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1908 TO PS5-08-85DC-1914 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1037 | PS5-08-85DC-1915-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1908 TO PS5-08-85DC-1915 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1038 | PS5-08-85DC-1916-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1909 TO PS5-08-85DC-1916 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1039 | PS5-08-85PB-0001-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0017 TO PS5-08-85PB-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1040 | PS5-08-85PB-1201-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1201 TO PS5-08-85PB-1201 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1041 | PS5-08-85PB-1202-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1202 TO PS5-08-85PB-1202 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1042 | PS5-08-85PB-1203-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1203 TO PS5-08-85PB-1203 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1043 | PS5-08-85PB-1204-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1205 TO PS5-08-85PB-1204 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1044 | PS5-08-85PB-1501-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85CP-1501 TO PS5-08-85PB-1501 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1045 | PS5-08-85PB-1601-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1603 TO PS5-08-85PB-1601 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1046 | PS5-08-85PB-1602-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1605 TO PS5-08-85PB-1602 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1047 | PS5-08-85PB-1603-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1606 TO PS5-08-85PB-1603 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1048 | PS5-08-85PB-1604-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1607 TO PS5-08-85PB-1604 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1049 | PS5-08-85PB-1605-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1608 TO PS5-08-85PB-1605 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1050 | PS5-08-85PB-1901-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1901 TO PS5-08-85PB-1901 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1051 | PS5-08-85PB-1902-CJ01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-1902 TO PS5-08-85PB-1902 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1052 | PS5-82-MBA-0001-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0021 TO PS5-82-MBA-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1053 | PS5-82-MBA-0002-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0023 TO PS5-82-MBA-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1054 | PS5-82-MBA-0003-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0020 TO PS5-82-MBA-0003 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1055 | PS5-82-MGV-0002-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0019 TO PS5-82-MGV-0002 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00280-1056 | PS5-82-MTL-0001-CC01 | TIX10 - Multicore cable telecom | #N/A | T | Cable FROM PS5-08-85BT-0022 TO PS5-82-MTL-0001 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00295-0408 | PS5-03-14_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room
T-00295-0409 | PS5-04-01_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-04-01 - Office Building PCS System
T-00295-0410 | PS5-04-03_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-04-03 - 33kV ICSS System
T-00295-0411 | PS5-04-04_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-04-04 - 33kV PCS System
T-00295-0412 | PS5-04-05_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-04-05 - 33kV SIS/FGS System
T-00295-0413 | PS5-06-01_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-06-01 - AC UPS - EITS Building
T-00295-0414 | PS5-08-01_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-01 - PAGA
T-00295-0415 | PS5-08-03_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-03 - Telephone
T-00295-0416 | PS5-08-04_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-04 - Hotline
T-00295-0417 | PS5-08-11_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-11 - Corporate LAN (SIE)
T-00295-0418 | PS5-08-12_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00295-0419 | PS5-08-13_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00295-0420 | PS5-08-14_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00295-0421 | PS5-08-15_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00295-0422 | PS5-08-23_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-23 - VHF Trunk Radio System
T-00295-0423 | PS5-08-34_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-34 - Satphone
T-00295-0424 | PS5-08-35_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-35 - Optical Transport Network
T-00295-0425 | PS5-08-36_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-36 - Pipeline FO Cable & EPRS
T-00295-0426 | PS5-08-51_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-51 - Entertainment
T-00295-0427 | PS5-08-52_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-52 - Process & Security CCTV
T-00295-0428 | PS5-08-55_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-55 - Videoconference
T-00295-0429 | PS5-08-61_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-61 - Meteocean
T-00295-0430 | PS5-08-71_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-71 - Structured Cabling (CAT6)
T-00295-0431 | PS5-08-81_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-81 - Guard tour
T-00295-0432 | PS5-08-82_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-82 - Key Management
T-00295-0433 | PS5-08-83_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-83 - Perimeter & Pipeline intrusion detection system
T-00295-0434 | PS5-08-85_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00295-0435 | PS5-08-86_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-86 - Integrated Security Management System
T-00295-0436 | PS5-08-92_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-92 - Telecom Mast
T-00295-0437 | PS5-08-93_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-08-93 - Telecom Monitoring System
T-00295-0438 | PS5-09-03_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-09-03 - HVAC for Generator Building
T-00295-0439 | PS5-09-05_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-09-05 - HVAC for EITS Building
T-00295-0440 | PS5-60-03_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs
T-00295-0441 | PS5-60-05_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-05 - Power Gen Package B (UCP)
T-00295-0442 | PS5-60-06_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs
T-00295-0443 | PS5-60-08_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-08 - Power Gen Package C (UCP)
T-00295-0444 | PS5-60-09_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs
T-00295-0445 | PS5-60-10_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-10 - Power Generation Package D
T-00295-0446 | PS5-60-11_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-11 - Power Gen Package D (UCP)
T-00295-0447 | PS5-60-12_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs
T-00295-0448 | PS5-60-14_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-14 - Power Gen Package E (UCP)
T-00295-0449 | PS5-60-15_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs
T-00295-0450 | PS5-60-16_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-16 - Power Generation Package F
T-00295-0451 | PS5-60-17_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-17 - Power Gen Package F (UCP)
T-00295-0452 | PS5-60-18_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs
T-00295-0453 | PS5-60-20_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-20 - Power Gen Package G (UCP)
T-00295-0454 | PS5-60-21_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs
T-00295-0455 | PS5-60-22_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-22 - Power Gen Master UCP
T-00295-0456 | PS5-60-49_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A
T-00295-0457 | PS5-60-50_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B
T-00295-0458 | PS5-60-51_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C
T-00295-0459 | PS5-60-52_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D
T-00295-0460 | PS5-60-53_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E
T-00295-0461 | PS5-60-54_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F
T-00295-0462 | PS5-60-55_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G
T-00295-0463 | PS5-60-57_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP)
T-00295-0464 | PS5-60-59_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP)
T-00295-0465 | PS5-60-61_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP)
T-00295-0466 | PS5-60-63_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP)
T-00295-0467 | PS5-60-65_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP)
T-00295-0468 | PS5-60-67_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP)
T-00295-0469 | PS5-60-69_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP)
T-00295-0470 | PS5-61-01_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00295-0471 | PS5-61-02_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010)
T-00295-0472 | PS5-61-03_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011)
T-00295-0473 | PS5-61-07_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001)
T-00295-0474 | PS5-61-08_PRC-TELECOM-EITS | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-61-08 - Electrical Control System
T-00295-0475 | PS5-71-07_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-71-07 - Crude Fuel Separation Module (UCP)
T-00295-0476 | PS5-71-09_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-71-09 - CFO Pre-Pressure Modules (UCP)
T-00295-0477 | PS5-71-19_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-71-19 - Diesel Separator Module (UCP)
T-00295-0478 | PS5-71-23_PRC-TELECOM-CPP | 2621T - Telecommunications | #N/A | T | PRC Telecom |  | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP)
T-00429-1489 | PS5-08-11CB-1201-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-11CB-1201 |  | PS5-08-11 - Corporate LAN (SIE)
T-00429-1490 | PS5-08-11CB-1501-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-11CB-1501 |  | PS5-08-11 - Corporate LAN (SIE) | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00429-1491 | PS5-08-11CB-1601-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-11CB-1601 |  | PS5-08-11 - Corporate LAN (SIE)
T-00429-1492 | PS5-08-11CB-1901-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-11CB-1901 |  | PS5-08-11 - Corporate LAN (SIE)
T-00429-1493 | PS5-08-12BT-0001-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1601 TO PS5-08-12BT-0001 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00429-1494 | PS5-08-12BT-0104-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-12BT-0104 |  | PS5-08-12 - Corporate Wireless LAN (SIE) | CPP-RFI-68-65-05-0028 | 11-May-2026 | Accepted | Ferdinand | Pulling
T-00429-1495 | PS5-08-12BT-0105-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-12BT-0105 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00429-1496 | PS5-08-12BT-0106-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-12BT-0106 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00429-1497 | PS5-08-12BT-0107-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-0107 |  | PS5-08-12 - Corporate Wireless LAN (SIE) | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00429-1498 | PS5-08-12BT-0108-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-0108 |  | PS5-08-12 - Corporate Wireless LAN (SIE) | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00429-1499 | PS5-08-12BT-0109-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1001 TO PS5-08-12BT-0109 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00429-1500 | PS5-08-12BT-1903-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-1903 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00429-1501 | PS5-08-12BT-1904-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-12BT-1904 |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00429-1502 | PS5-08-15CP-0001-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CP-0008 TO PS5-08-15CP-0001 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00429-1503 | PS5-08-15CP-0002-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CP-0001 TO PS5-08-15CP-0002 |  | PS5-08-15 - Security Data Network (SII SP3 SEC) | CPP-RFI-68-65-05-0023 | 2026-04-10 | Accepted | Bertus Wikael | PULLING
T-00429-1504 | PS5-08-15CP-0003-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CP-0002 TO PS5-08-15CP-0003 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00429-1505 | PS5-08-15CP-0004-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CP-0003 TO PS5-08-15CP-0004 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00429-1506 | PS5-08-15CP-0005-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CP-0004 TO PS5-08-15CP-0005 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00429-1507 | PS5-08-15CP-0005-CX02 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-15CP-0005 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00429-1508 | PS5-08-15CP-0006-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-15CP-0006 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00429-1509 | PS5-08-15CP-0007-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CP-0006 TO PS5-08-15CP-0007 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00429-1510 | PS5-08-15CP-0008-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CP-0007 TO PS5-08-15CP-0008 |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00429-1511 | PS5-08-36SP-0101-CX02 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-35CB-1001 TO PS5-08-36SP-0101 |  | PS5-08-36 - Pipeline FO Cable & EPRS
T-00429-1512 | PS5-08-36SP-0102-CX02 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-35CB-1001 TO PS5-08-36SP-0102 |  | PS5-08-36 - Pipeline FO Cable & EPRS
| PS5-08-52-CM-0132-CX01 | CIX | #N/A | T |  |  |  | CPP-RFI-68-65-05-0027 | 11-May-2026 | Accepted with Punchlist | Ferdinand | Pulling
T-00429-1513 | PS5-08-52CM-0131-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-52CM-0131 |  | PS5-08-52 - Process & Security CCTV | CPP-RFI-68-65-05-0027 | 11-May-2026 | Accepted with Punchlist | Ferdinand | Pulling
T-00429-1514 | PS5-08-52CM-0132-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-52CM-0132 |  | PS5-08-52 - Process & Security CCTV
T-00429-1515 | PS5-08-52CM-0133-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-52CM-0133 |  | PS5-08-52 - Process & Security CCTV | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
| PS5-08-85IN-0005-CA01 | CIX | #N/A | T |  |  |  | CPP-RFI-68-65-05-0036 | 06-July-2026 | open | Ferdinand | pulling
T-00429-1516 | PS5-08-52CM-0135-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-0135 |  | PS5-08-52 - Process & Security CCTV
T-00429-1517 | PS5-08-52CM-0136-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-11CB-1901 TO PS5-08-52CM-0136 |  | PS5-08-52 - Process & Security CCTV
T-00429-1518 | PS5-08-52CM-0138-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-52CM-0138 |  | PS5-08-52 - Process & Security CCTV
T-00429-1519 | PS5-08-52CM-0139-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-52CM-0139 |  | PS5-08-52 - Process & Security CCTV
T-00429-1520 | PS5-08-83SP-0001-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-83SP-0001 |  | PS5-08-83 - Perimeter & Pipeline intrusion detection system
T-00429-1521 | PS5-08-83SP-0001-CX02 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-83SP-0001 |  | PS5-08-83 - Perimeter & Pipeline intrusion detection system
T-00429-1522 | PS5-08-85CP-0024-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-85CP-0024 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00429-1523 | PS5-08-85CP-0024-CX02 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-85CP-0024 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00429-1524 | PS5-08-85CP-0025-CX01 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-85CP-0025 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00429-1525 | PS5-08-85CP-0025-CX02 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-15CB-1001 TO PS5-08-85CP-0025 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00429-1556 | PS5-61-IJ-0001-CX02 | CIX55 - Fiber Optic Cable | #N/A | T | Cable FROM PS5-08-35CB-1001 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00431-0008 | PS5-08-34LA-1201 | CIX52 - Lighting Arrestor | #N/A | T | Lightning Arrestor |  | PS5-08-34 - Satphone
T-00431-0009 | PS5-08-34LA-1501 | CIX52 - Lighting Arrestor | #N/A | T | Lightning Arrestor |  | PS5-08-34 - Satphone
T-00431-0052 | PS5-08-23LA-1201 | CIX52 - Lighting Arrestor | #N/A | T | Lightning arrestor |  | PS5-08-23 - VHF Trunk Radio System
T-00431-0053 | PS5-08-23LA-1202 | CIX52 - Lighting Arrestor | #N/A | T | Lightning arrestor |  | PS5-08-23 - VHF Trunk Radio System
T-00431-0054 | PS5-08-23LA-1501 | CIX52 - Lighting Arrestor | #N/A | T | Lightning arrestor |  | PS5-08-23 - VHF Trunk Radio System
T-00431-0055 | PS5-08-23LA-1601 | CIX52 - Lighting Arrestor | #N/A | T | Lightning arrestor |  | PS5-08-23 - VHF Trunk Radio System
T-00431-0070 | PS5-08-51LA-1201 | CIX52 - Lighting Arrestor | #N/A | T | Coaxial Surge Protector |  | PS5-08-51 - Entertainment
T-00431-0071 | PS5-08-51LA-1202 | CIX52 - Lighting Arrestor | #N/A | T | Coaxial Surge Protector |  | PS5-08-51 - Entertainment
T-00431-0072 | PS5-08-51LA-1203 | CIX52 - Lighting Arrestor | #N/A | T | Coaxial Surge Protector |  | PS5-08-51 - Entertainment
T-00431-0073 | PS5-08-51LA-1204 | CIX52 - Lighting Arrestor | #N/A | T | Coaxial Surge Protector |  | PS5-08-51 - Entertainment
T-00432-0005 | PS5-08-51AP-1201 | CIX53 - WIFI Access Point | #N/A | T | WIFI Access point |  | PS5-08-51 - Entertainment
T-00432-0006 | PS5-08-51AP-1202 | CIX53 - WIFI Access Point | #N/A | T | WIFI Access point |  | PS5-08-51 - Entertainment
T-00432-0016 | PS5-08-51AP-1203 | CIX53 - WIFI Access Point | #N/A | T | WIFI Access point |  | PS5-08-51 - Entertainment
T-00432-0172 | PS5-08-12AP-0001 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0173 | PS5-08-12AP-0002 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0174 | PS5-08-12AP-0003 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0175 | PS5-08-12AP-0101 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0176 | PS5-08-12AP-0103 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0177 | PS5-08-12AP-0104 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0178 | PS5-08-12AP-0105 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0179 | PS5-08-12AP-0106 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0180 | PS5-08-12AP-0107 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0181 | PS5-08-12AP-0108 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0182 | PS5-08-12AP-0109 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0185 | PS5-08-12AP-1201 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0186 | PS5-08-12AP-1202 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0187 | PS5-08-12AP-1203 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0188 | PS5-08-12AP-1204 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0189 | PS5-08-12AP-1205 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0190 | PS5-08-12AP-1206 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0191 | PS5-08-12AP-1501 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0192 | PS5-08-12AP-1502 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0193 | PS5-08-12AP-1601 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0194 | PS5-08-12AP-1602 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0195 | PS5-08-12AP-1603 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0196 | PS5-08-12AP-1901 | CIX53 - WIFI Access Point | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0197 | PS5-08-12AP-1903 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0198 | PS5-08-12AP-1904 | CIX53 - WIFI Access Point | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00432-0226 | PS5-08-05IN-1501 | CIX53 - WIFI Access Point | #N/A | T | Master Intercom |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00432-0227 | PS5-08-85AP-0001 | CIX53 - WIFI Access Point | #N/A | T | WiFi Access Point A - Primary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00432-0228 | PS5-08-85AP-0002 | CIX53 - WIFI Access Point | #N/A | T | WiFi Access Point B - Primary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00432-0229 | PS5-08-85AP-0003 | CIX53 - WIFI Access Point | #N/A | T | WiFi Access Point A - Secondary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00432-0230 | PS5-08-85AP-0004 | CIX53 - WIFI Access Point | #N/A | T | WiFi Access Point B - Secondary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00432-0231 | PS5-08-85AP-1201 | CIX53 - WIFI Access Point | #N/A | T | WiFi Access Point A - Safe Haven |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00432-0232 | PS5-08-85AP-1202 | CIX53 - WIFI Access Point | #N/A | T | WiFi Access Point B - Safe Haven |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00545-0037 | BF_PS5-08-01LS-01 | FI01L - Loudspeaker Test | #N/A | T | PS5-Loop 1 -Loudspeaker |  | PS5-08-01 - PAGA
T-00545-0038 | BF_PS5-08-01LS-02 | FI01L - Loudspeaker Test | #N/A | T | PS5-Loop 2 -Loudspeaker |  | PS5-08-01 - PAGA
T-00545-0039 | BF_PS5-08-01LS-03 | FI01L - Loudspeaker Test | #N/A | T | PS5-Loop 3 -Loudspeaker |  | PS5-08-01 - PAGA
T-00545-0040 | BF_PS5-08-01LS-04 | FI01L - Loudspeaker Test | #N/A | T | PS5-Loop 4 -Loudspeaker |  | PS5-08-01 - PAGA
T-00545-0041 | BF_PS5-08-01LS-05 | FI01L - Loudspeaker Test | #N/A | T | PS5-Loop 5 -Loudspeaker |  | PS5-08-01 - PAGA
T-00545-0042 | BF_PS5-08-01LS-06 | FI01L - Loudspeaker Test | #N/A | T | PS5-Loop 6 -Loudspeaker |  | PS5-08-01 - PAGA
T-00545-0043 | BF_PS5-08-01LS-07 | FI01L - Loudspeaker Test | #N/A | T | PS5-Loop 7 -Loudspeaker |  | PS5-08-01 - PAGA
T-00545-0044 | BF_PS5-08-01LS-08 | FI01L - Loudspeaker Test | #N/A | T | PS5-Loop 8 -Loudspeaker |  | PS5-08-01 - PAGA
T-00546-0015 | BF_PS5-08-01FB-09 | FI01L2 - Beacon Loop Test | #N/A | T | PS5-Loop 9 -Flashing Beacon |  | PS5-08-01 - PAGA
T-00546-0016 | BF_PS5-08-01FB-10 | FI01L2 - Beacon Loop Test | #N/A | T | PS5-Loop 10 Flashing Beacon |  | PS5-08-01 - PAGA
T-00546-0017 | BF_PS5-08-01FB-11 | FI01L2 - Beacon Loop Test | #N/A | T | PS5-Loop 11 Flashing Beacon |  | PS5-08-01 - PAGA
T-00546-0018 | BF_PS5-08-01FB-12 | FI01L2 - Beacon Loop Test | #N/A | T | PS5-Loop 12 Flashing Beacon |  | PS5-08-01 - PAGA
T-00548-0113 | BF_PS5-08-03TP-1001 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0114 | BF_PS5-08-03TP-1002 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0115 | BF_PS5-08-03TP-1201 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0116 | BF_PS5-08-03TP-1202 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0117 | BF_PS5-08-03TP-1203 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0118 | BF_PS5-08-03TP-1204 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0119 | BF_PS5-08-03TP-1205 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0120 | BF_PS5-08-03TP-1206 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0121 | BF_PS5-08-03TP-1207 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0122 | BF_PS5-08-03TP-1208 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0123 | BF_PS5-08-03TP-1209 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0124 | BF_PS5-08-03TP-1210 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0125 | BF_PS5-08-03TP-1211 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0126 | BF_PS5-08-03TP-1212 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0127 | BF_PS5-08-03TP-1213 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0128 | BF_PS5-08-03TP-1214 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0129 | BF_PS5-08-03TP-1215 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0130 | BF_PS5-08-03TP-1216 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0131 | BF_PS5-08-03TP-1217 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0132 | BF_PS5-08-03TP-1218 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0133 | BF_PS5-08-03TP-1219 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0134 | BF_PS5-08-03TP-1220 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0135 | BF_PS5-08-03TP-1221 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0136 | BF_PS5-08-03TP-1222 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0137 | BF_PS5-08-03TP-1223 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0138 | BF_PS5-08-03TP-1224 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0139 | BF_PS5-08-03TP-1225 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0140 | BF_PS5-08-03TP-1226 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0141 | BF_PS5-08-03TP-1501 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0142 | BF_PS5-08-03TP-1502 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0143 | BF_PS5-08-03TP-1601 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0144 | BF_PS5-08-03TP-1602 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0145 | BF_PS5-08-03TP-1603 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0146 | BF_PS5-08-03TP-1604 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0147 | BF_PS5-08-03TP-1605 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0148 | BF_PS5-08-03TP-1901 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00548-0149 | BF_PS5-08-03TP-1902 | FI03IPT - IP Telephone Test | #N/A | T | IP Phone |  | PS5-08-03 - Telephone
T-00549-0117 | BF_PS5-08-03TP-0001 | FI03T - Telephone Hazardous Area Test | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00549-0118 | BF_PS5-08-03TP-0002 | FI03T - Telephone Hazardous Area Test | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00549-0119 | BF_PS5-08-03TP-0003 | FI03T - Telephone Hazardous Area Test | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00549-0120 | BF_PS5-08-03TP-0004 | FI03T - Telephone Hazardous Area Test | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00549-0121 | BF_PS5-08-03TP-0101 | FI03T - Telephone Hazardous Area Test | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00549-0122 | BF_PS5-08-03TP-0102 | FI03T - Telephone Hazardous Area Test | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00549-0123 | BF_PS5-08-03TP-0103 | FI03T - Telephone Hazardous Area Test | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00549-0124 | BF_PS5-08-03TP-1903 | FI03T - Telephone Hazardous Area Test | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00549-0125 | BF_PS5-08-03TP-1904 | FI03T - Telephone Hazardous Area Test | #N/A | T | Outdoor Weather Proof Analog Phone |  | PS5-08-03 - Telephone
T-00550-0005 | BF_PS5-08-55VF-1201 | FI03VC - Video Conferencing system Test | #N/A | T | Video Conference Unit |  | PS5-08-55 - Videoconference
T-00551-0069 | BF_PS5-08-11CB-1001 | FI00CAB1 - AC Power up cabinet | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-11 - Corporate LAN (SIE)
T-00551-0070 | BF_PS5-08-11CB-1201 | FI00CAB1 - AC Power up cabinet | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-11 - Corporate LAN (SIE)
T-00551-0071 | BF_PS5-08-11CB-1501 | FI00CAB1 - AC Power up cabinet | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-11 - Corporate LAN (SIE)
T-00551-0072 | BF_PS5-08-11CB-1601 | FI00CAB1 - AC Power up cabinet | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-11 - Corporate LAN (SIE)
T-00551-0073 | BF_PS5-08-11CB-1901 | FI00CAB1 - AC Power up cabinet | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-11 - Corporate LAN (SIE)
T-00551-0074 | BF_PS5-08-13CB-1001 | FI00CAB1 - AC Power up cabinet | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00551-0075 | BF_PS5-08-13CB-1201 | FI00CAB1 - AC Power up cabinet | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00551-0076 | BF_PS5-08-14CB-1201 | FI00CAB1 - AC Power up cabinet | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-14 - Industrial Data Network (SII SP1)
T-00551-0077 | BF_PS5-08-15CB-1001 | FI00CAB1 - AC Power up cabinet | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00551-0078 | BF_PS5-08-35CB-1001 | FI00CAB1 - AC Power up cabinet | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-35 - Optical Transport Network
T-00553-0138 | BF_PS5-08-12AP-0001 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0139 | BF_PS5-08-12AP-0002 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0140 | BF_PS5-08-12AP-0003 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0141 | BF_PS5-08-12AP-0101 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0142 | BF_PS5-08-12AP-0103 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0143 | BF_PS5-08-12AP-0104 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0144 | BF_PS5-08-12AP-0105 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0145 | BF_PS5-08-12AP-0106 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0146 | BF_PS5-08-12AP-0107 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0147 | BF_PS5-08-12AP-0108 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0148 | BF_PS5-08-12AP-0109 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0149 | BF_PS5-08-12AP-1001 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0150 | BF_PS5-08-12AP-1002 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0151 | BF_PS5-08-12AP-1201 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0152 | BF_PS5-08-12AP-1202 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0153 | BF_PS5-08-12AP-1203 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0154 | BF_PS5-08-12AP-1204 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0155 | BF_PS5-08-12AP-1205 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0156 | BF_PS5-08-12AP-1206 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0157 | BF_PS5-08-12AP-1501 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0158 | BF_PS5-08-12AP-1502 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0159 | BF_PS5-08-12AP-1601 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0160 | BF_PS5-08-12AP-1602 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0161 | BF_PS5-08-12AP-1603 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0162 | BF_PS5-08-12AP-1901 | FI12AP - WIFI AP | #N/A | T | Indoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0163 | BF_PS5-08-12AP-1903 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0164 | BF_PS5-08-12AP-1904 | FI12AP - WIFI AP | #N/A | T | Outdoor Access Point |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00553-0165 | BF_PS5-08-51AP-1201 | FI12AP - WIFI AP | #N/A | T | WIFI Access point |  | PS5-08-51 - Entertainment
T-00553-0166 | BF_PS5-08-51AP-1202 | FI12AP - WIFI AP | #N/A | T | WIFI Access point |  | PS5-08-51 - Entertainment
T-00553-0167 | BF_PS5-08-51AP-1203 | FI12AP - WIFI AP | #N/A | T | WIFI Access point |  | PS5-08-51 - Entertainment
T-00553-0168 | BF_PS5-08-85AP-0001 | FI12AP - WIFI AP | #N/A | T | WiFi Access Point A - Primary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00553-0169 | BF_PS5-08-85AP-0002 | FI12AP - WIFI AP | #N/A | T | WiFi Access Point B - Primary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00553-0170 | BF_PS5-08-85AP-0003 | FI12AP - WIFI AP | #N/A | T | WiFi Access Point A - Secondary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00553-0171 | BF_PS5-08-85AP-0004 | FI12AP - WIFI AP | #N/A | T | WiFi Access Point B - Secondary Muster Point |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00553-0172 | BF_PS5-08-85AP-1201 | FI12AP - WIFI AP | #N/A | T | WiFi Access Point A - Safe Haven |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00553-0173 | BF_PS5-08-85AP-1202 | FI12AP - WIFI AP | #N/A | T | WiFi Access Point B - Safe Haven |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0055 | BF_PS5-08-85BR-1001 | FI85GAD - ACS controlled Door | #N/A | T | Biometric Badge Reader - ITR Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0056 | BF_PS5-08-85BR-1002 | FI85GAD - ACS controlled Door | #N/A | T | Biometric Badge Reader - ED Room Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0057 | BF_PS5-08-85BR-1201 | FI85GAD - ACS controlled Door | #N/A | T | Standard Badge Reader - Main Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0058 | BF_PS5-08-85BR-1202 | FI85GAD - ACS controlled Door | #N/A | T | Standard Badge Reader - Clinic Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0059 | BF_PS5-08-85BR-1203 | FI85GAD - ACS controlled Door | #N/A | T | Standard Badge Reader - Dining Area to Office Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0060 | BF_PS5-08-85BR-1204 | FI85GAD - ACS controlled Door | #N/A | T | Biometric Badge Reader - Telecom Room Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0061 | BF_PS5-08-85BR-1501 | FI85GAD - ACS controlled Door | #N/A | T | Biometric Badge Reader - Safe Haven Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0062 | BF_PS5-08-85BR-1601 | FI85GAD - ACS controlled Door | #N/A | T | Standard Badge Reader - Warehouse Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0063 | BF_PS5-08-85BR-1602 | FI85GAD - ACS controlled Door | #N/A | T | Standard Badge Reader - Warehouse Office Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0064 | BF_PS5-08-85BR-1603 | FI85GAD - ACS controlled Door | #N/A | T | Standard Badge Reader - Elec. Ins. Store Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0065 | BF_PS5-08-85BR-1604 | FI85GAD - ACS controlled Door | #N/A | T | Standard Badge Reader - AC Controlled Store |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0066 | BF_PS5-08-85BR-1605 | FI85GAD - ACS controlled Door | #N/A | T | Standard Badge Reader - Elec. Ins. Workshop Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0067 | BF_PS5-08-85BR-1901 | FI85GAD - ACS controlled Door | #N/A | T | Standard Badge Reader - Entrance 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0068 | BF_PS5-08-85BR-1902 | FI85GAD - ACS controlled Door | #N/A | T | Standard Badge Reader - Entrance 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00566-0069 | BF_PS5-08-85BT-0017 | FI85GAD - ACS controlled Door | #N/A | T | Junction Box - Personnel Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00578-0257 | PS5-06-GU-0001A-CA02 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001A |  | PS5-06-01 - AC UPS - EITS Building
T-00578-0258 | PS5-06-GU-0001A-CA04 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001A |  | PS5-06-01 - AC UPS - EITS Building
T-00578-0259 | PS5-06-GU-0001B-CA03 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001B |  | PS5-06-01 - AC UPS - EITS Building
T-00578-0260 | PS5-06-GU-0001B-CA05 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-06-GU-0001B |  | PS5-06-01 - AC UPS - EITS Building
T-00578-0261 | PS5-06-GU-0001-CA01 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-06-GU-0001 |  | PS5-06-01 - AC UPS - EITS Building
T-00578-0262 | PS5-09-LB-0001-CA01 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-09-LB-0001 TO PS5-09-ACU-0007A |  | PS5-09-05 - HVAC for EITS Building
T-00578-0263 | PS5-09-LB-0001-CA02 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-09-LB-0001 TO PS5-04-PNC-0001 |  | PS5-04-03 - 33kV ICSS System
T-00578-0264 | PS5-09-LB-0001-CA03 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-09-LB-0001 TO PS5-09-ACU-0007B |  | PS5-09-05 - HVAC for EITS Building
T-00578-0265 | PS5-61-IE-0101-CA01 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IE-0101 |  | PS5-61-08 - Electrical Control System
T-00578-0266 | PS5-61-IE-0101-CA02 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IE-0101 |  | PS5-61-08 - Electrical Control System
T-00578-0267 | PS5-61-IE-0101-CA03 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IE-0101 |  | PS5-61-08 - Electrical Control System
T-00578-0268 | PS5-61-IJ-0001-CA01 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00578-0269 | PS5-61-IJ-0001-CA02 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00578-0270 | PS5-61-IJ-0001-CA03 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00578-0271 | PS5-61-IJ-0001-CA04 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00578-0272 | PS5-61-IJ-0001-CA05 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00578-0273 | PS5-61-IJ-0001-CA06 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00578-0274 | PS5-61-IJ-0001-CA07 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00578-0275 | PS5-61-IJ-0001-CA08 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00578-0276 | PS5-61-IJ-0001-CA09 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00578-0277 | PS5-61-IJ-0001-CA10 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-61-IJ-0001 |  | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001)
T-00578-0278 | PS5-61-IJ-0010-CA01 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-61-IJ-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010)
T-00578-0279 | PS5-61-IJ-0010-CA02 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IJ-0010 |  | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010)
T-00578-0280 | PS5-61-IJ-0011-CA01 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-61-IJ-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011)
T-00578-0281 | PS5-61-IJ-0011-CA02 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IJ-0011 |  | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011)
T-00578-0282 | PS5-61-IK-0001-CA01 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001)
T-00578-0283 | PS5-61-IK-0001-CA02 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0003 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001)
T-00578-0284 | PS5-61-IK-0001-CA03 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001)
T-00578-0285 | PS5-61-IK-0001-CA04 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001)
T-00578-0286 | PS5-61-IK-0001-CA05 (Reconnection) | CIX60 - Telecom cable reconnection | #N/A | T | Cable FROM PS5-61-IE-0002 TO PS5-61-IK-0001 |  | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001)
T-00579-0005 | BF_PS5-08-03AF-1201 | FI03CONF - IP Conference phone Test | #N/A | T | Audio Conference Phone |  | PS5-08-03 - Telephone
T-00581-0059 | BF_PS5-08-52CM-0031 | FI52PCM - Outdoor PTZ Camera | #N/A | T | SAFE AREA PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0060 | BF_PS5-08-52CM-0032 | FI52PCM - Outdoor PTZ Camera | #N/A | T | SAFE AREA PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0061 | BF_PS5-08-52CM-0033 | FI52PCM - Outdoor PTZ Camera | #N/A | T | SAFE AREA PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0062 | BF_PS5-08-52CM-0131 | FI52PCM - Outdoor PTZ Camera | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0063 | BF_PS5-08-52CM-0132 | FI52PCM - Outdoor PTZ Camera | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0064 | BF_PS5-08-52CM-0133 | FI52PCM - Outdoor PTZ Camera | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0065 | BF_PS5-08-52CM-0134 | FI52PCM - Outdoor PTZ Camera | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0066 | BF_PS5-08-52CM-0135 | FI52PCM - Outdoor PTZ Camera | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0067 | BF_PS5-08-52CM-0136 | FI52PCM - Outdoor PTZ Camera | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0068 | BF_PS5-08-52CM-0137 | FI52PCM - Outdoor PTZ Camera | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0069 | BF_PS5-08-52CM-0138 | FI52PCM - Outdoor PTZ Camera | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0070 | BF_PS5-08-52CM-0139 | FI52PCM - Outdoor PTZ Camera | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0071 | BF_PS5-08-52CM-0140 | FI52PCM - Outdoor PTZ Camera | #N/A | T | PROCESS PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00581-0072 | BF_PS5-08-52CM-0931 | FI52PCM - Outdoor PTZ Camera | #N/A | T | SAFE AREA PTZ CAMERA |  | PS5-08-52 - Process & Security CCTV
T-00582-0322 | BF_PS5-08-85BT-0001 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Main Entrance Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0323 | BF_PS5-08-85BT-0002 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0324 | BF_PS5-08-85BT-0003 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0325 | BF_PS5-08-85BT-0004 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0326 | BF_PS5-08-85BT-0005 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0327 | BF_PS5-08-85BT-0006 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0328 | BF_PS5-08-85BT-0007 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0329 | BF_PS5-08-85BT-0008 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0330 | BF_PS5-08-85BT-0009 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Gate 6 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0331 | BF_PS5-08-85BT-0010 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0332 | BF_PS5-08-85BT-0011 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0333 | BF_PS5-08-85BT-0012 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0334 | BF_PS5-08-85BT-0013 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0335 | BF_PS5-08-85BT-0014 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0336 | BF_PS5-08-85BT-0015 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0337 | BF_PS5-08-85BT-0016 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Emergency Gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0338 | BF_PS5-08-85BT-0018 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Personnel Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0339 | BF_PS5-08-85BT-0024 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Gate 3 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0340 | BF_PS5-08-85BT-0025 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Gate 4 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0341 | BF_PS5-08-85BT-0026 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Gate 5 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0342 | BF_PS5-08-85BT-1002 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - ITR Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0343 | BF_PS5-08-85BT-1004 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - ED Room Emergency Escape 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0344 | BF_PS5-08-85BT-1005 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - ED Room Emergency Escape 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0345 | BF_PS5-08-85BT-1204 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Tel. Room - Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0346 | BF_PS5-08-85BT-1501 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box 1 - Search Area |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0347 | BF_PS5-08-85BT-1502 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box 2 - Search Area |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0348 | BF_PS5-08-85BT-1601 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Warehouse Ramp |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0349 | BF_PS5-08-85BT-1602 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Warehouse Emergency Escape - 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0350 | BF_PS5-08-85BT-1604 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Main Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0351 | BF_PS5-08-85BT-1609 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Workshop Entrance |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0352 | BF_PS5-08-85BT-1610 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Workshop Ramp |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0353 | BF_PS5-08-85BT-1611 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Workshop Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0354 | BF_PS5-08-85BT-1612 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - AC Controlled Store Emergency Escape |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0355 | BF_PS5-08-85BT-1613 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Oil Spill response store |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0356 | BF_PS5-08-85BT-1614 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Warehouse Emergency Escape - 2 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0357 | BF_PS5-08-85BT-1903 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Double Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0358 | BF_PS5-08-85BT-1904 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Double Door & Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0359 | BF_PS5-08-85BT-1905 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Double Door & Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0360 | BF_PS5-08-85BT-1906 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Double Door & Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0361 | BF_PS5-08-85BT-1907 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Double Door & Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0362 | BF_PS5-08-85BT-1908 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Double Door & Single Door 1 |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00582-0363 | BF_PS5-08-85BT-1909 | FI85DC - ACS uncontrolled door & Gates | #N/A | T | Junction Box - Single Door |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00583-0013 | BF_PS5-08-13CB-1001_TMS | FI93M - TMS Intercabinet test | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00583-0014 | BF_PS5-08-13CB-1201_TMS | FI93M - TMS Intercabinet test | #N/A | T | telecom cabinet - 230VAC |  | PS5-08-13 - Safety Data Network (SII SP3 SAF)
T-00585-0007 | BF_PS5-82-MBA-0001 | FI81GAB - ACS - Road Barrier | #N/A | T | Barrier - 1 - Site Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00585-0008 | BF_PS5-82-MBA-0002 | FI81GAB - ACS - Road Barrier | #N/A | T | Barrier - 2 - Site Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00585-0009 | BF_PS5-82-MBA-0003 | FI81GAB - ACS - Road Barrier | #N/A | T | Barrier - 3 - Site Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00586-0005 | BF_PS5-82-MGV-0002 | FI81GAG - ACS - Rolling Gate | #N/A | T | Main Sliding gate |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00588-0003 | BF_PS5-82-MTL-0001 | FI81GAT - ACS - Turnstile | #N/A | T | Turnstile - Site Access |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00589-0011 | BF_PS5-08-23BS-1201 | FI23VTM - VHF Trunk Handheld Radios | #N/A | T | Fixed Base station |  | PS5-08-23 - VHF Trunk Radio System
T-00589-0012 | BF_PS5-08-23BS-1501 | FI23VTM - VHF Trunk Handheld Radios | #N/A | T | Fixed Base station |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0074 | BF_PS5-08-23HP-3001 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0075 | BF_PS5-08-23HP-3002 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0076 | BF_PS5-08-23HP-3003 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0077 | BF_PS5-08-23HP-3004 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0078 | BF_PS5-08-23HP-3005 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0079 | BF_PS5-08-23HP-3006 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0080 | BF_PS5-08-23HP-3007 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0081 | BF_PS5-08-23HP-3008 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0082 | BF_PS5-08-23HP-3009 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0083 | BF_PS5-08-23HP-3010 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0084 | BF_PS5-08-23HP-3011 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0085 | BF_PS5-08-23HP-3012 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0086 | BF_PS5-08-23HP-3013 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0087 | BF_PS5-08-23HP-3014 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0088 | BF_PS5-08-23HP-3015 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0089 | BF_PS5-08-23HP-3016 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0090 | BF_PS5-08-23HP-3017 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0091 | BF_PS5-08-23HP-3018 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0092 | BF_PS5-08-23HP-3019 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0093 | BF_PS5-08-23HP-3020 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0094 | BF_PS5-08-23HP-3021 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0095 | BF_PS5-08-23HP-3022 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0096 | BF_PS5-08-23HP-3023 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0097 | BF_PS5-08-23HP-3024 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00590-0098 | BF_PS5-08-23HP-3025 | FI23VTM1 - VHF Trunk Radios | #N/A | T | ATEX handheld portable Radio |  | PS5-08-23 - VHF Trunk Radio System
T-00597-0111 | BF_PS5-08-35ON-1001 | FI35ON - OTN Node | #N/A | T | Non-SIL3 node A (note 3) |  | PS5-08-35 - Optical Transport Network
T-00597-0112 | BF_PS5-08-35ON-1002 | FI35ON - OTN Node | #N/A | T | Non-SIL3 node B (note 3) |  | PS5-08-35 - Optical Transport Network
T-00597-0113 | BF_PS5-08-35ON-1003 | FI35ON - OTN Node | #N/A | T | SIL3 node A (note 3) |  | PS5-08-35 - Optical Transport Network
T-00597-0114 | BF_PS5-08-35ON-1004 | FI35ON - OTN Node | #N/A | T | SIL3 node B (note 3) |  | PS5-08-35 - Optical Transport Network
T-00599-0097 | BF_PS5-08-12BT-0001 | FI00JB - Active Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00599-0098 | BF_PS5-08-12BT-0104 | FI00JB - Active Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00599-0099 | BF_PS5-08-12BT-0105 | FI00JB - Active Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00599-0100 | BF_PS5-08-12BT-0106 | FI00JB - Active Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00599-0101 | BF_PS5-08-12BT-0107 | FI00JB - Active Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00599-0102 | BF_PS5-08-12BT-0108 | FI00JB - Active Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00599-0103 | BF_PS5-08-12BT-0109 | FI00JB - Active Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00599-0104 | BF_PS5-08-12BT-1903 | FI00JB - Active Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00599-0105 | BF_PS5-08-12BT-1904 | FI00JB - Active Junction Box | #N/A | T | Junction Box |  | PS5-08-12 - Corporate Wireless LAN (SIE)
T-00599-0106 | BF_PS5-08-15CP-0001 | FI00JB - Active Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00599-0107 | BF_PS5-08-15CP-0002 | FI00JB - Active Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00599-0108 | BF_PS5-08-15CP-0003 | FI00JB - Active Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00599-0109 | BF_PS5-08-15CP-0004 | FI00JB - Active Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00599-0110 | BF_PS5-08-15CP-0005 | FI00JB - Active Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00599-0111 | BF_PS5-08-15CP-0006 | FI00JB - Active Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00599-0112 | BF_PS5-08-15CP-0007 | FI00JB - Active Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00599-0113 | BF_PS5-08-15CP-0008 | FI00JB - Active Junction Box | #N/A | T | Control Panel |  | PS5-08-15 - Security Data Network (SII SP3 SEC)
T-00599-0114 | BF_PS5-08-85CP-0024 | FI00JB - Active Junction Box | #N/A | T | Outdoor Muster Enclosure A |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00599-0115 | BF_PS5-08-85CP-0025 | FI00JB - Active Junction Box | #N/A | T | Outdoor Muster Enclosure B |  | PS5-08-85 - Access Control, POB & e-Mustering
T-00600-0017 | BF_PS5-08-83IU-1003 | FI83PID - PIDS | #N/A | T | Pipeline Interrogator x2 Channels (Processor Unit) |  | PS5-08-83 - Perimeter & Pipeline intrusion detection system
| PS5-71-BE-0363-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0123-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0309-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0018-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0130-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0015-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0133-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0298-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0026-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0309-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0018-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0130-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-IG-0001-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0002-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0003-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0004-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0005-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0006-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0007-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0008-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0009-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0010-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0011-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0012-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0001-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0002-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0003-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0004-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0005-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0006-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0007-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0008-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0009-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0010-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0011-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0012-CG01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0001-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0002-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0003-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0004-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0005-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0006-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0007-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0008-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0009-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0010-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0011-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IG-0012-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0316-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0315-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0168-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0170-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0163-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0167-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-SP-0167-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0169-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-SP-0169-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0159-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0164-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0151-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0356-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0206-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0148-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0314-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0149-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0234-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0114-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0165-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0166-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0157-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0153-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0313-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0188-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0202-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0103-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0317-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0306-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0197-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-71-BE-0361-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-BE-0181-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0184-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0302-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0185-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0182-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0303-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0304-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0325-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0311-CL01 | CPX EHT Power Cable | #N/A | E |  |  | . | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0312-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0173-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0183-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0355-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0354-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0201-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0172-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0180-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0191-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0192-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0193-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0196-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0179-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0326-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0238-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0174-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0244-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0199-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0187-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0190-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0023-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0278-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0307-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0198-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0046-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0195-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0252-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0253-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0200-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0194-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0246-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0189-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0210-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0186-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0279-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0260-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0211-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0305-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0322-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0346-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0348-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0352-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0242-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0109-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0113-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0106-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0351-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0243-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-60-BE-0365-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0280-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0331-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0327-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0266-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0265-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0212-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0049-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0329-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0285-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0220-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0217-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0219-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0237-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-SP-0237-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0282-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0213-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0086-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0214-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0283-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0092-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0216-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0215-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0099-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0171-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0264-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0281-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0284-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-60-BE-0366-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0332-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0330-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0269-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0267-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0268-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0334-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0333-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0272-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0270-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0271-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0335-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0339-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0275-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0273-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0274-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0328-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0061-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0218-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0229-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0223-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0224-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0221-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0235-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0222-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0350-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0228-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0236-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-60-BE-0367-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0136-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0027-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0039-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0037-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0025-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0343-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0118-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0137-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0024-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0150-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0203-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0204-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0262-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0102-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0081-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0036-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0066-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0067-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0245-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0134-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0063-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0154-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0319-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0290-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0152-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0002-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0005-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0146-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0041-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0135-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0239-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9901-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9101-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9102-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0247-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0084-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0090-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0085-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0082-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0101-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0156-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0107-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0020-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0147-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0043-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0344-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0019-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0100-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0112-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0068-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0042-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0121-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0072-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0116-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0145-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0155-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0071-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0083-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0291-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0003-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0143-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0059-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0006-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-BE-0144-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0240-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-IP-9902-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9103-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9104-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0241-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0208-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0292-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0058-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0140-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0004-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0007-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0161-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0139-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0162-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0074-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0142-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0160-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0077-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0075-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0053-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0076-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0070-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0158-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0060-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0115-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0108-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0111-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0062-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0141-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0207-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0205-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0044-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0045-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0261-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-BE-0209-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-IP-9903-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9105-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9106-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0064-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0057-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0021-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0128-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0008-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-SP-0008-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0047-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0052-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0056-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0055-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0028-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0294-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0293-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0129-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0073-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0010-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-SP-0010-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0124-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0295-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0030-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0127-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0051-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0032-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0033-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0126-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0125-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0011-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0301-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0001-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0009-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0014-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0034-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0353-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-71-BE-0362-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0132-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0131-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0040-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0233-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0054-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0022-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0078-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0105-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0029-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0035-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0094-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0120-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0095-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0087-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0119-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0117-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0323-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0096-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0079-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0345-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0104-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0230-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0093-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0088-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0089-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0091-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0097-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0321-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0227-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-60-BE-0364-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0286-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0347-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0289-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0342-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0232-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0231-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0288-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0225-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0324-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0080-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0065-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0287-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0277-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0276-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0226-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0340-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0336-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0031-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0016-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0038-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0341-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0337-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0050-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0048-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0069-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0349-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0338-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-60-BE-0368-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-60-BE-0369-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-60-BE-0370-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0251-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0297-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0296-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0012-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0259-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0257-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0258-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0098-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0300-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0248-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-BE-0254-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0310-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0263-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0122-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0110-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0256-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0320-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0255-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0017-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0250-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0249-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0318-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-SP-0018-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0299-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0308-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0013-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-SP-0133-CL01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0138-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-25-BE-0364-CL01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0316-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0315-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0168-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0170-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0163-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0167-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0169-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0159-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0164-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0151-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0356-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0206-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0148-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0314-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0149-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0234-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0114-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0165-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0166-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0157-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0153-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0313-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0188-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0202-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0103-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0317-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0306-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0197-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-71-TE-0361-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0322 | 2026-06-07 | Accepted With Punch | Bertus Wikael | Pulling
| PS5-79-TE-0181-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0184-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0302-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0185-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0182-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0303-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0304-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0325-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0311-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0312-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0173-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0183-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0355-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0354-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0201-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0172-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0180-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0191-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0192-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0193-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0196-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0179-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0326-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0238-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0174-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0244-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0199-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0187-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0190-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-71-TE-0363-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0023-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0278-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0307-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0198-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0046-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0195-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0252-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0253-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0200-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0194-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0246-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0189-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0210-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0186-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0279-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0260-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0211-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0305-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0322-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0346-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0269 | 2026-05-20 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0348-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0352-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0242-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0109-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0113-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0106-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0351-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0243-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-60-TE-0365-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0280-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0331-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0327-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0266-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0265-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0212-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0049-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0329-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0285-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0220-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0217-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0219-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0237-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0282-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0213-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0086-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0214-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0283-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0092-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0216-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0215-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0099-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0171-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0264-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0281-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0284-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-60-TE-0366-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0332-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0330-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0269-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0267-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0268-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0334-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0333-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0272-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0270-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0271-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0335-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0339-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0275-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0273-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0274-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0328-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0061-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0218-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0229-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0223-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0224-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0221-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0235-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0222-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0350-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0228-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0236-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-60-TE-0367-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0136-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0027-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0039-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0037-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0025-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0343-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0118-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0137-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0024-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0150-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0203-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0204-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0262-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0102-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0081-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0036-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0066-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0067-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0245-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0134-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0063-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0154-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0319-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0290-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0152-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0002-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0005-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0146-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0041-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0135-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0239-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0247-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0084-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0090-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0085-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0082-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0101-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0156-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-TE-0107-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0020-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0281 | 2026-05-25 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0147-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0043-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0344-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0019-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0100-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0112-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0068-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-TE-0042-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-TE-0121-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-TE-0072-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0116-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-TE-0145-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0155-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0071-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0083-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0291-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-TE-0003-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-TE-0143-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-TE-0059-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-TE-0006-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-TE-0144-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0240-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0315 | 2026-06-05 | HOLD By Eacop | Bertus Wikael | Pulling
| PS5-79-TE-0241-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0208-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0292-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0058-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0140-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0004-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0007-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0161-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0139-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0162-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0074-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0142-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0160-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0077-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0277 | 2026-05-23 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0075-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0053-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0076-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0070-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0158-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0060-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0115-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0108-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0111-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0062-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0141-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0207-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0205-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0044-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0045-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0261-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-05-0280 | 2026-05-24 | Accepted with comment | Bertus Wikael | Pulling
| PS5-79-TE-0209-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0064-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0057-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0021-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0128-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0008-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0047-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0052-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0056-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0055-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0028-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0294-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0293-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0129-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0073-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0010-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0124-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0295-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0030-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0127-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0051-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0032-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0033-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0126-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0125-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0011-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0301-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0001-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0009-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0014-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0034-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0353-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-71-TE-0362-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0132-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0131-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0040-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0233-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0054-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0022-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0078-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0105-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0029-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0035-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0094-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0120-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0095-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0087-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0119-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0117-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0323-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0096-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0079-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0345-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0104-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0230-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0093-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0088-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0089-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0091-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0097-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0321-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0227-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-60-TE-0364-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0286-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0347-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0289-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0342-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0232-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0231-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0288-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0225-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0324-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0080-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0065-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0287-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0277-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0276-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0226-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0340-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0336-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0031-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0016-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0038-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0341-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0337-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0050-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0048-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0069-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0349-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0338-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-60-TE-0368-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-60-TE-0369-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-60-TE-0370-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0251-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0297-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0296-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0012-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0259-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0257-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0258-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0098-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0300-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0123-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0248-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0254-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0310-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0263-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0122-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0110-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0256-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0320-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0255-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0017-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0250-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0249-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0318-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0299-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0308-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-TE-0013-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0015-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0133-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0298-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0026-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0274 | 2026-05-22 | Accepted with punch | Bertus Wikael | Pulling
| PS5-79-TE-0138-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-25-TE-0364-CD01 | CPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-05-0370 | 2026-06-20 | CLOSED | Bertus Wikael | Pulling
| PS5-79-BE-0175-CW01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9101-CW01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9102-CW01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0176-CW01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9103-CW01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9104-CW01 | CPX EHT Power Cable | #N/A | E
| PS5-79-BE-0177-CW01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9105-CW01 | CPX EHT Power Cable | #N/A | E
| PS5-79-IP-9106-CW01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0175-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0176-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0178-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-79-TE-0177-CD01 | CPX EHT Power Cable | #N/A | E
| PS5-71-BE-0363-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0123-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0309-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0018-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0130-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0015-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0133-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0298-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0026-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0309-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0018-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0130-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0001-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0002-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0003-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0004-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0005-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0006-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0007-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0008-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0009-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0010-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0011-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0012-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0001-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0002-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0003-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0004-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0005-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0006-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0007-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0008-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0009-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0010-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0011-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0012-CG01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0001-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0002-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0003-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0004-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0005-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0006-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0007-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0008-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0009-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0010-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0011-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IG-0012-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0316-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0315-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0168-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0170-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0163-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0167-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-SP-0167-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0169-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-SP-0169-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0159-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0164-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0151-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0356-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0206-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0148-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0314-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0149-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0234-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0114-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0165-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0166-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0157-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0153-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0313-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0188-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0202-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0103-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0317-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0306-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0197-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-71-BE-0361-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0181-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0184-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0302-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0185-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0182-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0303-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0304-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0325-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0311-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0312-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0173-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0183-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0355-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0354-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0201-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0172-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0180-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0191-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0192-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0193-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0196-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0179-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0326-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0238-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0174-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0244-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0199-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0187-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0190-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0023-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0278-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0307-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0198-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0046-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0195-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0252-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0253-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0200-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0194-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0246-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0189-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0210-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0186-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0279-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0260-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0211-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0305-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0322-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0346-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0348-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0352-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0242-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0109-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0113-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0106-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0351-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0243-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-60-BE-0365-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0280-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0331-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0327-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0266-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0265-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0212-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0049-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0329-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0285-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0220-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0217-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0219-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0237-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-SP-0237-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0282-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0213-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0086-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0214-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0283-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0092-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0216-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0215-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0099-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0171-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0264-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0281-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0284-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-60-BE-0366-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0332-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0330-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0269-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0267-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0268-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0334-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0333-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0272-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0270-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0271-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0335-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0339-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0275-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0273-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0274-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0328-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0061-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0218-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0229-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0223-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0224-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0221-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0235-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0222-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0350-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0228-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0236-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-60-BE-0367-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0136-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0027-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0039-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0037-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0025-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0343-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0118-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0137-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0024-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0150-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0203-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0204-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0262-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0102-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0081-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0036-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0066-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0067-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0245-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0134-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0063-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0154-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0319-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0290-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0152-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0002-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0005-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0146-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0041-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0135-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0239-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9901-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9101-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9102-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0247-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0084-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0090-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0085-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0082-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0101-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0156-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0107-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0020-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0147-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0043-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0344-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0019-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0100-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0112-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0068-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0042-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0121-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0072-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0116-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0145-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0155-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0071-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0083-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0291-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0003-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0143-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0059-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0006-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-BE-0144-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0240-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-IP-9902-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9103-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9104-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0241-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0208-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0292-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0058-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0140-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0004-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0007-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0161-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0139-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0162-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0074-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0142-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0160-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0077-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0075-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0053-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0076-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0070-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0158-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0060-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0115-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0108-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0111-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0062-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0141-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0207-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0205-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0044-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0045-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0261-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0209-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9903-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9105-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9106-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0064-CL01 | TPX EHT Power Cable | #N/A | E | [7 empty] | Testing
| PS5-79-BE-0057-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-BE-0021-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-BE-0128-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-BE-0008-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-SP-0008-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0047-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-BE-0052-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-BE-0056-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-BE-0055-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-BE-0028-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0294-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0293-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0129-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0073-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0010-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-SP-0010-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0124-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0295-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0030-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0127-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0051-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0032-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0033-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0126-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0125-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0011-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0301-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0001-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0009-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0014-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0034-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0353-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-71-BE-0362-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0132-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0131-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0040-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0233-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0054-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0022-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0078-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0105-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0029-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0035-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0094-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0120-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0095-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0087-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0119-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0117-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0323-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0096-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0079-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0345-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0104-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0230-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0093-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0088-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0089-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0091-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0097-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0321-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0227-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-60-BE-0364-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0286-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0347-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0289-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0342-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0232-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0231-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0288-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0225-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0324-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0080-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0065-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0287-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0277-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0276-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0226-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0340-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0336-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0031-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0016-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0038-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0341-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0337-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0050-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0048-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0069-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0349-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0338-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-60-BE-0368-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-60-BE-0369-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-60-BE-0370-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0251-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0297-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0296-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0012-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0259-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0257-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0258-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0098-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0300-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0248-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0254-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0310-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0263-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0122-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0110-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0256-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0320-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0255-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0017-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0250-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0249-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0318-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-SP-0018-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0299-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0308-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0013-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-SP-0133-CL01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0138-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-25-BE-0364-CL01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0316-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0315-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0168-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0170-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0163-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0167-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0169-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0159-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0164-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0151-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0356-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0206-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0148-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0314-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0149-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0234-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0114-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0165-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0166-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0157-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0153-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0313-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0188-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0202-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0103-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0317-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0306-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0197-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-71-TE-0361-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0323 | 2026-06-07 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0181-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0184-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0302-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0185-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0182-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0303-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0304-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0325-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0311-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0312-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0173-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0183-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0355-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0354-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0201-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0172-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0180-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0191-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0192-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0193-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0196-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0179-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0326-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0238-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0174-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0244-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0199-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0187-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0190-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-71-TE-0363-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0023-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0278-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0307-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0198-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0046-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0195-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0252-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0253-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0200-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0194-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0246-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0189-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0210-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0186-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0279-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0260-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0211-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0305-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0322-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0346-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0297 | 2026-05-21 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0348-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0352-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0242-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0109-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0113-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0106-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0351-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0243-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-60-TE-0365-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0280-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0331-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0327-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0266-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0265-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0212-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0049-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0329-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0285-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0220-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0217-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0219-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0237-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0282-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0213-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0086-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0214-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0283-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0092-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0305 | 2026-06-25 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0216-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0215-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0099-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0171-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0264-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0281-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0284-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-60-TE-0366-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0332-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0330-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0269-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0267-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0268-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0334-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0333-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0272-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0270-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0271-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0335-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0339-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0275-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0273-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0274-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0328-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0061-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0218-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0229-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0223-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0224-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0221-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0235-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0222-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0350-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0228-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0236-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-60-TE-0367-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0136-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0027-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0039-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0037-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0025-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0343-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0118-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0137-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0024-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0150-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0203-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0204-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0262-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0102-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0081-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0036-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0066-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0067-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0245-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0134-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0063-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0154-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0319-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0290-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0152-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0002-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0005-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0146-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0041-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0135-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0239-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0247-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0084-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0090-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0085-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0082-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0101-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0156-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0107-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0020-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0147-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0043-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0344-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0019-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0100-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0112-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0068-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0042-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0121-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0072-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0116-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0145-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0155-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0071-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0083-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0291-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0003-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0143-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0059-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0006-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0144-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0240-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0316 | 2026-06-05 | Accepted | Bertus Wikael | Testing
| PS5-79-TE-0241-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0208-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0292-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0058-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0140-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0004-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0007-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0161-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0139-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0162-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0074-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0142-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0160-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0077-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0075-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0053-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0076-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0070-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0158-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0060-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0115-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0108-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0111-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0062-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0141-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0207-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0205-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0044-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0045-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0261-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0209-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0064-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-TE-0057-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-TE-0021-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-TE-0128-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-TE-0008-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-TE-0047-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-TE-0052-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-TE-0056-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-TE-0055-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-33/1-07-0328 | 2026-06-10 | Acceptable | Ferdinand | TESTING
| PS5-79-TE-0028-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0294-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0293-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0129-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0073-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0010-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0124-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0295-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0030-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0127-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0051-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0032-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0033-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0126-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0125-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0011-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0301-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0001-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0009-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0014-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0034-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0353-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-71-TE-0362-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0132-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0131-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0040-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0233-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0054-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0022-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0078-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0105-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0029-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0035-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0094-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0120-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0095-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0087-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0119-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0117-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0323-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0096-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0079-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0345-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0104-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0230-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0093-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0088-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0089-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0091-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0097-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0321-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0227-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-60-TE-0364-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0286-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0347-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0289-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0342-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0232-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0231-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0288-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0225-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0324-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0080-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0065-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0287-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0277-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0276-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0226-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0340-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0336-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0031-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0016-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0038-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0341-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0337-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0050-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0048-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0069-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0349-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0338-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-60-TE-0368-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-60-TE-0369-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-60-TE-0370-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0251-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0297-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0296-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0012-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0259-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0257-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0258-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0098-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0300-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0123-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0248-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0254-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0310-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0263-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0122-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0110-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0256-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0320-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0255-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0017-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0250-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0249-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0318-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0299-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0308-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-TE-0013-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0015-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0133-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0298-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0026-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0138-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-25-TE-0364-CD01 | TPX EHT Power Cable | #N/A | E |  |  |  | CPP-RFI-68-331-07-0371 | 2026-06-20 | CLOSED | Bertus Wikael | Testing
| PS5-79-BE-0175-CW01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9101-CW01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9102-CW01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0176-CW01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9103-CW01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9104-CW01 | TPX EHT Power Cable | #N/A | E
| PS5-79-BE-0177-CW01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9105-CW01 | TPX EHT Power Cable | #N/A | E
| PS5-79-IP-9106-CW01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0175-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0176-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0178-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-79-TE-0177-CD01 | TPX EHT Power Cable | #N/A | E
| PS5-08-01FB-0903-CS01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
| PS5-08-01FB-0907-CS01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
| PS5-08-01FB-1009-CS01 | TPX LV CABLES | #N/A | E
| PS5-08-01FB-1011-CS01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
| PS5-08-01FB-1012-CS01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
| PS5-08-01FB-1104-CS01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
| PS5-08-03FB-0101-CS01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
| PS5-08-03FB-1904-CS01 | TPX LV CABLES | #N/A | E
| PS5-08-12BT-0107-CS01 | TPX LV CABLES | #N/A | E
| PS5-08-12BT-0108-CS01 | TPX LV CABLES | #N/A | E
| PS5-08-12BT-0109-CS01 | TPX LV CABLES | #N/A | E
| PS5-61-IE-0002-CD02 | TPX LV CABLES | #N/A | E
| PS5-61-IE-0002-CD45 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
| PS5-61-IE-0002-CD46 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
| PS5-61-IE-0002-CD47 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
| PS5-61-IE-0003-CD01 | TPX LV CABLES | #N/A | E
| PS5-61-IJ-0001-CD03 | TPX LV CABLES | #N/A | E
| PS5-61-IJ-0001-CD42 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0425 | 2026-07-20 | Accepted | Bertus Wikael | Testing
| PS5-61-IK-0001-CL09 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
| PS5-71-FIT-0011A-CL01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
| PS5-71-HE-2300-CD01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0449 | 2026-07-31 | OPEN | Bertus Wikael | TESTING
| PS5-75-DM-3100A-CL01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
| PS5-75-DM-3200A-CL01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
| PS5-75-IES-3100A-CD01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
| PS5-75-IES-3200A-CD01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
| PS5-75-IES-3200B-CD01 | TPX LV CABLES | #N/A | E |  |  |  | CPP-RFI-68-331-07-0434 | 2026-07-25 | CLOSED | Bertus Wikael | Testing
| PS5-82-IN-0001-CL01 | TPX LV CABLES | #N/A | E
| PS5-03-RDH-1902-CJ01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-03-RDOS-1703-CJ01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-03-RDOS-2101 -CJ01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-03-RDOS-2103 -CJ01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-03-RMAC-1409 -CJ01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-09-BI-2504-CC01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-09-LB-0006-CC05 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-50-IE-0001-CJ01 | CJX INSTRUMENT CABLES | PS5-50-IE-0001-CJ01 | I
| PS5-50-IE-0002-CJ01 | CJX INSTRUMENT CABLES | PS5-50-IE-0002-CJ01 | I
| PS5-60-BI-0001C-CC02 | CJX INSTRUMENT CABLES | PS5-60-BI-0001C-CC02 | I
| PS5-60-BI-0001D-CC02 | CJX INSTRUMENT CABLES | PS5-60-BI-0001D-CC02 | I
| PS5-60-BI-0001E-CC02 | CJX INSTRUMENT CABLES | PS5-60-BI-0001E-CC02 | I
| PS5-60-BI-0001F-CC02 | CJX INSTRUMENT CABLES | PS5-60-BI-0001F-CC02 | I
| PS5-60-BI-0001G-CC02 | CJX INSTRUMENT CABLES | PS5-60-BI-0001G-CC02 | I
| PS5-60-IE-0002C-CC01 | CJX INSTRUMENT CABLES | PS5-60-IE-0002C-CC01 | I
| PS5-60-IE-0002C-CC02 | CJX INSTRUMENT CABLES | PS5-60-IE-0002C-CC02 | I
| PS5-60-IE-0002C-CC03 | CJX INSTRUMENT CABLES | PS5-60-IE-0002C-CC03 | I
| PS5-60-IE-0002D-CC01 | CJX INSTRUMENT CABLES | PS5-60-IE-0002D-CC01 | I
| PS5-60-IE-0002D-CC02 | CJX INSTRUMENT CABLES | PS5-60-IE-0002D-CC02 | I
| PS5-60-IE-0002D-CC03 | CJX INSTRUMENT CABLES | PS5-60-IE-0002D-CC03 | I
| PS5-60-IE-0002E-CC01 | CJX INSTRUMENT CABLES | PS5-60-IE-0002E-CC01 | I
| PS5-60-IE-0002E-CC02 | CJX INSTRUMENT CABLES | PS5-60-IE-0002E-CC02 | I
| PS5-60-IE-0002E-CC03 | CJX INSTRUMENT CABLES | PS5-60-IE-0002E-CC03 | I
| PS5-60-IE-0002F-CC01 | CJX INSTRUMENT CABLES | PS5-60-IE-0002F-CC01 | I
| PS5-60-IE-0002F-CC02 | CJX INSTRUMENT CABLES | PS5-60-IE-0002F-CC02 | I
| PS5-60-IE-0002F-CC03 | CJX INSTRUMENT CABLES | PS5-60-IE-0002F-CC03 | I
| PS5-60-IE-0002G-CC01 | CJX INSTRUMENT CABLES | PS5-60-IE-0002G-CC01 | I
| PS5-60-IE-0002G-CC02 | CJX INSTRUMENT CABLES | PS5-60-IE-0002G-CC02 | I
| PS5-60-IE-0002G-CC03 | CJX INSTRUMENT CABLES | PS5-60-IE-0002G-CC03 | I
| PS5-60-IH-0001C-CC01 | CJX INSTRUMENT CABLES | PS5-60-IH-0001C-CC01 | I
| PS5-60-IH-0001C-CC02 | CJX INSTRUMENT CABLES | PS5-60-IH-0001C-CC02 | I
| PS5-60-IH-0001D-CC01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-IH-0001D-CC02 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-IH-0001E-CC01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-IH-0001E-CC02 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-IH-0001F-CC01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-IH-0001F-CC02 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-IH-0001G-CC01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-IH-0001G-CC02 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-PIT-8113C-CC01 | CJX INSTRUMENT CABLES | PS5-60-PIT-8113C-CC01 | I
| PS5-60-PIT-8113D-CC01 | CJX INSTRUMENT CABLES | PS5-60-PIT-8113D-CC01 | I
| PS5-60-PIT-8113E-CC01 | CJX INSTRUMENT CABLES | PS5-60-PIT-8113E-CC01 | I
| PS5-60-PIT-8113F-CC01 | CJX INSTRUMENT CABLES | PS5-60-PIT-8113F-CC01 | I
| PS5-60-PIT-8113G-CC01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-PIT-8114C-CC01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-PIT-8114D-CC01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-PIT-8114E-CC01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-PIT-8114F-CC01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-60-PIT-8114G-CC01 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-71-BI-2101-CC01 | CJX INSTRUMENT CABLES | PS5-71-BI-2101-CC01 | I
| PS5-71-IN-0004A-CC10 | CJX INSTRUMENT CABLES | #N/A | I
| PS5-74-LB-5101-CC02 | CJX INSTRUMENT CABLES | PS5-74-LB-5101-CC02 | I
| PS5-03-RDH-1902-CJ01 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-03-RDOS-1703-CJ01 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-03-RDOS-2101 -CJ01 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-03-RDOS-2103 -CJ01 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-03-RMAC-1409 -CJ01 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-09-BI-2504-CC01 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-09-LB-0006-CC05 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-50-IE-0001-CJ01 | TJX INSTRUMENT CABLE | PS5-50-IE-0001-CJ01 | I
| PS5-50-IE-0002-CJ01 | TJX INSTRUMENT CABLE | PS5-50-IE-0002-CJ01 | I
| PS5-60-BI-0001C-CC02 | TJX INSTRUMENT CABLE | PS5-60-BI-0001C-CC02 | I |  |  |  | CPP-68-64-12-0129 | 2026-07-31 | OPEN | Elizabeth | TESTING
| PS5-60-BI-0001D-CC02 | TJX INSTRUMENT CABLE | PS5-60-BI-0001D-CC02 | I |  |  |  | CPP-68-64-12-0129 | 2026-07-31 | OPEN | Elizabeth | TESTING
| PS5-60-BI-0001E-CC02 | TJX INSTRUMENT CABLE | PS5-60-BI-0001E-CC02 | I |  |  |  | CPP-68-64-12-0129 | 2026-07-31 | OPEN | Elizabeth | TESTING
| PS5-60-BI-0001F-CC02 | TJX INSTRUMENT CABLE | PS5-60-BI-0001F-CC02 | I |  |  |  | CPP-RFI-68-64-12-0130 | 2026-08-01 | OPEN | Bertus Wikael | Testing
| PS5-60-BI-0001G-CC02 | TJX INSTRUMENT CABLE | PS5-60-BI-0001G-CC02 | I |  |  |  | CPP-RFI-68-64-12-0130 | 2026-08-01 | OPEN | Bertus Wikael | Testing
| PS5-60-IE-0002C-CC01 | TJX INSTRUMENT CABLE | PS5-60-IE-0002C-CC01 | I |  |  |  | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
| PS5-60-IE-0002C-CC02 | TJX INSTRUMENT CABLE | PS5-60-IE-0002C-CC02 | I |  |  |  | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
| PS5-60-IE-0002C-CC03 | TJX INSTRUMENT CABLE | PS5-60-IE-0002C-CC03 | I |  |  |  | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
| PS5-60-IE-0002D-CC01 | TJX INSTRUMENT CABLE | PS5-60-IE-0002D-CC01 | I |  |  |  | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
| PS5-60-IE-0002D-CC02 | TJX INSTRUMENT CABLE | PS5-60-IE-0002D-CC02 | I |  |  |  | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
| PS5-60-IE-0002D-CC03 | TJX INSTRUMENT CABLE | PS5-60-IE-0002D-CC03 | I |  |  |  | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
| PS5-60-IE-0002E-CC01 | TJX INSTRUMENT CABLE | PS5-60-IE-0002E-CC01 | I
| PS5-60-IE-0002E-CC02 | TJX INSTRUMENT CABLE | PS5-60-IE-0002E-CC02 | I
| PS5-60-IE-0002E-CC03 | TJX INSTRUMENT CABLE | PS5-60-IE-0002E-CC03 | I
| PS5-60-IE-0002F-CC01 | TJX INSTRUMENT CABLE | PS5-60-IE-0002F-CC01 | I
| PS5-60-IE-0002F-CC02 | TJX INSTRUMENT CABLE | PS5-60-IE-0002F-CC02 | I
| PS5-60-IE-0002F-CC03 | TJX INSTRUMENT CABLE | PS5-60-IE-0002F-CC03 | I
| PS5-60-IE-0002G-CC01 | TJX INSTRUMENT CABLE | PS5-60-IE-0002G-CC01 | I
| PS5-60-IE-0002G-CC02 | TJX INSTRUMENT CABLE | PS5-60-IE-0002G-CC02 | I
| PS5-60-IE-0002G-CC03 | TJX INSTRUMENT CABLE | PS5-60-IE-0002G-CC03 | I
| PS5-60-IH-0001C-CC01 | TJX INSTRUMENT CABLE | PS5-60-IH-0001C-CC01 | I |  |  |  | CPP-RFI-68-65-20-0039 | 2026-07-30 | Accepted | G K RAO | TESTING
| PS5-60-IH-0001C-CC02 | TJX INSTRUMENT CABLE | PS5-60-IH-0001C-CC02 | I |  |  |  | CPP-RFI-68-65-20-0039 | 2026-07-30 | Accepted | G K RAO | TESTING
| PS5-60-IH-0001D-CC01 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-60-IH-0001D-CC02 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-60-IH-0001E-CC01 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-60-IH-0001E-CC02 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-60-IH-0001F-CC01 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-60-IH-0001F-CC02 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-60-IH-0001G-CC01 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-60-IH-0001G-CC02 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-60-PIT-8113C-CC01 | TJX INSTRUMENT CABLE | PS5-60-PIT-8113C-CC01 | I |  |  |  | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
| PS5-60-PIT-8113D-CC01 | TJX INSTRUMENT CABLE | PS5-60-PIT-8113D-CC01 | I |  |  |  | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
| PS5-60-PIT-8113E-CC01 | TJX INSTRUMENT CABLE | PS5-60-PIT-8113E-CC01 | I |  |  |  | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
| PS5-60-PIT-8113F-CC01 | TJX INSTRUMENT CABLE | PS5-60-PIT-8113F-CC01 | I |  |  |  | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
| PS5-60-PIT-8113G-CC01 | TJX INSTRUMENT CABLE | #N/A | I |  |  |  | CPP-RFI-68-64-12-0131 | 2026-07-31 | OPEN | Elizabeth | Testing
| PS5-60-PIT-8114C-CC01 | TJX INSTRUMENT CABLE | #N/A | I |  |  |  | CPP-RFI-68-64-12-0128 | 01-August-2026 | Open | Ferdinand | Testing
| PS5-60-PIT-8114D-CC01 | TJX INSTRUMENT CABLE | #N/A | I |  |  |  | CPP-RFI-68-64-12-0128 | 01-August-2026 | Open | Ferdinand | Testing
| PS5-60-PIT-8114E-CC01 | TJX INSTRUMENT CABLE | #N/A | I |  |  |  | CPP-RFI-68-64-12-0128 | 01-August-2026 | Open | Ferdinand | Testing
| PS5-60-PIT-8114F-CC01 | TJX INSTRUMENT CABLE | #N/A | I |  |  |  | CPP-RFI-68-64-12-0128 | 01-August-2026 | Open | Ferdinand | Testing
| PS5-60-PIT-8114G-CC01 | TJX INSTRUMENT CABLE | #N/A | I |  |  |  | CPP-RFI-68-64-12-0128 | 01-August-2026 | Open | Ferdinand | Testing
| PS5-71-BI-2101-CC01 | TJX INSTRUMENT CABLE | PS5-71-BI-2101-CC01 | I
| PS5-71-IN-0004A-CC10 | TJX INSTRUMENT CABLE | #N/A | I
| PS5-74-LB-5101-CC02 | TJX INSTRUMENT CABLE | PS5-74-LB-5101-CC02 | I
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
`

## Sheet1
CHECK
PS5-01-FIT-0003A-CJ01
PS5-01-FIT-0003B-CJ01
PS5-01-FIT-0004A-CJ01
PS5-01-FIT-0004B-CJ01
PS5-01-FY-0003A-CJ01
PS5-01-PIT-0003AA-CJ01
PS5-01-FY-0003B-CJ01
PS5-01-PIT-0003BA-CJ01
PS5-01-FY-0004A-CJ01
PS5-01-PIT-0004AA-CJ01
PS5-01-FY-0004B-CJ01
PS5-01-PIT-0004BA-CJ01
PS5-01-PIT-0010-CJ01
PS5-01-PDIT-0011A-CJ01
PS5-01-PDIT-0011B-CJ01
PS5-01-PDIT-0012A-CJ01
PS5-01-PDIT-0012B-CJ01
PS5-01-PIT-8101A-CJ01
PS5-01-PIT-8101B-CJ01
PS5-01-PIT-8101C-CJ01
PS5-01-PIT-8101D-CJ01
PS5-01-PIT-8101E-CJ01
PS5-01-PIT-8101F-CJ01
PS5-01-PIT-8101G-CJ01
PS5-01-PIT-8101H-CJ01
PS5-01-FXS-0003A-CJ01
PS5-01-FXS-0003B-CJ01
PS5-01-FXS-0004A-CJ01
PS5-01-FXS-0004B-CJ01
PS5-01-SY-8101A-CJ01
PS5-01-SY-8101B-CJ01
PS5-01-SY-8101C-CJ01
PS5-01-SY-8101D-CJ01
PS5-01-SY-8101E-CJ01
PS5-01-SY-8101F-CJ01
PS5-01-SY-8101G-CJ01
PS5-01-SY-8101H-CJ01
PS5-03-RDIR-0405-CJ01
PS5-03-RDIR-0403-CJ01
PS5-03-RDIR-0404-CJ01
PS5-03-RDIR-0409-CJ01
PS5-03-RDIR-0411-CJ01
PS5-03-RDIR-0122-CJ01
PS5-03-RDIR-0123-CJ01
PS5-03-RDIR-0121-CJ01
PS5-03-RDIR-0125-CJ01
PS5-03-RDIR-0126-CJ01
PS5-03-RDIR-0127-CJ01
PS5-03-RDIR-0104-CJ01
PS5-03-RDIR-0105-CJ01
PS5-03-RDIR-0106-CJ01
PS5-03-RDIR-0137-CJ01
PS5-03-RDIR-0141-CJ01
PS5-03-RDIR-0142-CJ01
PS5-03-RDIR-0108-CJ01
PS5-03-RDIR-0109-CJ01
PS5-03-RDIR-0110-CJ01
PS5-03-RDIR-0111-CJ01
PS5-03-RDIR-0113-CJ01
PS5-03-RDIR-0112-CJ01
PS5-03-RDIR-0138-CJ01
PS5-03-RDIR-0114-CJ01
PS5-03-RDIR-0115-CJ01
PS5-03-RDIR-0116-CJ01
PS5-03-RDIR-0117-CJ01
PS5-03-RDIR-0118-CJ01
PS5-03-RDIR-0819-CJ01
PS5-03-RDIR-0820-CJ01
PS5-03-RDIR-0832-CJ01
PS5-03-RDUIR-0701-CJ01
PS5-03-RDUIR-0702-CJ01
PS5-03-RDUIR-0703-CJ01
PS5-03-RDUIR-0704-CJ01
PS5-03-RDUIR-0705-CJ01
PS5-03-RDUIR-0907-CJ01
PS5-03-RDUIR-0908-CJ01
PS5-03-RDUIR-1007-CJ01
PS5-03-RDUIR-1008-CJ01
PS5-03-RDUIR-1107-CJ01
PS5-03-RDUIR-1108-CJ01
PS5-03-RDUIR-1208-CJ01
PS5-03-RDUIR-1207-CJ01
PS5-03-RDH-0614-CJ01
PS5-03-RDH-0615-CJ01
PS5-03-RDH-0616-CJ01
PS5-03-RDH-0601-CJ01
PS5-03-RDH-0602-CJ01
PS5-03-RDH-0603-CJ01
PS5-03-RDH-0604-CJ01
PS5-03-RDH-0605-CJ01
PS5-03-RDH-0606-CJ01
PS5-03-RDH-0617-CJ01
PS5-03-RDH-0618-CJ01
PS5-03-RDH-0620-CJ01
PS5-03-RDH-0607-CJ01
PS5-03-RDH-0608-CJ01
PS5-03-RDH-0609-CJ01
PS5-03-RDH-0610-CJ01
PS5-03-RDH-0611-CJ01
PS5-03-RDH-0612-CJ01
PS5-03-RMAC-0613-CJ01
PS5-03-RDH-0830-CJ01
PS5-03-RDH-0831-CJ01
PS5-03-RMAC-0101-CJ01
PS5-03-RMAC-0102-CJ01
PS5-03-RMAC-0103-CJ01
PS5-03-RDH-0828-CJ01
PS5-03-RDH-0829-CJ01
PS5-03-RMAC-0827-CJ01
PS5-03-RDH-0901-CJ01
PS5-03-RDH-0902-CJ01
PS5-03-RDH-0903-CJ01
PS5-03-RDH-0904-CJ01
PS5-03-RDH-0905-CJ01
PS5-03-RDH-0906-CJ01
PS5-03-RDH-0909-CJ01
PS5-03-RDH-0910-CJ01
PS5-03-RDH-0911-CJ01
PS5-03-RDH-0912-CJ01
PS5-03-RMAC-0825-CJ01
PS5-03-RDH-1001-CJ01
PS5-03-RDH-1002-CJ01
PS5-03-RDH-1003-CJ01
PS5-03-RDH-1004-CJ01
PS5-03-RDH-1005-CJ01
PS5-03-RDH-1006-CJ01
PS5-03-RDH-1009-CJ01
PS5-03-RDH-1010-CJ01
PS5-03-RDH-1011-CJ01
PS5-03-RDH-1012-CJ01
PS5-03-RDH-1101-CJ01
PS5-03-RDH-1102-CJ01
PS5-03-RDH-1103-CJ01
PS5-03-RDH-1104-CJ01
PS5-03-RDH-1105-CJ01
PS5-03-RDH-1106-CJ01
PS5-03-RDH-1109-CJ01
PS5-03-RDH-1110-CJ01
PS5-03-RDH-1111-CJ01
PS5-03-RDH-1112-CJ01
PS5-03-RMAC-0401-CJ01
PS5-03-RMAC-0402-CJ01
PS5-03-GDLHP-0137-CJ01
PS5-03-GDLHP-0142-CJ01
PS5-03-GDLHP-0143-CJ01
PS5-03-GDLHP-0144-CJ01
PS5-03-GDLHP-0146-CJ01
PS5-03-GDLHP-0147-CJ01
PS5-03-GDLHP-0149-CJ01
PS5-03-GDLHP-0150-CJ01
PS5-03-GDLHP-0401-CJ01
PS5-03-RDH-1201-CJ01
PS5-03-RDH-1202-CJ01
PS5-03-RDH-1203-CJ01
PS5-03-RDH-1204-CJ01
PS5-03-RDH-1205-CJ01
PS5-03-RMAC-0834-CJ01
PS5-03-RDH-1302-CJ01
PS5-03-RDH-1303-CJ01
PS5-03-RDH-1304-CJ01
PS5-03-RMAC-1301-CJ01
PS5-03-RMAC-0706-CJ01
PS5-03-RMAC-0707-CJ01
PS5-25-FIT-0001-CJ01
PS5-25-PIT-1102-CJ01
PS5-25-PIT-1202-CJ01
PS5-25-TIT-0001-CJ01
PS5-25-TIT-0004-CJ01
PS5-25-PIT-0001-CJ01
PS5-25-TIT-1101-CJ01
PS5-25-TIT-1201-CJ01
PS5-25-MOV-0026-CC02
PS5-25-MOV-0027-CC02
PS5-28-LI-1101C-CJ01
PS5-25-ZIT-0001-CC01
PS5-25-ZIT-0002-CC01
PS5-25-FIT-0003A-CJ01
PS5-25-FIT-0003B-CJ01
PS5-25-FY-0003A-CJ01
PS5-25-PIT-0003AA-CJ01
PS5-25-PIT-0005A-CJ01
PS5-25-PIT-0005B-CJ01
PS5-25-PIT-0007A-CJ01
PS5-25-PIT-0007B-CJ01
PS5-25-PIT-0018-CJ01
PS5-25-FY-0003B-CJ01
PS5-25-PIT-0003BA-CJ01
PS5-28-LIT-1301B-CJ01
PS5-25-TIT-0003A-CJ01
PS5-25-TIT-0003B-CJ01
PS5-25-PIT-0070-CJ01
PS5-28-LIT-1301A-CJ01
PS5-25-PDIT-0034B-CJ01
PS5-25-FIT-0003C-CJ01
PS5-25-FY-0003C-CJ01
PS5-25-PIT-0003CA-CJ01
PS5-25-PDIT-0034C-CJ01
PS5-25-PIT-0005C-CJ01
PS5-25-PIT-0007C-CJ01
PS5-25-TIT-0003C-CJ01
PS5-28-LIT-1301C-CJ01
PS5-25-PIT-0013-CJ01
PS5-25-FIT-0004-CJ01
PS5-25-FY-0004-CJ01
PS5-25-PIT-0004AA-CJ01
PS5-25-PIT-0053-CJ01
PS5-25-ESDV-0021-CC01
PS5-25-ESDV-0023-CC01
PS5-25-PIT-0008A-CJ01
PS5-25-PIT-0022-CJ01
PS5-25-TIT-0002A-CJ01
PS5-25-TIT-0002B-CJ01
PS5-25-PIT-0004B-CJ01
PS5-25-PIT-0004A-CJ01
PS5-25-PIT-0035A-CJ01
PS5-25-PIT-0035B-CJ01
PS5-25-PIT-0036A-CJ01
PS5-28-PIT-0053B-CJ01
PS5-25-PIT-0054A-CJ01
PS5-25-PIT-0008C-CJ01
PS5-25-TIT-0002C-CJ01
PS5-25-PIT-0004C-CJ01
PS5-25-PDIT-0050-CJ01
PS5-25-PIT-0008B-CJ01
PS5-25-PIT-0036B-CJ01
PS5-25-PIT-0036C-CJ01
PS5-25-PIT-0046-CJ01
PS5-25-PIT-0054C-CJ01
PS5-28-PIT-0053C-CJ01
PS5-25-PIT-0054B-CJ01
PS5-25-MXS-0001-CJ01
PS5-25-MOV-0001-CC01
PS5-25-MXS-0025-CJ01
PS5-25-MOV-0025-CC01
PS5-25-MOV-0002-CC01
PS5-25-MOV-0003-CC01
PS5-25-MXS-0008-CJ01
PS5-25-MOV-0008-CC01
PS5-25-MXS-0028-CJ01
PS5-25-MOV-0028-CC01
PS5-25-MOV-0012-CC01
PS5-25-MOV-0011-CC01
PS5-25-MOV-0026-CC01
PS5-25-MOV-0027-CC01
PS5-25-XV-0053-CC01
PS5-25-XV-0070-CC01
PS5-25-ZS-1101-CJ01
PS5-25-ZS-1201-CJ01
PS5-25-XXS-0053-CJ01
PS5-25-XXS-0070-CJ01
PS5-25-FXS-0004-CJ01
PS5-25-FXS-0003A-CJ01
PS5-25-FXS-0003B-CJ01
PS5-25-FXS-0003C-CJ01
PS5-25-SY-0035CB-CJ01
PS5-25-SY-0036BB-CJ01
PS5-25-SY-0036CB-CJ01
PS5-28-SY-0053CB-CJ01
PS5-25-SY-0054BB-CJ01
PS5-25-SY-0054CB-CJ01
PS5-25-SY-0035AB-CJ01
PS5-25-SY-0035BB-CJ01
PS5-25-SY-0036AB-CJ01
PS5-28-SY-0053AB-CJ01
PS5-28-SY-0053BB-CJ01
PS5-25-SY-0054AB-CJ01
PS5-28-SY-0045B-CJ01
PS5-25-SY-0046B-CJ01
PS5-25-XY-0053-CJ01
PS5-25-XY-0070-CJ01
PS5-25-ESDV-0021-CC02
PS5-25-ESDV-0023-CC02
PS5-25-ESDV-0021-CC03
PS5-25-ESDV-0023-CC03
PS5-25-ESY-0021A-CJ01
PS5-25-SXS-0035A-CJ01
PS5-25-SXS-0035B-CJ01
PS5-25-SXS-0036A-CJ01
PS5-28-SXS-0053A-CJ01
PS5-28-SXS-0053B-CJ01
PS5-25-SDV-0035A-CC01
PS5-25-SDV-0035B-CC01
PS5-25-SDV-0036A-CC01
PS5-25-SDV-0046-CC01
PS5-25-SDV-0054A-CC01
PS5-25-SDV-0054B-CC01
PS5-25-SDV-0022-CC01
PS5-28-SDV-0053A-CC01
PS5-25-HS-8101A-CJ01
PS5-25-HS-8101B-CJ01
PS5-25-HS-8101C-CJ01
PS5-25-HS-8102A-CJ01
PS5-25-HS-8102B-CJ01
PS5-25-HS-8102C-CJ01
PS5-25-SY-0035AA-CJ01
PS5-25-SY-0035BA-CJ01
PS5-25-SY-0036AA-CJ01
PS5-25-SY-0046A-CJ01
PS5-25-SY-0054AA-CJ01
PS5-25-SY-0022-CJ01
PS5-28-SY-0053AA-CJ01
PS5-28-SY-0053BA-CJ01
PS5-25-ESY-0021B-CJ01
PS5-25-ESY-0023B-CJ01
PS5-28-SY-0045A-CJ01
PS5-25-SXS-0035C-CJ01
PS5-25-SXS-0036B-CJ01
PS5-25-SXS-0036C-CJ01
PS5-25-SXS-0046-CJ01
PS5-28-SXS-0053C-CJ01
PS5-25-SXS-0054B-CJ01
PS5-25-SXS-0054C-CJ01
PS5-71-SXS-0001-CJ01
PS5-25-SDV-0035C-CC01
PS5-25-SDV-0036B-CC01
PS5-25-SDV-0036C-CC01
PS5-28-SDV-0053B-CC01
PS5-28-SDV-0053C-CC01
PS5-25-SDV-0054C-CC01
PS5-71-SDV-0001-CC01
PS5-25-SY-0035CA-CJ01
PS5-25-SY-0036CA-CJ01
PS5-25-SY-0036BA-CJ01
PS5-25-SY-0054BA-CJ01
PS5-25-SY-0054CA-CJ01
PS5-71-SY-0001-CJ01
PS5-25-SY-0052B-CJ01
PS5-28-PIT-0015-CJ01
PS5-28-LIT-1101-CJ01
PS5-28-TIT-1104-CJ01
PS5-28-HY-3901A-CJ01
PS5-28-HY-3901B-CJ01
PS5-28-LIT-1201-CJ01
PS5-28-PIT-0033-CJ01
PS5-28-TIT-1201-CJ01
PS5-28-TIT-1401-CJ01
PS5-28-LIT-1402-CJ01
PS5-28-LIT-1102-CJ01
PS5-28-LIT-1202-CJ01
PS5-28-PIT-0041-CJ01
PS5-28-PIT-0045-CJ01
PS5-28-TIT-1105-CJ01
PS5-28-TIT-2101-CJ01
PS5-28-PIT-3901A-CJ01
PS5-28-PIT-3901B-CJ01
PS5-28-TIT-1402-CJ01
PS5-28-LIT-1401-CJ01
PS5-28-TIT-2201-CJ01
PS5-71-LIT-1202-CJ01
PS5-71-PIT-0001-CJ01
PS5-28-SDV-0045-CC01
PS5-28-LIT-0002-CJ01
PS5-50-FIT-0001-CJ01
PS5-28-LIT-0008-CJ01
PS5-74-PIT-0002-CJ01
PS5-53-PIT-0005-CJ01
PS5-71-LY-4101-CJ01
PS5-71-PIT-4101A-CJ01
PS5-71-TIT-0003-CJ01
PS5-71-FIT-0011B-CJ01
PS5-71-PIT-2402A-CJ01
PS5-71-PIT-2402B-CJ01
PS5-71-PDIT-0030-CJ01
PS5-71-FIT-0011A-CJ01
PS5-71-TIT-0004-CJ01
PS5-71-PDIT-0056B-CJ01
PS5-71-FIT-0020-CJ01
PS5-71-FIT-0018-CJ01
PS5-71-FIT-0019-CJ01
PS5-71-PDIT-0056A-CJ01
PS5-71-PIT-3302A-CJ01
PS5-71-PIT-3302B-CJ01
PS5-71-PIT-3402A-CJ01
PS5-71-PIT-3402B-CJ01
PS5-71-FIT-0005-CJ01
PS5-71-LIT-4401-CJ01
PS5-71-PIT-0014-CJ01
PS5-71-FY-0019-CJ01
PS5-71-PIT-0019A-CJ01
PS5-71-LIT-1201-CJ01
PS5-71-PIT-0091-CJ01
PS5-71-PIT-0092-CJ01
PS5-60-LIT-4301-CJ01
PS5-60-LIT-4401-CJ01
PS5-71-FY-0018-CJ01
PS5-71-PIT-0018A-CJ01
PS5-71-FY-0020-CJ01
PS5-71-PIT-0020A-CJ01
PS5-71-PIT-0089-CJ01
PS5-71-PIT-0090-CJ01
PS5-71-XY-0089-CJ01
PS5-71-XY-0090-CJ01
PS5-71-PIT-0022-CJ01
PS5-71-TIT-0006-CJ01
PS5-71-TIT-2402AA-CJ01
PS5-71-TIT-2402BA-CJ01
PS5-71-PIT-0039-CJ01
PS5-71-TIT-0007-CJ01
PS5-71-PIT-3301A-CJ01
PS5-71-PIT-3301B-CJ01
PS5-71-PIT-3401A-CJ01
PS5-71-PIT-3401B-CJ01
PS5-71-LIT-4402-CJ01
PS5-71-PIT-0029-CJ01
PS5-71-LXS-4101-CJ01
PS5-71-FXS-0020-CJ01
PS5-71-FXS-0018-CJ01
PS5-71-XXS-0089-CJ01
PS5-71-XXS-0090-CJ01
PS5-71-XV-0091-CC01
PS5-71-XV-0092-CC01
PS5-71-BAV-0059-CC01
PS5-71-BAV-0058-CC01
PS5-71-XXS-0091-CJ01
PS5-71-XXS-0092-CJ01
PS5-71-FXS-0019-CJ01
PS5-71-XY-0091-CJ01
PS5-71-XY-0092-CJ01
PS5-71-XV-0089-CC01
PS5-71-XV-0090-CC01
PS5-71-MOV-0007-CC01
PS5-71-MOV-0008-CC01
PS5-71-MOV-0009-CC01
PS5-71-MOV-0010-CC01
PS5-60-MOV-0012-CC01
PS5-71-MOV-0001-CC01
PS5-71-MOV-0002-CC01
PS5-60-MOV-0005-CC01
PS5-71-MOV-0003-CC01
PS5-71-MOV-0004-CC01
PS5-60-MOV-0006-CC01
PS5-71-MOV-0007-CC02
PS5-71-MOV-0008-CC02
PS5-60-MOV-0011-CC02
PS5-71-MOV-0009-CC02
PS5-71-MOV-0010-CC02
PS5-60-MOV-0012-CC02
PS5-71-MOV-0001-CC02
PS5-71-MOV-0002-CC02
PS5-60-MOV-0005-CC02
PS5-71-MOV-0003-CC02
PS5-71-MOV-0004-CC02
PS5-60-MOV-0006-CC02
PS5-71-SDV-0022-CC01
PS5-71-SDV-0039-CC01
PS5-71-SDV-0029-CC01
PS5-71-SY-0039-CJ01
PS5-71-SY-0022-CJ01
PS5-71-SXS-0029-CJ01
PS5-71-SXS-0022-CJ01
PS5-71-SXS-0039-CJ01
PS5-71-SY-0029-CJ01
PS5-25-PI-1102B-CJ01
PS5-25-PI-1202B-CJ01
PS5-28-LI-1101B-CJ01
PS5-28-LI-1402B-CJ01
PS5-71-XV-0092-CC02
PS5-71-FCV-0019-CC01
PS5-71-SDV-0001-CC02
PS5-01-LIT-4101A-CJ01
PS5-01-LIT-4101B-CJ01
PS5-74-LB-5101-CC01
PS5-74-LB-5101-CC02
PS5-74-LB-5101-CJ01
PS5-01-BI-0001-CC01
PS5-01-BI-0002-CC01
PS5-01-BI-0003-CC01
PS5-01-BI-0004-CC01
PS5-01-BI-0005-CC01
PS5-01-BI-0006-CC01
PS5-01-BI-1117-CC01
PS5-01-BI-1118-CC01
PS5-01-BI-1501-CC01
PS5-01-BI-1515-CC01
PS5-01-BI-1520-CC01
PS5-01-BI-1571-CC01
PS5-01-BI-2110-CC01
PS5-01-BI-2520-CC01
PS5-01-BI-2571A-CC01
PS5-01-BI-2571B-CC01
PS5-01-IE-0002A-CC01
PS5-01-IE-0002A-CC02
PS5-01-IE-0002B-CC01
PS5-01-IE-0002B-CC02
PS5-01-IE-0009A-CC01
PS5-01-IE-0009B-CC01
PS5-01-LB-0004-CC01
PS5-01-LB-0004-CC02
PS5-01-LB-0004-CC03
PS5-01-LIT-4201-CJ01
PS5-01-PIT-0014-CJ01
PS5-01-PIT-0015-CJ01
PS5-01-PIT-0016-CJ01
PS5-01-PIT-0017-CJ01
PS5-03-BI-1502-CC01
PS5-03-BI-1503-CC01
PS5-03-BI-1506-CC01
PS5-03-BI-1507-CC01
PS5-03-BI-1508-CC01
PS5-03-BI-1509-CC01
PS5-03-BI-1510-CC01
PS5-03-BI-1511-CC01
PS5-03-BI-1512-CC01
PS5-03-BI-1513-CC01
PS5-03-BI-1514-CC01
PS5-03-BI-1516-CC01
PS5-03-BI-2501-CC01
PS5-03-BI-2502-CC01
PS5-03-BI-2503-CC01
PS5-03-BI-2504-CC01
PS5-03-BI-2505-CC01
PS5-03-BI-2506-CC01
PS5-03-BI-2507-CC01
PS5-03-BI-2508-CC01
PS5-03-BI-2509-CC01
PS5-03-BI-2511-CC01
PS5-03-BI-2512-CC01
PS5-03-BI-2514-CC01
PS5-03-BI-2515-CC01
PS5-03-HS-7002-CJ01
PS5-03-NMR-0801-CJ01
PS5-03-NMR-0802-CJ01
PS5-03-NMR-0803-CJ01
PS5-03-NMR-0804-CJ01
PS5-03-RMAC-0120-CJ01
PS5-03-RMAC-0824-CJ01
PS5-03-SEA-0002-CC01
PS5-03-SEA-0002-CJ01
PS5-03-SEA-0003-CC01
PS5-03-SEA-0003-CJ01
PS5-03-SEA-0006-CC01
PS5-03-SEA-0006-CJ01
PS5-06-GU-0003A-CC01
PS5-06-GU-0003B-CC01
PS5-09-BI-2501-CC01
PS5-09-BI-2503-CC01
PS5-09-LB-0007-CC01
PS5-09-LB-0007-CC02
PS5-09-LB-0007-CC03
PS5-09-LB-0007-CC04
PS5-09-LB-0008-CC01
PS5-09-LB-0008-CC02
PS5-09-LB-0008-CC03
PS5-09-LB-0008-CC04
PS5-09-LB-0008-CC05
PS5-09-LB-0008-CC06
PS5-09-LB-0008-CC07
PS5-09-LB-0008-CC08
PS5-25-BI-1101-CC01
PS5-25-BI-1102-CC01
PS5-25-BI-1103-CC01
PS5-25-BI-1104-CC01
PS5-25-BI-1115-CC01
PS5-25-BI-1201-CC01
PS5-25-BI-1301-CC01
PS5-25-BI-1302-CC01
PS5-25-BI-1310-CC01
PS5-25-BI-2101-CC01
PS5-25-BI-2102-CC01
PS5-25-BI-2103-CC01
PS5-25-BI-2104-CC01
PS5-25-BI-2105-CC01
PS5-25-BI-2106-CC01
PS5-25-BI-2108-CC01
PS5-25-BI-2109-CC01
PS5-25-BI-2201-CC01
PS5-25-BI-2203-CC01
PS5-25-BI-2205-CC01
PS5-25-BI-2301-CC01
PS5-25-BI-2302-CC01
PS5-25-BI-2305-CC01
PS5-25-BI-2308-CC01
PS5-25-BI-2309-CC01
PS5-25-BI-2312-CC01
PS5-25-BI-2315-CC01
PS5-25-BI-2316-CC01
PS5-25-SHSR-0052-CJ01
PS5-28-BI-1105-CC01
PS5-28-BI-1106-CC01
PS5-28-BI-1114-CC01
PS5-28-BI-1303-CC01
PS5-28-BI-1307-CC01
PS5-28-BI-2304-CC01
PS5-28-HXA-1101-CJ01
PS5-28-LB-8200-CC01
PS5-28-LB-8200-CJ01
PS5-50-BI-1107-CC01
PS5-50-IE-0001-CC01
PS5-50-IE-0001-CC02
PS5-50-IE-0002-CC01
PS5-50-IE-0002-CC02
PS5-50-IE-0001-CJ01
PS5-50-IE-0002-CJ01
PS5-53-BI-1108-CC01
PS5-53-BI-1304-CC01
PS5-53-LA-0001-CC01
PS5-53-LA-0001-CC02
PS5-60-IE-0003A-CC21
PS5-60-IE-0003A-CC22
PS5-60-IE-0003A-CC23
PS5-60-IE-0003A-CC24
PS5-60-IE-0003B-CC21
PS5-60-IE-0003B-CC22
PS5-60-IE-0003B-CC23
PS5-60-IE-0003B-CC24
PS5-60-IE-0003C-CC21
PS5-60-IE-0003C-CC22
PS5-60-IE-0003C-CC23
PS5-60-IE-0003C-CC24
PS5-60-IE-0003D-CC21
PS5-60-IE-0003D-CC22
PS5-60-IE-0003D-CC23
PS5-60-IE-0003D-CC24
PS5-60-IE-0003E-CC21
PS5-60-IE-0003E-CC22
PS5-60-IE-0003E-CC23
PS5-60-IE-0003E-CC24
PS5-60-IE-0003F-CC21
PS5-60-IE-0003F-CC22
PS5-60-IE-0003F-CC23
PS5-60-IE-0003F-CC24
PS5-60-IE-0003G-CC21
PS5-60-IE-0003G-CC22
PS5-60-IE-0003G-CC23
PS5-60-IE-0003G-CC24
PS5-60-IE-0004-CC08
PS5-60-IE-0004-CC11
PS5-60-IE-0004-CC12
PS5-60-SEA-0001-CC18
PS5-71-BI-1109-CC01
PS5-71-BI-1110-CC01
PS5-71-BI-1111-CC01
PS5-71-BI-1112-CC01
PS5-71-BI-1113-CC01
PS5-71-BI-1116-CC01
PS5-71-BI-1117-CC01
PS5-71-BI-2101-CC01
PS5-71-BI-1305-CC01
PS5-71-BI-1306-CC01
PS5-71-BI-1308-CC01
PS5-71-BI-2107-CC01
PS5-71-BI-2113-CC01
PS5-71-BI-2114-CC01
PS5-71-BI-2115-CC01
PS5-71-BI-2116-CC01
PS5-71-BI-2118-CC01
PS5-71-BI-2119-CC01
PS5-71-BI-2120-CC01
PS5-71-BI-2121-CC01
PS5-71-BI-2122-CC01
PS5-71-BI-2123-CC01
PS5-71-BI-2124-CC01
PS5-71-BI-2125-CC01
PS5-71-BI-2306-CC01
PS5-71-BI-2307-CC01
PS5-71-BI-2310-CC01
PS5-71-BI-2313-CC01
PS5-71-BI-2314-CC01
PS5-71-BI-2317-CC01
PS5-71-IN-0001-CC08
PS5-71-IN-0001-CC09
PS5-71-IN-0001-CC10
PS5-71-IN-0002-CC05
PS5-71-IN-0002-CC06
PS5-71-IN-0002-CC07
PS5-71-IN-0003-CC05
PS5-71-IN-0003-CC06
PS5-71-IN-0003-CC07
PS5-71-IN-0004A-CC08
PS5-71-IN-0004A-CC09
PS5-71-IN-0004A-CC12
PS5-71-IN-0004B-CC08
PS5-71-IN-0004B-CC09
PS5-71-IN-0004B-CC12
PS5-75-BI-1177-CC01
PS5-75-BI-1178-CC01
PS5-75-BI-1371-CC01
PS5-75-BI-1372-CC01
PS5-75-BI-0001-CC01
PS5-75-BI-0002-CC01
PS5-75-BI-0002-CC02
PS5-75-BI-0002-CC03
PS5-75-MOV-0001-CC01
PS5-75-MOV-0001-CC02
PS5-79-IG-0001-CJ01
PS5-79-IG-0002-CJ01
PS5-79-IG-0003-CJ01
PS5-79-IG-0004-CJ01
PS5-79-IG-0005-CJ01
PS5-79-IG-0006-CJ01
PS5-79-IG-0007-CJ01
PS5-79-IG-0008-CJ01
PS5-79-IG-0009-CJ01
PS5-79-IG-0010-CJ01
PS5-79-IG-0011-CJ01
PS5-79-IG-0012-CJ01
PS5-71-TIT-2403A-CJ01
PS5-71-TIT-2403B-CJ01
PS5-05-BI-0002-CC01
PS5-05-BI-0002-CC02
PS5-05-IE-8101-CC01
PS5-05-BI-0002-CJ01
PS5-05-BI-0002-CJ02
PS5-05-BI-0002-CC05
PS5-05-GC-8100-CC01
PS5-05-LIT-4101-CJ01
PS5-05-UH-8100-CC01
PS5-05-BI-0002-CC03
PS5-05-UH-8100-CC02
PS5-05-BI-0002-CJ03
PS5-03-SEA-0001-CC01
PS5-05-BI-0002-CC06
PS5-05-BI-0002-CC04
PS5-05-IG-0009-CC01
PS5-05-IG-0009-CC02
PS5-05-IG-0009-CJ01
PS5-05-BI-0002-CC11
PS5-05-BI-0002-CC12
PS5-05-IE-8100-CC01
PS5-05-IE-8100-CC02
PS5-25-BI-1174A-CC01
PS5-25-BI-1174B-CC01
PS5-25-BI-1174C-CC01
PS5-25-BI-1274A-CC01
PS5-25-BI-1274B-CC01
PS5-25-BI-1274C-CC01
PS5-61-IDH-3100A-CC01
PS5-61-IDH-3100A-CC02
PS5-61-IDH-3100A-CC03
PS5-61-IDH-3100B-CC01
PS5-61-IDH-3100B-CC02
PS5-61-IDH-3100B-CC03
PS5-61-IDH-3100C-CC01
PS5-61-IDH-3100C-CC02
PS5-25-MXS-3101AA-CJ01
PS5-25-MXS-3101BA-CJ01
PS5-25-MXS-3101CA-CJ01
PS5-83-EHO-0001A-CC01
PS5-83-EHO-0001B-CC01
PS5-83-EHO-0001C-CC01
PS5-83-EHO-0001A-CJ01
PS5-83-EHO-0001B-CJ01
PS5-83-EHO-0001C-CJ01
PS5-25-BI-1801A-CC01
PS5-25-BI-1802A-CC01
PS5-25-BI-1802A-CC02
PS5-25-BI-1803A-CC01
PS5-25-BI-1803A-CC02
PS5-25-BI-1801B-CC01
PS5-25-BI-1802B-CC01
PS5-25-BI-1802B-CC02
PS5-25-BI-1803B-CC01
PS5-25-BI-1803B-CC02
PS5-25-BI-1801C-CC01
PS5-25-BI-1802C-CC01
PS5-25-BI-1802C-CC02
PS5-25-BI-1803C-CC01
PS5-25-BI-1803C-CC02
PS5-71-BI-0001-CC01
PS5-71-BI-0021-CC02
PS5-25-MXS-3101AB-CJ01
PS5-25-MXS-3101BB-CJ01
PS5-25-MXS-3101CB-CJ01
PS5-25-PIT-0052-CJ01
PS5-25-PIT-0071A-CJ01
PS5-25-PIT-0071B-CJ01
PS5-25-PIT-0071C-CJ01
PS5-25-SDV-0052-CC01
PS5-25-SXS-0052-CJ01
PS5-25-SY-0052A-CJ01
PS5-25-SDV-0052-CJ01
PS5-09-LB-0008-CX01
PS5-09-LB-0007-CX01
PS5-60-IE-0004-CX03
PS5-60-IE-0004-CX04
PS5-60-LA-0003-CX01
PS5-74-LB-5101-CX01
PS5-82-LA-0001-CX01
PS5-53-LA-0001-CX01
PS5-60-IN-0001A-CA01
PS5-60-IN-0001B-CA01
PS5-60-IN-0001C-CA01
PS5-60-IN-0001D-CA01
PS5-60-IN-0001E-CA01
PS5-60-IN-0001F-CA01
PS5-60-IN-0001G-CA01
PS5-60-IE-0003B-CA03
PS5-60-IE-0003B-CA04
PS5-60-IE-0003B-CA05
PS5-60-IE-0003C-CA03
PS5-60-IE-0003C-CA04
PS5-60-IE-0003C-CA05
PS5-60-IE-0004-CA01
PS5-60-IE-0004-CA07
PS5-60-IE-0004-CA08
PS5-60-IE-0004-CA14
PS5-60-IE-0004-CA15
PS5-60-IE-0004-CA21
PS5-60-IN-0002A-CA01
PS5-60-IN-0002B-CA01
PS5-71-IN-0003-CA01
PS5-60-IN-0001A-CC02
PS5-60-IN-0001B-CC02
PS5-60-IN-0001C-CC02
PS5-60-IN-0001D-CC02
PS5-60-IN-0001E-CC02
PS5-60-IN-0001F-CC02
PS5-60-IN-0001G-CC02
PS5-60-IN-0001A-CC04
PS5-60-IN-0001B-CC04
PS5-60-IN-0001C-CC04
PS5-60-IN-0001D-CC04
PS5-60-IN-0001E-CC04
PS5-60-IN-0001F-CC04
PS5-60-IN-0001G-CC04
PS5-60-BI-0002-CC04
PS5-60-BI-0002-CC03
PS5-60-BI-0001A-CC03
PS5-60-BI-0001B-CC03
PS5-60-BI-0001C-CC03
PS5-60-BI-0001D-CC03
PS5-60-BI-0001E-CC03
PS5-60-BI-0001F-CC03
PS5-60-BI-0001G-CC03
PS5-60-BI-0001A-CC01
PS5-60-BI-0001B-CC01
PS5-60-BI-0001C-CC01
PS5-60-BI-0001D-CC01
PS5-60-BI-0001E-CC01
PS5-60-BI-0001F-CC01
PS5-60-BI-0001G-CC01
PS5-60-IE-0002B-CC05
PS5-60-IE-0002C-CC05
PS5-60-IE-0002D-CC05
PS5-60-IE-0002E-CC05
PS5-60-IE-0002F-CC05
PS5-60-IE-0002G-CC05
PS5-61-BI-0001-CC03
PS5-61-BI-0002-CC03
PS5-61-BI-0003-CC03
PS5-61-BI-0004-CC03
PS5-61-BI-0005-CC03
PS5-61-BI-0006-CC03
PS5-61-BI-0007-CC03
PS5-60-BE-0004A-CC01
PS5-60-BE-0004B-CC01
PS5-60-BE-0004C-CC01
PS5-60-BE-0004D-CC01
PS5-60-BE-0004E-CC01
PS5-60-BE-0004F-CC01
PS5-60-BE-0004G-CC01
PS5-60-BI-0016A-CC03
PS5-60-BI-0016B-CC03
PS5-60-BI-0016C-CC03
PS5-60-BI-0016D-CC03
PS5-60-BI-0016E-CC03
PS5-60-BI-0016F-CC03
PS5-60-BI-0016G-CC03
PS5-60-BE-0001-CC01
PS5-60-BE-0002-CC01
PS5-60-SY-0007-CC01
PS5-60-SY-0008-CC01
PS5-60-SY-0009-CC01
PS5-60-SY-0010-CC01
PS5-60-SY-0011-CC01
PS5-60-SY-0012-CC01
PS5-60-SY-0013-CC01
PS5-71-IN-0001-CC04
PS5-71-IN-0001-CC05
PS5-71-IN-0004A-CC04
PS5-71-IN-0004A-CC05
PS5-71-IN-0004B-CC04
PS5-71-IN-0004B-CC05
PS5-60-IE-0003A-CC25
PS5-60-IE-0003A-CC26
PS5-60-IE-0003B-CC25
PS5-60-IE-0003B-CC26
PS5-60-IE-0003C-CC25
PS5-60-IE-0003C-CC26
PS5-60-IE-0003D-CC25
PS5-60-IE-0003D-CC26
PS5-60-IE-0003E-CC25
PS5-60-IE-0003E-CC26
PS5-60-IE-0003F-CC25
PS5-60-IE-0003F-CC26
PS5-60-IE-0003G-CC25
PS5-60-IE-0003G-CC26
PS5-60-IN-0001A-CC01
PS5-60-IN-0001B-CC01
PS5-60-IN-0001C-CC01
PS5-60-IN-0001D-CC01
PS5-60-IN-0001E-CC01
PS5-60-IN-0001F-CC01
PS5-60-IN-0001G-CC01
PS5-60-IN-0001A-CC03
PS5-60-IN-0001B-CC03
PS5-60-IN-0001C-CC03
PS5-60-IN-0001D-CC03
PS5-60-IN-0001E-CC03
PS5-60-IN-0001F-CC03
PS5-60-IN-0001G-CC03
PS5-60-BI-0006A-CC05
PS5-60-BI-0006B-CC05
PS5-60-BI-0006C-CC05
PS5-60-BI-0006D-CC05
PS5-60-BI-0006E-CC05
PS5-60-BI-0006F-CC05
PS5-60-BI-0006G-CC05
PS5-60-IE-0003A-CC15
PS5-60-IE-0003B-CC15
PS5-60-LA-0003-CC01
PS5-71-BI-0009-CC02
PS5-71-BI-0009-CC03
PS5-60-BI-0003-CC01
PS5-60-IN-0002A-CC06
PS5-60-IN-0002B-CC06
PS5-60-IN-0002C-CC06
PS5-60-IN-0002D-CC06
PS5-60-IN-0002E-CC06
PS5-60-IN-0002F-CC06
PS5-60-IN-0002G-CC06
PS5-71-BI-0003-CC01
PS5-71-BI-0005-CC02
PS5-71-IN-0001-CC03
PS5-71-IN-0004A-CC03
PS5-60-BI-0003-CC02
PS5-60-BI-0006A-CC01
PS5-60-BI-0006B-CC01
PS5-60-BI-0006C-CC01
PS5-60-BI-0006D-CC01
PS5-60-BI-0006E-CC01
PS5-60-BI-0006F-CC01
PS5-60-BI-0006G-CC01
PS5-60-BI-0016A-CC01
PS5-60-BI-0016B-CC01
PS5-60-BI-0016C-CC01
PS5-60-BI-0016D-CC01
PS5-60-BI-0016E-CC01
PS5-60-BI-0016F-CC01
PS5-60-BI-0016G-CC01
PS5-60-BI-0002-CC02
PS5-60-BI-0005A-CC01
PS5-60-BI-0005A-CC02
PS5-60-BI-0005B-CC01
PS5-60-BI-0005B-CC02
PS5-60-BI-0005C-CC01
PS5-60-BI-0005C-CC02
PS5-60-BI-0005D-CC01
PS5-60-BI-0005D-CC02
PS5-60-BI-0005E-CC01
PS5-60-BI-0005E-CC02
PS5-60-BI-0005F-CC01
PS5-60-BI-0005F-CC02
PS5-60-BI-0005G-CC01
PS5-60-BI-0005G-CC02
PS5-60-BI-0006A-CC03
PS5-60-BI-0006A-CC06
PS5-60-BI-0006B-CC03
PS5-60-BI-0006B-CC06
PS5-60-BI-0006C-CC03
PS5-60-BI-0006C-CC06
PS5-60-BI-0006D-CC03
PS5-60-BI-0006D-CC06
PS5-60-BI-0006E-CC03
PS5-60-BI-0006E-CC06
PS5-60-BI-0006F-CC03
PS5-60-BI-0006F-CC06
PS5-60-BI-0006G-CC03
PS5-60-BI-0006G-CC06
PS5-60-IE-0003A-CC07
PS5-60-IE-0003B-CC06
PS5-60-IE-0003B-CC07
PS5-60-IE-0003C-CC06
PS5-60-IE-0003C-CC07
PS5-60-IE-0003D-CC06
PS5-60-IE-0003D-CC07
PS5-60-IE-0003E-CC06
PS5-60-IE-0003E-CC07
PS5-60-IE-0003F-CC06
PS5-60-IE-0003F-CC07
PS5-60-IE-0003G-CC06
PS5-60-IE-0003G-CC07
PS5-60-IN-0002A-CC01
PS5-60-IN-0002A-CC04
PS5-60-IN-0002B-CC01
PS5-60-IN-0002B-CC04
PS5-60-IN-0002C-CC01
PS5-60-IN-0002C-CC04
PS5-60-IN-0002D-CC01
PS5-60-IN-0002D-CC04
PS5-60-IN-0002E-CC01
PS5-60-IN-0002E-CC04
PS5-60-IN-0002F-CC01
PS5-60-IN-0002F-CC04
PS5-60-IN-0002G-CC01
PS5-60-IN-0002G-CC04
PS5-60-SEA-0001-CC10
PS5-60-VS-9101A-CC01
PS5-60-VS-9101B-CC01
PS5-60-VS-9101C-CC01
PS5-60-VS-9101D-CC01
PS5-60-VS-9101E-CC01
PS5-60-VS-9101F-CC01
PS5-60-VS-9101G-CC01
PS5-71-BI-0006-CC01
PS5-71-BI-0009-CC04
PS5-71-BI-0010-CC01
PS5-71-IN-0001-CC01
PS5-71-IN-0001-CC02
PS5-71-IN-0002-CC01
PS5-71-IN-0003-CC01
PS5-71-IN-0003-CC02
PS5-60-BI-0006A-CC02
PS5-60-BI-0006B-CC02
PS5-60-BI-0006C-CC02
PS5-60-BI-0006D-CC02
PS5-60-BI-0006E-CC02
PS5-60-BI-0006F-CC02
PS5-60-BI-0006G-CC02
PS5-60-IE-0003A-CC03
PS5-60-IE-0003B-CC03
PS5-60-IE-0003C-CC03
PS5-60-IE-0003D-CC03
PS5-60-IE-0003E-CC03
PS5-60-IE-0003F-CC03
PS5-60-IN-0002A-CC03
PS5-60-IN-0002A-CC05
PS5-60-IN-0002B-CC03
PS5-60-IN-0002B-CC05
PS5-60-IN-0002C-CC03
PS5-60-IN-0002C-CC05
PS5-60-IN-0002D-CC03
PS5-60-IN-0002D-CC05
PS5-60-IN-0002E-CC03
PS5-60-IN-0002E-CC05
PS5-60-IN-0002F-CC03
PS5-60-IN-0002F-CC05
PS5-60-IN-0002G-CC03
PS5-60-IN-0002G-CC05
PS5-60-LA-0002A-CC01
PS5-60-LA-0002A-CC02
PS5-60-LA-0002A-CC03
PS5-60-LA-0002A-CC04
PS5-60-LA-0002A-CC05
PS5-60-LA-0002A-CC06
PS5-60-LA-0002A-CC07
PS5-60-LA-0002A-CC08
PS5-60-LA-0002A-CC09
PS5-60-LA-0002B-CC01
PS5-60-LA-0002B-CC02
PS5-60-LA-0002B-CC03
PS5-60-LA-0002B-CC04
PS5-60-LA-0002C-CC01
PS5-60-LA-0002C-CC02
PS5-60-LA-0002C-CC03
PS5-60-LA-0002C-CC04
PS5-60-LA-0002C-CC05
PS5-60-LA-0002C-CC06
PS5-60-SEA-0001-CC01
PS5-60-SEA-0001-CC03
PS5-60-SEA-0001-CC04
PS5-60-SEA-0001-CC05
PS5-60-SEA-0001-CC06
PS5-60-SEA-0001-CC07
PS5-60-SEA-0001-CC11
PS5-60-SEA-0001-CC12
PS5-60-SEA-0001-CC14
PS5-60-SEA-0001-CC15
PS5-60-SEA-0001-CC16
PS5-60-SEA-0001-CC17
PS5-61-BI-0001-CC02
PS5-61-BI-0002-CC02
PS5-61-BI-0003-CC02
PS5-61-BI-0004-CC02
PS5-61-BI-0005-CC02
PS5-61-BI-0006-CC02
PS5-61-BI-0007-CC02
PS5-71-IN-0001-CC06
PS5-71-IN-0001-CC07
PS5-71-IN-0002-CC03
PS5-71-IN-0002-CC04
PS5-71-IN-0003-CC03
PS5-71-IN-0003-CC04
PS5-71-IN-0004A-CC06
PS5-71-IN-0004A-CC07
PS5-71-IN-0004B-CC06
PS5-71-IN-0004B-CC07
PS5-60-BI-0019A-CC01
PS5-60-BI-0019B-CC01
PS5-60-BI-0019C-CC01
PS5-60-BI-0019D-CC01
PS5-60-BI-0019E-CC01
PS5-60-BI-0019G-CC01
PS5-60-IE-0003C-CC15
PS5-60-IE-0003D-CC15
PS5-60-IE-0003E-CC15
PS5-60-IE-0003F-CC15
PS5-60-IE-0003G-CC15
PS5-60-BI-0019D-CC02
PS5-60-BI-0019E-CC02
PS5-60-BI-0019F-CC02
PS5-60-BI-0019G-CC02
PS5-60-IE-0003A-CC06
PS5-60-IE-0003A-CC16
PS5-60-IE-0003A-CC17
PS5-60-IE-0003B-CC16
PS5-60-IE-0003B-CC17
PS5-60-IE-0003C-CC16
PS5-60-IE-0003C-CC17
PS5-60-IE-0003D-CC16
PS5-60-IE-0003D-CC17
PS5-60-IE-0003E-CC16
PS5-60-IE-0003E-CC17
PS5-60-IE-0003F-CC16
PS5-60-IE-0003F-CC17
PS5-60-IE-0003G-CC03
PS5-60-IE-0003G-CC16
PS5-60-IE-0003G-CC17
PS5-60-BI-0017A-CC02
PS5-60-BI-0017B-CC02
PS5-60-BI-0017C-CC02
PS5-60-BI-0017D-CC02
PS5-60-BI-0017E-CC02
PS5-60-BI-0017F-CC02
PS5-60-BI-0017G-CC02
PS5-71-BI-0008A-CC01
PS5-71-BI-0008A-CC02
PS5-60-BI-0002-CC01
PS5-60-IE-0003A-CC08
PS5-60-IE-0003A-CC09
PS5-60-IE-0003A-CC10
PS5-60-IE-0003A-CC11
PS5-60-IE-0003B-CC08
PS5-60-IE-0003B-CC09
PS5-60-IE-0003B-CC10
PS5-60-IE-0003B-CC11
PS5-60-IE-0003C-CC08
PS5-60-IE-0003C-CC09
PS5-60-IE-0003C-CC10
PS5-60-IE-0003C-CC11
PS5-60-IE-0003D-CC08
PS5-60-IE-0003D-CC09
PS5-60-IE-0003D-CC10
PS5-60-IE-0003E-CC08
PS5-60-IE-0003E-CC09
PS5-60-IE-0003E-CC11
PS5-60-IE-0003F-CC08
PS5-60-IE-0003F-CC09
PS5-60-IE-0003F-CC10
PS5-60-IE-0003F-CC11
PS5-60-IE-0003G-CC08
PS5-60-IE-0003G-CC09
PS5-60-IE-0003G-CC10
PS5-60-IE-0003G-CC11
PS5-60-IN-0002A-CC02
PS5-60-IN-0002B-CC02
PS5-60-IN-0002C-CC02
PS5-60-IN-0002D-CC02
PS5-60-IN-0002E-CC02
PS5-60-IN-0002F-CC02
PS5-60-IN-0002G-CC02
PS5-71-IN-0002-CC02
PS5-71-IN-0004A-CC01
PS5-71-IN-0004A-CC02
PS5-71-IN-0004B-CC01
PS5-71-IN-0004B-CC02
PS5-60-IE-0003A-CC01
PS5-60-IE-0003A-CC02
PS5-60-IE-0003B-CC01
PS5-60-IE-0003B-CC02
PS5-60-IE-0003C-CC01
PS5-60-IE-0003C-CC02
PS5-60-IE-0003D-CC01
PS5-60-IE-0003D-CC02
PS5-60-IE-0003E-CC01
PS5-60-IE-0003E-CC02
PS5-60-IE-0003F-CC01
PS5-60-IE-0003F-CC02
PS5-60-IE-0003G-CC01
PS5-60-IE-0003G-CC02
PS5-60-IE-0003A-CC04
PS5-60-IE-0003B-CC04
PS5-60-IE-0003C-CC04
PS5-60-IE-0003D-CC04
PS5-60-IE-0003E-CC04
PS5-60-IE-0003F-CC04
PS5-60-IE-0003B-CC05
PS5-60-IE-0003D-CC05
PS5-60-IE-0003E-CC05
PS5-60-IE-0003F-CC05
PS5-60-IE-0003G-CC05
PS5-60-IE-0003A-CC05
PS5-71-BI-0011A-CC04
PS5-71-BI-0003-CC02
PS5-71-BI-0003-CC03
PS5-60-BI-0006A-CC04
PS5-60-BI-0006B-CC04
PS5-60-BI-0006C-CC04
PS5-60-BI-0006D-CC04
PS5-60-BI-0006E-CC04
PS5-60-BI-0006F-CC04
PS5-60-BI-0006G-CC04
PS5-60-BI-0016A-CCO4
PS5-60-BI-0016B-CCO4
PS5-60-BI-0008A-CC01
PS5-60-BI-0008B-CC01
PS5-60-BI-0009A-CC01
PS5-60-BI-0009B-CC01
PS5-60-BI-0010A-CC01
PS5-60-BI-0010B-CC01
PS5-60-BI-0011A-CC01
PS5-60-BI-0011B-CC01
PS5-60-BI-0012A-CC01
PS5-60-BI-0012B-CC01
PS5-60-BI-0013A-CC01
PS5-60-BI-0013B-CC01
PS5-60-BI-0014A-CC01
PS5-60-BI-0014B-CC01
PS5-60-BI-0016A-CC02
PS5-60-BI-0016B-CC02
PS5-60-BI-0016C-CC02
PS5-60-BI-0016D-CC02
PS5-60-BI-0016E-CC02
PS5-60-BI-0016F-CC02
PS5-60-BI-0016G-CC02
PS5-60-BI-0004A-CCO1
PS5-60-BI-0004B-CCO1
PS5-60-BI-0004C-CCO1
PS5-60-BI-0004D-CCO1
PS5-60-BI-0004E-CCO1
PS5-60-BI-0004F-CCO1
PS5-60-BI-0004G-CCO1
PS5-03-GDIR-0901-CC01
PS5-03-GDIR-0902-CC01
PS5-03-GDIR-0903-CC01
PS5-03-GDIR-0904-CC01
PS5-03-GDIR-0906-CC01
PS5-03-GDIR-0907-CC01
PS5-03-GDIR-0908-CC01
PS5-03-GDIR-0909-CC01
PS5-03-GDIR-1001-CC01
PS5-03-GDIR-1002-CC01
PS5-03-GDIR-1003-CC01
PS5-03-GDIR-1004-CC01
PS5-03-GDIR-1006-CC01
PS5-03-GDIR-1007-CC01
PS5-03-GDIR-1008-CC01
PS5-03-GDIR-1009-CC01
PS5-03-GDIR-1101-CC01
PS5-03-GDIR-1102-CC01
PS5-03-GDIR-1103-CC01
PS5-03-GDIR-1104-CC01
PS5-03-GDIR-1106-CC01
PS5-03-GDIR-1107-CC01
PS5-03-GDIR-1108-CC01
PS5-03-GDIR-1109-CC01
PS5-03-GDIR-1201-CC01
PS5-03-GDIR-1202-CC01
PS5-03-GDIR-1203-CC01
PS5-03-GDIR-1204-CC01
PS5-60-IE-0003B-CA02
PS5-60-IE-0003C-CA02
PS5-60-IE-0003D-CA02
PS5-60-IE-0003E-CA02
PS5-60-IE-0003F-CA02
PS5-60-IE-0004-CC01
PS5-60-IE-0004-CC02
PS5-60-IE-0004-CC03
PS5-60-IE-0004-CC04
PS5-60-IE-0004-CC05
PS5-60-IE-0004-CC06
PS5-71-IN-0001-CA11
PS5-71-IN-0004A-CC11
PS5-71-IN-0004A-CC13
PS5-71-IN-0004B-CC11
PS5-60-IE-0004-CC07
PS5-60-BI-0008A-CC02
PS5-60-BI-0008B-CC02
PS5-60-BI-0009A-CC02
PS5-60-BI-0009B-CC02
PS5-60-BI-0010A-CC02
PS5-60-BI-0010B-CC02
PS5-60-BI-0011A-CC02
PS5-60-BI-0011B-CC02
PS5-60-BI-0012A-CC02
PS5-60-BI-0012B-CC02
PS5-60-BI-0013A-CC02
PS5-60-BI-0013B-CC02
PS5-60-BI-0014A-CC02
PS5-61-BI-0001-CC01
PS5-61-BI-0002-CC01
PS5-61-BI-0003-CC01
PS5-61-BI-0004-CC01
PS5-61-BI-0005-CC01
PS5-61-BI-0006-CC01
PS5-61-BI-0007-CC01
PS5-60-IH-0001A-CA01
PS5-60-IH-0001B-CA01
PS5-60-IH-0001C-CA01
PS5-60-IH-0001D-CA01
PS5-60-IH-0001E-CA01
PS5-60-IH-0001F-CA01
PS5-60-IH-0001G-CA01
PS5-60-LA-0003-CC02
PS5-60-LA-0003-CC03
PS5-75-LA-6200-CX01
PS5-60-IE-0002A-CC01
PS5-60-IE-0002A-CC02
PS5-60-IE-0002A-CC03
PS5-60-IE-0002B-CC01
PS5-60-IE-0002B-CC02
PS5-60-IE-0002B-CC03
PS5-60-IE-0002C-CC01
PS5-60-IE-0002C-CC02
PS5-60-IE-0002C-CC03
PS5-60-IE-0002D-CC01
PS5-60-IE-0002D-CC02
PS5-60-IE-0002D-CC03
PS5-60-IE-0002E-CC01
PS5-60-IE-0002E-CC02
PS5-60-IE-0002E-CC03
PS5-60-IE-0002F-CC01
PS5-60-IE-0002F-CC02
PS5-60-IE-0002F-CC03
PS5-60-IE-0002G-CC01
PS5-60-IE-0002G-CC02
PS5-60-IE-0002G-CC03
PS5-60-IH-0001A-CC01
PS5-60-IH-0001A-CC02
PS5-60-IH-0001B-CC01
PS5-60-IH-0001B-CC02
PS5-60-IH-0001C-CC01
PS5-60-IH-0001C-CC02
PS5-60-LA-0003-CX02
PS5-71-BI-0011B-CC03
PS5-60-BI-0006A-CC01
PS5-60-BI-0006B-CC01
PS5-60-BI-0006C-CC01
PS5-60-BI-0006D-CC01
PS5-60-BI-0006E-CC01
PS5-60-BI-0006F-CC01
PS5-60-BI-0006G-CC01
PS5-71-BI-0011B-CC04
PS5-60-BI-0016E-CCO4
PS5-60-BI-0003-CC03
PS5-60-BI-0001A-CC02
PS5-60-BI-0001B-CC02
PS5-60-BI-0001C-CC02
PS5-60-BI-0001D-CC02
PS5-60-BI-0001E-CC02
PS5-60-BI-0001F-CC02
PS5-60-BI-0001G-CC02
PS5-60-IE-0002A-CC01
PS5-60-IE-0002A-CC02
PS5-60-IE-0002A-CC03
PS5-60-IE-0002B-CC01
PS5-60-IE-0002B-CC02
PS5-60-IE-0002B-CC03
PS5-60-IE-0002C-CC01
PS5-60-IE-0002C-CC02
PS5-60-IE-0002C-CC03
PS5-60-IE-0002D-CC01
PS5-60-IE-0002D-CC02
PS5-60-IE-0002D-CC03
PS5-60-IE-0002E-CC01
PS5-60-IE-0002E-CC02
PS5-60-IE-0002E-CC03
PS5-60-IE-0002F-CC01
PS5-60-IE-0002F-CC02
PS5-60-IE-0002F-CC03
PS5-60-IE-0002G-CC01
PS5-60-IE-0002G-CC02
PS5-60-IE-0002G-CC03
PS5-60-IH-0001B-CC01
PS5-60-IH-0001B-CC02
PS5-60-IH-0001C-CC01
PS5-60-IH-0001C-CC02
PS5-60-IH-0002-CC01
PS5-60-IH-0002-CC02
PS5-60-PIT-8113A-CC01
PS5-60-PIT-8113B-CC01
PS5-60-PIT-8113C-CC01
PS5-60-PIT-8113D-CC01
PS5-60-PIT-8113E-CC01
PS5-60-PIT-8113F-CC01
PS5-60-PIT-8113G-CC01
PS5-60-PIT-8114A-CC01
PS5-60-PIT-8114B-CC01
PS5-60-PIT-8114C-CC01
PS5-60-PIT-8114D-CC01
PS5-60-PIT-8114E-CC01
PS5-60-PIT-8114F-CC01
PS5-60-PIT-8114G-CC01